## B04_Capacity
IND-GLD6-2026091101
| * | 9月 Sep | 10月 Oct | 11月 Nov | 12月 Dec | 1月 Jan | 2月 Feb | 3月 Mar | 4月 Apr | 5月 May | 6月 Jun | 7月 Jul | 8月 Aug
A = B04_Gannt_Chart_Detail 裡面的實際標打+排線標打(不含無訂單產能) = 來源是底稿加工票 | 已排線產能 Scheduled Capacity | 47196.0106 | 54844.9766 | 53085.2491 | 41951.0436 | 17348.9562 | 0 | 0 | 0 |  |  | 59025.3942 | 39355.2192
B = B04_Gannt_Chart_Detail 裡面的無訂單產能 來源為Parameter設人數/效率/工時計算出，抓最後一組下線+30天，這樣至少讓尾數月的產能資料完整，後面不完整月份直接看產銷產能預估即可 | 未排線產能 Unscheduled Capacity |  |  |  | 12932 | 36358 | 50880 | 57240 | 50880
C = A+B | 總產能 Total Capacity | 47196.0106 | 54844.9766 | 53085.2491 | 54883.0436 | 53706.9562 | 50880 | 57240 | 50880 | 0 | 0 | 59025.3942 | 39355.2192
D = 產銷匯入最新預計產能 | 預估產能 Estimated Capacity | 46000 | 53500 | 49500 | 51500 | 50000 | 48000 | 37500 | 54000 | 45500 | 52000 | 59000 | 54500
E = ERP屬於該Maker的EXP標打數 | 出口總數 Confirmed Order | 34740.5708 | 52809.0467 | 38405.0575 | 31685.8742 | 3719.3917
F = B04_Gannt_Chart_Detail 裡面的實際標打+排線標打 / B04_Gannt_Chart_Detail人數工時計算出100%效率標打數 = 效率 = 來源是底稿加工票 | 已排線效率 Scheduled Efficiency | 1.5754 | 1.5408 | 1.6195 | 1.6088 | 1.6808 | [5 empty] | 1.7943 | 1.5841
G = B04_Gannt_Chart_Detail 裡面的實際人數 + 排線人數 加總除以各組加總工作天次 = 來源是底稿加工票 | 已排線人數 Scheduled Sewers | 36.755 | 36.9027 | 36.6723 | 36.4003 | 36.338 | [5 empty] | 36.2385 | 36.6825
H = Parameter 參數設定 | 排線標準工時 Standard Working Hours | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
I = B04_Gannt_Chart_Detail 裡面的實際工時 + 排線工時，加總起來扣除排線標準工時再除上排線標準工時得之 = 來源是底稿加工票 | 已排線加班率 Scheduled OT Rate | 0.10065 | 0.061355 | 0.062187 | 0.069454 | 0.075 | [5 empty] | 0.037247 | 0.0060144
J = 扣除禮拜天 & Holidays Table的工作天數 | 工作天 Working Days | 22 | 27 | 25 | 26 | 25 | 24 | 19 | 25 | 23 | 24 | 27 | 20
K = B04_Gannt_Chart_Detail 裡面的實際標打+排線標打 真正有訂單標打數的天數 除以 工作天 (換句話說單組休年假或拆組會少計) | 已排線數 Lines | 20 | 20 | 20 | 15.3077 | 6.28 |  |  | 20 | 20 | 20 | 20 | 20
L = 發生換款(同Style_N2不算換)的次數除以排線數 | 換款率 Turnover Rate | 1.05 | 1.05 | 0.85 | 0.32663 | [6 empty] | 0.95 | 1.05
M = B04_Gannt_Chart_Detail 裡面的Suspend work停工產能總計 | 停工產能 Suspend Work Capacity
N = 該月提前生產兩個月後交期訂單的比例 | 提前完成% Advance Production % | 0.15592 | 0.13258 | 0.016311 | 0.031985 | 0.016679 | 0 | 0 | 0.3053 | 0 | 0 | 0.26848 | 0.36131
O = 上週排線結果的已排線產能(因排線作業時間為五六日一，抓上一個作業區間的最新版本) | 上週產能 Last Week Plan Capacity | 47314.1417 | 52822.0842 | 52151.4625 | 52325.4492 | 52670.355 | 50880 | 57240 | 29680 | 0 | 0 | 59025.3942 | 39355.2192
| 總產能-預估產能 | 1196.0106 | 1344.9766 | 3585.2491 | 3383.0436 | 3706.9562 | 2880 | 19740 | -3120 | -45500 | -52000 | 25.3942 | -15144.7808
from Essbase 純目標產能 | 目標產能 Target Capacity | 52500 | 53000 | 49500 | 51500 | 0 | 0 | 0 | 0 |  |  | 54500 | 48500
| 出口/產能二維分析 | 產能月份 Month Capacity
| 出口月份 Exp Month | 9月 Sep | 10月 Oct | 11月 Nov | 12月 Dec | 1月 Jan | 2月 Feb | 3月 Mar | 4月 Apr | 5月 May | 6月 Jun | 7月 Jul | 8月 Aug
| 9月 Sep | 7380.5051 | [8 empty] | 2671.9245 | 12560.3547 | 12981.865
| 10月 Oct | 33382.6496 | 16841.8592 | [7 empty] | 1751.5781 | 1526.4347 | 11446.2828
| 11月 Nov | 5163.8159 | 30731.975 | 17251.7297 | [7 empty] | 1760.3863 | 1430.3138
| 12月 Dec | 2195.2202 | 7271.1424 | 34967.6224 | 27896.7927 | 379.26 | [6 empty] | 1343.034
| 1月 Jan |  |  | 865.897 | 12298.819 | 10800.4002
| 2月 Feb |  |  |  | 1506.204 | 5273.52
| 3月 Mar |  |  |  | 249.228 | 335.916
| 4月 Apr |  |  |  |  | 559.86
5月 May
| 6月 Jun | [7 empty] | 3783.2079 | 4560.6204 | 2645.6773
| 7月 Jul | [7 empty] | 11750.2978 | 22777.213 | 36867.6825 | 18539.6822
| 8月 Aug | 81.6147 | [7 empty] | 1661.1201 | 6007.8596 | 26906.5469 | 14177.6566
| Total | 48203.8055 | 54844.9766 | 53085.2491 | 41951.0436 | 17348.9562 | 0 | 0 | 15533.5057 | 28998.9535 | 49944.7219 | 61293.4048 | 41379.1522

## Production_Planning
Factory |  | Barcode Info Import Function | Version |  | Send to Manager |  | Excel版本： | 1.2.9 | Country: | ALL | Manual Data | Factory Schedule Data | Formula | System Data
[7 empty] | 組件版本： | 1.2.9 |  |  | 手動維護 | 系統資料 | 公式 | 系統帶入
[7 empty] | Lastest Version: | 1.2.9 | ReConnect:
Now is process data till row number 681 |  |  | CreateBy : GLD6ADMProduksi |  |  | IND-GLD6-2026091101
Line | BUYER | STYLE | Product Item | Special Production | Color (自選欄位1) | Shipmode (自選欄位2) | Order QTY | Allocate QTY | Barcode EQC QTY | Allocate unfinished | Alloctate Std Dz | CRFP | Cutting Date of acquistion | Sewing Start | Sewing Finish | Packing Finish | Delivery | Holiday | EFF | IE | Work HR | Sewing Workers Per Line | Daily Target | Days | Hourly Target | Garment Color | Delivery – Sewing Finish
組別 | 客戶 | 款式 | 產品 | 特工 | 顏色 | Shipmode | 訂單數 | 分配生產數(組) | 工票完成數 | 未完成 | 標打 | 可開裁日 | 開裁需求日 | 車縫上線日 | 車縫完成日 | 包裝完成日 | 交期 | 非例假 | 效率% | IE | 時數 | 人數 | 目標 | 天數 | 小時件數 | 成衣色 | 交期 – 車縫完成
2026-06-11
6-01 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 16401 | 16401 | 0 | 1899.7825 | 2026-06-03 | 2026-06-06 | 2026-06-09 | 2026-07-04 | 2026-07-06 | 2026-07-09 |  | 1.4696 | 1.39 | 9.2169 | 35.5696 | 873.476 | 18.7767 | 94.94 |  | 4
6-01 | TGT | 45M87P_C426 | Pull On Pants |  | all po |  |  | 15985 | 15985 | 0 | 2224.5792 | 2026-06-27 | 2026-06-30 | 2026-07-02 | 2026-07-27 | 2026-07-29 | 2026-08-19 |  | 1.8441 | 1.67 | 8.0771 | 37.1957 | 836.0225 | 19.1203 | 103.6922 |  | 17
6-01 | ONY | 1182430_HO26_HT | Pull On Pants |  | all po |  |  | 27270 | 27270 | 0 | 1772.55 | 2026-08-06 | 2026-07-22 | 2026-07-24 | 2026-08-31 | 2026-09-02 | 2026-09-24 |  | 1.1923 | 0.78 | 7.8679 | 37.4232 | 1134.2557 | 24.0422 | 144.4217 |  | 18
6-01 | SMA | PST840 | Pull On Pants |  | 1352813, _AH |  |  | 4108 | 4108 | 0 | 558.0033 | 2026-08-18 | 2026-08-24 | 2026-08-27 | 2026-09-09 | 2026-09-11 | 2026-09-22 |  | 1.1773 | 1.63 | 8.6405 | 36.512 | 574.2269 | 7.154 | 66.5777 |  | 9
6-01 | SMA | PST840 | Pull On Pants |  | 1354809_SS, _AH |  |  | 79 | 79 | 0 | 10.7308 | 2026-08-18 | 2026-09-03 | 2026-09-07 | 2026-09-09 | 2026-09-11 | 2026-09-23 |  | 1.3775 | 1.63 | 9 | 37 | 709.1562 | 0.1114 | 78.9372 |  | 10
6-01 | SMA | PST840 | Pull On Pants |  | 1352814, _AH |  |  | 7986 | 1130 | 6856 | 1084.765 | 2026-08-24 | 2026-09-03 | 2026-09-07 | 2026-09-22 | 2026-09-24 | 2026-10-02 |  | 1.62 | 1.63 | 9 | 38 | 856.5526 | 9.3234 | 95.3441 |  | 8
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 750 | 0 | 750 | 105 | 2026-09-12 | 2026-09-11 | 2026-09-18 | 2026-09-28 | 2026-09-30 | 2026-10-29 |  | 0.5 | 1.68 | 7 | 38 | 199.5 | 3.7594 | 28.5514 |  | 27
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 1500 | 0 | 1500 | 210 | 2026-09-12 | 2026-09-17 | 2026-09-24 | 2026-10-01 | 2026-10-03 | 2026-10-29 |  | 1 | 1.68 | 8.6 | 38 | 490.2 | 3.06 | 57.1028 |  | 24
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 2500 | 0 | 2500 | 350 | 2026-09-12 | 2026-09-22 | 2026-09-29 | 2026-10-07 | 2026-10-09 | 2026-10-29 |  | 1.1 | 1.68 | 8.6 | 38 | 539.22 | 4.6363 | 62.8131 |  | 19
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 3500 | 0 | 3500 | 490 | 2026-09-12 | 2026-09-29 | 2026-10-05 | 2026-10-14 | 2026-10-16 | 2026-10-29 |  | 1.2 | 1.68 | 8.6 | 38 | 588.24 | 5.95 | 68.5233 |  | 13
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 4000 | 0 | 4000 | 560 | 2026-09-12 | 2026-10-06 | 2026-10-12 | 2026-10-21 | 2026-10-23 | 2026-10-29 |  | 1.4 | 1.68 | 8.6 | 38 | 686.28 | 5.8285 | 79.9439 |  | 7
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 4750 | 0 | 4750 | 665 | 2026-09-12 | 2026-10-13 | 2026-10-19 | 2026-10-28 | 2026-10-30 | 2026-10-29 |  | 1.5 | 1.68 | 8.6 | 38 | 735.3 | 6.4599 | 85.6542 |  | 1
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0130 |  |  | 4332 | 0 | 4332 | 606.48 | 2026-10-03 | 2026-10-20 | 2026-10-26 | 2026-11-04 | 2026-11-06 | 2026-11-09 |  | 1.6 | 1.68 | 8.6 | 38 | 784.32 | 5.5233 | 91.3645 |  | 4
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0213 |  |  | 4000 | 0 | 4000 | 560 | 2026-10-17 | 2026-10-27 | 2026-11-02 | 2026-11-10 | 2026-11-12 | 2026-11-23 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 4.5333 | 102.785 |  | 11
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0227 |  |  | 6678 | 0 | 6678 | 934.92 | 2026-10-31 | 2026-11-02 | 2026-11-07 | 2026-11-19 | 2026-11-21 | 2026-12-07 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 7.5683 | 102.785 |  | 15
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0313 |  |  | 10896 | 0 | 10896 | 1525.44 | 2026-10-31 | 2026-11-11 | 2026-11-17 | 2026-12-03 | 2026-12-05 | 2026-12-28 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 12.3487 | 102.785 |  | 20
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0327 |  |  | 8952 | 0 | 8952 | 1253.28 | 2026-10-31 | 2026-11-25 | 2026-12-01 | 2026-12-15 | 2026-12-17 | 2027-01-09 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 10.1455 | 102.785 |  | 20
2026-06-05
6-02 | TGT | G917K0_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 87892 | 87892 | 0 | 9155.4167 | 2026-06-12 | 2026-05-26 | 2026-06-03 | 2026-09-02 | 2026-09-04 | 2026-09-05 |  | 2.0664 | 1.25 | 8.5997 | 35.7988 | 1282.5237 | 68.5305 | 149.4043 |  | 2
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014311_1219E |  |  | 2040 | 2040 | 0 | 142.8 | 2026-08-22 | 2026-08-21 | 2026-08-31 | 2026-09-04 | 2026-09-06 | 2026-09-28 |  | 0.96978 | 0.84 | 8 | 36.2304 | 843.254 | 2.4192 | 105.5968 |  | 16
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014298_SET_1212, 10002014297_T1_1212 |  |  | 33950 | 10149 | 23801 | 2376.5 | 2026-08-22 | 2026-08-26 | 2026-09-02 | 2026-10-01 | 2026-10-03 | 2026-10-01 |  | 1.81 | 0.84 | 9 | 36.2796 | 1772.985 | 19.1485 | 197.3536 |  | 0
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014310_1219 |  |  | 2640 | 0 | 2640 | 184.8 | 2026-08-29 | 2026-09-22 | 2026-09-29 | 2026-10-03 | 2026-10-05 | 2026-10-10 |  | 1.8 | 0.84 | 8.6 | 36.2796 | 1684.8256 | 1.5669 | 196.2632 |  | 6
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014306_E_0102 |  |  | 3600 | 0 | 3600 | 252 | 2026-08-29 | 2026-09-24 | 2026-10-01 | 2026-10-06 | 2026-10-08 | 2026-10-12 |  | 1.8 | 0.84 | 8.6 | 36.2796 | 1684.8256 | 2.1367 | 196.2632 |  | 5
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014305_0102 |  |  | 4704 | 0 | 4704 | 329.28 | 2026-08-29 | 2026-09-28 | 2026-10-03 | 2026-10-09 | 2026-10-11 | 2026-10-24 |  | 1.8 | 0.84 | 8.6 | 36.2796 | 1684.8256 | 2.792 | 196.2632 |  | 13
6-02 | ONY | 1195255_SP27 | Tee |  | 62345060 |  |  | 572 | 0 | 572 | 31.46 | 2026-10-07 | 2026-10-05 | 2026-10-07 | 2026-10-10 | 2026-10-12 | 2026-11-04 |  | 0.5 | 0.66 | 7 | 36.2796 | 484.8276 | 1.1798 | 69.386 |  | 21
6-02 | ONY | 1195255_SP27 | Tee |  | 62345060 |  |  | 800 | 0 | 800 | 44 | 2026-10-07 | 2026-10-06 | 2026-10-08 | 2026-10-12 | 2026-10-14 | 2026-11-04 |  | 1 | 0.66 | 8.6 | 36.2796 | 1191.2908 | 0.67154 | 138.772 |  | 20
6-02 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 1685 | 0 | 1685 | 92.675 | 2026-10-07 | 2026-10-07 | 2026-10-09 | 2026-10-13 | 2026-10-15 | 2026-11-05 |  | 1.1 | 0.66 | 8.6 | 36.2796 | 1310.4199 | 1.2858 | 152.6492 |  | 20
6-02 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 2500 | 0 | 2500 | 137.5 | 2026-10-07 | 2026-10-08 | 2026-10-10 | 2026-10-15 | 2026-10-17 | 2026-11-05 |  | 1.2 | 0.66 | 8.6 | 36.2796 | 1429.549 | 1.7488 | 166.5264 |  | 18
6-02 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 3500 | 0 | 3500 | 192.5 | 2026-10-07 | 2026-10-10 | 2026-10-13 | 2026-10-17 | 2026-10-19 | 2026-11-05 |  | 1.4 | 0.66 | 8.6 | 36.2796 | 1667.8071 | 2.0986 | 194.2808 |  | 16
6-02 | ONY | 1194431_SP27 | Tee |  | 62315014 |  |  | 329 | 0 | 329 | 35.0933 | 2026-10-07 | 2026-10-13 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 2026-10-29 |  | 0.5 | 1.28 | 7 | 36.2796 | 249.9893 | 1.3161 | 35.7771 |  | 9
6-02 | ONY | 1194431_SP27 | Tee |  | 62330730, 732, 735, 739 |  |  | 2611 | 0 | 2611 | 278.5067 | 2026-10-10 | 2026-10-14 | 2026-10-16 | 2026-10-23 | 2026-10-25 | 2026-11-05 |  | 1 | 1.28 | 8.6 | 36.2796 | 614.2593 | 4.2506 | 71.5543 |  | 11
6-02 | ONY | 1194431_SP27 | Tee |  | 62326898, 440 |  |  | 271 | 0 | 271 | 28.9067 | 2026-10-10 | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-10-25 | 2026-11-26 |  | 1.2 | 1.28 | 8.6 | 36.2796 | 737.1112 | 0.36765 | 85.8652 |  | 29
6-02 | ONY | 1194431_SP27 | Tee |  | 62330583, 585, 589, 590, 439, 441, 443, 445 |  |  | 3087 | 0 | 3087 | 329.28 | 2026-11-10 | 2026-10-19 | 2026-10-21 | 2026-10-28 | 2026-10-30 | 2026-12-03 |  | 1.4 | 1.28 | 8.6 | 36.2796 | 859.963 | 3.5897 | 100.176 |  | 31
6-02 | ONY | 1194431_SP27 | Tee |  | 62326668, 12.24 |  |  | 717 | 0 | 717 | 76.48 | 2026-11-03 | 2026-10-23 | 2026-10-26 | 2026-10-29 | 2026-10-31 | 2026-12-24 |  | 1.6 | 1.28 | 8.6 | 36.2796 | 982.8149 | 0.72954 | 114.4869 |  | 48
6-02 | ONY | 1194431_SP27 | Tee |  | 62330544, 548, 552, 556, 12.31 |  |  | 2253 | 0 | 2253 | 240.32 | 2026-11-03 | 2026-10-24 | 2026-10-27 | 2026-10-31 | 2026-11-02 | 2026-12-31 |  | 1.8 | 1.28 | 8.6 | 36.2796 | 1105.6668 | 2.0377 | 128.7977 |  | 51
6-02 | ONY | 1194431_SP27 | Tee |  | 62326618, 01.21 |  |  | 475 | 0 | 475 | 50.6667 | 2026-11-03 | 2026-10-27 | 2026-10-29 | 2026-10-31 | 2026-11-02 | 2027-01-21 |  | 1.8 | 1.28 | 8.6 | 36.2796 | 1105.6668 | 0.42961 | 128.7977 |  | 68
6-02 | ONY | 1194431_SP27 | Tee |  | 01.28 |  |  | 641 | 0 | 641 | 68.3733 | 2026-11-30 | 2026-10-27 | 2026-10-29 | 2026-11-02 | 2026-11-04 | 2027-01-28 |  | 1.8 | 1.28 | 8.6 | 36.2796 | 1105.6668 | 0.57974 | 128.7977 |  | 73
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 716 | 0 | 716 | 72.7933 | 2026-11-05 | 2026-10-28 | 2026-10-30 | 2026-11-05 | 2026-11-07 | 2026-11-30 |  | 0.5 | 1.22 | 7 | 36.2796 | 262.2838 | 2.7299 | 37.5367 |  | 21
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 1500 | 0 | 1500 | 152.5 | 2026-11-05 | 2026-10-31 | 2026-11-03 | 2026-11-07 | 2026-11-09 | 2026-11-30 |  | 1 | 1.22 | 8.6 | 36.2796 | 644.4688 | 2.3275 | 75.0734 |  | 19
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 2500 | 0 | 2500 | 254.1667 | 2026-11-05 | 2026-11-03 | 2026-11-05 | 2026-11-12 | 2026-11-14 | 2026-11-30 |  | 1.1 | 1.22 | 8.6 | 36.2796 | 708.9157 | 3.5265 | 82.5807 |  | 15
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 3500 | 0 | 3500 | 355.8333 | 2026-11-05 | 2026-11-07 | 2026-11-10 | 2026-11-18 | 2026-11-20 | 2026-11-30 |  | 1.2 | 1.22 | 8.6 | 36.2796 | 773.3625 | 4.5257 | 90.088 |  | 10
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 4500 | 0 | 4500 | 457.5 | 2026-11-05 | 2026-11-13 | 2026-11-16 | 2026-11-24 | 2026-11-26 | 2026-11-30 |  | 1.4 | 1.22 | 8.6 | 36.2796 | 902.2563 | 4.9875 | 105.1027 |  | 5
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 5000 | 0 | 5000 | 508.3333 | 2026-11-05 | 2026-11-19 | 2026-11-21 | 2026-11-30 | 2026-12-02 | 2026-12-07 |  | 1.6 | 1.22 | 8.6 | 36.2796 | 1031.1501 | 4.849 | 120.1174 |  | 6
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 8516 | 0 | 8516 | 865.7933 | 2026-11-05 | 2026-11-25 | 2026-11-27 | 2026-12-08 | 2026-12-10 | 2026-12-07 |  | 1.8 | 1.22 | 8.6 | 36.2796 | 1160.0438 | 7.3411 | 135.1321 |  | -3
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-12-03 | 2026-12-05 | 2026-12-10 | 2026-12-15 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 36.2796 | 347.8111 | 2.3432 | 49.7769 |  | 12
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-12-05 | 2026-12-08 | 2026-12-12 | 2026-12-17 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 36.2796 | 854.6217 | 1.7552 | 99.5538 |  | 10
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-12-08 | 2026-12-10 | 2026-12-16 | 2026-12-21 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 36.2796 | 940.0838 | 2.6593 | 109.5092 |  | 7
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-11 | 2026-12-14 | 2026-12-19 | 2026-12-24 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 36.2796 | 1025.546 | 2.9253 | 119.4646 |  | 4
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4942 | 0 | 4942 | 378.8867 | 2026-12-07 | 2026-12-15 | 2026-12-17 | 2026-12-24 | 2026-12-29 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 36.2796 | 1111.0082 | 4.4482 | 129.42 |  | 5
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-12-07 | 2026-12-19 | 2026-12-22 | 2026-12-30 | 2027-01-04 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 36.2796 | 1196.4703 | 4.179 | 139.3753 |  | 1
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-24 | 2026-12-28 | 2027-01-02 | 2027-01-07 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 36.2796 | 1281.9325 | 1.5009 | 149.3307 |  | 10
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-28 | 2026-12-30 | 2027-01-09 | 2027-01-14 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 36.2796 | 1281.9325 | 6.0814 | 149.3307 |  | 10
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-05 | 2027-01-07 | 2027-01-15 | 2027-01-20 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 36.2796 | 1281.9325 | 5.1555 | 149.3307 |  | 11
6-02 | [26 empty] | 0
2026-04-21
6-03 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 29699 | 29699 | 0 | 2598.6625 | 2026-05-04 | 2026-04-16 | 2026-04-18 | 2026-05-20 | 2026-05-25 | 2026-07-23 |  | 1.6453 | 1.05 | 9.1703 | 35.9036 | 1300.1298 | 22.8431 | 142.0323 |  | 52
6-03 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 19159 | 19159 | 0 | 1676.4125 | 2026-05-23 | 2026-05-15 | 2026-05-18 | 2026-06-09 | 2026-06-14 | 2026-07-02 |  | 1.6134 | 1.05 | 9.1023 | 35.7343 | 1259.5162 | 15.2114 | 138.6222 |  | 19
6-03 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 28598 | 28598 | 0 | 3312.6017 | 2026-06-03 | 2026-06-04 | 2026-06-06 | 2026-07-13 | 2026-07-15 | 2026-07-09 |  | 1.734 | 1.39 | 9.5107 | 33.6617 | 1006.3981 | 28.4162 | 106.0086 |  | -5
6-03 | ONY | 910047_HO26DIS | Pajama |  | all po |  |  | 11308 | 11308 | 0 | 1338.1133 | 2026-07-06 | 2026-07-08 | 2026-07-10 | 2026-07-25 | 2026-07-27 | 2026-08-06 |  | 1.8663 | 1.42 | 8.4758 | 36.2794 | 1018.4268 | 11.1034 | 120.3737 |  | 10
6-03 | HLF | CPW264TL38 | Tee | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 22323 | 22323 | 0 | 1674.225 | 2026-07-10 | 2026-07-17 | 2026-07-23 | 2026-08-24 | 2026-08-26 | 2026-08-21 |  | 1.3631 | 0.9 | 7.5879 | 37.546 | 1087.3719 | 20.5293 | 143.5626 |  | -3
6-03 | SMA | ST841_FA26 | Tee |  | all po |  |  | 7230 | 7193 | 37 | 1048.35 | 2026-07-23 | 2026-08-18 | 2026-08-20 | 2026-09-09 | 2026-09-11 | 2026-09-19 |  | 1.35 | 1.74 | 9 | 37.3361 | 656.9857 | 11.0048 | 73.13 |  | 7
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 728 | 4 | 724 | 59.4533 | 2026-09-07 | 2026-09-03 | 2026-09-07 | 2026-09-11 | 2026-09-16 | 2026-10-01 |  | 0.5 | 0.98 | 7 | 37.3361 | 336.0245 | 2.1665 | 48.0901 |  | 14
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 1500 | 0 | 1500 | 122.5 | 2026-09-07 | 2026-09-07 | 2026-09-09 | 2026-09-15 | 2026-09-20 | 2026-10-01 |  | 1 | 0.98 | 9 | 37.3361 | 864.0629 | 1.736 | 96.1801 |  | 12
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 2700 | 0 | 2700 | 220.5 | 2026-09-07 | 2026-09-09 | 2026-09-11 | 2026-09-18 | 2026-09-23 | 2026-10-01 |  | 1.2 | 0.98 | 9 | 37.3361 | 1036.8754 | 2.604 | 115.4161 |  | 9
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62239979, 378, 565, 268, 269 |  |  | 1503 | 0 | 1503 | 122.745 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 2026-09-21 | 2026-09-26 | 2026-10-08 |  | 1.4 | 0.98 | 9 | 37.3361 | 1209.688 | 1.2425 | 134.6522 |  | 14
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 5000 | 0 | 5000 | 408.3333 | 2026-09-07 | 2026-09-15 | 2026-09-17 | 2026-09-25 | 2026-09-30 | 2026-10-15 |  | 1.6 | 0.98 | 9 | 37.3361 | 1382.5006 | 3.6166 | 153.8882 |  | 16
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 11000 | 0 | 11000 | 898.3333 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 2026-10-05 | 2026-10-10 | 2026-10-15 |  | 1.8 | 0.98 | 9 | 37.3361 | 1555.3132 | 7.0725 | 173.1242 |  | 9
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 8966 | 0 | 8966 | 732.2233 | 2026-09-07 | 2026-09-30 | 2026-10-02 | 2026-10-12 | 2026-10-17 | 2026-10-15 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 6.0329 | 173.1242 |  | 3
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62369477, 752, 716, 717, 734, 740, 046, 049, 054, 056 |  |  | 3697 | 0 | 3697 | 301.9217 | 2026-10-10 | 2026-10-07 | 2026-10-09 | 2026-10-14 | 2026-10-19 | 2026-11-05 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 2.4876 | 173.1242 |  | 19
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62387718, 721, 722, 725, 735, 736, 742, 743 |  |  | 5239 | 0 | 5239 | 427.8517 | 2026-10-10 | 2026-10-09 | 2026-10-12 | 2026-10-19 | 2026-10-24 | 2026-11-12 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 3.5251 | 173.1242 |  | 21
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62369454, 413, 719, 720, 057, 079, 080 |  |  | 1938 | 0 | 1938 | 158.27 | 2026-11-07 | 2026-10-14 | 2026-10-16 | 2026-10-20 | 2026-10-25 | 2026-12-03 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 1.304 | 173.1242 |  | 38
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62387723, 724, 726, 727 |  |  | 1261 | 0 | 1261 | 102.9817 | 2026-11-07 | 2026-10-15 | 2026-10-17 | 2026-10-21 | 2026-10-26 | 2026-12-10 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 0.84848 | 173.1242 |  | 43
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62387728, 729 |  |  | 262 | 0 | 262 | 21.3967 | 2026-11-07 | 2026-10-16 | 2026-10-19 | 2026-10-21 | 2026-10-26 | 2026-12-31 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 0.17629 | 173.1242 |  | 60
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62387730, 731, 732, 733 |  |  | 638 | 0 | 638 | 52.1033 | 2026-11-07 | 2026-10-16 | 2026-10-19 | 2026-10-21 | 2026-10-26 | 2027-01-07 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 0.42929 | 173.1242 |  | 65
6-03 | ONY | 1195255_SP27 | Tee |  | 62345060 |  |  | 572 | 0 | 572 | 31.46 | 2026-10-07 | 2026-10-16 | 2026-10-19 | 2026-10-22 | 2026-10-24 | 2026-11-04 |  | 0.5 | 0.66 | 7 | 37.3361 | 498.9454 | 1.1464 | 71.4064 |  | 11
6-03 | ONY | 1195255_SP27 | Tee |  | 62345060 |  |  | 800 | 0 | 800 | 44 | 2026-10-07 | 2026-10-17 | 2026-10-20 | 2026-10-23 | 2026-10-25 | 2026-11-04 |  | 1 | 0.66 | 8.6 | 37.3361 | 1225.9801 | 0.65254 | 142.8129 |  | 10
6-03 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 1685 | 0 | 1685 | 92.675 | 2026-10-07 | 2026-10-19 | 2026-10-21 | 2026-10-24 | 2026-10-26 | 2026-11-05 |  | 1.1 | 0.66 | 8.6 | 37.3361 | 1348.5781 | 1.2495 | 157.0942 |  | 10
6-03 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 2500 | 0 | 2500 | 137.5 | 2026-10-07 | 2026-10-20 | 2026-10-22 | 2026-10-27 | 2026-10-29 | 2026-11-05 |  | 1.2 | 0.66 | 8.6 | 37.3361 | 1471.1761 | 1.6993 | 171.3755 |  | 8
6-03 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 3500 | 0 | 3500 | 192.5 | 2026-10-07 | 2026-10-22 | 2026-10-24 | 2026-10-29 | 2026-10-31 | 2026-11-05 |  | 1.4 | 0.66 | 8.6 | 37.3361 | 1716.3722 | 2.0392 | 199.938 |  | 6
6-03 | ONY | 1195255_SP27 | Tee |  | 62344872 |  |  | 484 | 0 | 484 | 26.62 | 2026-10-07 | 2026-10-24 | 2026-10-27 | 2026-10-29 | 2026-10-31 | 2026-11-11 |  | 1.4 | 0.66 | 8.6 | 37.3361 | 1716.3722 | 0.28199 | 199.938 |  | 11
6-03 | ONY | 1195255_SP27 | Tee |  | 62323334, 336, 338, 339, 843, 844 |  |  | 4076 | 0 | 4076 | 224.18 | 2026-10-07 | 2026-10-24 | 2026-10-27 | 2026-10-31 | 2026-11-02 | 2026-11-12 |  | 1.6 | 0.66 | 8.6 | 37.3361 | 1961.5682 | 2.0779 | 228.5006 |  | 10
6-03 | ONY | 1195255_SP27 | Tee |  | 62323334, 336, 338, 339, 843, 844 |  |  | 9500 | 0 | 9500 | 522.5 | 2026-10-07 | 2026-10-27 | 2026-10-29 | 2026-11-05 | 2026-11-07 | 2026-11-12 |  | 1.8 | 0.66 | 8.6 | 37.3361 | 2206.7642 | 4.3049 | 257.0632 |  | 6
6-03 | ONY | 1195255_SP27 | Tee |  | 62323824, 861 |  |  | 11020 | 0 | 11020 | 606.1 | 2026-10-07 | 2026-10-31 | 2026-11-03 | 2026-11-11 | 2026-11-13 | 2026-12-03 |  | 1.8 | 0.66 | 8.6 | 37.3361 | 2206.7642 | 4.9937 | 257.0632 |  | 19
6-03 | ONY | 1195255_SP27 | Tee |  | 62323388, 390, 392, 394, 463, 466, 468, 469, 826, 827, 862, 863 |  |  | 30372 | 0 | 30372 | 1670.46 | 2026-10-07 | 2026-11-06 | 2026-11-09 | 2026-11-27 | 2026-11-29 | 2026-12-10 |  | 1.8 | 0.66 | 8.6 | 36.8624 | 2178.7713 | 13.94 | 253.8023 |  | 11
6-03 | ONY | 1195255_SP27 | Tee |  | 12.31 |  |  | 732 | 0 | 732 | 40.26 | 2026-10-07 | 2026-11-23 | 2026-11-25 | 2026-11-27 | 2026-11-29 | 2026-12-31 |  | 1.8 | 0.66 | 8.6 | 36.8624 | 2178.7713 | 0.33597 | 253.8023 |  | 28
6-03 | ONY | 1195255_SP27 | Tee |  | 01.07 |  |  | 1709 | 0 | 1709 | 93.995 | 2026-10-07 | 2026-11-23 | 2026-11-25 | 2026-11-28 | 2026-11-30 | 2027-01-07 |  | 1.8 | 0.66 | 8.6 | 36.8624 | 2178.7713 | 0.78439 | 253.8023 |  | 32
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-11-24 | 2026-11-26 | 2026-12-01 | 2026-12-06 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 36.8624 | 353.3986 | 2.3062 | 50.5766 |  | 20
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-11-26 | 2026-11-28 | 2026-12-03 | 2026-12-08 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 36.8624 | 868.3509 | 1.7274 | 101.1531 |  | 18
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-11-28 | 2026-12-01 | 2026-12-07 | 2026-12-12 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 36.8624 | 955.186 | 2.6173 | 111.2684 |  | 15
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-02 | 2026-12-04 | 2026-12-10 | 2026-12-15 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 36.8624 | 1042.021 | 2.879 | 121.3837 |  | 12
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 3450 | 0 | 3450 | 264.5 | 2026-12-07 | 2026-12-05 | 2026-12-08 | 2026-12-14 | 2026-12-19 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 36.8624 | 1128.8561 | 3.0562 | 131.499 |  | 14
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 5992 | 0 | 5992 | 459.3867 | 2026-12-07 | 2026-12-09 | 2026-12-11 | 2026-12-19 | 2026-12-24 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 36.8624 | 1215.6912 | 4.9289 | 141.6143 |  | 9
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 8550 | 0 | 8550 | 655.5 | 2026-12-07 | 2026-12-15 | 2026-12-17 | 2026-12-29 | 2027-01-03 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 6.5642 | 151.7297 |  | 2
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-23 | 2026-12-26 | 2026-12-30 | 2027-01-04 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 1.4771 | 151.7297 |  | 12
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-24 | 2026-12-28 | 2027-01-07 | 2027-01-12 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 5.9853 | 151.7297 |  | 12
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-02 | 2027-01-05 | 2027-01-13 | 2027-01-18 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 5.074 | 151.7297 |  | 13
2026-04-19
6-04 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 26479 | 26479 | 0 | 2316.9125 | 2026-04-25 | 2026-04-15 | 2026-04-17 | 2026-05-18 | 2026-05-23 | 2026-06-04 |  | 1.489 | 1.05 | 8.8333 | 36.727 | 1159.316 | 22.8402 | 131.4811 |  | 13
6-04 | ONY | 915810_FA26 | Tee |  | all po |  |  | 6456 | 6456 | 0 | 634.84 | 2026-05-15 | 2026-05-12 | 2026-05-15 | 2026-06-02 | 2026-06-04 | 2026-06-11 |  | 0.8934 | 1.18 | 8.7965 | 36.3618 | 610.2657 | 10.579 | 69.5009 |  | 8
6-04 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 18832 | 18832 | 0 | 2181.3733 | 2026-06-03 | 2026-05-26 | 2026-05-29 | 2026-06-30 | 2026-07-02 | 2026-07-09 |  | 1.4109 | 1.39 | 9.1249 | 34.9781 | 816.4257 | 23.0664 | 89.6341 |  | 8
6-04 | ONY | 915810_FA26 | Tee |  | all po |  |  | 3182 | 3182 | 0 | 312.8967 | 2026-06-04 | 2026-06-25 | 2026-06-27 | 2026-07-06 | 2026-07-08 | 2026-07-09 |  | 0.99489 | 1.18 | 7.7074 | 36.4515 | 596.92 | 5.3307 | 77.5873 |  | 3
6-04 | ONY | 766362_HO26 | Pull On Pants |  | all po |  |  | 24434 | 24434 | 0 | 1751.1033 | 2026-07-09 | 2026-07-01 | 2026-07-03 | 2026-07-29 | 2026-07-31 | 2026-08-06 |  | 1.3668 | 0.86 | 8.2229 | 37.6497 | 1239.9326 | 19.7059 | 151.0617 |  | 7
6-04 | HLF | CPM263TL32_26Q4 | Tee | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 12021 | 12021 | 0 | 901.575 | 2026-07-10 | 2026-07-21 | 2026-07-27 | 2026-08-12 | 2026-08-14 | 2026-08-21 |  | 1.3542 | 0.9 | 7.4953 | 37.7324 | 1072.3844 | 11.2096 | 143.3328 |  | 6
6-04 | ONY | 766362_HO26 | Pull On Pants |  | all po |  |  | 27675 | 27442 | 233 | 1983.375 | 2026-08-18 | 2026-08-06 | 2026-08-10 | 2026-09-07 | 2026-09-09 | 2026-12-17 |  | 1.7 | 0.86 | 9 | 38 | 1703.6372 | 16.2447 | 189.6344 |  | 84
6-04 | ONY | 766362_V1 | Pull On Pants |  | 10.28 |  |  | 855 | 842 | 13 | 61.275 | 2026-05-22 | 2026-09-01 | 2026-09-03 | 2026-09-08 | 2026-09-10 | 2026-10-28 |  | 1.7 | 0.86 | 9 | 38 | 1703.6372 | 0.50187 | 189.6344 |  | 40
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004922_T1_W |  |  | 720 | 720 | 0 | 63.6 | 2026-08-24 | 2026-08-28 | 2026-09-04 | 2026-09-10 | 2026-09-12 | 2026-10-01 |  | 0.63617 | 1.06 | 8 | 37.2693 | 450.9301 | 1.5967 | 56.4679 |  | 15
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 1500 | 411 | 1089 | 132.5 | 2026-08-24 | 2026-09-01 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 2026-10-08 |  | 1 | 1.06 | 9 | 38 | 813.0566 | 1.8449 | 90.5025 |  | 19
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 2500 | 0 | 2500 | 220.8333 | 2026-08-24 | 2026-09-03 | 2026-09-10 | 2026-09-17 | 2026-09-19 | 2026-10-08 |  | 1.1 | 1.06 | 9 | 38 | 894.3623 | 2.7953 | 99.5528 |  | 16
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 3500 | 0 | 3500 | 309.1667 | 2026-08-24 | 2026-09-08 | 2026-09-15 | 2026-09-23 | 2026-09-25 | 2026-10-08 |  | 1.2 | 1.06 | 9 | 38 | 975.6679 | 3.5873 | 108.603 |  | 12
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 3500 | 0 | 3500 | 309.1667 | 2026-08-24 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-09-30 | 2026-10-08 |  | 1.4 | 1.06 | 9 | 38 | 1138.2792 | 3.0748 | 126.7035 |  | 9
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 3999 | 0 | 3999 | 353.245 | 2026-08-24 | 2026-09-17 | 2026-09-24 | 2026-10-01 | 2026-10-03 | 2026-10-08 |  | 1.6 | 1.06 | 9 | 38 | 1300.8906 | 3.074 | 144.804 |  | 6
6-04 | ONY | 766362_V1 | Pull On Pants |  | 10.28 |  |  | 1118 | 0 | 1118 | 80.1233 | 2026-05-22 | 2026-09-25 | 2026-09-29 | 2026-10-05 | 2026-10-07 | 2026-10-28 |  | 0.5 | 0.86 | 7 | 38 | 389.7209 | 2.8687 | 55.7748 |  | 20
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62215028, 029, 030, 031 |  |  | 1850 | 0 | 1850 | 132.5833 | 2026-05-22 | 2026-09-30 | 2026-10-02 | 2026-10-07 | 2026-10-09 | 2026-10-29 |  | 1 | 0.86 | 8.6 | 38 | 957.6 | 1.9319 | 111.5496 |  | 19
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62215028, 029, 030, 031 |  |  | 2000 | 0 | 2000 | 143.3333 | 2026-05-22 | 2026-10-02 | 2026-10-05 | 2026-10-09 | 2026-10-11 | 2026-10-29 |  | 1.2 | 0.86 | 8.6 | 38 | 1149.12 | 1.7405 | 133.8596 |  | 17
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62047539, 028, 030, 031 |  |  | 3467 | 0 | 3467 | 248.4683 | 2026-05-22 | 2026-10-05 | 2026-10-07 | 2026-10-13 | 2026-10-15 | 2026-11-05 |  | 1.4 | 0.86 | 8.6 | 38 | 1340.64 | 2.5861 | 156.1695 |  | 20
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62047539, 028, 030, 031 |  |  | 4500 | 0 | 4500 | 322.5 | 2026-05-22 | 2026-10-08 | 2026-10-10 | 2026-10-16 | 2026-10-18 | 2026-11-05 |  | 1.6 | 0.86 | 8.6 | 38 | 1532.16 | 2.937 | 178.4794 |  | 17
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62047540, 029 |  |  | 4726 | 0 | 4726 | 338.6967 | 2026-05-22 | 2026-10-12 | 2026-10-14 | 2026-10-20 | 2026-10-22 | 2026-11-12 |  | 1.7 | 0.86 | 8.6 | 38 | 1627.92 | 2.9031 | 189.6344 |  | 20
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 960 | 0 | 960 | 25.6 | 2026-10-12 | 2026-10-15 | 2026-10-17 | 2026-10-21 | 2026-10-23 | 2026-11-02 |  | 0.5 | 0.32 | 7 | 38 | 1047.375 | 0.91658 | 149.8948 |  | 10
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 1500 | 0 | 1500 | 40 | 2026-10-12 | 2026-10-16 | 2026-10-19 | 2026-10-22 | 2026-10-24 | 2026-11-02 |  | 1 | 0.32 | 8.6 | 38 | 2573.55 | 0.58285 | 299.7896 |  | 9
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 2500 | 0 | 2500 | 66.6667 | 2026-10-12 | 2026-10-17 | 2026-10-20 | 2026-10-23 | 2026-10-25 | 2026-11-02 |  | 1.1 | 0.32 | 8.6 | 38 | 2830.905 | 0.88311 | 329.7686 |  | 8
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 3500 | 0 | 3500 | 93.3333 | 2026-10-12 | 2026-10-19 | 2026-10-21 | 2026-10-24 | 2026-10-26 | 2026-11-02 |  | 1.2 | 0.32 | 8.6 | 38 | 3088.26 | 1.1333 | 359.7475 |  | 7
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 4500 | 0 | 4500 | 120 | 2026-10-12 | 2026-10-20 | 2026-10-22 | 2026-10-26 | 2026-10-28 | 2026-11-02 |  | 1.3 | 0.32 | 8.6 | 38 | 3345.615 | 1.345 | 389.7265 |  | 6
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0130_W |  |  | 1044 | 0 | 1044 | 27.84 | 2026-10-20 | 2026-10-21 | 2026-10-23 | 2026-10-26 | 2026-10-28 | 2026-11-11 |  | 1.4 | 0.32 | 8.6 | 38 | 3602.97 | 0.28976 | 419.7055 |  | 14
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 5000 | 0 | 5000 | 133.3333 | 2026-10-12 | 2026-10-21 | 2026-10-23 | 2026-10-27 | 2026-10-29 | 2026-11-12 |  | 1.6 | 0.32 | 8.6 | 38 | 4117.68 | 1.2143 | 479.6634 |  | 14
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 7000 | 0 | 7000 | 186.6667 | 2026-10-12 | 2026-10-22 | 2026-10-24 | 2026-10-29 | 2026-10-31 | 2026-11-12 |  | 1.8 | 0.32 | 8.6 | 38 | 4632.39 | 1.5111 | 539.6213 |  | 12
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 33180 | 0 | 33180 | 884.8 | 2026-10-12 | 2026-10-24 | 2026-10-27 | 2026-11-05 | 2026-11-07 | 2026-11-12 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 6.4463 | 599.5792 |  | 6
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0213_W |  |  | 9108 | 0 | 9108 | 242.88 | 2026-10-20 | 2026-10-31 | 2026-11-03 | 2026-11-07 | 2026-11-09 | 2026-11-25 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7695 | 599.5792 |  | 15
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0220_W |  |  | 8892 | 0 | 8892 | 237.12 | 2026-10-27 | 2026-11-03 | 2026-11-05 | 2026-11-10 | 2026-11-12 | 2026-12-02 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7276 | 599.5792 |  | 19
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0227_W |  |  | 8892 | 0 | 8892 | 237.12 | 2026-10-27 | 2026-11-05 | 2026-11-07 | 2026-11-12 | 2026-11-14 | 2026-12-09 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7276 | 599.5792 |  | 23
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0306_W |  |  | 8892 | 0 | 8892 | 237.12 | 2026-10-27 | 2026-11-07 | 2026-11-10 | 2026-11-14 | 2026-11-16 | 2026-12-16 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7276 | 599.5792 |  | 27
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0313_W |  |  | 17784 | 0 | 17784 | 474.24 | 2026-10-27 | 2026-11-10 | 2026-11-12 | 2026-11-18 | 2026-11-20 | 2026-12-23 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 3.4551 | 599.5792 |  | 30
6-04 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 1500 | 0 | 1500 | 52.5 | 2026-11-13 | 2026-11-13 | 2026-11-16 | 2026-11-19 | 2026-11-21 | 2026-12-12 |  | 1.5 | 0.42 | 7 | 38 | 2394 | 0.62657 | 342.6167 |  | 20
6-04 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 3500 | 0 | 3500 | 122.5 | 2026-11-13 | 2026-11-14 | 2026-11-17 | 2026-11-20 | 2026-11-22 | 2026-12-12 |  | 1.8 | 0.42 | 8.6 | 38 | 3529.44 | 0.99166 | 411.1401 |  | 19
6-04 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 75000 | 0 | 75000 | 2625 | 2026-11-13 | 2026-11-16 | 2026-11-18 | 2026-12-12 | 2026-12-14 | 2026-12-12 |  | 2 | 0.42 | 8.6 | 38 | 3921.6 | 19.1248 | 456.8223 |  | 0
6-04 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0328 |  |  | 75000 | 0 | 75000 | 2625 | 2026-12-11 | 2026-12-08 | 2026-12-10 | 2027-01-06 | 2027-01-08 | 2027-01-09 |  | 2 | 0.42 | 8.6 | 38 | 3921.6 | 19.1248 | 456.8223 |  | 3
6-04 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0425 |  |  | 80000 | 0 | 80000 | 2800 | 2027-01-08 | 2026-12-31 | 2027-01-04 | 2027-01-29 | 2027-01-31 | 2027-02-06 |  | 2 | 0.42 | 8.6 | 38 | 3921.6 | 20.3998 | 456.8223 |  | 7
2026-04-02
6-05 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 56118 | 56118 | 0 | 4910.325 | 2026-05-07 | 2026-03-28 | 2026-03-31 | 2026-05-29 | 2026-06-03 | 2026-07-30 |  | 1.6939 | 1.05 | 8.9946 | 34.4529 | 1259.8102 | 44.5448 | 140.3152 |  | 51
6-05 | WMT | HQ263487_FA26 | Pull On Pants |  | all po |  |  | 20277 | 20277 | 0 | 1436.2875 | 2026-05-21 | 2026-05-23 | 2026-05-26 | 2026-06-18 | 2026-06-20 | 2026-06-27 |  | 1.4761 | 0.85 | 9.1873 | 32.7131 | 1315.2706 | 15.4166 | 143.4206 |  | 8
6-05 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 31058 | 31058 | 0 | 2717.575 | 2026-05-26 | 2026-06-12 | 2026-06-15 | 2026-07-14 | 2026-07-19 | 2026-07-16 |  | 1.7623 | 1.05 | 9.1485 | 36.1574 | 1399.0404 | 22.1995 | 153.2011 |  | 2
6-05 | TGT | 5GK4L2_C426 | Jumper |  | all po |  |  | 2892 | 2892 | 0 | 383.19 | 2026-07-03 | 2026-07-09 | 2026-07-11 | 2026-07-22 | 2026-07-24 | 2026-08-21 |  | 0.91766 | 1.59 | 7.5859 | 35.6461 | 393.2819 | 7.3535 | 51.9374 |  | 23
6-05 | ONY | 1184404_HO26 | Tee |  | all po |  |  | 5350 | 5350 | 0 | 347.75 | 2026-07-13 | 2026-07-17 | 2026-07-20 | 2026-07-31 | 2026-08-02 | 2026-08-13 |  | 0.85133 | 0.78 | 6.9853 | 34.9478 | 671.4355 | 7.968 | 96.2951 |  | 10
6-05 | HLF | CPW264TL38 | Tee | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 17942 | 17942 | 0 | 1345.65 | 2026-07-10 | 2026-07-23 | 2026-07-29 | 2026-08-21 | 2026-08-23 | 2026-08-21 |  | 1.5414 | 0.9 | 7.746 | 34.9112 | 1167.0888 | 15.3733 | 150.9414 |  | 0
6-05 | SMA | LPST840 | Pull On Pants |  | 1352772, _AH |  |  | 4836 | 4836 | 0 | 596.44 | 2026-08-18 | 2026-08-14 | 2026-08-19 | 2026-09-03 | 2026-09-05 | 2026-09-22 |  | 1.1327 | 1.48 | 8.586 | 35.7551 | 592.0812 | 8.1678 | 69.0835 |  | 13
6-05 | SMA | LPST840 | Pull On Pants |  | 1354810_SS, _AH |  |  | 79 | 79 | 0 | 9.7433 | 2026-08-18 | 2026-08-28 | 2026-09-01 | 2026-09-03 | 2026-09-05 | 2026-09-23 |  | 0.32267 | 1.48 | 9 | 36 | 178.0081 | 0.4438 | 19.8143 |  | 14
6-05 | SMA | LPST840 | Pull On Pants |  | 1352773, _AH |  |  | 3544 | 3539 | 5 | 437.0933 | 2026-08-24 | 2026-08-28 | 2026-09-01 | 2026-09-09 | 2026-09-11 | 2026-10-02 |  | 1.67 | 1.48 | 9 | 34.9478 | 894.3719 | 3.9626 | 99.5539 |  | 17
6-05 | TGT | 5GK4L2_C127 | Jumper |  | 10002064559_0110 |  |  | 500 | 140 | 360 | 66.25 | 2026-09-10 | 2026-09-03 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 2026-10-10 |  | 0.5 | 1.59 | 7 | 35 | 194.1509 | 2.5753 | 27.7859 |  | 21
6-05 | TGT | 5GK4L2_C127 | Jumper |  | 10002064559_0110 |  |  | 650 | 0 | 650 | 86.125 | 2026-09-10 | 2026-09-08 | 2026-09-10 | 2026-09-16 | 2026-09-18 | 2026-10-10 |  | 0.8 | 1.59 | 9 | 35 | 399.3962 | 1.6275 | 44.4574 |  | 19
6-05 | TGT | 5GK4L2_C127 | Jumper |  | 10002064559_0110 |  |  | 1766 | 0 | 1766 | 233.995 | 2026-09-10 | 2026-09-10 | 2026-09-14 | 2026-09-22 | 2026-09-24 | 2026-10-10 |  | 1 | 1.59 | 9 | 35 | 499.2453 | 3.5373 | 55.5717 |  | 15
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 795 | 0 | 795 | 113.95 | 2026-09-21 | 2026-09-11 | 2026-09-18 | 2026-09-28 | 2026-09-30 | 2026-11-02 |  | 0.5 | 1.72 | 7 | 35 | 179.4767 | 4.4295 | 25.6858 |  | 30
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 1500 | 0 | 1500 | 215 | 2026-09-21 | 2026-09-17 | 2026-09-24 | 2026-10-01 | 2026-10-03 | 2026-11-02 |  | 1 | 1.72 | 8.6 | 35 | 441 | 3.4014 | 51.3715 |  | 27
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 2500 | 0 | 2500 | 358.3333 | 2026-09-21 | 2026-09-22 | 2026-09-29 | 2026-10-07 | 2026-10-09 | 2026-11-02 |  | 1.1 | 1.72 | 8.6 | 35 | 485.1 | 5.1536 | 56.5087 |  | 22
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 3000 | 0 | 3000 | 430 | 2026-09-21 | 2026-09-29 | 2026-10-05 | 2026-10-14 | 2026-10-16 | 2026-11-02 |  | 1.2 | 1.72 | 8.6 | 35 | 529.2 | 5.6689 | 61.6458 |  | 16
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 3200 | 0 | 3200 | 458.6667 | 2026-09-21 | 2026-10-06 | 2026-10-12 | 2026-10-20 | 2026-10-22 | 2026-11-02 |  | 1.4 | 1.72 | 8.6 | 35 | 617.4 | 5.183 | 71.9202 |  | 11
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 6000 | 0 | 6000 | 860 | 2026-09-21 | 2026-10-12 | 2026-10-17 | 2026-10-30 | 2026-11-01 | 2026-11-02 |  | 1.5 | 1.72 | 8.6 | 35 | 661.5 | 9.0703 | 77.0573 |  | 2
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041497 |  |  | 2994 | 0 | 2994 | 429.14 | 2026-10-19 | 2026-10-22 | 2026-10-28 | 2026-11-05 | 2026-11-07 | 2026-11-16 |  | 1.5 | 1.72 | 8.6 | 35 | 661.5 | 4.5261 | 77.0573 |  | 9
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041486 |  |  | 3318 | 0 | 3318 | 475.58 | 2026-10-19 | 2026-10-28 | 2026-11-03 | 2026-11-11 | 2026-11-13 | 2026-11-30 |  | 1.5 | 1.72 | 8.6 | 35 | 661.5 | 5.0159 | 77.0573 |  | 16
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041480 |  |  | 3556 | 0 | 3556 | 509.6933 | 2026-11-02 | 2026-11-03 | 2026-11-09 | 2026-11-17 | 2026-11-19 | 2026-12-14 |  | 1.5 | 1.72 | 8.6 | 35 | 661.5 | 5.3757 | 77.0573 |  | 23
6-05 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 1500 | 0 | 1500 | 52.5 | 2026-11-13 | 2026-11-12 | 2026-11-14 | 2026-11-19 | 2026-11-21 | 2026-12-12 |  | 0.5 | 0.42 | 7 | 35 | 735 | 2.0408 | 105.1893 |  | 20
6-05 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 3500 | 0 | 3500 | 122.5 | 2026-11-13 | 2026-11-14 | 2026-11-17 | 2026-11-21 | 2026-11-23 | 2026-12-12 |  | 1 | 0.42 | 8.6 | 35 | 1806 | 1.938 | 210.3787 |  | 18
6-05 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 5000 | 0 | 5000 | 175 | 2026-11-13 | 2026-11-17 | 2026-11-19 | 2026-11-24 | 2026-11-26 | 2026-12-12 |  | 1.2 | 0.42 | 8.6 | 35 | 2167.2 | 2.3071 | 252.4544 |  | 16
6-05 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 7000 | 0 | 7000 | 245 | 2026-11-13 | 2026-11-19 | 2026-11-21 | 2026-11-27 | 2026-11-29 | 2026-12-12 |  | 1.4 | 0.42 | 8.6 | 35 | 2528.4 | 2.7685 | 294.5302 |  | 13
6-05 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 10000 | 0 | 10000 | 350 | 2026-11-13 | 2026-11-23 | 2026-11-25 | 2026-12-01 | 2026-12-03 | 2026-12-12 |  | 1.6 | 0.42 | 8.6 | 35 | 2889.6 | 3.4607 | 336.6059 |  | 10
6-05 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 10000 | 0 | 10000 | 350 | 2026-11-13 | 2026-11-26 | 2026-11-28 | 2026-12-04 | 2026-12-06 | 2026-12-12 |  | 1.8 | 0.42 | 8.6 | 35 | 3250.8 | 3.0762 | 378.6816 |  | 7
6-05 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 25000 | 0 | 25000 | 875 | 2026-11-13 | 2026-11-30 | 2026-12-02 | 2026-12-12 | 2026-12-14 | 2026-12-12 |  | 2 | 0.42 | 8.6 | 35 | 3612 | 6.9214 | 420.7574 |  | 0
6-05 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0328 |  |  | 70000 | 0 | 70000 | 2450 | 2026-12-11 | 2026-12-08 | 2026-12-10 | 2027-01-06 | 2027-01-08 | 2027-01-09 |  | 2 | 0.42 | 8.6 | 35 | 3612 | 19.3798 | 420.7574 |  | 3
6-05 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0425 |  |  | 73189 | 0 | 73189 | 2561.615 | 2027-01-08 | 2026-12-31 | 2027-01-04 | 2027-01-29 | 2027-01-31 | 2027-02-06 |  | 2 | 0.42 | 8.6 | 35 | 3612 | 20.2627 | 420.7574 |  | 7
2026-04-12
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 24866 | 24866 | 0 | 2175.775 | 2026-04-13 | 2026-04-08 | 2026-04-10 | 2026-05-06 | 2026-05-11 | 2026-06-25 |  | 1.592 | 1.05 | 8.7258 | 36.5651 | 1219.0291 | 20.3982 | 139.9557 |  | 39
6-06 | ONY | 890955_FA26 | Pull On Pants |  | all po |  |  | 7023 | 7023 | 0 | 550.135 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-15 | 2026-05-17 | 2026-06-04 |  | 1.2371 | 0.94 | 8.5835 | 36.7291 | 1045.603 | 6.7167 | 122.0354 |  | 15
6-06 | ONY | 905200_FA26 | Pull On Pants |  | all po |  |  | 26558 | 26558 | 0 | 2478.7467 | 2026-05-02 | 2026-05-09 | 2026-05-12 | 2026-06-17 | 2026-06-19 | 2026-06-11 |  | 1.3726 | 1.12 | 9.4741 | 36.0936 | 1056.0642 | 25.1481 | 111.6698 |  | -6
6-06 | ONY | 890955_FA26 | Pull On Pants |  | all po |  |  | 3293 | 3293 | 0 | 257.9517 | 2026-04-13 | 2026-06-11 | 2026-06-13 | 2026-06-20 | 2026-06-22 | 2026-07-16 |  | 1.2036 | 0.94 | 9.4007 | 36.6757 | 1112.5004 | 2.96 | 118.5556 |  | 22
6-06 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 25055 | 25055 | 0 | 2192.3125 | 2026-05-26 | 2026-06-15 | 2026-06-18 | 2026-07-10 | 2026-07-15 | 2026-07-16 |  | 1.9617 | 1.05 | 9.4584 | 33.9307 | 1510.9939 | 16.5818 | 160.0393 |  | 5
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 29586 | 29586 | 0 | 2588.775 | 2026-06-23 | 2026-07-06 | 2026-07-08 | 2026-08-04 | 2026-08-09 | 2026-09-24 |  | 1.9974 | 1.05 | 8.1876 | 36.0189 | 1413.7104 | 20.9279 | 172.977 |  | 35
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 38318 | 37973 | 345 | 3352.825 | 2026-08-01 | 2026-07-30 | 2026-08-01 | 2026-09-07 | 2026-09-12 | 2026-10-15 |  | 2.19 | 1.05 | 9 | 36.8624 | 1743.7409 | 21.9746 | 194.0984 |  | 30
6-06 | ONY | 777362_HO26_GLD | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 62212924, 927, 931, 933 |  |  | 6081 | 4939 | 1142 | 532.0875 | 2026-08-29 | 2026-09-01 | 2026-09-03 | 2026-09-11 | 2026-09-16 | 2026-09-24 |  | 2.01 | 1.05 | 9 | 36.8624 | 1600.4197 | 3.7996 | 178.1451 |  | 9
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 30000 | 0 | 30000 | 2625 | 2026-08-01 | 2026-09-07 | 2026-09-09 | 2026-10-05 | 2026-10-10 | 2026-10-15 |  | 2.2 | 1.05 | 9 | 36.8624 | 1751.7031 | 17.1262 | 194.9847 |  | 9
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 4880 | 0 | 4880 | 427 | 2026-08-01 | 2026-09-30 | 2026-10-02 | 2026-10-08 | 2026-10-13 | 2026-10-15 |  | 2.2 | 1.05 | 8.6 | 36.8624 | 1673.8497 | 2.9154 | 194.9847 |  | 6
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.29 |  |  | 330 | 0 | 330 | 28.875 | 2026-08-18 | 2026-10-03 | 2026-10-06 | 2026-10-08 | 2026-10-13 | 2026-10-29 |  | 2.2 | 1.05 | 8.6 | 36.8624 | 1673.8497 | 0.19715 | 194.9847 |  | 18
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 11.12 |  |  | 8954 | 0 | 8954 | 783.475 | 2026-08-20 | 2026-10-03 | 2026-10-06 | 2026-10-14 | 2026-10-19 | 2026-11-12 |  | 2.2 | 1.05 | 8.6 | 36.8624 | 1673.8497 | 5.3493 | 194.9847 |  | 25
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 11.26 |  |  | 330 | 0 | 330 | 28.875 | 2026-08-20 | 2026-10-09 | 2026-10-12 | 2026-10-14 | 2026-10-19 | 2026-11-26 |  | 2.2 | 1.05 | 8.6 | 36.8624 | 1673.8497 | 0.19715 | 194.9847 |  | 37
6-06 | ONY | 1204591_SP27_ID | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 11.06 |  |  | 750 | 0 | 750 | 80 | 2026-10-12 | 2026-10-09 | 2026-10-12 | 2026-10-17 | 2026-10-22 | 2026-11-06 |  | 0.5 | 1.28 | 7 | 36.8624 | 254.0053 | 2.9527 | 36.3519 |  | 17
6-06 | ONY | 1204591_SP27_ID | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 11.06 |  |  | 1750 | 0 | 1750 | 186.6667 | 2026-10-12 | 2026-10-13 | 2026-10-15 | 2026-10-21 | 2026-10-26 | 2026-11-06 |  | 1 | 1.28 | 8.6 | 36.8624 | 624.1272 | 2.8039 | 72.7038 |  | 14
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 720 | 0 | 720 | 43.2 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-23 | 2026-10-25 | 2026-11-06 |  | 0.5 | 0.72 | 7 | 36.8624 | 451.5649 | 1.5945 | 64.6256 |  | 12
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 1500 | 0 | 1500 | 90 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 2026-10-24 | 2026-10-26 | 2026-11-06 |  | 1 | 0.72 | 8.6 | 36.8624 | 1109.5594 | 1.3519 | 129.2512 |  | 11
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 2000 | 0 | 2000 | 120 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-10-27 | 2026-10-29 | 2026-11-06 |  | 1.2 | 0.72 | 8.6 | 36.8624 | 1331.4713 | 1.5021 | 155.1014 |  | 9
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 3000 | 0 | 3000 | 180 | 2026-10-15 | 2026-10-22 | 2026-10-24 | 2026-10-29 | 2026-10-31 | 2026-11-06 |  | 1.4 | 0.72 | 8.6 | 36.8624 | 1553.3832 | 1.9313 | 180.9517 |  | 7
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 4000 | 0 | 4000 | 240 | 2026-10-15 | 2026-10-24 | 2026-10-27 | 2026-10-31 | 2026-11-02 | 2026-11-06 |  | 1.6 | 0.72 | 8.6 | 36.8624 | 1775.2951 | 2.2531 | 206.8019 |  | 5
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 5000 | 0 | 5000 | 300 | 2026-10-15 | 2026-10-27 | 2026-10-29 | 2026-11-04 | 2026-11-06 | 2026-11-06 |  | 1.8 | 0.72 | 8.6 | 36.8624 | 1997.207 | 2.5035 | 232.6521 |  | 2
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 12.10 |  |  | 884 | 0 | 884 | 77.35 | 2026-08-20 | 2026-10-30 | 2026-11-02 | 2026-11-05 | 2026-11-10 | 2026-12-10 |  | 1 | 1.05 | 7 | 36.8624 | 619.289 | 1.4274 | 88.6294 |  | 30
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 12.10 |  |  | 1500 | 0 | 1500 | 131.25 | 2026-08-20 | 2026-10-31 | 2026-11-03 | 2026-11-07 | 2026-11-12 | 2026-12-10 |  | 1.3 | 1.05 | 8.6 | 36.8624 | 989.093 | 1.5165 | 115.2182 |  | 28
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 12.10 |  |  | 2000 | 0 | 2000 | 175 | 2026-08-20 | 2026-11-03 | 2026-11-05 | 2026-11-10 | 2026-11-15 | 2026-12-10 |  | 1.5 | 1.05 | 8.6 | 36.8624 | 1141.2611 | 1.7524 | 132.9441 |  | 26
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 12.10 |  |  | 3000 | 0 | 3000 | 262.5 | 2026-08-20 | 2026-11-05 | 2026-11-07 | 2026-11-12 | 2026-11-17 | 2026-12-10 |  | 1.6 | 1.05 | 8.6 | 36.8624 | 1217.3452 | 2.4644 | 141.807 |  | 24
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 12.10 |  |  | 3000 | 0 | 3000 | 262.5 | 2026-08-20 | 2026-11-07 | 2026-11-10 | 2026-11-14 | 2026-11-19 | 2026-12-10 |  | 1.8 | 1.05 | 8.6 | 36.8624 | 1369.5134 | 2.1906 | 159.5329 |  | 22
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 12.24 |  |  | 1518 | 0 | 1518 | 132.825 | 2026-08-20 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-21 | 2026-12-24 |  | 2 | 1.05 | 8.6 | 36.8624 | 1521.6815 | 0.99758 | 177.2588 |  | 33
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 01.07 |  |  | 506 | 0 | 506 | 44.275 | 2026-08-20 | 2026-11-11 | 2026-11-13 | 2026-11-16 | 2026-11-21 | 2027-01-07 |  | 2 | 1.05 | 8.6 | 36.8624 | 1521.6815 | 0.33253 | 177.2588 |  | 43
6-06 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 728 | 0 | 728 | 57.0267 | 2026-11-09 | 2026-11-07 | 2026-11-13 | 2026-11-18 | 2026-11-20 | 2026-12-03 |  | 0.5 | 0.94 | 7 | 36.8624 | 345.8795 | 2.1048 | 49.5005 |  | 13
6-06 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 1500 | 0 | 1500 | 117.5 | 2026-11-09 | 2026-11-10 | 2026-11-16 | 2026-11-20 | 2026-11-22 | 2026-12-03 |  | 1 | 0.94 | 8.6 | 36.8624 | 849.8753 | 1.765 | 99.0009 |  | 11
6-06 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 2500 | 0 | 2500 | 195.8333 | 2026-11-09 | 2026-11-12 | 2026-11-18 | 2026-11-24 | 2026-11-26 | 2026-12-03 |  | 1.1 | 0.94 | 8.6 | 36.8624 | 934.8629 | 2.6742 | 108.901 |  | 8
6-06 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 3500 | 0 | 3500 | 274.1667 | 2026-11-09 | 2026-11-16 | 2026-11-21 | 2026-11-27 | 2026-11-29 | 2026-12-03 |  | 1.2 | 0.94 | 8.6 | 36.8624 | 1019.8504 | 3.4319 | 118.8011 |  | 5
6-06 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 5300 | 0 | 5300 | 415.1667 | 2026-11-09 | 2026-11-19 | 2026-11-25 | 2026-12-02 | 2026-12-04 | 2026-12-03 |  | 1.4 | 0.94 | 8.6 | 36.8624 | 1189.8254 | 4.4544 | 138.6013 |  | 1
6-06 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1210, 4500041655_BJSHVS_1210, 4500041655_BJSHVS_HTR_1210, 4500041657_HTR_1210 |  |  | 5000 | 0 | 5000 | 391.6667 | 2026-11-09 | 2026-11-24 | 2026-11-30 | 2026-12-07 | 2026-12-09 | 2026-12-10 |  | 1.6 | 0.94 | 8.6 | 36.8624 | 1359.8005 | 3.677 | 158.4015 |  | 3
6-06 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1210, 4500041655_BJSHVS_1210, 4500041655_BJSHVS_HTR_1210, 4500041657_HTR_1210 |  |  | 6484 | 0 | 6484 | 507.9133 | 2026-11-09 | 2026-11-28 | 2026-12-04 | 2026-12-11 | 2026-12-13 | 2026-12-10 |  | 1.8 | 0.94 | 8.6 | 36.8624 | 1529.7756 | 4.2385 | 178.2016 |  | -3
2026-06-05
6-07 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 24374 | 24374 | 0 | 2823.3217 | 2026-06-03 | 2026-05-30 | 2026-06-03 | 2026-07-09 | 2026-07-11 | 2026-07-09 |  | 1.4647 | 1.39 | 9.211 | 35.496 | 868.1993 | 28.0742 | 94.4264 |  | 0
6-07 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 11906 | 11906 | 0 | 1041.775 | 2026-05-07 | 2026-07-04 | 2026-07-07 | 2026-07-23 | 2026-07-28 | 2026-07-30 |  | 1.5471 | 1.05 | 8.2762 | 33.6826 | 1035.0792 | 11.5025 | 125.2931 |  | 6
6-07 | HLF | CPM263PA05_26Q4 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 17364 | 17364 | 0 | 1750.87 | 2026-07-10 | 2026-07-15 | 2026-07-21 | 2026-08-24 | 2026-08-26 | 2026-08-21 |  | 1.304 | 1.21 | 7.6793 | 36.2259 | 755.5279 | 22.9826 | 98.5623 |  | -3
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014226_TRN |  |  | 2160 | 2160 | 0 | 129.6 | 2026-08-15 | 2026-08-12 | 2026-08-20 | 2026-08-27 | 2026-08-29 | 2026-10-01 |  | 0.88104 | 0.72 | 8 | 36.1737 | 892.3775 | 2.4205 | 111.7483 |  | 25
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002008674_SET |  |  | 13794 | 13794 | 0 | 827.64 | 2026-08-24 | 2026-08-14 | 2026-08-24 | 2026-09-08 | 2026-09-10 | 2026-10-08 |  | 1.5488 | 0.72 | 8.7773 | 37 | 1760.4271 | 7.8356 | 200.9276 |  | 23
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014233 |  |  | 5496 | 5496 | 0 | 329.76 | 2026-08-22 | 2026-08-28 | 2026-09-04 | 2026-09-10 | 2026-09-12 | 2026-10-12 |  | 1.9029 | 0.72 | 9 | 37.6268 | 2255.4172 | 2.4368 | 251.0538 |  | 24
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014232 |  |  | 7296 | 1043 | 6253 | 437.76 | 2026-08-18 | 2026-09-01 | 2026-09-08 | 2026-09-15 | 2026-09-17 | 2026-10-24 |  | 1.79 | 0.72 | 9 | 37 | 2086.245 | 3.4972 | 232.223 |  | 32
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014238 |  |  | 4536 | 0 | 4536 | 272.16 | 2026-08-22 | 2026-09-04 | 2026-09-11 | 2026-09-17 | 2026-09-19 | 2026-10-26 |  | 2 | 0.72 | 9 | 37 | 2331 | 1.9459 | 259.467 |  | 31
6-07 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014298_SET_1212, 10002014297_T1_1212 |  |  | 1350 | 0 | 1350 | 94.5 | 2026-08-22 | 2026-09-08 | 2026-09-15 | 2026-09-18 | 2026-09-20 | 2026-10-01 |  | 1.2 | 0.84 | 9 | 37 | 1198.8 | 1.1261 | 133.4402 |  | 9
6-07 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014298_SET_1212, 10002014297_T1_1212 |  |  | 2550 | 0 | 2550 | 178.5 | 2026-08-22 | 2026-09-09 | 2026-09-16 | 2026-09-22 | 2026-09-24 | 2026-10-01 |  | 1.5 | 0.84 | 9 | 37 | 1498.5 | 1.7017 | 166.8002 |  | 7
6-07 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014298_SET_1212, 10002014297_T1_1212 |  |  | 5000 | 0 | 5000 | 350 | 2026-08-22 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-09-27 | 2026-10-01 |  | 1.8 | 0.84 | 9 | 37 | 1798.2 | 2.7806 | 200.1603 |  | 4
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014236 |  |  | 4200 | 0 | 4200 | 252 | 2026-08-24 | 2026-09-16 | 2026-09-23 | 2026-09-29 | 2026-10-01 | 2026-11-07 |  | 2 | 0.72 | 9 | 37 | 2331 | 1.8018 | 259.467 |  | 34
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014237 |  |  | 3624 | 0 | 3624 | 217.44 | 2026-08-29 | 2026-09-18 | 2026-09-25 | 2026-10-01 | 2026-10-03 | 2026-11-09 |  | 2 | 0.72 | 9 | 37 | 2331 | 1.5547 | 259.467 |  | 33
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014235 |  |  | 4872 | 0 | 4872 | 292.32 | 2026-08-29 | 2026-09-22 | 2026-09-29 | 2026-10-03 | 2026-10-05 | 2026-11-21 |  | 2 | 0.72 | 8.6 | 37 | 2227.4 | 2.1873 | 259.467 |  | 42
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014240 |  |  | 3624 | 0 | 3624 | 217.44 | 2026-09-05 | 2026-09-24 | 2026-10-01 | 2026-10-06 | 2026-10-08 | 2026-11-23 |  | 2 | 0.72 | 8.6 | 37 | 2227.4 | 1.627 | 259.467 |  | 41
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014239 |  |  | 4872 | 0 | 4872 | 292.32 | 2026-09-05 | 2026-09-28 | 2026-10-03 | 2026-10-08 | 2026-10-10 | 2026-12-05 |  | 2 | 0.72 | 8.6 | 37 | 2227.4 | 2.1873 | 259.467 |  | 50
6-07 | ONY | 1194432_SP27 | Tee |  | 62344810 |  |  | 761 | 0 | 761 | 40.5867 | 2026-10-09 | 2026-10-03 | 2026-10-06 | 2026-10-09 | 2026-10-11 | 2026-10-28 |  | 0.5 | 0.64 | 7 | 37.461 | 516.2597 | 1.4741 | 73.8844 |  | 16
6-07 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 1586 | 0 | 1586 | 84.5867 | 2026-10-09 | 2026-10-05 | 2026-10-07 | 2026-10-10 | 2026-10-12 | 2026-10-29 |  | 1 | 0.64 | 8.6 | 37.461 | 1268.5238 | 1.2503 | 147.7688 |  | 16
6-07 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 2500 | 0 | 2500 | 133.3333 | 2026-10-09 | 2026-10-06 | 2026-10-08 | 2026-10-13 | 2026-10-15 | 2026-10-29 |  | 1.2 | 0.64 | 8.6 | 37.461 | 1522.2285 | 1.6423 | 177.3225 |  | 14
6-07 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 3500 | 0 | 3500 | 186.6667 | 2026-10-09 | 2026-10-08 | 2026-10-10 | 2026-10-15 | 2026-10-17 | 2026-10-29 |  | 1.4 | 0.64 | 8.6 | 37.461 | 1775.9333 | 1.9708 | 206.8762 |  | 12
6-07 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 4000 | 0 | 4000 | 213.3333 | 2026-10-09 | 2026-10-10 | 2026-10-13 | 2026-10-17 | 2026-10-19 | 2026-10-29 |  | 1.6 | 0.64 | 8.6 | 37.461 | 2029.6381 | 1.9708 | 236.43 |  | 10
6-07 | ONY | 1194432_SP27 | Tee |  | 62344978 |  |  | 288 | 0 | 288 | 15.36 | 2026-10-09 | 2026-10-13 | 2026-10-15 | 2026-10-17 | 2026-10-19 | 2026-11-04 |  | 1.8 | 0.64 | 8.6 | 37.461 | 2283.3428 | 0.12613 | 265.9837 |  | 15
6-07 | ONY | 1194432_SP27 | Tee |  | 62323026, 027, 733, 738, 744, 745 |  |  | 15000 | 0 | 15000 | 800 | 2026-10-09 | 2026-10-13 | 2026-10-15 | 2026-10-26 | 2026-10-28 | 2026-11-05 |  | 1.8 | 0.64 | 8.6 | 37.461 | 2283.3428 | 6.5693 | 265.9837 |  | 9
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0214_E |  |  | 751 | 0 | 751 | 57.5767 | 2026-10-17 | 2026-10-21 | 2026-10-23 | 2026-10-28 | 2026-10-30 | 2026-11-16 |  | 0.5 | 0.92 | 7 | 37.461 | 359.1372 | 2.0911 | 51.3978 |  | 16
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0214_E |  |  | 1500 | 0 | 1500 | 115 | 2026-10-17 | 2026-10-23 | 2026-10-26 | 2026-10-30 | 2026-11-01 | 2026-11-16 |  | 1 | 0.92 | 8.6 | 37.461 | 882.4513 | 1.6998 | 102.7957 |  | 14
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0214_E |  |  | 3200 | 0 | 3200 | 245.3333 | 2026-10-17 | 2026-10-26 | 2026-10-28 | 2026-11-03 | 2026-11-05 | 2026-11-16 |  | 1.1 | 0.92 | 8.6 | 37.461 | 970.6965 | 3.2966 | 113.0752 |  | 11
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_E |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-10-24 | 2026-10-29 | 2026-10-31 | 2026-11-09 | 2026-11-11 | 2026-11-23 |  | 1.2 | 0.92 | 8.6 | 37.461 | 1058.9416 | 4.7217 | 123.3548 |  | 12
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_E |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-10-24 | 2026-11-04 | 2026-11-06 | 2026-11-13 | 2026-11-15 | 2026-11-23 |  | 1.4 | 0.92 | 8.6 | 37.461 | 1235.4319 | 4.0472 | 143.9139 |  | 8
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_E |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-10-24 | 2026-11-09 | 2026-11-11 | 2026-11-18 | 2026-11-20 | 2026-11-23 |  | 1.6 | 0.92 | 8.6 | 37.461 | 1411.9221 | 3.5413 | 164.473 |  | 4
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_E |  |  | 6812 | 0 | 6812 | 522.2533 | 2026-10-24 | 2026-11-13 | 2026-11-16 | 2026-11-23 | 2026-11-25 | 2026-11-23 |  | 1.8 | 0.92 | 8.6 | 37.461 | 1588.4124 | 4.2886 | 185.0322 |  | 0
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_W |  |  | 14360 | 0 | 14360 | 1100.9333 | 2026-10-31 | 2026-11-18 | 2026-11-20 | 2026-12-02 | 2026-12-04 | 2026-12-03 |  | 2 | 0.92 | 8.6 | 37.461 | 1764.9027 | 8.1364 | 205.5913 |  | 1
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0307_E |  |  | 5904 | 0 | 5904 | 452.64 | 2026-10-31 | 2026-11-27 | 2026-11-30 | 2026-12-05 | 2026-12-07 | 2026-12-07 |  | 2 | 0.92 | 8.6 | 37.461 | 1764.9027 | 3.3452 | 205.5913 |  | 1
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0307_W |  |  | 13634 | 0 | 13634 | 1045.2733 | 2026-10-31 | 2026-12-01 | 2026-12-03 | 2026-12-15 | 2026-12-17 | 2026-12-17 |  | 2 | 0.92 | 8.6 | 37.461 | 1764.9027 | 7.7251 | 205.5913 |  | 2
2026-04-22
6-08 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 43947 | 43947 | 0 | 3845.3625 | 2026-05-07 | 2026-04-17 | 2026-04-20 | 2026-06-02 | 2026-06-07 | 2026-07-30 |  | 1.6982 | 1.05 | 9.3938 | 37.476 | 1434.8257 | 30.6288 | 153.0167 |  | 49
6-08 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 7260 | 7260 | 0 | 635.25 | 2026-05-26 | 2026-05-26 | 2026-05-29 | 2026-06-09 | 2026-06-14 | 2026-07-09 |  | 1.6754 | 1.05 | 8.7363 | 37.2525 | 1308.6032 | 5.5479 | 150.0591 |  | 25
6-08 | ONY | 766362_V1 | Pull On Pants |  | all po Juni, Juli, Agustus |  |  | 39555 | 39555 | 0 | 2834.775 | 2026-05-22 | 2026-06-04 | 2026-06-06 | 2026-07-13 | 2026-07-15 | 2026-10-08 |  | 1.4081 | 0.86 | 9.3671 | 37.1994 | 1437.6838 | 27.513 | 153.7592 |  | 65
6-08 | ONY | 766362_HO26 | Pull On Pants |  | all po |  |  | 43769 | 43769 | 0 | 3136.7783 | 2026-08-04 | 2026-07-08 | 2026-07-10 | 2026-08-19 | 2026-08-21 | 2026-11-05 |  | 1.7416 | 0.86 | 7.985 | 37.6745 | 1535.2206 | 28.5099 | 192.6093 |  | 60
6-08 | ONY | 766362_V1 | Pull On Pants |  | 10.08 |  |  | 10549 | 10549 | 0 | 756.0117 | 2026-05-22 | 2026-08-12 | 2026-08-14 | 2026-08-31 | 2026-09-02 | 2026-10-08 |  | 1.7658 | 0.86 | 7.9478 | 37.9015 | 1558.6804 | 6.7679 | 196.4674 |  | 29
6-08 | ONY | 766362_V1 | Pull On Pants |  | 10.28 |  |  | 5346 | 5346 | 0 | 383.13 | 2026-05-22 | 2026-08-24 | 2026-08-27 | 2026-09-07 | 2026-09-09 | 2026-10-28 |  | 1.1699 | 0.86 | 8.2043 | 38.3749 | 1079.3018 | 4.9532 | 131.7911 |  | 41
6-08 | SMA | PST840 | Pull On Pants |  | 1352813, _AH |  |  | 3708 | 3056 | 652 | 503.67 | 2026-08-18 | 2026-09-01 | 2026-09-03 | 2026-09-14 | 2026-09-16 | 2026-09-22 |  | 1.46 | 1.63 | 9 | 38 | 771.9548 | 4.8034 | 85.9274 |  | 6
6-08 | SMA | PST840 | Pull On Pants |  | 1354809_SS, _AH |  |  | 79 | 0 | 79 | 10.7308 | 2026-08-18 | 2026-09-08 | 2026-09-10 | 2026-09-14 | 2026-09-16 | 2026-09-23 |  | 1.5 | 1.63 | 9 | 38 | 793.1043 | 0.099609 | 88.2816 |  | 7
6-08 | SMA | PST840 | Pull On Pants |  | 1352814, _AH |  |  | 6438 | 0 | 6438 | 874.495 | 2026-08-24 | 2026-09-08 | 2026-09-10 | 2026-09-24 | 2026-09-26 | 2026-10-02 |  | 1.5 | 1.63 | 9 | 38 | 793.1043 | 8.1175 | 88.2816 |  | 6
6-08 | SMA | PST840 | Pull On Pants |  | 1352815, _AH |  |  | 2876 | 0 | 2876 | 390.6567 | 2026-09-14 | 2026-09-18 | 2026-09-22 | 2026-09-30 | 2026-10-02 | 2026-11-02 |  | 1.5 | 1.63 | 9 | 38 | 793.1043 | 3.6263 | 88.2816 |  | 28
6-08 | SMA | PST840 | Pull On Pants |  | 1352815, _AH |  |  | 7000 | 0 | 7000 | 950.8333 | 2026-09-14 | 2026-09-24 | 2026-09-28 | 2026-10-10 | 2026-10-12 | 2026-11-02 |  | 1.5 | 1.63 | 8.6 | 38 | 757.8552 | 9.2366 | 88.2816 |  | 19
6-08 | SMA | PST840 | Pull On Pants |  | 1352816, _AH |  |  | 2500 | 0 | 2500 | 339.5833 | 2026-09-14 | 2026-10-06 | 2026-10-08 | 2026-10-14 | 2026-10-16 | 2026-12-03 |  | 1.5 | 1.63 | 8.6 | 38 | 757.8552 | 3.2988 | 88.2816 |  | 43
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 1140 | 0 | 1140 | 28.5 | 2026-10-13 | 2026-10-09 | 2026-10-12 | 2026-10-15 | 2026-10-17 | 2026-11-14 |  | 0.5 | 0.3 | 7 | 37.8178 | 1111.8424 | 1.0253 | 159.1211 |  | 26
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 2500 | 0 | 2500 | 62.5 | 2026-10-13 | 2026-10-10 | 2026-10-13 | 2026-10-16 | 2026-10-18 | 2026-11-14 |  | 1 | 0.3 | 8.6 | 37.8178 | 2731.9557 | 0.9151 | 318.2421 |  | 25
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 3500 | 0 | 3500 | 87.5 | 2026-10-13 | 2026-10-12 | 2026-10-14 | 2026-10-17 | 2026-10-19 | 2026-11-14 |  | 1.2 | 0.3 | 8.6 | 37.8178 | 3278.3468 | 1.0676 | 381.8905 |  | 24
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 5000 | 0 | 5000 | 125 | 2026-10-13 | 2026-10-13 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 2026-11-14 |  | 1.4 | 0.3 | 8.6 | 37.8178 | 3824.738 | 1.3073 | 445.5389 |  | 23
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 10000 | 0 | 10000 | 250 | 2026-10-13 | 2026-10-14 | 2026-10-16 | 2026-10-21 | 2026-10-23 | 2026-11-14 |  | 1.6 | 0.3 | 8.6 | 37.8178 | 4371.1291 | 2.2877 | 509.1874 |  | 21
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 10000 | 0 | 10000 | 250 | 2026-10-13 | 2026-10-16 | 2026-10-19 | 2026-10-23 | 2026-10-25 | 2026-11-14 |  | 1.8 | 0.3 | 8.6 | 37.8178 | 4917.5203 | 2.0335 | 572.8358 |  | 19
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 84140 | 0 | 84140 | 2103.5 | 2026-10-13 | 2026-10-19 | 2026-10-21 | 2026-11-10 | 2026-11-12 | 2026-11-14 |  | 2 | 0.3 | 8.6 | 37.8178 | 5463.9114 | 15.3992 | 636.4842 |  | 4
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0130_TRN |  |  | 2088 | 0 | 2088 | 52.2 | 2026-10-27 | 2026-11-05 | 2026-11-07 | 2026-11-10 | 2026-11-12 | 2026-11-18 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 0.3474 | 700.1326 |  | 7
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0213_BA |  |  | 18216 | 0 | 18216 | 455.4 | 2026-10-27 | 2026-11-05 | 2026-11-07 | 2026-11-13 | 2026-11-15 | 2026-12-03 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 3.0308 | 700.1326 |  | 17
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0220_BA |  |  | 17784 | 0 | 17784 | 444.6 | 2026-10-27 | 2026-11-09 | 2026-11-11 | 2026-11-17 | 2026-11-19 | 2026-12-09 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 2.9589 | 700.1326 |  | 19
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0227_BA |  |  | 17784 | 0 | 17784 | 444.6 | 2026-10-27 | 2026-11-12 | 2026-11-14 | 2026-11-20 | 2026-11-22 | 2026-12-16 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 2.9589 | 700.1326 |  | 22
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0306_BA |  |  | 17784 | 0 | 17784 | 444.6 | 2026-10-27 | 2026-11-16 | 2026-11-18 | 2026-11-24 | 2026-11-26 | 2026-12-23 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 2.9589 | 700.1326 |  | 25
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0313_BA |  |  | 17784 | 0 | 17784 | 444.6 | 2026-10-27 | 2026-11-19 | 2026-11-21 | 2026-11-27 | 2026-11-29 | 2026-12-30 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 2.9589 | 700.1326 |  | 27
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-11-23 | 2026-11-25 | 2026-11-30 | 2026-12-05 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 37.8178 | 362.5573 | 2.2479 | 51.8873 |  | 21
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-11-25 | 2026-11-27 | 2026-12-02 | 2026-12-07 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 37.8178 | 890.8551 | 1.6838 | 103.7746 |  | 19
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-11-27 | 2026-11-30 | 2026-12-05 | 2026-12-10 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 37.8178 | 979.9406 | 2.5512 | 114.1521 |  | 16
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-01 | 2026-12-03 | 2026-12-09 | 2026-12-14 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 37.8178 | 1069.0261 | 2.8063 | 124.5295 |  | 13
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4942 | 0 | 4942 | 378.8867 | 2026-12-07 | 2026-12-04 | 2026-12-07 | 2026-12-14 | 2026-12-19 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 37.8178 | 1158.1117 | 4.2673 | 134.907 |  | 14
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-12-07 | 2026-12-09 | 2026-12-11 | 2026-12-18 | 2026-12-23 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 37.8178 | 1247.1972 | 4.009 | 145.2844 |  | 10
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 11600 | 0 | 11600 | 889.3333 | 2026-12-07 | 2026-12-14 | 2026-12-16 | 2026-12-30 | 2027-01-04 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 8.6808 | 155.6619 |  | 1
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-24 | 2026-12-28 | 2026-12-31 | 2027-01-05 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 1.4398 | 155.6619 |  | 11
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-26 | 2026-12-29 | 2027-01-08 | 2027-01-13 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 5.8341 | 155.6619 |  | 11
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-04 | 2027-01-06 | 2027-01-14 | 2027-01-19 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 4.9458 | 155.6619 |  | 12
2026-05-20
6-09 | TGT | G9M018_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 65630 | 65630 | 0 | 4648.7917 | 2026-05-25 | 2026-05-11 | 2026-05-18 | 2026-07-04 | 2026-07-06 | 2026-07-11 |  | 1.8566 | 0.85 | 9.5019 | 35.1267 | 1837.1199 | 35.7244 | 193.6912 |  | 6
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874451_BA_E |  |  | 171876 | 171876 | 0 | 3151.06 | 2026-06-27 | 2026-06-26 | 2026-07-02 | 2026-07-25 | 2026-07-27 | 2026-08-05 |  | 2.8155 | 0.22 | 8.2809 | 35.8848 | 9583.592 | 17.9344 | 1159.3956 |  | 9
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874422_TRN_W |  |  | 8820 | 8820 | 0 | 161.7 | 2026-06-27 | 2026-07-17 | 2026-07-23 | 2026-07-27 | 2026-07-29 | 2026-08-13 |  | 2.7968 | 0.22 | 5.7489 | 36.7452 | 6767.434 | 1.3033 | 1179.2848 |  | 14
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874468_BA_E |  |  | 50484 | 50484 | 0 | 925.54 | 2026-06-27 | 2026-07-18 | 2026-07-24 | 2026-08-01 | 2026-08-03 | 2026-08-19 |  | 3.1087 | 0.22 | 7.8624 | 36.8167 | 10307.4771 | 4.8978 | 1313.3442 |  | 12
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874454_BA_E |  |  | 43596 | 43596 | 0 | 799.26 | 2026-07-04 | 2026-07-24 | 2026-07-30 | 2026-08-06 | 2026-08-08 | 2026-08-26 |  | 3.1177 | 0.22 | 7.4896 | 36.8259 | 9849.5364 | 4.4262 | 1317.4754 |  | 12
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874439_BA_E |  |  | 107016 | 107016 | 0 | 1961.96 | 2026-07-01 | 2026-07-29 | 2026-08-04 | 2026-08-21 | 2026-08-23 | 2026-09-02 |  | 3.0555 | 0.22 | 8.0034 | 36.8073 | 10310.2236 | 10.3796 | 1290.5535 |  | 7
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874453_BA_E |  |  | 42420 | 42420 | 0 | 777.7 | 2026-07-11 | 2026-08-11 | 2026-08-19 | 2026-08-28 | 2026-08-30 | 2026-09-09 |  | 3.1185 | 0.22 | 9 | 36.5442 | 11748.7388 | 3.6106 | 1307.7694 |  | 8
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874469_BA_E |  |  | 28896 | 28896 | 0 | 529.76 | 2026-07-08 | 2026-08-18 | 2026-08-26 | 2026-09-01 | 2026-09-03 | 2026-10-07 |  | 3.1658 | 0.22 | 9 | 36.4113 | 11883.5329 | 2.4316 | 1322.7735 |  | 27
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874471_BA_E |  |  | 55356 | 55356 | 0 | 1014.86 | 2026-07-11 | 2026-08-20 | 2026-08-28 | 2026-09-08 | 2026-09-10 | 2026-10-14 |  | 3.0441 | 0.22 | 9 | 37.1892 | 11670.8478 | 4.7431 | 1299.0992 |  | 28
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874444_BA_E |  |  | 49392 | 26080 | 23312 | 905.52 | 2026-07-11 | 2026-08-28 | 2026-09-04 | 2026-09-14 | 2026-09-16 | 2026-10-21 |  | 2.82 | 0.22 | 9 | 37.8178 | 10994.2446 | 4.4925 | 1223.7855 |  | 30
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874473_BA_E |  |  | 49560 | 0 | 49560 | 908.6 | 2026-07-11 | 2026-09-03 | 2026-09-10 | 2026-09-18 | 2026-09-20 | 2026-11-04 |  | 2.9 | 0.22 | 9 | 37.8178 | 11306.138 | 4.3835 | 1258.5029 |  | 38
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021697_T1 |  |  | 704 | 0 | 704 | 64.5333 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 2026-09-22 | 2026-09-24 | 2026-10-22 |  | 0.5 | 1.1 | 7 | 37.8178 | 303.2298 | 2.3217 | 43.3967 |  | 25
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021697_T1 |  |  | 1800 | 0 | 1800 | 165 | 2026-09-08 | 2026-09-16 | 2026-09-18 | 2026-09-24 | 2026-09-26 | 2026-10-22 |  | 1 | 1.1 | 9 | 37.8178 | 779.7337 | 2.3085 | 86.7933 |  | 23
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 2666 | 0 | 2666 | 244.3833 | 2026-09-08 | 2026-09-18 | 2026-09-22 | 2026-09-29 | 2026-10-01 | 2026-10-29 |  | 1.1 | 1.1 | 9 | 37.8178 | 857.707 | 3.1083 | 95.4726 |  | 26
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 3000 | 0 | 3000 | 275 | 2026-09-08 | 2026-09-23 | 2026-09-25 | 2026-10-02 | 2026-10-04 | 2026-10-29 |  | 1.2 | 1.1 | 8.6 | 37.8178 | 894.0946 | 3.3553 | 104.152 |  | 23
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 3500 | 0 | 3500 | 320.8333 | 2026-09-08 | 2026-09-28 | 2026-09-30 | 2026-10-06 | 2026-10-08 | 2026-10-29 |  | 1.4 | 1.1 | 8.6 | 37.8178 | 1043.1104 | 3.3553 | 121.5106 |  | 20
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021703 |  |  | 4440 | 0 | 4440 | 407 | 2026-09-08 | 2026-10-01 | 2026-10-03 | 2026-10-10 | 2026-10-12 | 2026-11-18 |  | 1.6 | 1.1 | 8.6 | 37.8178 | 1192.1261 | 3.7244 | 138.8693 |  | 33
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021703 |  |  | 5000 | 0 | 5000 | 458.3333 | 2026-09-08 | 2026-10-06 | 2026-10-08 | 2026-10-15 | 2026-10-17 | 2026-11-18 |  | 1.8 | 1.1 | 8.6 | 37.8178 | 1341.1419 | 3.7282 | 156.2279 |  | 29
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021702 |  |  | 12160 | 0 | 12160 | 1114.6667 | 2026-09-08 | 2026-10-10 | 2026-10-13 | 2026-10-26 | 2026-10-28 | 2026-12-02 |  | 1.8 | 1.1 | 8.6 | 37.8178 | 1341.1419 | 9.0669 | 156.2279 |  | 32
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021705 |  |  | 7584 | 0 | 7584 | 695.2 | 2026-09-08 | 2026-10-21 | 2026-10-23 | 2026-11-02 | 2026-11-04 | 2026-12-16 |  | 1.8 | 1.1 | 8.6 | 37.8178 | 1341.1419 | 5.6549 | 156.2279 |  | 38
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0130_TRN |  |  | 2940 | 0 | 2940 | 53.9 | 2026-10-13 | 2026-10-24 | 2026-10-30 | 2026-11-04 | 2026-11-06 | 2026-11-18 |  | 0.5 | 0.22 | 7 | 37.8178 | 1516.1488 | 1.9391 | 216.9833 |  | 12
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0206_BA |  |  | 10000 | 0 | 10000 | 183.3333 | 2026-10-13 | 2026-10-27 | 2026-11-02 | 2026-11-07 | 2026-11-09 | 2026-11-25 |  | 1 | 0.22 | 8.6 | 37.8178 | 3725.3941 | 2.6843 | 433.9665 |  | 15
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0206_BA |  |  | 15000 | 0 | 15000 | 275 | 2026-10-13 | 2026-10-30 | 2026-11-05 | 2026-11-11 | 2026-11-13 | 2026-11-25 |  | 1.5 | 0.22 | 8.6 | 37.8178 | 5588.0912 | 2.6843 | 650.9498 |  | 12
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0206_BA |  |  | 17244 | 0 | 17244 | 316.14 | 2026-10-13 | 2026-11-03 | 2026-11-09 | 2026-11-13 | 2026-11-15 | 2026-11-25 |  | 2 | 0.22 | 8.6 | 37.8178 | 7450.7883 | 2.3144 | 867.933 |  | 10
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0206_BA |  |  | 20000 | 0 | 20000 | 366.6667 | 2026-10-13 | 2026-11-05 | 2026-11-11 | 2026-11-16 | 2026-11-18 | 2026-11-25 |  | 2.5 | 0.22 | 8.6 | 37.8178 | 9313.4854 | 2.1474 | 1084.9163 |  | 8
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0213_BA |  |  | 16548 | 0 | 16548 | 303.38 | 2026-10-13 | 2026-11-07 | 2026-11-13 | 2026-11-18 | 2026-11-20 | 2026-12-02 |  | 2.7 | 0.22 | 8.6 | 37.8178 | 10058.5642 | 1.6452 | 1171.7096 |  | 12
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0220_BA |  |  | 16548 | 0 | 16548 | 303.38 | 2026-10-27 | 2026-11-10 | 2026-11-16 | 2026-11-20 | 2026-11-22 | 2026-12-09 |  | 2.8 | 0.22 | 8.6 | 37.8178 | 10431.1036 | 1.5864 | 1215.1062 |  | 16
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0227_BA |  |  | 16548 | 0 | 16548 | 303.38 | 2026-10-27 | 2026-11-12 | 2026-11-18 | 2026-11-23 | 2026-11-25 | 2026-12-16 |  | 2.9 | 0.22 | 8.6 | 37.8178 | 10803.643 | 1.5317 | 1258.5029 |  | 20
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0306_BA |  |  | 16548 | 0 | 16548 | 303.38 | 2026-10-27 | 2026-11-14 | 2026-11-20 | 2026-11-25 | 2026-11-27 | 2026-12-23 |  | 2.9 | 0.22 | 8.6 | 37.8178 | 10803.643 | 1.5317 | 1258.5029 |  | 24
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0313_BA |  |  | 16548 | 0 | 16548 | 303.38 | 2026-10-27 | 2026-11-17 | 2026-11-23 | 2026-11-27 | 2026-11-29 | 2026-12-30 |  | 2.9 | 0.22 | 8.6 | 37.8178 | 10803.643 | 1.5317 | 1258.5029 |  | 27
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-11-23 | 2026-11-25 | 2026-11-30 | 2026-12-05 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 37.8178 | 362.5573 | 2.2479 | 51.8873 |  | 21
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-11-25 | 2026-11-27 | 2026-12-02 | 2026-12-07 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 37.8178 | 890.8551 | 1.6838 | 103.7746 |  | 19
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-11-27 | 2026-11-30 | 2026-12-05 | 2026-12-10 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 37.8178 | 979.9406 | 2.5512 | 114.1521 |  | 16
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-01 | 2026-12-03 | 2026-12-09 | 2026-12-14 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 37.8178 | 1069.0261 | 2.8063 | 124.5295 |  | 13
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4042 | 0 | 4042 | 309.8867 | 2026-12-07 | 2026-12-04 | 2026-12-07 | 2026-12-12 | 2026-12-17 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 37.8178 | 1158.1117 | 3.4902 | 134.907 |  | 15
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4000 | 0 | 4000 | 306.6667 | 2026-12-07 | 2026-12-08 | 2026-12-10 | 2026-12-16 | 2026-12-21 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 37.8178 | 1247.1972 | 3.2072 | 145.2844 |  | 12
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 14540 | 0 | 14540 | 1114.7333 | 2026-12-07 | 2026-12-11 | 2026-12-14 | 2026-12-30 | 2027-01-04 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 10.8809 | 155.6619 |  | 1
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-24 | 2026-12-28 | 2026-12-31 | 2027-01-05 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 1.4398 | 155.6619 |  | 11
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-26 | 2026-12-29 | 2027-01-08 | 2027-01-13 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 5.8341 | 155.6619 |  | 11
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-04 | 2027-01-06 | 2027-01-14 | 2027-01-19 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 4.9458 | 155.6619 |  | 12
2026-04-17
6-10 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 15160 | 15160 | 0 | 1326.5 | 2026-04-25 | 2026-04-13 | 2026-04-15 | 2026-05-05 | 2026-05-10 | 2026-06-04 |  | 1.4219 | 1.05 | 8.5757 | 37.7094 | 1103.5488 | 13.7375 | 128.9159 |  | 23
6-10 | ONY | 962148_FA26 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | all po |  |  | 4540 | 4540 | 0 | 211.8667 | 2026-04-15 | 2026-04-29 | 2026-05-02 | 2026-05-09 | 2026-05-11 | 2026-08-06 |  | 0.88245 | 0.56 | 8.0175 | 38 | 1209.8277 | 3.7526 | 151.1709 |  | 72
6-10 | ONY | 905200_FA26 | Pull On Pants |  | all po |  |  | 57498 | 57498 | 0 | 5366.48 | 2026-05-15 | 2026-05-05 | 2026-05-07 | 2026-07-14 | 2026-07-16 | 2026-07-16 |  | 1.4275 | 1.12 | 9.3511 | 36.6522 | 1100.8636 | 52.2299 | 117.9376 |  | 2
6-10 | TGT | X25413_C426 | Pull On Pants |  | all po |  |  | 3123 | 3123 | 0 | 379.965 | 2026-07-06 | 2026-07-09 | 2026-07-11 | 2026-07-20 | 2026-07-22 | 2026-08-15 |  | 1.2038 | 1.46 | 7.7928 | 35.9876 | 582.7032 | 5.3595 | 74.9092 |  | 21
6-10 | ONY | 826369_HO26 | Pull On Pants |  | all po |  |  | 2235 | 2235 | 0 | 167.625 | 2026-07-13 | 2026-07-15 | 2026-07-17 | 2026-07-24 | 2026-07-26 | 2026-08-13 |  | 0.82751 | 0.9 | 7.2576 | 37.0282 | 622.6666 | 3.5894 | 85.9499 |  | 16
6-10 | ONY | 1184403_HO26 | Pull On Pants |  | all po |  |  | 7414 | 7414 | 0 | 716.6867 | 2026-07-13 | 2026-07-20 | 2026-07-22 | 2026-08-10 | 2026-08-12 | 2026-08-20 |  | 0.95783 | 1.16 | 7.2192 | 37.4439 | 562.4717 | 13.1811 | 78.0539 |  | 7
6-10 | ONY | 1182719_HO26 | Skorts |  | all po |  |  | 23350 | 23350 | 0 | 1148.0417 | 2026-07-11 | 2026-08-04 | 2026-08-06 | 2026-09-01 | 2026-09-03 | 2026-08-27 |  | 1.2859 | 0.59 | 8 | 37.7782 | 1659.9607 | 14.0666 | 207.8692 |  | -5
6-10 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 20253 | 18613 | 1640 | 894.5075 | 2026-08-06 | 2026-08-26 | 2026-08-28 | 2026-09-11 | 2026-09-13 | 2026-09-17 |  | 1.55 | 0.53 | 9 | 38 | 2520.4755 | 8.0354 | 280.5578 |  | 4
6-10 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 9074 | 0 | 9074 | 400.7683 | 2026-08-06 | 2026-09-07 | 2026-09-09 | 2026-09-16 | 2026-09-18 | 2026-09-17 |  | 1.6 | 0.53 | 9 | 38 | 2601.7811 | 3.4876 | 289.6081 |  | 1
6-10 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016283, 292, 296 |  |  | 4000 | 0 | 4000 | 176.6667 | 2026-08-06 | 2026-09-10 | 2026-09-14 | 2026-09-18 | 2026-09-20 | 2026-10-15 |  | 1.6 | 0.53 | 9 | 38 | 2601.7811 | 1.5374 | 289.6081 |  | 21
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 728 | 0 | 728 | 59.4533 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 2026-09-22 | 2026-09-27 | 2026-10-01 |  | 0.5 | 0.98 | 7 | 38 | 342 | 2.1287 | 48.9452 |  | 7
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 1500 | 0 | 1500 | 122.5 | 2026-09-07 | 2026-09-16 | 2026-09-18 | 2026-09-24 | 2026-09-29 | 2026-10-01 |  | 1 | 0.98 | 9 | 38 | 879.4286 | 1.7057 | 97.8905 |  | 5
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 2700 | 0 | 2700 | 220.5 | 2026-09-07 | 2026-09-18 | 2026-09-22 | 2026-09-29 | 2026-10-04 | 2026-10-01 |  | 1.2 | 0.98 | 9 | 38 | 1055.3143 | 2.5585 | 117.4686 |  | 2
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62239979, 378, 565, 268, 269 |  |  | 1503 | 0 | 1503 | 122.745 | 2026-09-07 | 2026-09-23 | 2026-09-25 | 2026-09-30 | 2026-10-05 | 2026-10-08 |  | 1.4 | 0.98 | 8.6 | 38 | 1176.48 | 1.2775 | 137.0467 |  | 7
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 4500 | 0 | 4500 | 367.5 | 2026-09-07 | 2026-09-24 | 2026-09-28 | 2026-10-03 | 2026-10-08 | 2026-10-15 |  | 1.6 | 0.98 | 8.6 | 38 | 1344.5486 | 3.3468 | 156.6248 |  | 10
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 6250 | 0 | 6250 | 510.4167 | 2026-09-07 | 2026-09-29 | 2026-10-01 | 2026-10-08 | 2026-10-13 | 2026-10-15 |  | 1.8 | 0.98 | 8.6 | 38 | 1512.6171 | 4.1319 | 176.2029 |  | 6
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 960 | 0 | 960 | 25.6 | 2026-10-12 | 2026-10-03 | 2026-10-06 | 2026-10-09 | 2026-10-11 | 2026-11-02 |  | 0.5 | 0.32 | 7 | 38 | 1047.375 | 0.91658 | 149.8948 |  | 20
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 1500 | 0 | 1500 | 40 | 2026-10-12 | 2026-10-05 | 2026-10-07 | 2026-10-10 | 2026-10-12 | 2026-11-02 |  | 1 | 0.32 | 8.6 | 38 | 2573.55 | 0.58285 | 299.7896 |  | 19
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 2500 | 0 | 2500 | 66.6667 | 2026-10-12 | 2026-10-06 | 2026-10-08 | 2026-10-12 | 2026-10-14 | 2026-11-02 |  | 1.1 | 0.32 | 8.6 | 38 | 2830.905 | 0.88311 | 329.7686 |  | 18
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 3500 | 0 | 3500 | 93.3333 | 2026-10-12 | 2026-10-07 | 2026-10-09 | 2026-10-13 | 2026-10-15 | 2026-11-02 |  | 1.2 | 0.32 | 8.6 | 38 | 3088.26 | 1.1333 | 359.7475 |  | 17
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 4500 | 0 | 4500 | 120 | 2026-10-12 | 2026-10-08 | 2026-10-10 | 2026-10-14 | 2026-10-16 | 2026-11-02 |  | 1.3 | 0.32 | 8.6 | 38 | 3345.615 | 1.345 | 389.7265 |  | 16
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0130_W |  |  | 1044 | 0 | 1044 | 27.84 | 2026-10-20 | 2026-10-09 | 2026-10-12 | 2026-10-14 | 2026-10-16 | 2026-11-11 |  | 1.4 | 0.32 | 8.6 | 38 | 3602.97 | 0.28976 | 419.7055 |  | 24
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 5000 | 0 | 5000 | 133.3333 | 2026-10-12 | 2026-10-09 | 2026-10-12 | 2026-10-15 | 2026-10-17 | 2026-11-12 |  | 1.6 | 0.32 | 8.6 | 38 | 4117.68 | 1.2143 | 479.6634 |  | 24
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 7000 | 0 | 7000 | 186.6667 | 2026-10-12 | 2026-10-10 | 2026-10-13 | 2026-10-17 | 2026-10-19 | 2026-11-12 |  | 1.8 | 0.32 | 8.6 | 38 | 4632.39 | 1.5111 | 539.6213 |  | 22
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 33180 | 0 | 33180 | 884.8 | 2026-10-12 | 2026-10-13 | 2026-10-15 | 2026-10-24 | 2026-10-26 | 2026-11-12 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 6.4463 | 599.5792 |  | 16
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0213_W |  |  | 9108 | 0 | 9108 | 242.88 | 2026-10-20 | 2026-10-20 | 2026-10-22 | 2026-10-27 | 2026-10-29 | 2026-11-25 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7695 | 599.5792 |  | 25
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0220_W |  |  | 8892 | 0 | 8892 | 237.12 | 2026-10-27 | 2026-10-22 | 2026-10-24 | 2026-10-29 | 2026-10-31 | 2026-12-02 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7276 | 599.5792 |  | 29
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0227_W |  |  | 8892 | 0 | 8892 | 237.12 | 2026-10-27 | 2026-10-24 | 2026-10-27 | 2026-10-31 | 2026-11-02 | 2026-12-09 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7276 | 599.5792 |  | 33
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0306_W |  |  | 8892 | 0 | 8892 | 237.12 | 2026-10-27 | 2026-10-27 | 2026-10-29 | 2026-11-03 | 2026-11-05 | 2026-12-16 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7276 | 599.5792 |  | 37
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_W |  |  | 860 | 0 | 860 | 65.9333 | 2026-10-31 | 2026-10-29 | 2026-10-31 | 2026-11-05 | 2026-11-07 | 2026-12-03 |  | 0.5 | 0.92 | 7 | 38 | 364.3043 | 2.3607 | 52.1373 |  | 24
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_W |  |  | 1500 | 0 | 1500 | 115 | 2026-10-31 | 2026-10-31 | 2026-11-03 | 2026-11-07 | 2026-11-09 | 2026-12-03 |  | 1 | 0.92 | 8.6 | 38 | 895.1478 | 1.6757 | 104.2747 |  | 22
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_W |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-10-31 | 2026-11-03 | 2026-11-05 | 2026-11-11 | 2026-11-13 | 2026-12-03 |  | 1.1 | 0.92 | 8.6 | 38 | 984.6626 | 2.5389 | 114.7021 |  | 19
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_W |  |  | 3000 | 0 | 3000 | 230 | 2026-10-31 | 2026-11-06 | 2026-11-09 | 2026-11-14 | 2026-11-16 | 2026-12-03 |  | 1.2 | 0.92 | 8.6 | 38 | 1074.1774 | 2.7928 | 125.1296 |  | 16
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_W |  |  | 4000 | 0 | 4000 | 306.6667 | 2026-10-31 | 2026-11-10 | 2026-11-12 | 2026-11-18 | 2026-11-20 | 2026-12-03 |  | 1.4 | 0.92 | 8.6 | 38 | 1253.207 | 3.1918 | 145.9845 |  | 13
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_W |  |  | 6500 | 0 | 6500 | 498.3333 | 2026-10-31 | 2026-11-13 | 2026-11-16 | 2026-11-24 | 2026-11-26 | 2026-12-03 |  | 1.6 | 0.92 | 8.6 | 38 | 1432.2365 | 4.5384 | 166.8394 |  | 8
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0307_E |  |  | 15904 | 0 | 15904 | 1219.3067 | 2026-10-31 | 2026-11-19 | 2026-11-21 | 2026-12-05 | 2026-12-07 | 2026-12-07 |  | 1.8 | 0.92 | 8.6 | 38 | 1611.2661 | 9.8705 | 187.6944 |  | 1
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0307_W |  |  | 13634 | 0 | 13634 | 1045.2733 | 2026-10-31 | 2026-12-01 | 2026-12-03 | 2026-12-15 | 2026-12-17 | 2026-12-17 |  | 2 | 0.92 | 8.6 | 38 | 1790.2957 | 7.6155 | 208.5493 |  | 2
2026-05-19
6-11 | TGT | MRLPMM_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 98283 | 98283 | 0 | 7371.225 | 2026-06-08 | 2026-05-09 | 2026-05-16 | 2026-08-04 | 2026-08-06 | 2026-08-22 |  | 2.1566 | 0.9 | 8.7955 | 29.273 | 1554.7148 | 63.2161 | 177.0823 |  | 12
6-11 | ONY | 1182719_HO26 | Skorts |  | all po |  |  | 17407 | 17407 | 0 | 855.8442 | 2026-07-11 | 2026-07-30 | 2026-08-01 | 2026-08-26 | 2026-08-28 | 2026-08-27 |  | 1.242 | 0.59 | 8 | 30.358 | 1288.3006 | 13.5116 | 161.328 |  | 1
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004922_T1_W |  |  | 720 | 720 | 0 | 63.6 | 2026-08-24 | 2026-08-13 | 2026-08-21 | 2026-08-27 | 2026-08-29 | 2026-10-01 |  | 0.88836 | 1.06 | 8 | 29.4464 | 497.5125 | 1.4472 | 62.3012 |  | 25
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 21000 | 9826 | 11174 | 1855 | 2026-08-24 | 2026-08-14 | 2026-08-24 | 2026-09-23 | 2026-09-25 | 2026-10-08 |  | 1.63 | 1.06 | 9 | 31 | 1081.1513 | 19.4237 | 120.3445 |  | 12
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004937_BA_E |  |  | 6792 | 0 | 6792 | 599.96 | 2026-09-10 | 2026-09-14 | 2026-09-21 | 2026-09-30 | 2026-10-02 | 2026-10-12 |  | 2 | 1.06 | 9 | 31 | 1326.566 | 5.12 | 147.662 |  | 10
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004936_BA_E |  |  | 7078 | 0 | 7078 | 625.2233 | 2026-08-29 | 2026-09-21 | 2026-09-28 | 2026-10-07 | 2026-10-09 | 2026-10-24 |  | 2 | 1.06 | 8.6 | 31 | 1267.6075 | 5.5837 | 147.662 |  | 15
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004947_BA_E |  |  | 6792 | 0 | 6792 | 599.96 | 2026-09-05 | 2026-09-29 | 2026-10-05 | 2026-10-13 | 2026-10-15 | 2026-10-26 |  | 2 | 1.06 | 8.6 | 31 | 1267.6075 | 5.3581 | 147.662 |  | 11
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004946_BA_E |  |  | 9078 | 0 | 9078 | 801.89 | 2026-09-05 | 2026-10-05 | 2026-10-10 | 2026-10-21 | 2026-10-23 | 2026-11-07 |  | 2 | 1.06 | 8.6 | 31 | 1267.6075 | 7.1615 | 147.662 |  | 15
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004950_BA_E |  |  | 3792 | 0 | 3792 | 334.96 | 2026-09-05 | 2026-10-13 | 2026-10-19 | 2026-10-24 | 2026-10-26 | 2026-11-09 |  | 2 | 1.06 | 8.6 | 31 | 1267.6075 | 2.9915 | 147.662 |  | 13
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004948_BA_E |  |  | 9078 | 0 | 9078 | 801.89 | 2026-09-05 | 2026-10-16 | 2026-10-22 | 2026-11-02 | 2026-11-04 | 2026-11-21 |  | 2 | 1.06 | 8.6 | 31 | 1267.6075 | 7.1615 | 147.662 |  | 17
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004939_BA_E |  |  | 6792 | 0 | 6792 | 599.96 | 2026-09-05 | 2026-10-24 | 2026-10-30 | 2026-11-07 | 2026-11-09 | 2026-11-23 |  | 2 | 1.06 | 8.6 | 31 | 1267.6075 | 5.3581 | 147.662 |  | 13
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004938_BA_E |  |  | 8928 | 0 | 8928 | 788.64 | 2026-09-05 | 2026-10-30 | 2026-11-05 | 2026-11-16 | 2026-11-18 | 2026-12-05 |  | 2 | 1.06 | 8.6 | 31 | 1267.6075 | 7.0432 | 147.662 |  | 17
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 580 | 0 | 580 | 25.1333 | 2026-10-24 | 2026-11-11 | 2026-11-13 | 2026-11-17 | 2026-11-19 | 2026-11-27 |  | 0.5 | 0.52 | 7 | 31 | 525.8077 | 1.1031 | 75.2508 |  | 9
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 1500 | 0 | 1500 | 65 | 2026-10-24 | 2026-11-12 | 2026-11-14 | 2026-11-18 | 2026-11-20 | 2026-11-27 |  | 1 | 0.52 | 8.6 | 31 | 1291.9846 | 1.161 | 150.5017 |  | 8
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 2500 | 0 | 2500 | 108.3333 | 2026-10-24 | 2026-11-13 | 2026-11-16 | 2026-11-20 | 2026-11-22 | 2026-11-27 |  | 1.2 | 0.52 | 8.6 | 31 | 1550.3815 | 1.6125 | 180.602 |  | 6
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 3000 | 0 | 3000 | 130 | 2026-10-24 | 2026-11-16 | 2026-11-18 | 2026-11-23 | 2026-11-25 | 2026-11-27 |  | 1.4 | 0.52 | 8.6 | 31 | 1808.7785 | 1.6586 | 210.7023 |  | 4
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_W |  |  | 5000 | 0 | 5000 | 216.6667 | 2026-10-26 | 2026-11-18 | 2026-11-20 | 2026-11-25 | 2026-11-27 | 2026-12-08 |  | 1.6 | 0.52 | 8.6 | 31 | 2067.1754 | 2.4188 | 240.8027 |  | 11
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_W |  |  | 7000 | 0 | 7000 | 303.3333 | 2026-10-26 | 2026-11-20 | 2026-11-23 | 2026-11-28 | 2026-11-30 | 2026-12-08 |  | 1.8 | 0.52 | 8.6 | 31 | 2325.5723 | 3.01 | 270.903 |  | 8
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_W |  |  | 18318 | 0 | 18318 | 793.78 | 2026-10-26 | 2026-11-24 | 2026-11-26 | 2026-12-07 | 2026-12-09 | 2026-12-08 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 7.0891 | 301.0033 |  | 1
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0328_E |  |  | 3138 | 0 | 3138 | 135.98 | 2026-11-02 | 2026-12-02 | 2026-12-04 | 2026-12-08 | 2026-12-10 | 2026-12-24 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 1.2144 | 301.0033 |  | 14
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0328_W |  |  | 12548 | 0 | 12548 | 543.7467 | 2026-11-02 | 2026-12-03 | 2026-12-05 | 2026-12-14 | 2026-12-16 | 2027-01-05 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 4.8561 | 301.0033 |  | 17
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0425_E |  |  | 6266 | 0 | 6266 | 271.5267 | 2026-11-09 | 2026-12-09 | 2026-12-11 | 2026-12-16 | 2026-12-18 | 2027-01-22 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 2.425 | 301.0033 |  | 30
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0425_W |  |  | 25066 | 0 | 25066 | 1086.1933 | 2026-11-09 | 2026-12-11 | 2026-12-14 | 2026-12-29 | 2026-12-31 | 2027-02-02 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 9.7006 | 301.0033 |  | 29
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0530_E |  |  | 1880 | 0 | 1880 | 81.4667 | 2026-11-16 | 2026-12-23 | 2026-12-26 | 2026-12-30 | 2027-01-01 | 2027-02-26 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 0.72756 | 301.0033 |  | 49
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0530_W |  |  | 7522 | 0 | 7522 | 325.9533 | 2026-11-16 | 2026-12-24 | 2026-12-28 | 2027-01-04 | 2027-01-06 | 2027-03-09 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 2.911 | 301.0033 |  | 55
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0627_E |  |  | 3138 | 0 | 3138 | 135.98 | 2026-11-23 | 2026-12-29 | 2026-12-31 | 2027-01-05 | 2027-01-07 | 2027-03-26 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 1.2144 | 301.0033 |  | 69
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0627_W |  |  | 12548 | 0 | 12548 | 543.7467 | 2026-11-23 | 2026-12-30 | 2027-01-02 | 2027-01-11 | 2027-01-13 | 2027-04-06 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 4.8561 | 301.0033 |  | 73
2026-04-23
6-12 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 36158 | 36158 | 0 | 3163.825 | 2026-05-04 | 2026-04-18 | 2026-04-21 | 2026-05-26 | 2026-05-31 | 2026-07-23 |  | 1.6893 | 1.05 | 9.1441 | 37.1237 | 1376.3212 | 26.2715 | 150.7858 |  | 47
6-12 | ONY | 907938_FA26 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | all po |  |  | 1178 | 1178 | 0 | 89.3317 | 2026-05-07 | 2026-05-21 | 2026-05-23 | 2026-05-29 | 2026-05-31 | 2026-06-11 |  | 0.65017 | 0.91 | 7.881 | 35.392 | 502.1956 | 2.3457 | 63.837 |  | 10
6-12 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 31999 | 31999 | 0 | 3706.5508 | 2026-06-03 | 2026-05-23 | 2026-05-26 | 2026-07-09 | 2026-07-11 | 2026-07-09 |  | 1.5521 | 1.39 | 9.4353 | 36.0815 | 957.9881 | 33.4023 | 101.7153 |  | 0
6-12 | ONY | 910047_HO26DIS | Pajama |  | all po |  |  | 27677 | 27677 | 0 | 3275.1117 | 2026-07-06 | 2026-07-04 | 2026-07-07 | 2026-08-13 | 2026-08-15 | 2026-09-03 |  | 1.7232 | 1.42 | 8.2028 | 37.8066 | 948.3748 | 29.1836 | 115.8242 |  | 13
6-12 | TGT | X25413_C426 | Pull On Pants |  | all po |  |  | 3075 | 3075 | 0 | 374.125 | 2026-07-06 | 2026-08-07 | 2026-08-11 | 2026-08-26 | 2026-08-28 | 2026-09-01 |  | 0.88558 | 1.46 | 8 | 37.3443 | 456.6583 | 6.7337 | 57.1852 |  | 4
6-12 | KOH | ZC6HY000 | Gown |  | 16439999, 00, 001 |  |  | 18169 | 17198 | 971 | 999.295 | 2026-07-30 | 2026-08-19 | 2026-08-21 | 2026-09-11 | 2026-09-13 | 2026-09-28 |  | 1.16 | 0.66 | 9 | 38.2541 | 1524.8768 | 11.9151 | 169.7363 |  | 11
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021697_T1 |  |  | 704 | 0 | 704 | 64.5333 | 2026-09-08 | 2026-09-07 | 2026-09-09 | 2026-09-15 | 2026-09-17 | 2026-10-22 |  | 0.5 | 1.1 | 7 | 38.2541 | 306.7281 | 2.2952 | 43.8973 |  | 30
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021697_T1 |  |  | 1800 | 0 | 1800 | 165 | 2026-09-08 | 2026-09-09 | 2026-09-11 | 2026-09-17 | 2026-09-19 | 2026-10-22 |  | 1 | 1.1 | 9 | 38.2541 | 788.7294 | 2.2822 | 87.7946 |  | 28
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021697_T1 |  |  | 2504 | 0 | 2504 | 229.5333 | 2026-09-08 | 2026-09-11 | 2026-09-15 | 2026-09-22 | 2026-09-24 | 2026-10-22 |  | 1.1 | 1.1 | 9 | 38.2541 | 867.6023 | 2.8861 | 96.5741 |  | 25
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 2666 | 0 | 2666 | 244.3833 | 2026-09-08 | 2026-09-16 | 2026-09-18 | 2026-09-25 | 2026-09-27 | 2026-10-29 |  | 1.2 | 1.1 | 9 | 38.2541 | 946.4752 | 2.8168 | 105.3536 |  | 28
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 3000 | 0 | 3000 | 275 | 2026-09-08 | 2026-09-21 | 2026-09-23 | 2026-09-30 | 2026-10-02 | 2026-10-29 |  | 1.4 | 1.1 | 9 | 38.2541 | 1104.2211 | 2.7168 | 122.9125 |  | 25
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 3500 | 0 | 3500 | 320.8333 | 2026-09-08 | 2026-09-24 | 2026-09-28 | 2026-10-03 | 2026-10-05 | 2026-10-29 |  | 1.6 | 1.1 | 8.6 | 38.2541 | 1205.8796 | 2.9024 | 140.4714 |  | 22
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 9166 | 0 | 9166 | 840.2167 | 2026-09-08 | 2026-09-29 | 2026-10-01 | 2026-10-12 | 2026-10-14 | 2026-10-29 |  | 1.8 | 1.1 | 8.6 | 38.2541 | 1356.6145 | 6.7565 | 158.0303 |  | 15
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021703 |  |  | 12880 | 0 | 12880 | 1180.6667 | 2026-09-08 | 2026-10-07 | 2026-10-09 | 2026-10-22 | 2026-10-24 | 2026-11-18 |  | 1.8 | 1.1 | 8.6 | 38.2541 | 1356.6145 | 9.4942 | 158.0303 |  | 23
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021702 |  |  | 10160 | 0 | 10160 | 931.3333 | 2026-09-08 | 2026-10-17 | 2026-10-20 | 2026-10-30 | 2026-11-01 | 2026-12-02 |  | 1.8 | 1.1 | 8.6 | 38.2541 | 1356.6145 | 7.4892 | 158.0303 |  | 28
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021705 |  |  | 14737 | 0 | 14737 | 1350.8917 | 2026-09-08 | 2026-10-26 | 2026-10-28 | 2026-11-12 | 2026-11-14 | 2026-12-16 |  | 1.8 | 1.1 | 8.6 | 38.2541 | 1356.6145 | 10.8631 | 158.0303 |  | 29
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021704 |  |  | 22320 | 0 | 22320 | 2046 | 2026-09-15 | 2026-11-07 | 2026-11-10 | 2026-12-01 | 2026-12-03 | 2026-12-30 |  | 1.8 | 1.1 | 8.6 | 38.2541 | 1356.6145 | 16.4527 | 158.0303 |  | 24
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021707 |  |  | 22320 | 0 | 22320 | 2046 | 2026-11-16 | 2026-11-26 | 2026-11-28 | 2026-12-19 | 2026-12-21 | 2027-01-13 |  | 1.8 | 1.1 | 8.6 | 38.2541 | 1356.6145 | 16.4527 | 158.0303 |  | 19
2026-07-04
6-13 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 15589 | 15589 | 0 | 1364.0375 | 2026-05-26 | 2026-06-30 | 2026-07-02 | 2026-07-20 | 2026-07-25 | 2026-07-30 |  | 1.5565 | 1.05 | 9.3933 | 34.0142 | 1193.554 | 13.061 | 127.2931 |  | 9
6-13 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 10000 | 10000 | 0 | 875 | 2026-06-23 | 2026-07-15 | 2026-07-17 | 2026-07-30 | 2026-08-04 | 2026-08-20 |  | 1.7463 | 1.05 | 7.9762 | 33.0413 | 1104.5568 | 9.0534 | 138.7318 |  | 15
6-13 | ONY | 1182723_HO26 | Skorts |  | all po |  |  | 32276 | 32276 | 0 | 2447.5967 | 2026-07-14 | 2026-07-25 | 2026-07-28 | 2026-09-08 | 2026-09-10 | 2026-10-01 |  | 1.5586 | 0.91 | 7.8718 | 34.6897 | 1178.6229 | 27.3845 | 149.9965 |  | 17
6-13 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 18847 | 11444 | 7403 | 832.4092 | 2026-08-06 | 2026-09-02 | 2026-09-04 | 2026-09-18 | 2026-09-20 | 2026-09-17 |  | 1.56 | 0.53 | 9 | 35 | 2336.4679 | 8.0664 | 260.0757 |  | -3
6-13 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016283, 292, 296 |  |  | 17338 | 0 | 17338 | 765.7617 | 2026-08-06 | 2026-09-14 | 2026-09-16 | 2026-09-30 | 2026-10-02 | 2026-10-15 |  | 1.5 | 0.53 | 9 | 35 | 2246.6038 | 7.7174 | 250.0728 |  | 13
6-13 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016287 |  |  | 7319 | 0 | 7319 | 323.2558 | 2026-08-06 | 2026-09-24 | 2026-09-28 | 2026-10-03 | 2026-10-05 | 2026-11-12 |  | 1.5 | 0.53 | 9 | 35 | 2246.6038 | 3.2578 | 250.0728 |  | 34
6-13 | ONY | 1194432_SP27 | Tee |  | 62344810 |  |  | 761 | 0 | 761 | 40.5867 | 2026-10-09 | 2026-09-29 | 2026-10-01 | 2026-10-06 | 2026-10-08 | 2026-10-28 |  | 0.5 | 0.64 | 7 | 35 | 482.3438 | 1.5777 | 69.0305 |  | 19
6-13 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 1586 | 0 | 1586 | 84.5867 | 2026-10-09 | 2026-10-01 | 2026-10-03 | 2026-10-07 | 2026-10-09 | 2026-10-29 |  | 1 | 0.64 | 8.6 | 35 | 1185.1875 | 1.3382 | 138.061 |  | 19
6-13 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 2500 | 0 | 2500 | 133.3333 | 2026-10-09 | 2026-10-02 | 2026-10-05 | 2026-10-09 | 2026-10-11 | 2026-10-29 |  | 1.2 | 0.64 | 8.6 | 35 | 1422.225 | 1.7578 | 165.6732 |  | 17
6-13 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 3500 | 0 | 3500 | 186.6667 | 2026-10-09 | 2026-10-05 | 2026-10-07 | 2026-10-12 | 2026-10-14 | 2026-10-29 |  | 1.4 | 0.64 | 8.6 | 35 | 1659.2625 | 2.1094 | 193.2854 |  | 15
6-13 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 4000 | 0 | 4000 | 213.3333 | 2026-10-09 | 2026-10-07 | 2026-10-09 | 2026-10-14 | 2026-10-16 | 2026-10-29 |  | 1.6 | 0.64 | 8.6 | 35 | 1896.3 | 2.1094 | 220.8976 |  | 13
6-13 | ONY | 1194432_SP27 | Tee |  | 62344978 |  |  | 288 | 0 | 288 | 15.36 | 2026-10-09 | 2026-10-09 | 2026-10-12 | 2026-10-14 | 2026-10-16 | 2026-11-04 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 0.135 | 248.5098 |  | 18
6-13 | ONY | 1194432_SP27 | Tee |  | 62323026, 027, 733, 738, 744, 745 |  |  | 32475 | 0 | 32475 | 1732 | 2026-10-09 | 2026-10-09 | 2026-10-12 | 2026-10-31 | 2026-11-02 | 2026-11-05 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 15.2226 | 248.5098 |  | 4
6-13 | ONY | 1194432_SP27 | Tee |  | 62377441, 442, 182, 113, 170, 255 |  |  | 6632 | 0 | 6632 | 353.7067 | 2026-11-13 | 2026-10-27 | 2026-10-29 | 2026-11-04 | 2026-11-06 | 2026-11-26 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 3.1087 | 248.5098 |  | 19
6-13 | ONY | 1194432_SP27 | Tee |  | 62344833 |  |  | 126 | 0 | 126 | 6.72 | 2026-11-13 | 2026-10-30 | 2026-11-02 | 2026-11-04 | 2026-11-06 | 2026-12-02 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 0.059062 | 248.5098 |  | 24
6-13 | ONY | 1194432_SP27 | Tee |  | 62379115 |  |  | 30924 | 0 | 30924 | 1649.28 | 2026-11-06 | 2026-10-30 | 2026-11-02 | 2026-11-20 | 2026-11-22 | 2026-12-03 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 14.4956 | 248.5098 |  | 11
6-13 | ONY | 1194432_SP27 | Tee |  | 12.24 |  |  | 5933 | 0 | 5933 | 316.4267 | 2026-11-30 | 2026-11-16 | 2026-11-18 | 2026-11-24 | 2026-11-26 | 2026-12-24 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 2.7811 | 248.5098 |  | 26
6-13 | ONY | 1194432_SP27 | Tee |  | 12.31 |  |  | 13279 | 0 | 13279 | 708.2133 | 2026-11-30 | 2026-11-19 | 2026-11-21 | 2026-12-01 | 2026-12-03 | 2026-12-31 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 6.2245 | 248.5098 |  | 25
6-13 | ONY | 1194432_SP27 | Tee |  | 01.21 |  |  | 4451 | 0 | 4451 | 237.3867 | 2026-11-30 | 2026-11-26 | 2026-11-28 | 2026-12-03 | 2026-12-05 | 2027-01-21 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 2.0864 | 248.5098 |  | 40
6-13 | ONY | 1194432_SP27 | Tee |  | 01.28 |  |  | 9889 | 0 | 9889 | 527.4133 | 2026-11-30 | 2026-11-28 | 2026-12-01 | 2026-12-09 | 2026-12-11 | 2027-01-28 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 4.6355 | 248.5098 |  | 41
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-12-04 | 2026-12-07 | 2026-12-11 | 2026-12-16 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 35 | 335.5435 | 2.4289 | 48.0212 |  | 11
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-12-07 | 2026-12-09 | 2026-12-14 | 2026-12-19 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 35 | 824.4783 | 1.8193 | 96.0424 |  | 9
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-12-09 | 2026-12-11 | 2026-12-17 | 2026-12-22 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 35 | 906.9261 | 2.7566 | 105.6467 |  | 6
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-12 | 2026-12-15 | 2026-12-21 | 2026-12-26 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 35 | 989.3739 | 3.0322 | 115.2509 |  | 3
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4442 | 0 | 4442 | 340.5533 | 2026-12-07 | 2026-12-16 | 2026-12-18 | 2026-12-26 | 2026-12-31 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 35 | 1071.8217 | 4.1443 | 124.8552 |  | 4
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-12-07 | 2026-12-21 | 2026-12-23 | 2026-12-31 | 2027-01-05 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 35 | 1154.2696 | 4.3317 | 134.4594 |  | 0
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 5550 | 0 | 5550 | 425.5 | 2026-12-07 | 2026-12-26 | 2026-12-29 | 2027-01-06 | 2027-01-11 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 35 | 1236.7174 | 4.4877 | 144.0637 |  | -6
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-31 | 2027-01-04 | 2027-01-08 | 2027-01-13 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 35 | 1236.7174 | 1.5557 | 144.0637 |  | 5
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2027-01-04 | 2027-01-06 | 2027-01-15 | 2027-01-20 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 35 | 1236.7174 | 6.3038 | 144.0637 |  | 5
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-11 | 2027-01-13 | 2027-01-21 | 2027-01-26 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 35 | 1236.7174 | 5.344 | 144.0637 |  | 6
2026-05-28
6-14 | TGT | MRLPMM_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 41982 | 41982 | 0 | 3148.65 | 2026-05-26 | 2026-05-19 | 2026-05-25 | 2026-06-29 | 2026-07-01 | 2026-07-25 |  | 1.9917 | 0.9 | 9.4588 | 31.818 | 1678.4133 | 25.0129 | 177.7655 |  | 23
6-14 | TGT | G9M018_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 67974 | 67974 | 0 | 4814.825 | 2026-06-25 | 2026-06-20 | 2026-06-26 | 2026-08-14 | 2026-08-16 | 2026-08-22 |  | 1.8952 | 0.85 | 8.5318 | 36.0905 | 1730.0941 | 39.2892 | 203.1487 |  | 4
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 10002039574, 76, 78 |  |  | 10452 | 10452 | 0 | 1315.21 | 2026-08-22 | 2026-08-10 | 2026-08-12 | 2026-09-10 | 2026-09-12 | 2026-10-05 |  | 1.1829 | 1.51 | 8.5852 | 36.4735 | 618.1324 | 16.909 | 72.13 |  | 18
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 10002039579 |  |  | 4176 | 154 | 4022 | 525.48 | 2026-08-22 | 2026-09-04 | 2026-09-08 | 2026-09-17 | 2026-09-19 | 2026-11-16 |  | 1.66 | 1.51 | 9 | 35.1606 | 876.6588 | 4.7635 | 97.5822 |  | 49
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 10002039580 |  |  | 4176 | 0 | 4176 | 525.48 | 2026-08-22 | 2026-09-11 | 2026-09-15 | 2026-09-24 | 2026-09-26 | 2026-11-30 |  | 1.7 | 1.51 | 9 | 35.1606 | 897.7831 | 4.6515 | 99.9336 |  | 56
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 10002039581 |  |  | 4176 | 0 | 4176 | 525.48 | 2026-08-22 | 2026-09-18 | 2026-09-22 | 2026-10-01 | 2026-10-03 | 2026-12-14 |  | 1.7 | 1.51 | 9 | 35.1606 | 897.7831 | 4.6515 | 99.9336 |  | 63
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 10002039582 |  |  | 3036 | 0 | 3036 | 382.03 | 2026-08-22 | 2026-09-25 | 2026-09-29 | 2026-10-06 | 2026-10-08 | 2026-12-28 |  | 1.7 | 1.51 | 8.6 | 35.1606 | 857.8816 | 3.5389 | 99.9336 |  | 70
6-14 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 750 | 0 | 750 | 105 | 2026-09-12 | 2026-09-28 | 2026-10-03 | 2026-10-10 | 2026-10-12 | 2026-10-29 |  | 0.5 | 1.68 | 7 | 35.1606 | 184.5932 | 4.063 | 26.418 |  | 16
6-14 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 1500 | 0 | 1500 | 210 | 2026-09-12 | 2026-10-02 | 2026-10-08 | 2026-10-14 | 2026-10-16 | 2026-10-29 |  | 1 | 1.68 | 8.6 | 35.1606 | 453.5719 | 3.3071 | 52.836 |  | 13
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 740 | 0 | 740 | 45.0167 | 2026-10-15 | 2026-10-09 | 2026-10-12 | 2026-10-16 | 2026-10-18 | 2026-11-06 |  | 0.5 | 0.73 | 7 | 35.1606 | 424.8172 | 1.7419 | 60.7976 |  | 18
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 1500 | 0 | 1500 | 91.25 | 2026-10-15 | 2026-10-12 | 2026-10-14 | 2026-10-17 | 2026-10-19 | 2026-11-06 |  | 1 | 0.73 | 8.6 | 35.1606 | 1043.8366 | 1.437 | 121.5952 |  | 17
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 2500 | 0 | 2500 | 152.0833 | 2026-10-15 | 2026-10-13 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-11-06 |  | 1.2 | 0.73 | 8.6 | 35.1606 | 1252.604 | 1.9958 | 145.9143 |  | 15
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 3500 | 0 | 3500 | 212.9167 | 2026-10-15 | 2026-10-15 | 2026-10-17 | 2026-10-22 | 2026-10-24 | 2026-11-06 |  | 1.4 | 0.73 | 8.6 | 35.1606 | 1461.3713 | 2.395 | 170.2333 |  | 13
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 5000 | 0 | 5000 | 304.1667 | 2026-10-15 | 2026-10-17 | 2026-10-20 | 2026-10-26 | 2026-10-28 | 2026-11-09 |  | 1.6 | 0.73 | 8.6 | 35.1606 | 1670.1386 | 2.9938 | 194.5524 |  | 12
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 5000 | 0 | 5000 | 304.1667 | 2026-10-15 | 2026-10-21 | 2026-10-23 | 2026-10-29 | 2026-10-31 | 2026-11-06 |  | 1.8 | 0.73 | 8.6 | 35.1606 | 1878.9059 | 2.6611 | 218.8714 |  | 7
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 16000 | 0 | 16000 | 973.3333 | 2026-10-15 | 2026-10-24 | 2026-10-27 | 2026-11-07 | 2026-11-09 | 2026-11-06 |  | 2 | 0.73 | 8.6 | 35.1606 | 2087.6733 | 7.664 | 243.1904 |  | -3
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 716 | 0 | 716 | 72.7933 | 2026-11-05 | 2026-11-03 | 2026-11-05 | 2026-11-11 | 2026-11-13 | 2026-11-30 |  | 0.5 | 1.22 | 7 | 35.1606 | 254.1939 | 2.8167 | 36.3789 |  | 16
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 1500 | 0 | 1500 | 152.5 | 2026-11-05 | 2026-11-06 | 2026-11-09 | 2026-11-13 | 2026-11-15 | 2026-11-30 |  | 1 | 1.22 | 8.6 | 35.1606 | 624.5908 | 2.4016 | 72.7578 |  | 14
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 2500 | 0 | 2500 | 254.1667 | 2026-11-05 | 2026-11-09 | 2026-11-11 | 2026-11-18 | 2026-11-20 | 2026-11-30 |  | 1.1 | 1.22 | 8.6 | 35.1606 | 687.0498 | 3.6387 | 80.0336 |  | 10
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 3000 | 0 | 3000 | 305 | 2026-11-05 | 2026-11-13 | 2026-11-16 | 2026-11-23 | 2026-11-25 | 2026-11-30 |  | 1.2 | 1.22 | 8.6 | 35.1606 | 749.5089 | 4.0026 | 87.3094 |  | 6
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 4000 | 0 | 4000 | 406.6667 | 2026-11-05 | 2026-11-18 | 2026-11-20 | 2026-11-28 | 2026-11-30 | 2026-11-30 |  | 1.4 | 1.22 | 8.6 | 35.1606 | 874.4271 | 4.5744 | 101.8609 |  | 1
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 3000 | 0 | 3000 | 305 | 2026-11-05 | 2026-11-24 | 2026-11-26 | 2026-12-02 | 2026-12-04 | 2026-12-07 |  | 1.6 | 1.22 | 8.6 | 35.1606 | 999.3452 | 3.002 | 116.4125 |  | 4
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 4016 | 0 | 4016 | 408.2933 | 2026-11-05 | 2026-11-27 | 2026-11-30 | 2026-12-07 | 2026-12-09 | 2026-12-07 |  | 1.8 | 1.22 | 8.6 | 35.1606 | 1124.2634 | 3.5721 | 130.964 |  | 0
6-14 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-12-02 | 2026-12-04 | 2026-12-09 | 2026-12-14 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 35.1606 | 337.0832 | 2.4178 | 48.2416 |  | 13
6-14 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-12-04 | 2026-12-07 | 2026-12-11 | 2026-12-16 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 35.1606 | 828.2617 | 1.811 | 96.4832 |  | 11
6-14 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-12-07 | 2026-12-09 | 2026-12-15 | 2026-12-20 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 35.1606 | 911.0878 | 2.744 | 106.1315 |  | 8
6-14 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-10 | 2026-12-12 | 2026-12-18 | 2026-12-23 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 35.1606 | 993.914 | 3.0184 | 115.7798 |  | 5
6-14 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4042 | 0 | 4042 | 309.8867 | 2026-12-07 | 2026-12-14 | 2026-12-16 | 2026-12-23 | 2026-12-28 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 35.1606 | 1076.7402 | 3.7539 | 125.4281 |  | 6
6-14 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4000 | 0 | 4000 | 306.6667 | 2026-12-07 | 2026-12-18 | 2026-12-21 | 2026-12-28 | 2027-01-02 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 35.1606 | 1159.5663 | 3.4496 | 135.0764 |  | 3
6-14 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4000 | 0 | 4000 | 306.6667 | 2026-12-07 | 2026-12-22 | 2026-12-24 | 2026-12-31 | 2027-01-05 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 35.1606 | 1242.3925 | 3.2196 | 144.7247 |  | 0
6-14 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-26 | 2026-12-29 | 2027-01-04 | 2027-01-09 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 35.1606 | 1242.3925 | 1.5486 | 144.7247 |  | 9
6-14 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-29 | 2026-12-31 | 2027-01-11 | 2027-01-16 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 35.1606 | 1242.3925 | 6.275 | 144.7247 |  | 9
6-14 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-06 | 2027-01-08 | 2027-01-16 | 2027-01-21 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 35.1606 | 1242.3925 | 5.3196 | 144.7247 |  | 10
2026-06-10
6-15 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 12675 | 12675 | 0 | 1468.1875 | 2026-06-03 | 2026-06-05 | 2026-06-08 | 2026-06-27 | 2026-06-29 | 2026-07-09 |  | 1.4468 | 1.39 | 9.1261 | 37.5708 | 899.3507 | 14.0935 | 98.7251 |  | 10
6-15 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 24345 | 24345 | 0 | 2130.1875 | 2026-05-26 | 2026-06-23 | 2026-06-25 | 2026-07-16 | 2026-07-21 | 2026-07-30 |  | 1.8746 | 1.05 | 9.3739 | 36.7685 | 1550.6758 | 15.6996 | 165.723 |  | 12
6-15 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 5783 | 5783 | 0 | 506.0125 | 2026-06-23 | 2026-07-11 | 2026-07-14 | 2026-07-22 | 2026-07-27 | 2026-08-20 |  | 1.6985 | 1.05 | 7.855 | 37.8144 | 1210.7956 | 4.7762 | 154.4219 |  | 22
6-15 | HLF | CPM263TL32_26Q4 | Tee | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 25311 | 25311 | 0 | 1898.325 | 2026-07-10 | 2026-07-14 | 2026-07-20 | 2026-08-20 | 2026-08-22 | 2026-08-21 |  | 1.4303 | 0.9 | 7.6394 | 37.2943 | 1140.9978 | 22.1832 | 149.6259 |  | 1
6-15 | SMA | LPST840 | Pull On Pants |  | 1352772, _AH |  |  | 4836 | 4836 | 0 | 596.44 | 2026-08-18 | 2026-08-13 | 2026-08-18 | 2026-09-02 | 2026-09-04 | 2026-09-22 |  | 1.1218 | 1.48 | 8.4698 | 37.5236 | 607.0652 | 7.9662 | 71.8036 |  | 14
6-15 | SMA | LPST840 | Pull On Pants |  | 1354810_SS, _AH |  |  | 79 | 79 | 0 | 9.7433 | 2026-08-18 | 2026-08-27 | 2026-08-31 | 2026-09-02 | 2026-09-04 | 2026-09-23 |  | 0.32977 | 1.48 | 9 | 37 | 186.9822 | 0.4225 | 20.8133 |  | 15
6-15 | SMA | LPST840 | Pull On Pants |  | 1352773, _AH |  |  | 5900 | 5700 | 200 | 727.6667 | 2026-08-24 | 2026-08-27 | 2026-08-31 | 2026-09-10 | 2026-09-12 | 2026-10-02 |  | 1.65 | 1.48 | 9 | 37 | 935.55 | 6.3065 | 104.1374 |  | 16
6-15 | SMA | PST840 | Pull On Pants |  | 1352813, _AH |  |  | 2006 | 20 | 1986 | 272.4817 | 2026-08-18 | 2026-09-04 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 2026-09-22 |  | 1.65 | 1.63 | 9 | 36.6361 | 841.1024 | 2.385 | 93.6243 |  | 6
6-15 | SMA | LPST840 | Pull On Pants |  | 1352773, _AH |  |  | 1884 | 0 | 1884 | 232.36 | 2026-08-24 | 2026-09-08 | 2026-09-10 | 2026-09-16 | 2026-09-18 | 2026-10-02 |  | 1.65 | 1.48 | 9 | 37 | 935.55 | 2.0138 | 104.1374 |  | 12
6-15 | SMA | LPST840 | Pull On Pants |  | 1352774, _AH |  |  | 7368 | 0 | 7368 | 908.72 | 2026-09-14 | 2026-09-10 | 2026-09-14 | 2026-09-28 | 2026-09-30 | 2026-11-02 |  | 1.65 | 1.48 | 9 | 37 | 935.55 | 7.8756 | 104.1374 |  | 30
6-15 | SMA | PST840 | Pull On Pants |  | 1352814, _AH |  |  | 1500 | 0 | 1500 | 203.75 | 2026-08-24 | 2026-09-22 | 2026-09-24 | 2026-09-30 | 2026-10-02 | 2026-11-02 |  | 1.65 | 1.63 | 9 | 37 | 849.4564 | 1.7658 | 94.5542 |  | 28
6-15 | SMA | PST840 | Pull On Pants |  | 1352816, _AH |  |  | 5132 | 0 | 5132 | 697.0967 | 2026-10-05 | 2026-09-24 | 2026-09-28 | 2026-10-07 | 2026-10-09 | 2026-12-03 |  | 1.65 | 1.63 | 8.6 | 37.461 | 821.8166 | 6.2447 | 95.7324 |  | 49
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 750 | 0 | 750 | 105 | 2026-09-12 | 2026-09-29 | 2026-10-05 | 2026-10-12 | 2026-10-14 | 2026-10-29 |  | 0.5 | 1.68 | 7 | 37 | 194.25 | 3.861 | 27.8 |  | 15
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 1500 | 0 | 1500 | 210 | 2026-09-12 | 2026-10-03 | 2026-10-09 | 2026-10-15 | 2026-10-17 | 2026-10-29 |  | 1 | 1.68 | 8.6 | 37 | 477.3 | 3.1427 | 55.6001 |  | 12
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 2000 | 0 | 2000 | 280 | 2026-09-12 | 2026-10-07 | 2026-10-13 | 2026-10-20 | 2026-10-22 | 2026-10-29 |  | 1.1 | 1.68 | 8.6 | 37 | 525.03 | 3.8093 | 61.1601 |  | 8
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 2000 | 0 | 2000 | 280 | 2026-09-12 | 2026-10-12 | 2026-10-17 | 2026-10-23 | 2026-10-25 | 2026-10-29 |  | 1.2 | 1.68 | 8.6 | 37 | 572.76 | 3.4919 | 66.7201 |  | 5
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 2500 | 0 | 2500 | 350 | 2026-09-12 | 2026-10-15 | 2026-10-21 | 2026-10-28 | 2026-10-30 | 2026-10-29 |  | 1.4 | 1.68 | 8.6 | 37 | 668.22 | 3.7413 | 77.8401 |  | 1
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0130 |  |  | 4332 | 0 | 4332 | 606.48 | 2026-10-03 | 2026-10-20 | 2026-10-26 | 2026-11-04 | 2026-11-06 | 2026-11-09 |  | 1.5 | 1.68 | 8.6 | 37 | 715.95 | 6.0507 | 83.4001 |  | 4
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0213 |  |  | 4000 | 0 | 4000 | 560 | 2026-10-17 | 2026-10-27 | 2026-11-02 | 2026-11-10 | 2026-11-12 | 2026-11-23 |  | 1.6 | 1.68 | 8.6 | 37 | 763.68 | 5.2378 | 88.9601 |  | 11
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 1500 | 0 | 1500 | 52.5 | 2026-11-13 | 2026-11-05 | 2026-11-07 | 2026-11-12 | 2026-11-14 | 2026-12-12 |  | 0.5 | 0.42 | 7 | 35 | 735 | 2.0408 | 105.1893 |  | 26
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 3500 | 0 | 3500 | 122.5 | 2026-11-13 | 2026-11-07 | 2026-11-10 | 2026-11-14 | 2026-11-16 | 2026-12-12 |  | 1 | 0.42 | 8.6 | 35 | 1806 | 1.938 | 210.3787 |  | 24
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 5000 | 0 | 5000 | 175 | 2026-11-13 | 2026-11-10 | 2026-11-12 | 2026-11-17 | 2026-11-19 | 2026-12-12 |  | 1.2 | 0.42 | 8.6 | 35 | 2167.2 | 2.3071 | 252.4544 |  | 22
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 7000 | 0 | 7000 | 245 | 2026-11-13 | 2026-11-12 | 2026-11-14 | 2026-11-20 | 2026-11-22 | 2026-12-12 |  | 1.4 | 0.42 | 8.6 | 35 | 2528.4 | 2.7685 | 294.5302 |  | 19
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 10000 | 0 | 10000 | 350 | 2026-11-13 | 2026-11-16 | 2026-11-18 | 2026-11-24 | 2026-11-26 | 2026-12-12 |  | 1.6 | 0.42 | 8.6 | 35 | 2889.6 | 3.4607 | 336.6059 |  | 16
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 10000 | 0 | 10000 | 350 | 2026-11-13 | 2026-11-19 | 2026-11-21 | 2026-11-27 | 2026-11-29 | 2026-12-12 |  | 1.8 | 0.42 | 8.6 | 35 | 3250.8 | 3.0762 | 378.6816 |  | 13
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 45000 | 0 | 45000 | 1575 | 2026-11-13 | 2026-11-23 | 2026-11-25 | 2026-12-11 | 2026-12-13 | 2026-12-12 |  | 2 | 0.42 | 8.6 | 35 | 3612 | 12.4585 | 420.7574 |  | 1
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0328 |  |  | 68132 | 0 | 68132 | 2384.62 | 2026-12-11 | 2026-12-07 | 2026-12-09 | 2027-01-05 | 2027-01-07 | 2027-01-09 |  | 2 | 0.42 | 8.6 | 35 | 3612 | 18.8627 | 420.7574 |  | 4
2026-04-14
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 55281 | 55281 | 0 | 4837.0875 | 2026-05-07 | 2026-04-09 | 2026-04-11 | 2026-06-03 | 2026-06-08 | 2026-07-30 |  | 1.7381 | 1.05 | 9.2232 | 36.7546 | 1414.0742 | 39.0934 | 153.5931 |  | 48
6-16 | TGT | G917K0_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 43173 | 43173 | 0 | 4497.1875 | 2026-05-26 | 2026-05-23 | 2026-05-30 | 2026-07-14 | 2026-07-16 | 2026-07-25 |  | 1.8617 | 1.25 | 9.2646 | 36.899 | 1283.0131 | 33.6497 | 138.7353 |  | 10
6-16 | TGT | G9M018_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 41073 | 41073 | 0 | 2909.3375 | 2026-06-25 | 2026-07-06 | 2026-07-11 | 2026-08-11 | 2026-08-13 | 2026-08-22 |  | 1.9856 | 0.85 | 8.0933 | 37.783 | 1800.1043 | 22.817 | 222.8196 |  | 7
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 3586 | 3586 | 0 | 313.775 | 2026-06-23 | 2026-08-05 | 2026-08-07 | 2026-08-14 | 2026-08-19 | 2026-09-24 |  | 1.5382 | 1.05 | 8 | 37.0838 | 1095.2295 | 3.2742 | 137.1506 |  | 27
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 54087 | 31111 | 22976 | 4732.6125 | 2026-08-20 | 2026-08-10 | 2026-08-12 | 2026-09-30 | 2026-10-05 | 2026-10-15 |  | 2.12 | 1.05 | 9 | 38 | 1740.096 | 31.0828 | 193.6926 |  | 13
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 5873 | 0 | 5873 | 513.8875 | 2026-08-20 | 2026-09-24 | 2026-09-28 | 2026-10-05 | 2026-10-10 | 2026-10-15 |  | 2.1 | 1.05 | 8.6 | 38 | 1647.072 | 3.5657 | 191.8654 |  | 9
6-16 | ONY | 1194585_HO26_NB | Pull On Pants | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); Normal Garment Wash 清水洗/普通水洗; | 62242721, 726, 728, 729, 837, 838, 839 |  |  | 490 | 0 | 490 | 33.8917 | 2026-09-10 | 2026-09-25 | 2026-10-02 | 2026-10-06 | 2026-10-11 | 2026-10-08 |  | 0.5 | 0.83 | 7 | 38 | 403.8072 | 1.2135 | 57.7908 |  | 2
6-16 | ONY | 1194585_HO26_NB | Pull On Pants | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); Normal Garment Wash 清水洗/普通水洗; | 62242721, 726, 728, 729, 837, 838, 839 |  |  | 1000 | 0 | 1000 | 69.1667 | 2026-09-10 | 2026-09-28 | 2026-10-03 | 2026-10-07 | 2026-10-12 | 2026-10-08 |  | 1 | 0.83 | 8.6 | 38 | 992.212 | 1.0078 | 115.5815 |  | 1
6-16 | ONY | 1194585_HO26_NB | Pull On Pants | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); Normal Garment Wash 清水洗/普通水洗; | 62242165, 169, 172, 174 |  |  | 1510 | 0 | 1510 | 104.4417 | 2026-09-10 | 2026-09-29 | 2026-10-05 | 2026-10-09 | 2026-10-14 | 2026-10-29 |  | 1 | 0.83 | 8.6 | 38 | 992.212 | 1.5219 | 115.5815 |  | 17
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62385693 |  |  | 510 | 0 | 510 | 31.025 | 2026-10-09 | 2026-10-01 | 2026-10-07 | 2026-10-10 | 2026-10-12 | 2026-10-28 |  | 0.5 | 0.73 | 7 | 38 | 459.1233 | 1.1108 | 65.7073 |  | 15
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62385693 |  |  | 1500 | 0 | 1500 | 91.25 | 2026-10-09 | 2026-10-02 | 2026-10-08 | 2026-10-12 | 2026-10-14 | 2026-10-28 |  | 1 | 0.73 | 8.6 | 38 | 1128.1315 | 1.3296 | 131.4146 |  | 14
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62377531, 116, 287 |  |  | 3099 | 0 | 3099 | 188.5225 | 2026-10-09 | 2026-10-03 | 2026-10-09 | 2026-10-14 | 2026-10-16 | 2026-10-29 |  | 1.1 | 0.73 | 8.6 | 38 | 1240.9447 | 2.4973 | 144.5561 |  | 13
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62385611 |  |  | 480 | 0 | 480 | 29.2 | 2026-10-09 | 2026-10-06 | 2026-10-12 | 2026-10-14 | 2026-10-16 | 2026-11-04 |  | 1.2 | 0.73 | 8.6 | 38 | 1353.7578 | 0.35457 | 157.6976 |  | 18
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62379119, 121, 451, 452, 453, 454 |  |  | 4426 | 0 | 4426 | 269.2483 | 2026-10-09 | 2026-10-06 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 2026-11-05 |  | 1.4 | 0.73 | 8.6 | 38 | 1579.3841 | 2.8024 | 183.9805 |  | 16
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62379119, 121, 451, 452, 453, 454 |  |  | 7000 | 0 | 7000 | 425.8333 | 2026-10-09 | 2026-10-09 | 2026-10-15 | 2026-10-22 | 2026-10-24 | 2026-11-05 |  | 1.6 | 0.73 | 8.6 | 38 | 1805.0104 | 3.8781 | 210.2634 |  | 12
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62377481, 168, 252 |  |  | 2079 | 0 | 2079 | 126.4725 | 2026-11-04 | 2026-10-14 | 2026-10-20 | 2026-10-23 | 2026-10-25 | 2026-11-26 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 1.0238 | 236.5463 |  | 29
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62383169, 171, 483, 485, 487, 489 |  |  | 10557 | 0 | 10557 | 642.2175 | 2026-11-04 | 2026-10-15 | 2026-10-21 | 2026-10-29 | 2026-10-31 | 2026-12-03 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 5.1989 | 236.5463 |  | 30
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 12.24 |  |  | 1889 | 0 | 1889 | 114.9142 | 2026-12-04 | 2026-10-21 | 2026-10-27 | 2026-10-30 | 2026-11-01 | 2026-12-24 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 0.93025 | 236.5463 |  | 47
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 12.31 |  |  | 3707 | 0 | 3707 | 225.5092 | 2026-12-04 | 2026-10-22 | 2026-10-28 | 2026-11-02 | 2026-11-04 | 2026-12-31 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 1.8255 | 236.5463 |  | 50
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 01.21 |  |  | 1614 | 0 | 1614 | 98.185 | 2026-12-04 | 2026-10-24 | 2026-10-30 | 2026-11-03 | 2026-11-05 | 2027-01-21 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 0.79482 | 236.5463 |  | 66
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 01.28 |  |  | 3066 | 0 | 3066 | 186.515 | 2026-12-04 | 2026-10-26 | 2026-10-31 | 2026-11-05 | 2026-11-07 | 2027-01-28 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 1.5099 | 236.5463 |  | 70
6-16 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 716 | 0 | 716 | 72.7933 | 2026-11-05 | 2026-10-31 | 2026-11-03 | 2026-11-09 | 2026-11-11 | 2026-11-30 |  | 0.5 | 1.22 | 7 | 38 | 274.7213 | 2.6063 | 39.3167 |  | 18
6-16 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 1500 | 0 | 1500 | 152.5 | 2026-11-05 | 2026-11-04 | 2026-11-06 | 2026-11-11 | 2026-11-13 | 2026-11-30 |  | 1 | 1.22 | 8.6 | 38 | 675.0295 | 2.2221 | 78.6333 |  | 16
6-16 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 2500 | 0 | 2500 | 254.1667 | 2026-11-05 | 2026-11-06 | 2026-11-09 | 2026-11-14 | 2026-11-16 | 2026-11-30 |  | 1.1 | 1.22 | 8.6 | 38 | 742.5325 | 3.3669 | 86.4967 |  | 13
6-16 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 3900 | 0 | 3900 | 396.5 | 2026-11-05 | 2026-11-10 | 2026-11-12 | 2026-11-20 | 2026-11-22 | 2026-11-30 |  | 1.2 | 1.22 | 8.6 | 38 | 810.0354 | 4.8146 | 94.36 |  | 8
6-16 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 4000 | 0 | 4000 | 406.6667 | 2026-11-05 | 2026-11-16 | 2026-11-18 | 2026-11-25 | 2026-11-27 | 2026-12-07 |  | 1.4 | 1.22 | 8.6 | 38 | 945.0413 | 4.2326 | 110.0867 |  | 10
6-16 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 8516 | 0 | 8516 | 865.7933 | 2026-11-05 | 2026-11-20 | 2026-11-23 | 2026-12-04 | 2026-12-06 | 2026-12-07 |  | 1.6 | 1.22 | 8.6 | 38 | 1080.0472 | 7.8848 | 125.8133 |  | 2
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2026-12-07 | 2026-12-12 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 38 | 364.3043 | 2.2371 | 52.1373 |  | 15
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-12-02 | 2026-12-04 | 2026-12-09 | 2026-12-14 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 38 | 895.1478 | 1.6757 | 104.2747 |  | 13
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-12-04 | 2026-12-07 | 2026-12-12 | 2026-12-17 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 38 | 984.6626 | 2.5389 | 114.7021 |  | 10
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-08 | 2026-12-10 | 2026-12-16 | 2026-12-21 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 38 | 1074.1774 | 2.7928 | 125.1296 |  | 7
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4942 | 0 | 4942 | 378.8867 | 2026-12-07 | 2026-12-11 | 2026-12-14 | 2026-12-21 | 2026-12-26 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 38 | 1163.6922 | 4.2468 | 135.557 |  | 8
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-12-07 | 2026-12-16 | 2026-12-18 | 2026-12-26 | 2026-12-31 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 38 | 1253.207 | 3.9898 | 145.9845 |  | 4
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 5550 | 0 | 5550 | 425.5 | 2026-12-07 | 2026-12-21 | 2026-12-23 | 2026-12-31 | 2027-01-05 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 4.1334 | 156.412 |  | 0
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-26 | 2026-12-29 | 2027-01-02 | 2027-01-07 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 1.4329 | 156.412 |  | 10
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-28 | 2026-12-30 | 2027-01-09 | 2027-01-14 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 5.8061 | 156.412 |  | 10
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-05 | 2027-01-07 | 2027-01-15 | 2027-01-20 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 4.9221 | 156.412 |  | 11
2026-05-26
6-17 | TGT | G9M018_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 114421 | 114421 | 0 | 8104.8208 | 2026-06-25 | 2026-05-18 | 2026-05-23 | 2026-08-12 | 2026-08-14 | 2026-08-22 |  | 1.8494 | 0.85 | 9.0274 | 36.6846 | 1815.7792 | 63.0148 | 201.5045 |  | 6
6-17 | ONY | 1182430_HO26_HT | Pull On Pants |  | all po |  |  | 17242 | 17242 | 0 | 1120.73 | 2026-08-24 | 2026-08-06 | 2026-08-10 | 2026-09-04 | 2026-09-06 | 2026-10-15 |  | 1.1456 | 0.78 | 8.3389 | 37.797 | 1166.5206 | 14.7807 | 140.1413 |  | 31
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004922_T1_W |  |  | 720 | 720 | 0 | 63.6 | 2026-08-24 | 2026-08-26 | 2026-09-02 | 2026-09-07 | 2026-09-09 | 2026-10-01 |  | 0.87336 | 1.06 | 8 | 38 | 631.1914 | 1.1407 | 79.0412 |  | 18
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 7500 | 5104 | 2396 | 662.5 | 2026-08-24 | 2026-08-27 | 2026-09-03 | 2026-09-14 | 2026-09-16 | 2026-10-08 |  | 1.74 | 1.06 | 9 | 38 | 1414.7185 | 5.3014 | 157.4744 |  | 19
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 10499 | 0 | 10499 | 927.4117 | 2026-08-24 | 2026-09-03 | 2026-09-10 | 2026-09-22 | 2026-09-24 | 2026-10-08 |  | 2 | 1.06 | 9 | 38 | 1626.1132 | 6.4565 | 181.0051 |  | 13
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004937_BA_E |  |  | 6792 | 0 | 6792 | 599.96 | 2026-09-10 | 2026-09-11 | 2026-09-18 | 2026-09-28 | 2026-09-30 | 2026-10-12 |  | 2 | 1.06 | 9 | 38 | 1626.1132 | 4.1768 | 181.0051 |  | 12
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004936_BA_E |  |  | 4000 | 0 | 4000 | 353.3333 | 2026-08-29 | 2026-09-17 | 2026-09-24 | 2026-09-30 | 2026-10-02 | 2026-10-24 |  | 2 | 1.06 | 9 | 38 | 1626.1132 | 2.4599 | 181.0051 |  | 21
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004936_BA_E |  |  | 7078 | 0 | 7078 | 625.2233 | 2026-08-29 | 2026-09-21 | 2026-09-28 | 2026-10-06 | 2026-10-08 | 2026-10-24 |  | 2 | 1.06 | 8.6 | 38 | 1553.8415 | 4.5552 | 181.0051 |  | 16
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004947_BA_E |  |  | 6792 | 0 | 6792 | 599.96 | 2026-09-05 | 2026-09-28 | 2026-10-03 | 2026-10-10 | 2026-10-12 | 2026-10-26 |  | 2 | 1.06 | 8.6 | 38 | 1553.8415 | 4.3711 | 181.0051 |  | 13
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004946_BA_E |  |  | 9078 | 0 | 9078 | 801.89 | 2026-09-05 | 2026-10-02 | 2026-10-08 | 2026-10-17 | 2026-10-19 | 2026-11-07 |  | 2 | 1.06 | 8.6 | 38 | 1553.8415 | 5.8423 | 181.0051 |  | 18
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004950_BA_E |  |  | 9792 | 0 | 9792 | 864.96 | 2026-09-05 | 2026-10-09 | 2026-10-15 | 2026-10-24 | 2026-10-26 | 2026-11-09 |  | 2 | 1.06 | 8.6 | 38 | 1553.8415 | 6.3018 | 181.0051 |  | 13
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004948_BA_E |  |  | 9078 | 0 | 9078 | 801.89 | 2026-09-05 | 2026-10-16 | 2026-10-22 | 2026-10-31 | 2026-11-02 | 2026-11-21 |  | 2 | 1.06 | 8.6 | 38 | 1553.8415 | 5.8423 | 181.0051 |  | 18
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004939_BA_E |  |  | 6792 | 0 | 6792 | 599.96 | 2026-09-05 | 2026-10-23 | 2026-10-29 | 2026-11-05 | 2026-11-07 | 2026-11-23 |  | 2 | 1.06 | 8.6 | 38 | 1553.8415 | 4.3711 | 181.0051 |  | 15
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004938_BA_E |  |  | 10928 | 0 | 10928 | 965.3067 | 2026-09-05 | 2026-10-28 | 2026-11-03 | 2026-11-13 | 2026-11-15 | 2026-12-05 |  | 2 | 1.06 | 8.6 | 38 | 1553.8415 | 7.0329 | 181.0051 |  | 19
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 728 | 0 | 728 | 57.0267 | 2026-11-09 | 2026-11-05 | 2026-11-11 | 2026-11-16 | 2026-11-18 | 2026-12-03 |  | 0.5 | 0.94 | 7 | 38 | 356.5532 | 2.0418 | 51.028 |  | 15
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 1500 | 0 | 1500 | 117.5 | 2026-11-09 | 2026-11-07 | 2026-11-13 | 2026-11-18 | 2026-11-20 | 2026-12-03 |  | 1 | 0.94 | 8.6 | 38 | 876.1021 | 1.7121 | 102.056 |  | 13
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 2500 | 0 | 2500 | 195.8333 | 2026-11-09 | 2026-11-10 | 2026-11-16 | 2026-11-21 | 2026-11-23 | 2026-12-03 |  | 1.1 | 0.94 | 8.6 | 38 | 963.7123 | 2.5941 | 112.2616 |  | 10
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 3500 | 0 | 3500 | 274.1667 | 2026-11-09 | 2026-11-13 | 2026-11-19 | 2026-11-25 | 2026-11-27 | 2026-12-03 |  | 1.2 | 0.94 | 8.6 | 38 | 1051.3226 | 3.3291 | 122.4672 |  | 7
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 5300 | 0 | 5300 | 415.1667 | 2026-11-09 | 2026-11-17 | 2026-11-23 | 2026-11-30 | 2026-12-02 | 2026-12-03 |  | 1.4 | 0.94 | 8.6 | 38 | 1226.543 | 4.3211 | 142.8785 |  | 3
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1210, 4500041655_BJSHVS_1210, 4500041655_BJSHVS_HTR_1210, 4500041657_HTR_1210 |  |  | 6000 | 0 | 6000 | 470 | 2026-11-09 | 2026-11-21 | 2026-11-27 | 2026-12-04 | 2026-12-06 | 2026-12-10 |  | 1.6 | 0.94 | 8.6 | 38 | 1401.7634 | 4.2803 | 163.2897 |  | 5
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1210, 4500041655_BJSHVS_1210, 4500041655_BJSHVS_HTR_1210, 4500041657_HTR_1210 |  |  | 10484 | 0 | 10484 | 821.2467 | 2026-11-09 | 2026-11-26 | 2026-12-02 | 2026-12-12 | 2026-12-14 | 2026-12-10 |  | 1.8 | 0.94 | 8.6 | 38 | 1576.9838 | 6.6481 | 183.7009 |  | -4
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-12-08 | 2026-12-10 | 2026-12-15 | 2026-12-20 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 38 | 364.3043 | 2.2371 | 52.1373 |  | 8
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-12-10 | 2026-12-12 | 2026-12-17 | 2026-12-22 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 38 | 895.1478 | 1.6757 | 104.2747 |  | 6
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-12-12 | 2026-12-15 | 2026-12-21 | 2026-12-26 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 38 | 984.6626 | 2.5389 | 114.7021 |  | 3
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-16 | 2026-12-18 | 2026-12-24 | 2026-12-29 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 38 | 1074.1774 | 2.7928 | 125.1296 |  | 0
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4942 | 0 | 4942 | 378.8867 | 2026-12-07 | 2026-12-19 | 2026-12-22 | 2026-12-30 | 2027-01-04 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 38 | 1163.6922 | 4.2468 | 135.557 |  | 1
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-24 | 2026-12-28 | 2027-01-02 | 2027-01-07 | 2027-01-14 |  | 1.4 | 0.92 | 8.6 | 38 | 1253.207 | 1.5353 | 145.9845 |  | 10
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-28 | 2026-12-30 | 2027-01-09 | 2027-01-14 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 5.8061 | 156.412 |  | 10
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-05 | 2027-01-07 | 2027-01-15 | 2027-01-20 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 4.9221 | 156.412 |  | 11
2026-04-07
6-18 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 58617 | 58617 | 0 | 5128.9875 | 2026-05-07 | 2026-04-01 | 2026-04-04 | 2026-05-25 | 2026-05-30 | 2026-07-30 |  | 1.8839 | 1.05 | 9.0947 | 36.6174 | 1505.6912 | 38.9303 | 165.8552 |  | 54
6-18 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 36668 | 36668 | 0 | 4247.3767 | 2026-06-03 | 2026-05-20 | 2026-05-22 | 2026-07-08 | 2026-07-10 | 2026-07-09 |  | 1.6867 | 1.39 | 9.4411 | 36.547 | 1055.0911 | 34.7534 | 111.9562 |  | 1
6-18 | ONY | 910047_HO26DIS | Pajama |  | all po |  |  | 38392 | 38392 | 0 | 4543.0533 | 2026-07-06 | 2026-07-03 | 2026-07-06 | 2026-08-19 | 2026-08-21 | 2026-09-03 |  | 2.054 | 1.42 | 8.2635 | 38.6602 | 1164.4988 | 32.9687 | 141.1757 |  | 10
6-18 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 2978 | 2978 | 0 | 260.575 | 2026-06-23 | 2026-08-12 | 2026-08-14 | 2026-08-21 | 2026-08-26 | 2026-10-15 |  | 1.7247 | 1.05 | 8.0143 | 37.9956 | 1260.476 | 2.3626 | 157.5616 |  | 40
6-18 | ONY | 910047_HO26DIS | Pajama |  | all po |  |  | 8515 | 8515 | 0 | 1007.6083 | 2026-07-06 | 2026-08-14 | 2026-08-19 | 2026-09-02 | 2026-09-04 | 2026-09-03 |  | 1.9776 | 1.42 | 8.5299 | 38.1355 | 1141.6509 | 7.4585 | 134.0827 |  | 1
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004914_T1_W |  |  | 2160 | 2160 | 0 | 140.4 | 2026-08-18 | 2026-08-21 | 2026-08-31 | 2026-09-04 | 2026-09-06 | 2026-10-01 |  | 1.1932 | 0.78 | 8 | 38 | 1171.875 | 1.8432 | 146.7485 |  | 19
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004915_SET_W |  |  | 32825 | 7940 | 24885 | 2133.625 | 2026-08-18 | 2026-08-26 | 2026-09-02 | 2026-09-25 | 2026-09-27 | 2026-10-08 |  | 2.04 | 0.78 | 9 | 38 | 2254.0431 | 14.5627 | 250.9009 |  | 10
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004943_BA_E |  |  | 3816 | 0 | 3816 | 248.04 | 2026-08-18 | 2026-09-16 | 2026-09-23 | 2026-09-29 | 2026-10-01 | 2026-10-12 |  | 2 | 0.78 | 9 | 38 | 2209.8462 | 1.7268 | 245.9812 |  | 11
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004944_BA_W |  |  | 5064 | 0 | 5064 | 329.16 | 2026-08-18 | 2026-09-18 | 2026-09-25 | 2026-10-01 | 2026-10-03 | 2026-10-24 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 2.3981 | 245.9812 |  | 20
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004935_BA_E |  |  | 3132 | 0 | 3132 | 203.58 | 2026-08-18 | 2026-09-22 | 2026-09-29 | 2026-10-02 | 2026-10-04 | 2026-10-26 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.4832 | 245.9812 |  | 20
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004934_BA_W |  |  | 4200 | 0 | 4200 | 273 | 2026-08-24 | 2026-09-23 | 2026-09-30 | 2026-10-05 | 2026-10-07 | 2026-11-07 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.989 | 245.9812 |  | 29
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004949_BA_E |  |  | 2508 | 0 | 2508 | 163.02 | 2026-09-05 | 2026-09-25 | 2026-10-02 | 2026-10-06 | 2026-10-08 | 2026-11-09 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.1877 | 245.9812 |  | 29
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004945_BA_W |  |  | 3348 | 0 | 3348 | 217.62 | 2026-09-05 | 2026-09-28 | 2026-10-03 | 2026-10-08 | 2026-10-10 | 2026-11-21 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.5855 | 245.9812 |  | 38
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004942_BA_E |  |  | 2508 | 0 | 2508 | 163.02 | 2026-08-24 | 2026-09-30 | 2026-10-06 | 2026-10-09 | 2026-10-11 | 2026-11-23 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.1877 | 245.9812 |  | 38
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004941_BA_W |  |  | 3348 | 0 | 3348 | 217.62 | 2026-08-29 | 2026-10-01 | 2026-10-07 | 2026-10-12 | 2026-10-14 | 2026-12-05 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.5855 | 245.9812 |  | 47
6-18 | TGT | 1KE9E9_SSLLC127 | Pajama |  | 1206 |  |  | 840 | 0 | 840 | 48.3 | 2026-10-15 | 2026-10-07 | 2026-10-09 | 2026-10-13 | 2026-10-15 | 2026-11-06 |  | 1.5 | 0.69 | 7 | 38 | 1457.2174 | 0.57644 | 208.5493 |  | 21
6-18 | TGT | 1KE9E9_SSLLC127 | Pajama |  | 1206 |  |  | 1500 | 0 | 1500 | 86.25 | 2026-10-15 | 2026-10-08 | 2026-10-10 | 2026-10-14 | 2026-10-16 | 2026-11-06 |  | 1.6 | 0.69 | 8.6 | 38 | 1909.6487 | 0.78548 | 222.4526 |  | 20
6-18 | TGT | 1KE9E9_SSLLC127 | Pajama |  | 1206 |  |  | 3500 | 0 | 3500 | 201.25 | 2026-10-15 | 2026-10-09 | 2026-10-12 | 2026-10-16 | 2026-10-18 | 2026-11-06 |  | 1.8 | 0.69 | 8.6 | 38 | 2148.3548 | 1.6292 | 250.2592 |  | 18
6-18 | TGT | 1KE9E9_SSLLC127 | Pajama |  | 1206 |  |  | 14000 | 0 | 14000 | 805 | 2026-10-15 | 2026-10-12 | 2026-10-14 | 2026-10-23 | 2026-10-25 | 2026-11-06 |  | 2 | 0.69 | 8.6 | 38 | 2387.0609 | 5.865 | 278.0657 |  | 12
6-18 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 720 | 0 | 720 | 43.2 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 2026-10-24 | 2026-10-26 | 2026-11-06 |  | 1.5 | 0.72 | 7 | 38 | 1396.5 | 0.51557 | 199.8597 |  | 11
6-18 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 1500 | 0 | 1500 | 90 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-10-26 | 2026-10-28 | 2026-11-06 |  | 1.6 | 0.72 | 8.6 | 38 | 1830.08 | 0.81964 | 213.1837 |  | 10
6-18 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 3500 | 0 | 3500 | 210 | 2026-10-15 | 2026-10-21 | 2026-10-23 | 2026-10-28 | 2026-10-30 | 2026-11-06 |  | 1.8 | 0.72 | 8.6 | 38 | 2058.84 | 1.7 | 239.8317 |  | 8
6-18 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 8378 | 0 | 8378 | 502.68 | 2026-10-15 | 2026-10-23 | 2026-10-26 | 2026-11-02 | 2026-11-04 | 2026-11-06 |  | 2 | 0.72 | 8.6 | 38 | 2287.6 | 3.6624 | 266.4797 |  | 4
6-18 | ONY | 1194432_SP27 | Tee |  | 62377441, 442, 182, 113, 170, 255 |  |  | 635 | 0 | 635 | 33.8667 | 2026-11-13 | 2026-10-28 | 2026-10-30 | 2026-11-03 | 2026-11-05 | 2026-11-26 |  | 0.5 | 0.64 | 7 | 35 | 482.3438 | 1.3165 | 69.0305 |  | 20
6-18 | ONY | 1194432_SP27 | Tee |  | 62377441, 442, 182, 113, 170, 255 |  |  | 1500 | 0 | 1500 | 80 | 2026-11-13 | 2026-10-29 | 2026-10-31 | 2026-11-04 | 2026-11-06 | 2026-11-26 |  | 1 | 0.64 | 8.6 | 35 | 1185.1875 | 1.2656 | 138.061 |  | 19
6-18 | ONY | 1194432_SP27 | Tee |  | 62377441, 442, 182, 113, 170, 255 |  |  | 2500 | 0 | 2500 | 133.3333 | 2026-11-13 | 2026-10-30 | 2026-11-02 | 2026-11-06 | 2026-11-08 | 2026-11-26 |  | 1.2 | 0.64 | 8.6 | 35 | 1422.225 | 1.7578 | 165.6732 |  | 17
6-18 | ONY | 1194432_SP27 | Tee |  | 62377441, 442, 182, 113, 170, 255 |  |  | 3500 | 0 | 3500 | 186.6667 | 2026-11-13 | 2026-11-02 | 2026-11-04 | 2026-11-09 | 2026-11-11 | 2026-11-26 |  | 1.4 | 0.64 | 8.6 | 35 | 1659.2625 | 2.1094 | 193.2854 |  | 15
6-18 | ONY | 1194432_SP27 | Tee |  | 62377441, 442, 182, 113, 170, 255 |  |  | 5132 | 0 | 5132 | 273.7067 | 2026-11-13 | 2026-11-04 | 2026-11-06 | 2026-11-12 | 2026-11-14 | 2026-11-26 |  | 1.6 | 0.64 | 8.6 | 35 | 1896.3 | 2.7063 | 220.8976 |  | 12
6-18 | ONY | 1194432_SP27 | Tee |  | 62344833 |  |  | 126 | 0 | 126 | 6.72 | 2026-11-13 | 2026-11-07 | 2026-11-10 | 2026-11-12 | 2026-11-14 | 2026-12-02 |  | 1.6 | 0.64 | 8.6 | 35 | 1896.3 | 0.066445 | 220.8976 |  | 17
6-18 | ONY | 1194432_SP27 | Tee |  | 62379115 |  |  | 5924 | 0 | 5924 | 315.9467 | 2026-11-06 | 2026-11-07 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 2026-12-03 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 2.7769 | 248.5098 |  | 15
6-18 | ONY | 1194432_SP27 | Tee |  | 62379115 |  |  | 25000 | 0 | 25000 | 1333.3333 | 2026-11-06 | 2026-11-11 | 2026-11-13 | 2026-11-30 | 2026-12-02 | 2026-12-03 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 11.7187 | 248.5098 |  | 3
6-18 | ONY | 1194432_SP27 | Tee |  | 12.24 |  |  | 5933 | 0 | 5933 | 316.4267 | 2026-11-30 | 2026-11-25 | 2026-11-27 | 2026-12-03 | 2026-12-05 | 2026-12-24 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 2.7811 | 248.5098 |  | 18
6-18 | ONY | 1194432_SP27 | Tee |  | 12.31 |  |  | 13279 | 0 | 13279 | 708.2133 | 2026-11-30 | 2026-11-28 | 2026-12-01 | 2026-12-10 | 2026-12-12 | 2026-12-31 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 6.2245 | 248.5098 |  | 17
6-18 | ONY | 1194432_SP27 | Tee |  | 01.21 |  |  | 4451 | 0 | 4451 | 237.3867 | 2026-11-30 | 2026-12-05 | 2026-12-08 | 2026-12-12 | 2026-12-14 | 2027-01-21 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 2.0864 | 248.5098 |  | 32
6-18 | ONY | 1194432_SP27 | Tee |  | 01.28 |  |  | 9889 | 0 | 9889 | 527.4133 | 2026-11-30 | 2026-12-08 | 2026-12-10 | 2026-12-18 | 2026-12-20 | 2027-01-28 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 4.6355 | 248.5098 |  | 33
2026-06-05
6-19 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 30137 | 30137 | 0 | 3490.8692 | 2026-06-03 | 2026-05-30 | 2026-06-03 | 2026-07-11 | 2026-07-13 | 2026-07-09 |  | 1.6466 | 1.39 | 9.3862 | 35.7151 | 1000.7301 | 30.115 | 106.8093 |  | -4
6-19 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 17165 | 17165 | 0 | 1501.9375 | 2026-06-23 | 2026-07-07 | 2026-07-09 | 2026-07-28 | 2026-08-02 | 2026-09-24 |  | 1.8451 | 1.05 | 8.0928 | 35.1592 | 1260.0109 | 13.6229 | 155.977 |  | 41
6-19 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 176 | 176 | 0 | 15.4 | 2026-05-23 | 2026-07-23 | 2026-07-25 | 2026-07-28 | 2026-08-02 | 2026-07-30 |  | 1.3031 | 1.05 | 7.482 | 34.9354 | 817.4638 | 0.2153 | 109.4549 |  | 2
6-19 | ONY | 1182723_HO26 | Skorts |  | all po |  |  | 36303 | 36303 | 0 | 2752.9775 | 2026-07-14 | 2026-07-23 | 2026-07-25 | 2026-09-04 | 2026-09-06 | 2026-10-01 |  | 1.628 | 0.91 | 7.9417 | 37.2825 | 1334.8651 | 27.196 | 168.3851 |  | 19
6-19 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 23273 | 12579 | 10694 | 1027.8908 | 2026-08-06 | 2026-08-31 | 2026-09-02 | 2026-09-17 | 2026-09-19 | 2026-09-17 |  | 1.57 | 0.53 | 9 | 38 | 2552.9977 | 9.116 | 284.1779 |  | 0
6-19 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016283, 292, 296 |  |  | 8000 | 0 | 8000 | 353.3333 | 2026-08-06 | 2026-09-11 | 2026-09-15 | 2026-09-22 | 2026-09-24 | 2026-10-15 |  | 1.6 | 0.53 | 9 | 38 | 2601.7811 | 3.0748 | 289.6081 |  | 19
6-19 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 728 | 0 | 728 | 59.4533 | 2026-09-07 | 2026-09-16 | 2026-09-18 | 2026-09-24 | 2026-09-29 | 2026-10-01 |  | 0.5 | 0.98 | 7 | 38 | 342 | 2.1287 | 48.9452 |  | 5
6-19 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 1500 | 0 | 1500 | 122.5 | 2026-09-07 | 2026-09-18 | 2026-09-22 | 2026-09-28 | 2026-10-03 | 2026-10-01 |  | 1 | 0.98 | 9 | 38 | 879.4286 | 1.7057 | 97.8905 |  | 3
6-19 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 2700 | 0 | 2700 | 220.5 | 2026-09-07 | 2026-09-22 | 2026-09-24 | 2026-10-01 | 2026-10-06 | 2026-10-01 |  | 1.2 | 0.98 | 9 | 38 | 1055.3143 | 2.5585 | 117.4686 |  | 0
6-19 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62239979, 378, 565, 268, 269 |  |  | 1503 | 0 | 1503 | 122.745 | 2026-09-07 | 2026-09-25 | 2026-09-29 | 2026-10-02 | 2026-10-07 | 2026-10-08 |  | 1.4 | 0.98 | 8.6 | 38 | 1176.48 | 1.2775 | 137.0467 |  | 5
6-19 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 6500 | 0 | 6500 | 530.8333 | 2026-09-07 | 2026-09-28 | 2026-09-30 | 2026-10-08 | 2026-10-13 | 2026-10-15 |  | 1.6 | 0.98 | 8.6 | 38 | 1344.5486 | 4.8343 | 156.6248 |  | 6
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 750 | 0 | 750 | 105 | 2026-09-12 | 2026-09-30 | 2026-10-06 | 2026-10-13 | 2026-10-15 | 2026-10-29 |  | 0.5 | 1.68 | 7 | 38 | 199.5 | 3.7594 | 28.5514 |  | 14
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 1500 | 0 | 1500 | 210 | 2026-09-12 | 2026-10-05 | 2026-10-10 | 2026-10-16 | 2026-10-18 | 2026-10-29 |  | 1 | 1.68 | 8.6 | 38 | 490.2 | 3.06 | 57.1028 |  | 11
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 2000 | 0 | 2000 | 280 | 2026-09-12 | 2026-10-08 | 2026-10-14 | 2026-10-21 | 2026-10-23 | 2026-10-29 |  | 1.1 | 1.68 | 8.6 | 38 | 539.22 | 3.7091 | 62.8131 |  | 7
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 3547 | 0 | 3547 | 496.58 | 2026-09-12 | 2026-10-13 | 2026-10-19 | 2026-10-28 | 2026-10-30 | 2026-10-29 |  | 1.2 | 1.68 | 8.6 | 38 | 588.24 | 6.0299 | 68.5233 |  | 1
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0130 |  |  | 2000 | 0 | 2000 | 280 | 2026-10-03 | 2026-10-20 | 2026-10-26 | 2026-10-31 | 2026-11-02 | 2026-11-09 |  | 1.4 | 1.68 | 8.6 | 38 | 686.28 | 2.9143 | 79.9439 |  | 7
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0130 |  |  | 2332 | 0 | 2332 | 326.48 | 2026-10-03 | 2026-10-23 | 2026-10-29 | 2026-11-04 | 2026-11-06 | 2026-11-09 |  | 1.5 | 1.68 | 8.6 | 38 | 735.3 | 3.1715 | 85.6542 |  | 4
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0213 |  |  | 4000 | 0 | 4000 | 560 | 2026-10-17 | 2026-10-27 | 2026-11-02 | 2026-11-10 | 2026-11-12 | 2026-11-23 |  | 1.6 | 1.68 | 8.6 | 38 | 784.32 | 5.1 | 91.3645 |  | 11
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0227 |  |  | 6678 | 0 | 6678 | 934.92 | 2026-10-31 | 2026-11-02 | 2026-11-07 | 2026-11-19 | 2026-11-21 | 2026-12-07 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 7.5683 | 102.785 |  | 15
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0228_E |  |  | 1318 | 0 | 1318 | 59.31 | 2026-10-26 | 2026-11-14 | 2026-11-17 | 2026-11-21 | 2026-11-23 | 2026-11-27 |  | 0.5 | 0.54 | 7 | 38 | 620.6667 | 2.1235 | 88.8266 |  | 5
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0228_W |  |  | 2278 | 0 | 2278 | 102.51 | 2026-10-26 | 2026-11-17 | 2026-11-19 | 2026-11-23 | 2026-11-25 | 2026-12-08 |  | 1 | 0.54 | 8.6 | 38 | 1525.0667 | 1.4937 | 177.6531 |  | 13
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0228_W |  |  | 3000 | 0 | 3000 | 135 | 2026-10-26 | 2026-11-18 | 2026-11-20 | 2026-11-25 | 2026-11-27 | 2026-12-08 |  | 1.2 | 0.54 | 8.6 | 38 | 1830.08 | 1.6393 | 213.1837 |  | 11
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0323_E |  |  | 1448 | 0 | 1448 | 65.16 | 2026-11-06 | 2026-11-20 | 2026-11-23 | 2026-11-26 | 2026-11-28 | 2026-12-19 |  | 1.4 | 0.54 | 8.6 | 38 | 2135.0933 | 0.67819 | 248.7144 |  | 20
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0328_E |  |  | 1048 | 0 | 1048 | 47.16 | 2026-11-06 | 2026-11-21 | 2026-11-24 | 2026-11-26 | 2026-11-28 | 2026-12-24 |  | 1.6 | 0.54 | 8.6 | 38 | 2440.1067 | 0.42949 | 284.245 |  | 24
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0323_W |  |  | 5800 | 0 | 5800 | 261 | 2026-11-07 | 2026-11-21 | 2026-11-24 | 2026-11-28 | 2026-11-30 | 2026-12-31 |  | 1.8 | 0.54 | 8.6 | 38 | 2745.12 | 2.1128 | 319.7756 |  | 27
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0328_W |  |  | 4190 | 0 | 4190 | 188.55 | 2026-11-07 | 2026-11-24 | 2026-11-26 | 2026-11-30 | 2026-12-02 | 2027-01-05 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 1.3737 | 355.3062 |  | 29
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0427_E |  |  | 638 | 0 | 638 | 28.71 | 2026-11-16 | 2026-11-25 | 2026-11-27 | 2026-11-30 | 2026-12-02 | 2027-01-23 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.20917 | 355.3062 |  | 45
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0502_E |  |  | 460 | 0 | 460 | 20.7 | 2026-11-20 | 2026-11-25 | 2026-11-27 | 2026-11-30 | 2026-12-02 | 2027-01-29 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.15081 | 355.3062 |  | 50
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0427_W |  |  | 2552 | 0 | 2552 | 114.84 | 2026-11-16 | 2026-11-25 | 2026-11-27 | 2026-12-01 | 2026-12-03 | 2027-02-04 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.83668 | 355.3062 |  | 54
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0502_W |  |  | 1844 | 0 | 1844 | 82.98 | 2026-11-20 | 2026-11-26 | 2026-11-28 | 2026-12-02 | 2026-12-04 | 2027-02-09 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.60456 | 355.3062 |  | 57
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0530_E |  |  | 288 | 0 | 288 | 12.96 | 2026-11-30 | 2026-11-27 | 2026-11-30 | 2026-12-02 | 2026-12-04 | 2027-02-26 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.094422 | 355.3062 |  | 72
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0604_E |  |  | 396 | 0 | 396 | 17.82 | 2026-12-07 | 2026-11-27 | 2026-11-30 | 2026-12-02 | 2026-12-04 | 2027-03-03 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.12983 | 355.3062 |  | 76
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0530_W |  |  | 1146 | 0 | 1146 | 51.57 | 2026-11-30 | 2026-11-27 | 2026-11-30 | 2026-12-02 | 2026-12-04 | 2027-03-09 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.37572 | 355.3062 |  | 81
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0604_W |  |  | 1578 | 0 | 1578 | 71.01 | 2026-12-07 | 2026-11-27 | 2026-11-30 | 2026-12-03 | 2026-12-05 | 2027-03-13 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.51735 | 355.3062 |  | 84
2026-04-13
6-20 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 138695 | 138695 | 0 | 12135.8125 | 2026-05-23 | 2026-04-08 | 2026-04-10 | 2026-07-18 | 2026-07-23 | 2026-07-30 |  | 2.1304 | 1.05 | 9.4002 | 37.0349 | 1779.9917 | 77.9189 | 189.6972 |  | 10
6-20 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 770 | 770 | 0 | 67.375 | 2026-06-23 | 2026-07-14 | 2026-07-16 | 2026-07-20 | 2026-07-25 | 2026-08-20 |  | 2.0801 | 1.05 | 7.995 | 36 | 1436.8349 | 0.5359 | 180.0417 |  | 24
6-20 | HLF | CPM263PA81 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 31 | 31 | 0 | 2.7642 | 2026-05-23 | 2026-07-11 | 2026-07-17 | 2026-07-20 | 2026-07-22 | 2026-08-21 |  | 1.3516 | 1.07 | 8 | 37 | 942.2492 | 0.0329 | 117.9935 |  | 25
6-20 | HLF | CPM263PA05_26Q4 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 20835 | 20835 | 0 | 2100.8625 | 2026-07-10 | 2026-07-11 | 2026-07-17 | 2026-08-24 | 2026-08-26 | 2026-08-21 |  | 1.3551 | 1.21 | 7.7377 | 37.0102 | 808.2034 | 25.7794 | 104.6388 |  | -3
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025143 |  |  | 7812 | 7812 | 0 | 826.77 | 2026-08-18 | 2026-08-18 | 2026-08-20 | 2026-09-07 | 2026-09-09 | 2026-10-21 |  | 1.3827 | 1.27 | 8.781 | 35.519 | 855.7067 | 9.1293 | 97.6255 |  | 35
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025140 |  |  | 96 | 96 | 0 | 10.16 | 2026-08-18 | 2026-09-01 | 2026-09-03 | 2026-09-07 | 2026-09-09 | 2026-10-22 |  | 1.3376 | 1.27 | 9 | 34 | 812.1827 | 0.1182 | 90.4053 |  | 36
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025142 |  |  | 4384 | 3954 | 430 | 463.9733 | 2026-08-18 | 2026-09-01 | 2026-09-03 | 2026-09-11 | 2026-09-13 | 2026-11-18 |  | 1.72 | 1.27 | 9 | 37 | 1136.5002 | 3.8575 | 126.5055 |  | 55
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025142 |  |  | 5000 | 0 | 5000 | 529.1667 | 2026-08-18 | 2026-09-07 | 2026-09-09 | 2026-09-17 | 2026-09-19 | 2026-11-18 |  | 1.8 | 1.27 | 9 | 37 | 1189.3606 | 4.2039 | 132.3895 |  | 51
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025144 |  |  | 11000 | 0 | 11000 | 1164.1667 | 2026-08-18 | 2026-09-11 | 2026-09-15 | 2026-09-30 | 2026-10-02 | 2026-12-16 |  | 1.8 | 1.27 | 9 | 37 | 1189.3606 | 9.2487 | 132.3895 |  | 66
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025144 |  |  | 1504 | 0 | 1504 | 159.1733 | 2026-08-18 | 2026-09-24 | 2026-09-28 | 2026-10-01 | 2026-10-03 | 2026-12-16 |  | 1.8 | 1.27 | 9 | 37 | 1189.3606 | 1.2645 | 132.3895 |  | 65
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 795 | 0 | 795 | 113.95 | 2026-09-21 | 2026-09-22 | 2026-09-29 | 2026-10-06 | 2026-10-08 | 2026-11-02 |  | 0.5 | 1.72 | 7 | 37 | 189.7326 | 4.1901 | 27.1535 |  | 23
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 1400 | 0 | 1400 | 200.6667 | 2026-09-21 | 2026-09-28 | 2026-10-03 | 2026-10-09 | 2026-10-11 | 2026-11-02 |  | 1 | 1.72 | 8.6 | 37 | 466.2 | 3.003 | 54.3071 |  | 20
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 1500 | 0 | 1500 | 215 | 2026-09-21 | 2026-10-01 | 2026-10-07 | 2026-10-13 | 2026-10-15 | 2026-11-02 |  | 1.1 | 1.72 | 8.6 | 37 | 512.82 | 2.925 | 59.7378 |  | 17
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 2500 | 0 | 2500 | 358.3333 | 2026-09-21 | 2026-10-05 | 2026-10-10 | 2026-10-17 | 2026-10-19 | 2026-11-02 |  | 1.2 | 1.72 | 8.6 | 37 | 559.44 | 4.4688 | 65.1685 |  | 13
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 2795 | 0 | 2795 | 400.6167 | 2026-09-21 | 2026-10-09 | 2026-10-15 | 2026-10-22 | 2026-10-24 | 2026-11-02 |  | 1.4 | 1.72 | 8.6 | 37 | 652.68 | 4.2823 | 76.0299 |  | 9
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 5500 | 0 | 5500 | 788.3333 | 2026-09-21 | 2026-10-14 | 2026-10-20 | 2026-10-31 | 2026-11-02 | 2026-11-02 |  | 1.5 | 1.72 | 8.6 | 37 | 699.3 | 7.865 | 81.4606 |  | 1
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041497 |  |  | 2994 | 0 | 2994 | 429.14 | 2026-10-19 | 2026-10-23 | 2026-10-29 | 2026-11-05 | 2026-11-07 | 2026-11-16 |  | 1.6 | 1.72 | 8.6 | 37 | 745.92 | 4.0138 | 86.8913 |  | 9
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041486 |  |  | 3318 | 0 | 3318 | 475.58 | 2026-10-19 | 2026-10-28 | 2026-11-03 | 2026-11-10 | 2026-11-12 | 2026-11-30 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 3.954 | 97.7527 |  | 17
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041480 |  |  | 7556 | 0 | 7556 | 1083.0267 | 2026-11-02 | 2026-11-02 | 2026-11-07 | 2026-11-20 | 2026-11-22 | 2026-12-14 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 9.0042 | 97.7527 |  | 20
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041498 |  |  | 5748 | 0 | 5748 | 823.88 | 2026-11-02 | 2026-11-12 | 2026-11-18 | 2026-11-28 | 2026-11-30 | 2026-12-28 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 6.8497 | 97.7527 |  | 24
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041488 |  |  | 1992 | 0 | 1992 | 285.52 | 2026-11-02 | 2026-11-20 | 2026-11-26 | 2026-12-01 | 2026-12-03 | 2027-01-11 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 2.3738 | 97.7527 |  | 33
DATA END |  |  |  |  | PLEASE DO NOT REMOVE THIS ROW. NEW DATA PLEASE INSERT ABOVE ↑
| TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228 |  |  | 75715 |  |  |  | 2026-11-02: 2026-11-13; 2027-01-11: 2026-12-12 |  |  | 0.42
ORDER DATA FIRST |  |  |  |  | PLEASE DO NOT REMOVE THIS ROW. NEW DATA PLEASE INSERT BELOW ↓

## Holidays_Table
2025-01-01 | New Year's Day | 停工請C欄打勾"V"
2025-01-27 | Isra Mi'raj
2025-01-29 | Chinese New Year
2025-03-15 | Off
2025-03-22 | Off
2025-03-28 | Off
2025-03-29 | Hindu New Year
2025-03-31 | Eid Al-Fitr
2025-04-01 | Eid Al-Fitr
2025-04-02 | Eid Al-Fitr
2025-04-03 | Eid Al-Fitr
2025-04-04 | Eid Al-Fitr
2025-04-05 | Eid Al-Fitr
2025-04-07 | Off
2025-04-18 | Good Friday
2025-05-01 | World Labor Day
2025-05-12 | Waisak Day
2025-05-29 | Ascension Day of Jesus Christ
2025-06-06 | Eid Al Adha
2025-06-27 | Islamic New Year
2025-08-16 | Off
2025-08-23 | Off
2025-08-30 | Off
2025-09-05 | Prophet Muhammad's Birthday
2025-09-06 | Off
2025-12-25 | Christmas Day
2026-01-01 | New Year's Day
2026-01-16 | Isra Mi'raj
2026-02-17 | Chinese New Year
2026-03-19 | Hindu New Year
2026-03-20 | Eid Al-Fitr
2026-03-21 | Eid Al-Fitr
2026-03-23 | Eid Al-Fitr
2026-03-24 | Eid Al-Fitr
2026-03-25 | Eid Al-Fitr
2026-03-26 | Eid Al-Fitr
2026-04-03 | Good Friday
2026-05-01 | World Labor Day
2026-05-14 | Ascension Day of Jesus Christ
2026-05-27 | Eid Al Adha
2026-06-01 | Pancasila Day
2026-06-16 | Islamic New Year
2026-08-08 | Off
2026-08-15 | Off
2026-08-17 | Independent Day
2026-08-22 | Off
2026-08-25 | Prophet Muhammad's Birthday
2026-08-29 | Off
2026-09-05 | Off
2026-09-12 | Off
2026-09-19 | Off
2026-09-26 | Off
2026-12-25 | Christmas Day
2027-01-01 | New Year's Day

## B01_Summary
Line | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK
6-01 | PST840 | 2026-08-18 | 2026-09-03 | 2026-09-22 | 2026-10-02 | L6-01,6-08,6-15 | Z2850Y_C127 | 2026-09-12 | 2026-09-11 | 2026-12-15 | 2027-01-09 | L6-01,6-14,6-15,6-19
6-02 | X048GZ_C127 | 2026-08-22 | 2026-08-26 | 2026-10-09 | 2026-10-24 | L6-02,6-07 | 1195255_SP27 | 2026-10-07 | 2026-10-05 | 2026-10-17 | 2026-11-05 | L6-02,6-03 | 1194431_SP27 | 2026-10-07 | 2026-10-13 | 2026-11-02 | 2027-01-28 | L6-02 | CFM271SH09 | 2026-11-05 | 2026-10-28 | 2026-12-08 | 2026-12-07 | L6-02,6-14,6-16 | 1197198/1197204 | 2026-11-30 | 2026-12-03 | 2027-01-15 | 2027-01-28 | L6-02,6-03,6-08,6-09,6-13,6-14,6-16,6-17
6-03 | 1196262_HO26_PF/1196262_SP27 | 2026-09-07 | 2026-09-03 | 2026-10-21 | 2027-01-07 | L6-03,6-10,6-19 | 1195255_SP27 | 2026-10-07 | 2026-10-16 | 2026-11-28 | 2027-01-07 | L6-02,6-03 | 1197198/1197204 | 2026-11-30 | 2026-11-24 | 2027-01-13 | 2027-01-28 | L6-02,6-03,6-08,6-09,6-13,6-14,6-16,6-17
6-04 | MRLPMM_3PC_C127 | 2026-08-24 | 2026-09-01 | 2026-10-01 | 2026-10-08 | L6-04,6-11,6-17 | 766362_V1 | 2026-05-22 | 2026-09-25 | 2026-10-20 | 2026-11-12 | L6-04 | L0303X_6PK_C127 | 2026-10-12 | 2026-10-15 | 2026-11-18 | 2026-12-23 | L6-04,6-10 | 44ZEP9_3PK_C127 | 2026-11-13 | 2026-11-13 | 2027-01-29 | 2027-02-06 | L6-04,6-05,6-15
6-05 | 5GK4L2_C127 | 2026-09-10 | 2026-09-03 | 2026-09-22 | 2026-10-10 | L6-05 | 6ZE54X_C127 | 2026-09-21 | 2026-09-11 | 2026-11-17 | 2026-12-14 | L6-05,6-20 | 44ZEP9_3PK_C127 | 2026-11-13 | 2026-11-12 | 2027-01-29 | 2027-02-06 | L6-04,6-05,6-15
6-06 | 777362_HO26_GLD | 2026-08-29 | 2026-09-01 | 2026-09-11 | 2026-09-24 | L6-06 | 777362_VMI | 2026-08-01 | 2026-09-07 | 2026-10-14 | 2026-11-26 | L6-06,6-16 | 1204591_SP27_ID | 2026-10-12 | 2026-10-09 | 2026-10-21 | 2026-11-06 | L6-06 | MRLPMM_SSLLC127 | 2026-10-15 | 2026-10-16 | 2026-11-04 | 2026-11-06 | L6-06,6-18 | 777362_VMI | 2026-08-20 | 2026-10-30 | 2026-11-16 | 2027-01-07 | L6-06,6-16 | CFW271SH01 | 2026-11-09 | 2026-11-07 | 2026-12-11 | 2026-12-10 | L6-06,6-17
6-07 | 352E6Y_SL_C127 | 2026-08-24 | 2026-08-14 | 2026-09-17 | 2026-10-26 | L6-07 | X048GZ_C127 | 2026-08-22 | 2026-09-08 | 2026-09-25 | 2026-10-01 | L6-02,6-07 | 352E6Y_SL_C127 | 2026-08-24 | 2026-09-16 | 2026-10-08 | 2026-12-05 | L6-07 | 1194432_SP27 | 2026-10-09 | 2026-10-03 | 2026-10-26 | 2026-11-05 | L6-07,6-13,6-18 | 440ZP9_C127 | 2026-10-17 | 2026-10-21 | 2026-12-15 | 2026-12-17 | L6-07,6-10
6-08 | PST840 | 2026-08-18 | 2026-09-01 | 2026-10-14 | 2026-12-03 | L6-01,6-08,6-15 | 546462_6PK_C127 | 2026-10-13 | 2026-10-09 | 2026-11-27 | 2026-12-30 | L6-08 | 1197198/1197204 | 2026-11-30 | 2026-11-23 | 2027-01-14 | 2027-01-28 | L6-02,6-03,6-08,6-09,6-13,6-14,6-16,6-17
6-09 | W9ZMM8_7PK_C426 | 2026-06-27 | 2026-07-17 | 2026-09-18 | 2026-11-04 | L6-09 | 9KM9L2_C127 | 2026-09-08 | 2026-09-14 | 2026-11-02 | 2026-12-16 | L6-09,6-12 | W9ZMM8_7PK_C127 | 2026-10-13 | 2026-10-24 | 2026-11-27 | 2026-12-30 | L6-09 | 1197198/1197204 | 2026-11-30 | 2026-11-23 | 2027-01-14 | 2027-01-28 | L6-02,6-03,6-08,6-09,6-13,6-14,6-16,6-17
6-10 | 1188289_HO26 | 2026-08-06 | 2026-08-26 | 2026-09-18 | 2026-10-15 | L6-10,6-13,6-19 | 1196262_HO26_PF | 2026-09-07 | 2026-09-14 | 2026-10-08 | 2026-10-15 | L6-03,6-10,6-19 | L0303X_6PK_C127 | 2026-10-12 | 2026-10-03 | 2026-11-03 | 2026-12-16 | L6-04,6-10 | 440ZP9_C127 | 2026-10-31 | 2026-10-29 | 2026-12-15 | 2026-12-17 | L6-07,6-10
6-11 | MRLPMM_3PC_C127 | 2026-08-24 | 2026-08-14 | 2026-11-16 | 2026-12-05 | L6-04,6-11,6-17 | 458476_2PK_C127 | 2026-10-24 | 2026-11-11 | 2027-01-11 | 2027-04-06 | L6-11
6-12 | ZC6HY000 | 2026-07-30 | 2026-08-19 | 2026-09-11 | 2026-09-28 | L6-12 | 9KM9L2_C127 | 2026-09-08 | 2026-09-07 | 2026-12-19 | 2027-01-13 | L6-09,6-12
6-13 | 1188289_HO26 | 2026-08-06 | 2026-09-02 | 2026-10-03 | 2026-11-12 | L6-10,6-13,6-19 | 1194432_SP27 | 2026-10-09 | 2026-09-29 | 2026-12-09 | 2027-01-28 | L6-07,6-13,6-18 | 1197198/1197204 | 2026-11-30 | 2026-12-04 | 2027-01-21 | 2027-01-28 | L6-02,6-03,6-08,6-09,6-13,6-14,6-16,6-17
6-14 | 00GG4Z_C127IND | 2026-08-22 | 2026-09-04 | 2026-10-06 | 2026-12-28 | L6-14 | Z2850Y_C127 | 2026-09-12 | 2026-09-28 | 2026-10-14 | 2026-10-29 | L6-01,6-14,6-15,6-19 | L06X27_SSLLC127 | 2026-10-15 | 2026-10-09 | 2026-11-07 | 2026-11-06 | L6-14 | CFM271SH09 | 2026-11-05 | 2026-11-03 | 2026-12-07 | 2026-12-07 | L6-02,6-14,6-16 | 1197198/1197204 | 2026-11-30 | 2026-12-02 | 2027-01-16 | 2027-01-28 | L6-02,6-03,6-08,6-09,6-13,6-14,6-16,6-17
6-15 | PST840 | 2026-08-18 | 2026-09-04 | 2026-09-14 | 2026-09-22 | L6-01,6-08,6-15 | LPST840 | 2026-08-24 | 2026-09-08 | 2026-09-28 | 2026-11-02 | L6-15 | PST840 | 2026-08-24 | 2026-09-22 | 2026-10-07 | 2026-12-03 | L6-01,6-08,6-15 | Z2850Y_C127 | 2026-09-12 | 2026-09-29 | 2026-11-10 | 2026-11-23 | L6-01,6-14,6-15,6-19 | 44ZEP9_3PK_C127 | 2026-11-13 | 2026-11-05 | 2027-01-05 | 2027-01-09 | L6-04,6-05,6-15
6-16 | 777362_VMI | 2026-06-23 | 2026-08-05 | 2026-10-05 | 2026-10-15 | L6-06,6-16 | 1194585_HO26_NB | 2026-09-10 | 2026-09-25 | 2026-10-09 | 2026-10-29 | L6-16 | 1193182_SP27 | 2026-10-09 | 2026-10-01 | 2026-11-05 | 2027-01-28 | L6-16 | CFM271SH09 | 2026-11-05 | 2026-10-31 | 2026-12-04 | 2026-12-07 | L6-02,6-14,6-16 | 1197198/1197204 | 2026-11-30 | 2026-11-30 | 2027-01-15 | 2027-01-28 | L6-02,6-03,6-08,6-09,6-13,6-14,6-16,6-17
6-17 | MRLPMM_3PC_C127 | 2026-08-24 | 2026-08-27 | 2026-11-13 | 2026-12-05 | L6-04,6-11,6-17 | CFW271SH01 | 2026-11-09 | 2026-11-05 | 2026-12-12 | 2026-12-10 | L6-06,6-17 | 1197198/1197204 | 2026-11-30 | 2026-12-08 | 2027-01-15 | 2027-01-28 | L6-02,6-03,6-08,6-09,6-13,6-14,6-16,6-17
6-18 | 352E6Y_LL_C127 | 2026-08-18 | 2026-08-26 | 2026-10-12 | 2026-12-05 | L6-18 | 1KE9E9_SSLLC127 | 2026-10-15 | 2026-10-07 | 2026-10-23 | 2026-11-06 | L6-18 | MRLPMM_SSLLC127 | 2026-10-15 | 2026-10-19 | 2026-11-02 | 2026-11-06 | L6-06,6-18 | 1194432_SP27 | 2026-11-13 | 2026-10-28 | 2026-12-18 | 2027-01-28 | L6-07,6-13,6-18
6-19 | 1188289_HO26 | 2026-08-06 | 2026-08-31 | 2026-09-22 | 2026-10-15 | L6-10,6-13,6-19 | 1196262_HO26_PF | 2026-09-07 | 2026-09-16 | 2026-10-08 | 2026-10-15 | L6-03,6-10,6-19 | Z2850Y_C127 | 2026-09-12 | 2026-09-30 | 2026-11-19 | 2026-12-07 | L6-01,6-14,6-15,6-19 | G92X13_2PK_C127 | 2026-10-26 | 2026-11-14 | 2026-12-03 | 2027-03-13 | L6-19
6-20 | 4401EW_C127 | 2026-08-18 | 2026-09-01 | 2026-10-01 | 2026-12-16 | L6-20 | 6ZE54X_C127 | 2026-09-21 | 2026-09-22 | 2026-12-01 | 2027-01-11 | L6-05,6-20

## B02_Summary_By _Order
款式 Style | 產品 Product Item | 可開裁日 CRFP | 組別 Line | 預計開裁日 Est. Start Cut | 預計上線日 Sewing Start | 工作時數 Work hr | 預計日產 Target Output | 預計下線日 Est. Sewing Fin. | 剩餘工作天 Need Work Days | 剩餘數量 Remainning Qty | 分配訂單數量 Allocate Qty
00GG4Z_C127IND | Pull On Pants | 2026-08-22 | 6-14 | 2026-08-10 | 2026-08-12 | 8.7557 | 753.7722 | 2026-10-06 | 20.4438 | 15410 | 26016
00GG4Z_C127IND 合計 | [9 empty] | 15410 | 26016
1182430_HO26_HT | Pull On Pants | 2026-08-06 | 6-01 | 2026-07-22 | 2026-07-24 | 7.8679 | 1134.2557 | 2026-08-31 | 0 | 0 | 27270
| Pull On Pants | 2026-08-24 | 6-17 | 2026-08-06 | 2026-08-10 | 8.3389 | 1166.5206 | 2026-09-04 | 0 | 0 | 17242
1182430_HO26_HT 合計 | [9 empty] | 0 | 44512
1182719_HO26 | Skorts | 2026-07-11 | 6-10 | 2026-08-04 | 2026-08-06 | 8 | 1659.9607 | 2026-09-01 | 0 | 0 | 23350
| Skorts | 2026-07-11 | 6-11 | 2026-07-30 | 2026-08-01 | 8 | 1288.3006 | 2026-08-26 | 0 | 0 | 17407
1182719_HO26 合計 | [9 empty] | 0 | 40757
1182723_HO26 | Skorts | 2026-07-14 | 6-13 | 2026-07-25 | 2026-07-28 | 7.8718 | 1178.6229 | 2026-09-08 | 0 | 0 | 32276
| Skorts | 2026-07-14 | 6-19 | 2026-07-23 | 2026-07-25 | 7.9417 | 1334.8651 | 2026-09-04 | 0 | 0 | 36303
1182723_HO26 合計 | [9 empty] | 0 | 68579
1184403_HO26 | Pull On Pants | 2026-07-13 | 6-10 | 2026-07-20 | 2026-07-22 | 7.2192 | 562.4717 | 2026-08-10 | 0 | 0 | 7414
1184403_HO26 合計 | [9 empty] | 0 | 7414
1184404_HO26 | Tee | 2026-07-13 | 6-05 | 2026-07-17 | 2026-07-20 | 6.9853 | 671.4355 | 2026-07-31 | 0 | 0 | 5350
1184404_HO26 合計 | [9 empty] | 0 | 5350
1188289_HO26 | Pull On Pants | 2026-08-06 | 6-10 | 2026-08-26 | 2026-08-28 | 9 | 2551.758 | 2026-09-18 | 5.7662 | 14714 | 33327
| Pull On Pants | 2026-08-06 | 6-13 | 2026-09-02 | 2026-09-04 | 9 | 2284.6721 | 2026-10-03 | 14.0326 | 32060 | 43504
| Pull On Pants | 2026-08-06 | 6-19 | 2026-08-31 | 2026-09-02 | 9 | 2565.3021 | 2026-09-22 | 7.2873 | 18694 | 31273
1188289_HO26 合計 | [9 empty] | 65468 | 108104
1193182_SP27 | Tee | 2026-10-09 | 6-16 | 2026-10-01 | 2026-10-07 | 8.5236 | 1716.8534 | 2026-11-05 | 23.2559 | 39927 | 39927
1193182_SP27 合計 | [9 empty] | 39927 | 39927
1194431_SP27 | Tee | 2026-10-07 | 6-02 | 2026-10-13 | 2026-10-15 | 8.4417 | 780.7159 | 2026-11-02 | 13.3006 | 10384 | 10384
1194431_SP27 合計 | [9 empty] | 10384 | 10384
1194432_SP27 | Tee | 2026-10-09 | 6-07 | 2026-10-03 | 2026-10-06 | 8.4428 | 1841.8788 | 2026-10-26 | 15.0037 | 27635 | 27635
| Tee | 2026-10-09 | 6-13 | 2026-09-29 | 2026-10-01 | 8.5562 | 2018.4262 | 2026-12-09 | 57.6409 | 116344 | 116344
| Tee | 2026-11-13 | 6-18 | 2026-10-28 | 2026-10-30 | 8.5466 | 1974.1096 | 2026-12-18 | 39.4451 | 77869 | 77869
1194432_SP27 合計 | [9 empty] | 221848 | 221848
1194585_HO26_NB | Pull On Pants | 2026-09-10 | 6-16 | 2026-09-25 | 2026-10-02 | 8.0813 | 801.4637 | 2026-10-09 | 3.7432 | 3000 | 3000
1194585_HO26_NB 合計 | [9 empty] | 3000 | 3000
1195255_SP27 | Tee | 2026-10-07 | 6-02 | 2026-10-05 | 2026-10-07 | 8.3297 | 1296.7181 | 2026-10-17 | 6.9846 | 9057 | 9057
| Tee | 2026-10-07 | 6-03 | 2026-10-16 | 2026-10-19 | 8.5453 | 1998.1584 | 2026-11-28 | 33.5059 | 66950 | 66950
1195255_SP27 合計 | [9 empty] | 76007 | 76007
1196262_HO26_PF | Tee | 2026-09-07 | 6-03 | 2026-09-03 | 2026-09-07 | 8.7243 | 1283.0295 | 2026-10-12 | 24.4679 | 31393 | 31397
| Tee | 2026-09-07 | 6-10 | 2026-09-14 | 2026-09-16 | 8.4878 | 1134.1278 | 2026-10-08 | 15.1491 | 17181 | 17181
| Tee | 2026-09-07 | 6-19 | 2026-09-16 | 2026-09-18 | 8.464 | 1034.0942 | 2026-10-08 | 12.5047 | 12931 | 12931
1196262_HO26_PF 合計 | [9 empty] | 61505 | 61509
1196262_SP27 | Tee | 2026-10-10 | 6-03 | 2026-10-07 | 2026-10-09 | 8.6 | 1486.1881 | 2026-10-21 | 8.7708 | 13035 | 13035
1196262_SP27 合計 | [9 empty] | 13035 | 13035
1197198/1197204 | Dress | 2026-11-30 | 6-02 | 2026-12-03 | 2026-12-05 | 8.4792 | 1097.8496 | 2027-01-15 | 31.048 | 34086 | 34086
| Dress | 2026-11-30 | 6-03 | 2026-11-24 | 2026-11-26 | 8.4992 | 1150.7679 | 2027-01-13 | 36.6156 | 42136 | 42136
| Dress | 2026-11-30 | 6-08 | 2026-11-23 | 2026-11-25 | 8.5065 | 1187.6994 | 2027-01-14 | 38.466 | 45686 | 45686
| Dress | 2026-11-30 | 6-09 | 2026-11-23 | 2026-11-25 | 8.508 | 1195.4306 | 2027-01-14 | 39.0872 | 46726 | 46726
| Dress | 2026-11-30 | 6-13 | 2026-12-04 | 2026-12-07 | 8.4927 | 1080.9769 | 2027-01-21 | 36.2043 | 39136 | 39136
| Dress | 2026-11-30 | 6-14 | 2026-12-02 | 2026-12-04 | 8.4847 | 1078.3303 | 2027-01-16 | 33.5574 | 36186 | 36186
| Dress | 2026-11-30 | 6-16 | 2026-11-30 | 2026-12-02 | 8.494 | 1173.5056 | 2027-01-15 | 33.7757 | 39636 | 39636
| Dress | 2026-11-30 | 6-17 | 2026-12-08 | 2026-12-10 | 8.461 | 1129.3378 | 2027-01-15 | 25.7549 | 29086 | 29086
1197198/1197204 合計 | [9 empty] | 312678 | 312678
1204591_SP27_ID | Pull On Pants | 2026-10-12 | 6-06 | 2026-10-09 | 2026-10-12 | 7.7793 | 434.2833 | 2026-10-21 | 5.7566 | 2500 | 2500
1204591_SP27_ID 合計 | [9 empty] | 2500 | 2500
1KE9E9_SSLLC127 | Pajama | 2026-10-15 | 6-18 | 2026-10-07 | 2026-10-09 | 8.4959 | 2240.2808 | 2026-10-23 | 8.856 | 19840 | 19840
1KE9E9_SSLLC127 合計 | [9 empty] | 19840 | 19840
352E6Y_LL_C127 | Pajama | 2026-08-18 | 6-18 | 2026-08-21 | 2026-08-31 | 8.7831 | 2128.9357 | 2026-10-12 | 24.8054 | 52809 | 62909
352E6Y_LL_C127 合計 | [9 empty] | 52809 | 62909
352E6Y_SL_C127 | Pajama | 2026-08-15 | 6-07 | 2026-08-12 | 2026-08-20 | 8.7703 | 1835.1308 | 2026-09-17 | 5.8791 | 10789 | 33282
| Pajama | 2026-08-24 | 6-07 | 2026-09-16 | 2026-09-23 | 8.7435 | 2264.5585 | 2026-10-08 | 9.3581 | 21192 | 21192
352E6Y_SL_C127 合計 | [9 empty] | 31981 | 54474
4401EW_C127 | Robe | 2026-08-18 | 6-20 | 2026-08-18 | 2026-08-20 | 8.9281 | 1070.947 | 2026-10-01 | 16.7459 | 17934 | 29796
4401EW_C127 合計 | [9 empty] | 17934 | 29796
440ZP9_C127 | Pull On Pants | 2026-10-17 | 6-07 | 2026-10-21 | 2026-10-23 | 8.522 | 1425.8985 | 2026-12-15 | 42.893 | 61161 | 61161
| Pull On Pants | 2026-10-31 | 6-10 | 2026-10-29 | 2026-10-31 | 8.4908 | 1384.9634 | 2026-12-15 | 34.5843 | 47898 | 47898
440ZP9_C127 合計 | [9 empty] | 109059 | 109059
44ZEP9_3PK_C127 | Boxer | 2026-11-13 | 6-04 | 2026-11-13 | 2026-11-16 | 8.5834 | 3899.2658 | 2027-01-29 | 60.2678 | 235000 | 235000
| Boxer | 2026-11-13 | 6-05 | 2026-11-12 | 2026-11-14 | 8.5475 | 3301.232 | 2027-01-29 | 62.1553 | 205189 | 205189
| Boxer | 2026-11-13 | 6-15 | 2026-11-05 | 2026-11-07 | 8.5304 | 3200.2572 | 2027-01-05 | 46.9125 | 150132 | 150132
44ZEP9_3PK_C127 合計 | [9 empty] | 590321 | 590321
458476_2PK_C127 | Boxer | 2026-10-24 | 6-11 | 2026-11-11 | 2026-11-13 | 8.5616 | 2393.569 | 2027-01-11 | 45.9581 | 110004 | 110004
458476_2PK_C127 合計 | [9 empty] | 110004 | 110004
45M87P_C426 | Pull On Pants | 2026-06-27 | 6-01 | 2026-06-30 | 2026-07-02 | 8.0771 | 836.0225 | 2026-07-27 | 0 | 0 | 15985
45M87P_C426 合計 | [9 empty] | 0 | 15985
546462_6PK_C127 | Panties | 2026-10-13 | 6-08 | 2026-10-09 | 2026-10-12 | 8.5582 | 5292.2703 | 2026-11-27 | 39.2497 | 207720 | 207720
546462_6PK_C127 合計 | [9 empty] | 207720 | 207720
5GK4L2_C127 | Jumper | 2026-09-10 | 6-05 | 2026-09-03 | 2026-09-07 | 8.3346 | 376.7387 | 2026-09-22 | 7.3685 | 2776 | 2916
5GK4L2_C127 合計 | [9 empty] | 2776 | 2916
5GK4L2_C426 | Jumper | 2026-07-03 | 6-05 | 2026-07-09 | 2026-07-11 | 7.5859 | 393.2819 | 2026-07-22 | 0 | 0 | 2892
5GK4L2_C426 合計 | [9 empty] | 0 | 2892
6ZE54X_C127 | Pull On Pants | 2026-09-21 | 6-05 | 2026-09-11 | 2026-09-18 | 8.4518 | 561.7014 | 2026-11-17 | 47.8243 | 26863 | 26863
| Pull On Pants | 2026-09-21 | 6-20 | 2026-09-22 | 2026-09-29 | 8.4733 | 681.9982 | 2026-12-01 | 52.9298 | 36098 | 36098
6ZE54X_C127 合計 | [9 empty] | 62961 | 62961
766362_HO26 | Pull On Pants | 2026-07-09 | 6-04 | 2026-07-01 | 2026-07-03 | 8.2229 | 1239.9326 | 2026-07-29 | 0 | 0 | 24434
| Pull On Pants | 2026-08-18 | 6-04 | 2026-08-06 | 2026-08-10 | 9 | 1703.6372 | 2026-09-07 | 0.13677 | 233 | 27675
| Pull On Pants | 2026-08-04 | 6-08 | 2026-07-08 | 2026-07-10 | 7.985 | 1535.2206 | 2026-08-19 | 0 | 0 | 43769
766362_HO26 合計 | [9 empty] | 233 | 95878
766362_V1 | Pull On Pants | 2026-05-22 | 6-04 | 2026-09-01 | 2026-09-03 | 9 | 1703.6372 | 2026-09-08 | 0.0076307 | 13 | 855
| Pull On Pants | 2026-05-22 | 6-04 | 2026-09-25 | 2026-09-29 | 8.2933 | 1179.9728 | 2026-10-20 | 14.9673 | 17661 | 17661
| Pull On Pants | 2026-05-22 | 6-08 | 2026-06-04 | 2026-06-06 | 9.3671 | 1437.6838 | 2026-07-13 | 0 | 0 | 39555
| Pull On Pants | 2026-05-22 | 6-08 | 2026-08-12 | 2026-08-14 | 8.0562 | 1356.1006 | 2026-09-07 | 0 | 0 | 15895
766362_V1 合計 | [9 empty] | 17674 | 73966
777362_FA26 | Pull On Pants | 2026-05-23 | 6-03 | 2026-05-15 | 2026-05-18 | 9.1023 | 1259.5162 | 2026-06-09 | 0 | 0 | 19159
| Pull On Pants | 2026-04-25 | 6-04 | 2026-04-15 | 2026-04-17 | 8.8333 | 1159.316 | 2026-05-18 | 0 | 0 | 26479
| Pull On Pants | 2026-05-26 | 6-05 | 2026-06-12 | 2026-06-15 | 9.1485 | 1399.0404 | 2026-07-14 | 0 | 0 | 31058
| Pull On Pants | 2026-05-26 | 6-06 | 2026-06-15 | 2026-06-18 | 9.4584 | 1510.9939 | 2026-07-10 | 0 | 0 | 25055
| Pull On Pants | 2026-05-26 | 6-08 | 2026-05-26 | 2026-05-29 | 8.7363 | 1308.6032 | 2026-06-09 | 0 | 0 | 7260
| Pull On Pants | 2026-04-25 | 6-10 | 2026-04-13 | 2026-04-15 | 8.5757 | 1103.5488 | 2026-05-05 | 0 | 0 | 15160
| Pull On Pants | 2026-05-26 | 6-13 | 2026-06-30 | 2026-07-02 | 9.3933 | 1193.554 | 2026-07-20 | 0 | 0 | 15589
| Pull On Pants | 2026-05-26 | 6-15 | 2026-06-23 | 2026-06-25 | 9.3739 | 1550.6758 | 2026-07-16 | 0 | 0 | 24345
| Pull On Pants | 2026-05-23 | 6-19 | 2026-07-23 | 2026-07-25 | 7.482 | 817.4638 | 2026-07-28 | 0 | 0 | 176
| Pull On Pants | 2026-05-23 | 6-20 | 2026-04-08 | 2026-04-10 | 9.4002 | 1779.9917 | 2026-07-18 | 0 | 0 | 138695
777362_FA26 合計 | [9 empty] | 0 | 302976
777362_HO26_GLD | Pull On Pants | 2026-08-29 | 6-06 | 2026-09-01 | 2026-09-03 | 9 | 1600.4197 | 2026-09-11 | 0.71356 | 1142 | 6081
777362_HO26_GLD 合計 | [9 empty] | 1142 | 6081
777362_VMI | Pull On Pants | 2026-05-04 | 6-03 | 2026-04-16 | 2026-04-18 | 9.1703 | 1300.1298 | 2026-05-20 | 0 | 0 | 29699
| Pull On Pants | 2026-05-07 | 6-05 | 2026-03-28 | 2026-03-31 | 8.9946 | 1259.8102 | 2026-05-29 | 0 | 0 | 56118
| Pull On Pants | 2026-04-13 | 6-06 | 2026-04-08 | 2026-04-10 | 8.7258 | 1219.0291 | 2026-05-06 | 0 | 0 | 24866
| Pull On Pants | 2026-06-23 | 6-06 | 2026-07-06 | 2026-07-08 | 8.6037 | 1582.7515 | 2026-09-07 | 0.21797 | 345 | 67904
| Pull On Pants | 2026-08-01 | 6-06 | 2026-09-07 | 2026-09-09 | 8.8657 | 1725.5588 | 2026-10-14 | 25.7853 | 44494 | 44494
| Pull On Pants | 2026-08-20 | 6-06 | 2026-10-30 | 2026-11-02 | 8.3862 | 1161.6371 | 2026-11-16 | 10.6815 | 12408 | 12408
| Pull On Pants | 2026-05-07 | 6-07 | 2026-07-04 | 2026-07-07 | 8.2762 | 1035.0792 | 2026-07-23 | 0 | 0 | 11906
| Pull On Pants | 2026-05-07 | 6-08 | 2026-04-17 | 2026-04-20 | 9.3938 | 1434.8257 | 2026-06-02 | 0 | 0 | 43947
| Pull On Pants | 2026-05-04 | 6-12 | 2026-04-18 | 2026-04-21 | 9.1441 | 1376.3212 | 2026-05-26 | 0 | 0 | 36158
| Pull On Pants | 2026-06-23 | 6-13 | 2026-07-15 | 2026-07-17 | 7.9762 | 1104.5568 | 2026-07-30 | 0 | 0 | 10000
| Pull On Pants | 2026-06-23 | 6-15 | 2026-07-11 | 2026-07-14 | 7.855 | 1210.7956 | 2026-07-22 | 0 | 0 | 5783
| Pull On Pants | 2026-05-07 | 6-16 | 2026-04-09 | 2026-04-11 | 9.2232 | 1414.0742 | 2026-06-03 | 0 | 0 | 55281
| Pull On Pants | 2026-06-23 | 6-16 | 2026-08-05 | 2026-08-07 | 8.8761 | 1675.6723 | 2026-10-05 | 17.2164 | 28849 | 63546
| Pull On Pants | 2026-05-07 | 6-18 | 2026-04-01 | 2026-04-04 | 9.0947 | 1505.6912 | 2026-05-25 | 0 | 0 | 58617
| Pull On Pants | 2026-06-23 | 6-18 | 2026-08-12 | 2026-08-14 | 8.0143 | 1260.476 | 2026-08-21 | 0 | 0 | 2978
| Pull On Pants | 2026-06-23 | 6-19 | 2026-07-07 | 2026-07-09 | 8.0928 | 1260.0109 | 2026-07-28 | 0 | 0 | 17165
| Pull On Pants | 2026-06-23 | 6-20 | 2026-07-14 | 2026-07-16 | 7.995 | 1436.8349 | 2026-07-20 | 0 | 0 | 770
777362_VMI 合計 | [9 empty] | 86096 | 541640
826369_HO26 | Pull On Pants | 2026-07-13 | 6-10 | 2026-07-15 | 2026-07-17 | 7.2576 | 622.6666 | 2026-07-24 | 0 | 0 | 2235
826369_HO26 合計 | [9 empty] | 0 | 2235
890955_FA26 | Pull On Pants | 2026-04-30 | 6-06 | 2026-04-30 | 2026-05-04 | 8.5835 | 1045.603 | 2026-05-15 | 0 | 0 | 7023
| Pull On Pants | 2026-04-13 | 6-06 | 2026-06-11 | 2026-06-13 | 9.4007 | 1112.5004 | 2026-06-20 | 0 | 0 | 3293
890955_FA26 合計 | [9 empty] | 0 | 10316
905200_FA26 | Pull On Pants | 2026-05-02 | 6-06 | 2026-05-09 | 2026-05-12 | 9.4741 | 1056.0642 | 2026-06-17 | 0 | 0 | 26558
| Pull On Pants | 2026-05-15 | 6-10 | 2026-05-05 | 2026-05-07 | 9.3511 | 1100.8636 | 2026-07-14 | 0 | 0 | 57498
905200_FA26 合計 | [9 empty] | 0 | 84056
907938_FA26 | Leggings | 2026-05-07 | 6-12 | 2026-05-21 | 2026-05-23 | 7.881 | 502.1956 | 2026-05-29 | 0 | 0 | 1178
907938_FA26 合計 | [9 empty] | 0 | 1178
910047_FA26 | Pajama | 2026-06-03 | 6-01 | 2026-06-06 | 2026-06-09 | 9.2169 | 873.476 | 2026-07-04 | 0 | 0 | 16401
| Pajama | 2026-06-03 | 6-03 | 2026-06-04 | 2026-06-06 | 9.5107 | 1006.3981 | 2026-07-13 | 0 | 0 | 28598
| Pajama | 2026-06-03 | 6-04 | 2026-05-26 | 2026-05-29 | 9.1249 | 816.4257 | 2026-06-30 | 0 | 0 | 18832
| Pajama | 2026-06-03 | 6-07 | 2026-05-30 | 2026-06-03 | 9.211 | 868.1993 | 2026-07-09 | 0 | 0 | 24374
| Pajama | 2026-06-03 | 6-12 | 2026-05-23 | 2026-05-26 | 9.4353 | 957.9881 | 2026-07-09 | 0 | 0 | 31999
| Pajama | 2026-06-03 | 6-15 | 2026-06-05 | 2026-06-08 | 9.1261 | 899.3507 | 2026-06-27 | 0 | 0 | 12675
| Pajama | 2026-06-03 | 6-18 | 2026-05-20 | 2026-05-22 | 9.4411 | 1055.0911 | 2026-07-08 | 0 | 0 | 36668
| Pajama | 2026-06-03 | 6-19 | 2026-05-30 | 2026-06-03 | 9.3862 | 1000.7301 | 2026-07-11 | 0 | 0 | 30137
910047_FA26 合計 | [9 empty] | 0 | 199684
910047_HO26DIS | Pajama | 2026-07-06 | 6-03 | 2026-07-08 | 2026-07-10 | 8.4758 | 1018.4268 | 2026-07-25 | 0 | 0 | 11308
| Pajama | 2026-07-06 | 6-12 | 2026-07-04 | 2026-07-07 | 8.2028 | 948.3748 | 2026-08-13 | 0 | 0 | 27677
| Pajama | 2026-07-06 | 6-18 | 2026-07-03 | 2026-07-06 | 8.2635 | 1164.4988 | 2026-08-19 | 0 | 0 | 38392
| Pajama | 2026-07-06 | 6-18 | 2026-08-14 | 2026-08-19 | 8.5299 | 1141.6509 | 2026-09-02 | 0 | 0 | 8515
910047_HO26DIS 合計 | [9 empty] | 0 | 85892
915810_FA26 | Tee | 2026-05-15 | 6-04 | 2026-05-12 | 2026-05-15 | 8.7965 | 610.2657 | 2026-06-02 | 0 | 0 | 6456
| Tee | 2026-06-04 | 6-04 | 2026-06-25 | 2026-06-27 | 7.7074 | 596.92 | 2026-07-06 | 0 | 0 | 3182
915810_FA26 合計 | [9 empty] | 0 | 9638
962148_FA26 | Leggings | 2026-04-15 | 6-10 | 2026-04-29 | 2026-05-02 | 8.0175 | 1209.8277 | 2026-05-09 | 0 | 0 | 4540
962148_FA26 合計 | [9 empty] | 0 | 4540
9KM9L2_C127 | Pull On Pants | 2026-09-08 | 6-09 | 2026-09-14 | 2026-09-16 | 8.5577 | 1115.5124 | 2026-11-02 | 36.6235 | 40854 | 40854
| Pull On Pants | 2026-09-08 | 6-12 | 2026-09-07 | 2026-09-09 | 8.6073 | 1267.9478 | 2026-12-19 | 83.408 | 105757 | 105757
9KM9L2_C127 合計 | [9 empty] | 146611 | 146611
CFM271SH09 | Pull On Pants | 2026-11-05 | 6-02 | 2026-10-28 | 2026-10-30 | 8.4558 | 866.1107 | 2026-12-08 | 30.2871 | 26232 | 26232
| Pull On Pants | 2026-11-05 | 6-14 | 2026-11-03 | 2026-11-05 | 8.4123 | 780.2337 | 2026-12-07 | 24.0082 | 18732 | 18732
| Pull On Pants | 2026-11-05 | 6-16 | 2026-10-31 | 2026-11-03 | 8.434 | 840.9969 | 2026-12-04 | 25.1273 | 21132 | 21132
CFM271SH09 合計 | [9 empty] | 66096 | 66096
CFW271SH01 | Pull On Pants | 2026-11-09 | 6-06 | 2026-11-07 | 2026-11-13 | 8.4493 | 1119.3163 | 2026-12-11 | 22.3458 | 25012 | 25012
| Pull On Pants | 2026-11-09 | 6-17 | 2026-11-05 | 2026-11-11 | 8.4689 | 1204.0092 | 2026-12-12 | 24.9267 | 30012 | 30012
CFW271SH01 合計 | [9 empty] | 55024 | 55024
CPM263PA05_26Q4 | Pull On Pants | 2026-07-10 | 6-07 | 2026-07-15 | 2026-07-21 | 7.6793 | 755.5279 | 2026-08-24 | 0 | 0 | 17364
| Pull On Pants | 2026-07-10 | 6-20 | 2026-07-11 | 2026-07-17 | 7.7377 | 808.2034 | 2026-08-24 | 0 | 0 | 20835
CPM263PA05_26Q4 合計 | [9 empty] | 0 | 38199
CPM263PA81 | Pull On Pants | 2026-05-23 | 6-20 | 2026-07-11 | 2026-07-17 | 8 | 942.2492 | 2026-07-20 | 0 | 0 | 31
CPM263PA81 合計 | [9 empty] | 0 | 31
CPM263TL32_26Q4 | Tee | 2026-07-10 | 6-04 | 2026-07-21 | 2026-07-27 | 7.4953 | 1072.3844 | 2026-08-12 | 0 | 0 | 12021
| Tee | 2026-07-10 | 6-15 | 2026-07-14 | 2026-07-20 | 7.6394 | 1140.9978 | 2026-08-20 | 0 | 0 | 25311
CPM263TL32_26Q4 合計 | [9 empty] | 0 | 37332
CPW264TL38 | Tee | 2026-07-10 | 6-03 | 2026-07-17 | 2026-07-23 | 7.5879 | 1087.3719 | 2026-08-24 | 0 | 0 | 22323
| Tee | 2026-07-10 | 6-05 | 2026-07-23 | 2026-07-29 | 7.746 | 1167.0888 | 2026-08-21 | 0 | 0 | 17942
CPW264TL38 合計 | [9 empty] | 0 | 40265
G917K0_C426 | Pajama | 2026-06-12 | 6-02 | 2026-05-26 | 2026-06-03 | 8.5997 | 1282.5237 | 2026-09-02 | 0 | 0 | 87892
| Pajama | 2026-05-26 | 6-16 | 2026-05-23 | 2026-05-30 | 9.2646 | 1283.0131 | 2026-07-14 | 0 | 0 | 43173
G917K0_C426 合計 | [9 empty] | 0 | 131065
G92X13_2PK_C127 | Boxer | 2026-10-26 | 6-19 | 2026-11-14 | 2026-11-17 | 8.3339 | 2191.5075 | 2026-12-03 | 12.7693 | 27984 | 27984
G92X13_2PK_C127 合計 | [9 empty] | 27984 | 27984
G9M018_C426 | Pajama | 2026-05-25 | 6-09 | 2026-05-11 | 2026-05-18 | 9.5019 | 1837.1199 | 2026-07-04 | 0 | 0 | 65630
| Pajama | 2026-06-25 | 6-14 | 2026-06-20 | 2026-06-26 | 8.5318 | 1730.0941 | 2026-08-14 | 0 | 0 | 67974
| Pajama | 2026-06-25 | 6-16 | 2026-07-06 | 2026-07-11 | 8.0933 | 1800.1043 | 2026-08-11 | 0 | 0 | 41073
| Pajama | 2026-06-25 | 6-17 | 2026-05-18 | 2026-05-23 | 9.0274 | 1815.7792 | 2026-08-12 | 0 | 0 | 114421
G9M018_C426 合計 | [9 empty] | 0 | 289098
HQ263487_FA26 | Pull On Pants | 2026-05-21 | 6-05 | 2026-05-23 | 2026-05-26 | 9.1873 | 1315.2706 | 2026-06-18 | 0 | 0 | 20277
HQ263487_FA26 合計 | [9 empty] | 0 | 20277
L0303X_6PK_C127 | Panties | 2026-10-12 | 6-04 | 2026-10-15 | 2026-10-17 | 8.5407 | 4559.3564 | 2026-11-18 | 24.7298 | 112752 | 112752
| Panties | 2026-10-12 | 6-10 | 2026-10-03 | 2026-10-06 | 8.5311 | 4463.9028 | 2026-11-03 | 21.2747 | 94968 | 94968
L0303X_6PK_C127 合計 | [9 empty] | 207720 | 207720
L06X27_SSLLC127 | Pajama | 2026-10-15 | 6-14 | 2026-10-09 | 2026-10-12 | 8.4666 | 1639.1633 | 2026-11-07 | 20.8887 | 34240 | 34240
L06X27_SSLLC127 合計 | [9 empty] | 34240 | 34240
LPST840 | Pull On Pants | 2026-08-18 | 6-05 | 2026-08-14 | 2026-08-19 | 8.7311 | 672.7291 | 2026-09-09 | 0.0074324 | 5 | 8459
| Pull On Pants | 2026-08-18 | 6-15 | 2026-08-13 | 2026-08-18 | 8.7126 | 735.9573 | 2026-09-10 | 0.27175 | 200 | 10815
| Pull On Pants | 2026-08-24 | 6-15 | 2026-09-08 | 2026-09-10 | 9 | 935.55 | 2026-09-28 | 9.8894 | 9252 | 9252
LPST840 合計 | [9 empty] | 9457 | 28526
MRLPMM_3PC_C127 | Pajama | 2026-08-24 | 6-04 | 2026-08-28 | 2026-09-04 | 8.9 | 984.0964 | 2026-10-01 | 14.8238 | 14588 | 15719
| Pajama | 2026-08-24 | 6-11 | 2026-08-13 | 2026-08-21 | 8.7343 | 1201.0752 | 2026-11-16 | 57.8682 | 69504 | 80050
| Pajama | 2026-08-24 | 6-17 | 2026-08-26 | 2026-09-02 | 8.7154 | 1539.2569 | 2026-11-13 | 54.0683 | 83225 | 89049
MRLPMM_3PC_C127 合計 | [9 empty] | 167317 | 184818
MRLPMM_C426 | Pajama | 2026-06-08 | 6-11 | 2026-05-09 | 2026-05-16 | 8.7955 | 1554.7148 | 2026-08-04 | 0 | 0 | 98283
| Pajama | 2026-05-26 | 6-14 | 2026-05-19 | 2026-05-25 | 9.4588 | 1678.4133 | 2026-06-29 | 0 | 0 | 41982
MRLPMM_C426 合計 | [9 empty] | 0 | 140265
MRLPMM_SSLLC127 | Pajama | 2026-10-15 | 6-06 | 2026-10-16 | 2026-10-19 | 8.3709 | 1456.4913 | 2026-11-04 | 11.1364 | 16220 | 16220
| Pajama | 2026-10-15 | 6-18 | 2026-10-19 | 2026-10-21 | 8.4768 | 2104.9485 | 2026-11-02 | 6.6976 | 14098 | 14098
MRLPMM_SSLLC127 合計 | [9 empty] | 30318 | 30318
PST840 | Pull On Pants | 2026-08-18 | 6-01 | 2026-08-24 | 2026-08-27 | 8.845 | 733.8089 | 2026-09-22 | 9.343 | 6856 | 12173
| Pull On Pants | 2026-08-18 | 6-08 | 2026-09-01 | 2026-09-03 | 8.8282 | 774.4816 | 2026-10-14 | 25.2362 | 19545 | 22601
| Pull On Pants | 2026-08-18 | 6-15 | 2026-09-04 | 2026-09-08 | 9 | 841.1024 | 2026-09-14 | 2.3612 | 1986 | 2006
| Pull On Pants | 2026-08-24 | 6-15 | 2026-09-22 | 2026-09-24 | 8.6882 | 827.9095 | 2026-10-07 | 8.0105 | 6632 | 6632
PST840 合計 | [9 empty] | 35019 | 43412
ST841_FA26 | Tee | 2026-07-23 | 6-03 | 2026-08-18 | 2026-08-20 | 9 | 656.9857 | 2026-09-09 | 0.056318 | 37 | 7230
ST841_FA26 合計 | [9 empty] | 37 | 7230
W9ZMM8_7PK_C127 | Panties | 2026-10-13 | 6-09 | 2026-10-24 | 2026-10-30 | 8.4417 | 7548.6125 | 2026-11-27 | 19.5962 | 147924 | 147924
W9ZMM8_7PK_C127 合計 | [9 empty] | 147924 | 147924
W9ZMM8_7PK_C426 | Panties | 2026-06-27 | 6-09 | 2026-06-26 | 2026-07-02 | 8.322 | 10365.0012 | 2026-09-18 | 7.0306 | 72872 | 607416
W9ZMM8_7PK_C426 合計 | [9 empty] | 72872 | 607416
X048GZ_C127 | Pajama | 2026-08-22 | 6-02 | 2026-08-21 | 2026-08-31 | 8.8212 | 1672.4319 | 2026-10-09 | 20.7751 | 34745 | 46934
| Pajama | 2026-08-22 | 6-07 | 2026-09-08 | 2026-09-15 | 9 | 1586.9093 | 2026-09-25 | 5.6084 | 8900 | 8900
X048GZ_C127 合計 | [9 empty] | 43645 | 55834
X25413_C426 | Pull On Pants | 2026-07-06 | 6-10 | 2026-07-09 | 2026-07-11 | 7.7928 | 582.7032 | 2026-07-20 | 0 | 0 | 3123
| Pull On Pants | 2026-07-06 | 6-12 | 2026-08-07 | 2026-08-11 | 8 | 456.6583 | 2026-08-26 | 0 | 0 | 3075
X25413_C426 合計 | [9 empty] | 0 | 6198
Z2850Y_C127 | Pull On Pants | 2026-09-12 | 6-01 | 2026-09-11 | 2026-09-18 | 8.5138 | 742.8104 | 2026-12-15 | 69.8132 | 51858 | 51858
| Pull On Pants | 2026-09-12 | 6-14 | 2026-09-28 | 2026-10-03 | 7.7179 | 305.2888 | 2026-10-14 | 7.3701 | 2250 | 2250
| Pull On Pants | 2026-09-12 | 6-15 | 2026-09-29 | 2026-10-05 | 8.3894 | 582.3151 | 2026-11-10 | 29.3346 | 17082 | 17082
| Pull On Pants | 2026-09-12 | 6-19 | 2026-09-30 | 2026-10-06 | 8.4297 | 645.8648 | 2026-11-19 | 35.3123 | 22807 | 22807
Z2850Y_C127 合計 | [9 empty] | 93997 | 93997
ZC6HY000 | Gown | 2026-07-30 | 6-12 | 2026-08-19 | 2026-08-21 | 9 | 1524.8768 | 2026-09-11 | 0.63677 | 971 | 18169
總計 | [10 empty] | 6186626