## B04_Capacity
IND-GLD6-2026090701
| * | 9月 Sep | 10月 Oct | 11月 Nov | 12月 Dec | 1月 Jan | 2月 Feb | 3月 Mar | 4月 Apr | 5月 May | 6月 Jun | 7月 Jul | 8月 Aug
A = B04_Gannt_Chart_Detail 裡面的實際標打+排線標打(不含無訂單產能) = 來源是底稿加工票 | 已排線產能 Scheduled Capacity | 48965.9588 | 53124.9917 | 49960.6063 | 26119.6234 | 8680.6793 | 0 | 0 | 0 |  |  | 59025.3942 | 39355.2192
B = B04_Gannt_Chart_Detail 裡面的無訂單產能 來源為Parameter設人數/效率/工時計算出，抓最後一組下線+30天，這樣至少讓尾數月的產能資料完整，後面不完整月份直接看產銷產能預估即可 | 未排線產能 Unscheduled Capacity |  |  | 2332 | 26076 | 43990 | 50880 | 57240 | 25440
C = A+B | 總產能 Total Capacity | 48965.9588 | 53124.9917 | 52292.6063 | 52195.6234 | 52670.6793 | 50880 | 57240 | 25440 | 0 | 0 | 59025.3942 | 39355.2192
D = 產銷匯入最新預計產能 | 預估產能 Estimated Capacity | 45000 | 53500 | 49500 | 51500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E = ERP屬於該Maker的EXP標打數 | 出口總數 Confirmed Order | 34182.8458 | 53568.3217 | 38325.0575 | 31824.1292 | 3703.3392
F = B04_Gannt_Chart_Detail 裡面的實際標打+排線標打 / B04_Gannt_Chart_Detail人數工時計算出100%效率標打數 = 效率 = 來源是底稿加工票 | 已排線效率 Scheduled Efficiency | 1.535 | 1.5001 | 1.5891 | 1.4487 | 1.5377 | [5 empty] | 1.7943 | 1.5841
G = B04_Gannt_Chart_Detail 裡面的實際人數 + 排線人數 加總除以各組加總工作天次 = 來源是底稿加工票 | 已排線人數 Scheduled Sewers | 36.7561 | 36.8077 | 36.7486 | 36.5995 | 36.7085 | [5 empty] | 36.2385 | 36.6825
H = Parameter 參數設定 | 排線標準工時 Standard Working Hours | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
I = B04_Gannt_Chart_Detail 裡面的實際工時 + 排線工時，加總起來扣除排線標準工時再除上排線標準工時得之 = 來源是底稿加工票 | 已排線加班率 Scheduled OT Rate | 0.074315 | 0.058638 | 0.06346 | 0.068275 | 0.075 | [5 empty] | 0.037247 | 0.0060144
J = 扣除禮拜天 & Holidays Table的工作天數 | 工作天 Working Days | 24 | 27 | 25 | 26 | 25 | 24 | 19 | 25 | 23 | 24 | 27 | 20
K = B04_Gannt_Chart_Detail 裡面的實際標打+排線標打 真正有訂單標打數的天數 除以 工作天 (換句話說單組休年假或拆組會少計) | 已排線數 Lines | 20 | 20 | 19.12 | 10.5385 | 3.4 |  |  | 20 | 20 | 20 | 20 | 20
L = 發生換款(同Style_N2不算換)的次數除以排線數 | 換款率 Turnover Rate | 1 | 1.1 | 0.73222 | 0.37956 | [6 empty] | 0.95 | 1.05
M = B04_Gannt_Chart_Detail 裡面的Suspend work停工產能總計 | 停工產能 Suspend Work Capacity
N = 該月提前生產兩個月後交期訂單的比例 | 提前完成% Advance Production % | 0.18392 | 0.15775 | 0.0091591 | 0 | 0 | 0 | 0 | 0.65004 | 0 | 0 | 0.22473 | 0.32578
O = 上週排線結果的已排線產能(因排線作業時間為五六日一，抓上一個作業區間的最新版本) | 上週產能 Last Week Plan Capacity | 42917.3517 | 51436.6225 | 52885.25 | 52331.0633 | 52045.2133 | 50880 | 57240 | 36040 | 0 | 55264.7075 | 61683.96 | 39330.98
| 總產能-預估產能 | 3965.9588 | -375.0083 | 2792.6063 | 695.6234 | 52670.6793 | 50880 | 57240 | 25440 | 0 | 0 | 59025.3942 | 39355.2192
from Essbase 純目標產能 | 目標產能 Target Capacity | 52500 | 53000 | 49500 | 51500 | 0 | 0 | 0 | 0 |  |  | 54500 | 48500
| 出口/產能二維分析 | 產能月份 Month Capacity
| 出口月份 Exp Month | 9月 Sep | 10月 Oct | 11月 Nov | 12月 Dec | 1月 Jan | 2月 Feb | 3月 Mar | 4月 Apr | 5月 May | 6月 Jun | 7月 Jul | 8月 Aug
| 9月 Sep | 6954.8898 | [8 empty] | 2805.5207 | 12421.8695 | 13382.1565
| 10月 Oct | 33722.8743 | 16297.88 | [8 empty] | 842.7154 | 11681.2182
| 11月 Nov | 6475.1173 | 28446.6403 | 20826.5219 | [8 empty] | 1139.7904
| 12月 Dec | 2530.9277 | 8262.5336 | 28655.1332 | 21183.7904
| 1月 Jan |  | 117.9378 | 478.9512 | 4935.8331 | 8680.6793
2月 Feb
3月 Mar
4月 Apr
5月 May
| 6月 Jun | [7 empty] | 4285.529 | 4211.4737 | 2492.5028
| 7月 Jul | [7 empty] | 12251.5411 | 22787.4581 | 38822.4202 | 18958.4083
| 8月 Aug | [8 empty] | 1170.6775 | 5885.3113 | 29317.3787 | 15113.6456
| Total | 49683.8092 | 53124.9917 | 49960.6063 | 26119.6234 | 8680.6793 | 0 | 0 | 16537.0701 | 28169.6093 | 50005.755 | 61540.3719 | 41316.8106

## Production_Planning
Factory |  | Barcode Info Import Function | Version |  | Send to Manager |  | Excel版本： | 1.2.9 | Country: | ALL | Manual Data | Factory Schedule Data | Formula | System Data
[7 empty] | 組件版本： | 1.2.9 |  |  | 手動維護 | 系統資料 | 公式 | 系統帶入
[7 empty] | Lastest Version: | 1.2.9 | ReConnect:
Now is process data till row number 671 |  |  | CreateBy : GLD6ADMProduksi |  |  | IND-GLD6-2026090701
Line | BUYER | STYLE | Product Item | Special Production | Color (自選欄位1) | Shipmode (自選欄位2) | Order QTY | Allocate QTY | Barcode EQC QTY | Allocate unfinished | Alloctate Std Dz | CRFP | Cutting Date of acquistion | Sewing Start | Sewing Finish | Packing Finish | Delivery | Holiday | EFF | IE | Work HR | Sewing Workers Per Line | Daily Target | Days | Hourly Target | Garment Color | Delivery – Sewing Finish
組別 | 客戶 | 款式 | 產品 | 特工 | 顏色 | Shipmode | 訂單數 | 分配生產數(組) | 工票完成數 | 未完成 | 標打 | 可開裁日 | 開裁需求日 | 車縫上線日 | 車縫完成日 | 包裝完成日 | 交期 | 非例假 | 效率% | IE | 時數 | 人數 | 目標 | 天數 | 小時件數 | 成衣色 | 交期 – 車縫完成
2026-06-13
6-01 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 16401 | 16401 | 0 | 1899.7825 | 2026-06-03 | 2026-06-09 | 2026-06-11 | 2026-07-07 | 2026-07-09 | 2026-07-09 |  | 1.4696 | 1.39 | 9.2169 | 35.5696 | 873.476 | 18.7767 | 94.94 |  | 2
6-01 | TGT | 45M87P_C426 | Pull On Pants |  | all po |  |  | 15985 | 15985 | 0 | 2224.5792 | 2026-06-27 | 2026-07-02 | 2026-07-04 | 2026-07-29 | 2026-07-31 | 2026-08-19 |  | 1.8441 | 1.67 | 8.0771 | 37.1957 | 836.0225 | 19.1203 | 103.6922 |  | 15
6-01 | ONY | 1182430_HO26_HT | Pull On Pants |  | all po |  |  | 27270 | 27270 | 0 | 1772.55 | 2026-08-06 | 2026-07-24 | 2026-07-27 | 2026-09-02 | 2026-09-04 | 2026-09-24 |  | 1.1923 | 0.78 | 7.8679 | 37.4232 | 1134.2557 | 24.0422 | 144.4217 |  | 17
6-01 | SMA | PST840 | Pull On Pants |  | 1352813, _AH |  |  | 4608 | 2155 | 2453 | 625.92 | 2026-08-18 | 2026-08-27 | 2026-08-31 | 2026-09-10 | 2026-09-12 | 2026-09-22 |  | 1.44 | 1.63 | 9 | 36.6361 | 734.053 | 6.2775 | 81.7085 |  | 9
6-01 | SMA | PST840 | Pull On Pants |  | 1354809_SS, _AH |  |  | 79 | 0 | 79 | 10.7308 | 2026-08-18 | 2026-09-04 | 2026-09-08 | 2026-09-10 | 2026-09-12 | 2026-09-23 |  | 1.5 | 1.63 | 8.6 | 38 | 757.8552 | 0.10424 | 88.2816 |  | 10
6-01 | SMA | PST840 | Pull On Pants |  | 1352814, _AH |  |  | 2500 | 0 | 2500 | 339.5833 | 2026-08-24 | 2026-09-04 | 2026-09-08 | 2026-09-15 | 2026-09-17 | 2026-10-02 |  | 1.5 | 1.63 | 8.6 | 38 | 757.8552 | 3.2988 | 88.2816 |  | 15
6-01 | SMA | PST840 | Pull On Pants |  | 1352814, _AH |  |  | 4986 | 0 | 4986 | 677.265 | 2026-08-24 | 2026-09-09 | 2026-09-11 | 2026-09-23 | 2026-09-25 | 2026-10-02 |  | 1.5 | 1.63 | 8.6 | 38 | 757.8552 | 6.5791 | 88.2816 |  | 8
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 732 | 0 | 732 | 102.48 | 2026-09-12 | 2026-09-15 | 2026-09-21 | 2026-09-28 | 2026-09-30 | 2026-10-29 |  | 0.5 | 1.68 | 7 | 38 | 199.5 | 3.6692 | 28.5514 |  | 27
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 1500 | 0 | 1500 | 210 | 2026-09-12 | 2026-09-19 | 2026-09-25 | 2026-10-01 | 2026-10-03 | 2026-10-29 |  | 1 | 1.68 | 8.6 | 38 | 490.2 | 3.06 | 57.1028 |  | 24
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 2500 | 0 | 2500 | 350 | 2026-09-12 | 2026-09-23 | 2026-09-29 | 2026-10-07 | 2026-10-09 | 2026-10-29 |  | 1.1 | 1.68 | 8.6 | 38 | 539.22 | 4.6363 | 62.8131 |  | 19
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 3500 | 0 | 3500 | 490 | 2026-09-12 | 2026-09-29 | 2026-10-05 | 2026-10-14 | 2026-10-16 | 2026-10-29 |  | 1.2 | 1.68 | 8.6 | 38 | 588.24 | 5.95 | 68.5233 |  | 13
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 4000 | 0 | 4000 | 560 | 2026-09-12 | 2026-10-06 | 2026-10-12 | 2026-10-21 | 2026-10-23 | 2026-10-29 |  | 1.4 | 1.68 | 8.6 | 38 | 686.28 | 5.8285 | 79.9439 |  | 7
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 4500 | 0 | 4500 | 630 | 2026-09-12 | 2026-10-13 | 2026-10-19 | 2026-10-28 | 2026-10-30 | 2026-10-29 |  | 1.5 | 1.68 | 8.6 | 38 | 735.3 | 6.12 | 85.6542 |  | 1
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0130 |  |  | 4332 | 0 | 4332 | 606.48 | 2026-10-03 | 2026-10-20 | 2026-10-26 | 2026-11-04 | 2026-11-06 | 2026-11-09 |  | 1.6 | 1.68 | 8.6 | 38 | 784.32 | 5.5233 | 91.3645 |  | 4
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0213 |  |  | 4000 | 0 | 4000 | 560 | 2026-10-17 | 2026-10-27 | 2026-11-02 | 2026-11-10 | 2026-11-12 | 2026-11-23 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 4.5333 | 102.785 |  | 11
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0227 |  |  | 6678 | 0 | 6678 | 934.92 | 2026-10-31 | 2026-11-02 | 2026-11-07 | 2026-11-19 | 2026-11-21 | 2026-12-07 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 7.5683 | 102.785 |  | 15
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0301_GLAM |  |  | 1064 | 0 | 1064 | 148.96 | 2026-10-31 | 2026-11-11 | 2026-11-17 | 2026-11-20 | 2026-11-22 | 2026-12-16 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 1.2059 | 102.785 |  | 22
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0313 |  |  | 10896 | 0 | 10896 | 1525.44 | 2026-10-31 | 2026-11-12 | 2026-11-18 | 2026-12-04 | 2026-12-06 | 2026-12-28 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 12.3487 | 102.785 |  | 19
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0327 |  |  | 8952 | 0 | 8952 | 1253.28 | 2026-10-31 | 2026-11-26 | 2026-12-02 | 2026-12-16 | 2026-12-18 | 2027-01-09 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 10.1455 | 102.785 |  | 19
2026-06-04
6-02 | TGT | G917K0_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 87714 | 87714 | 0 | 9136.875 | 2026-06-12 | 2026-05-25 | 2026-06-02 | 2026-08-31 | 2026-09-02 | 2026-09-05 |  | 2.0664 | 1.25 | 8.5997 | 35.7988 | 1282.5237 | 68.3917 | 149.4043 |  | 4
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014311_1219E |  |  | 2040 | 2040 | 0 | 142.8 | 2026-08-22 | 2026-08-19 | 2026-08-27 | 2026-09-02 | 2026-09-04 | 2026-09-28 |  | 0.96978 | 0.84 | 8 | 36.2304 | 843.254 | 2.4192 | 105.5968 |  | 20
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014298_SET_1212, 10002014297_T1_1212 |  |  | 6000 | 3699 | 2301 | 420 | 2026-08-22 | 2026-08-21 | 2026-08-31 | 2026-09-08 | 2026-09-10 | 2026-10-01 |  | 1.65 | 0.84 | 9 | 36.2796 | 1616.2571 | 3.7123 | 179.908 |  | 19
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014298_SET_1212, 10002014297_T1_1212 |  |  | 3675 | 0 | 3675 | 257.25 | 2026-08-22 | 2026-08-28 | 2026-09-04 | 2026-09-10 | 2026-09-12 | 2026-10-01 |  | 1.8 | 0.84 | 9 | 36.2796 | 1763.1895 | 2.0843 | 196.2632 |  | 17
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014298_SET_1212, 10002014297_T1_1212 |  |  | 33175 | 0 | 33175 | 2322.25 | 2026-08-22 | 2026-09-01 | 2026-09-08 | 2026-10-02 | 2026-10-04 | 2026-10-01 |  | 2 | 0.84 | 8.6 | 36.2796 | 1872.0284 | 17.7214 | 218.0702 |  | -3
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014310_1219 |  |  | 2640 | 0 | 2640 | 184.8 | 2026-08-29 | 2026-09-24 | 2026-09-30 | 2026-10-03 | 2026-10-05 | 2026-10-10 |  | 2 | 0.84 | 8.6 | 36.2796 | 1872.0284 | 1.4102 | 218.0702 |  | 6
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014306_E_0102 |  |  | 3600 | 0 | 3600 | 252 | 2026-08-29 | 2026-09-25 | 2026-10-01 | 2026-10-06 | 2026-10-08 | 2026-10-12 |  | 2 | 0.84 | 8.6 | 36.2796 | 1872.0284 | 1.923 | 218.0702 |  | 5
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014305_0102 |  |  | 4704 | 0 | 4704 | 329.28 | 2026-08-29 | 2026-09-28 | 2026-10-03 | 2026-10-09 | 2026-10-11 | 2026-10-24 |  | 2 | 0.84 | 8.6 | 36.2796 | 1872.0284 | 2.5128 | 218.0702 |  | 13
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | GLAM |  |  | 430 | 0 | 430 | 30.1 | 2026-09-05 | 2026-10-01 | 2026-10-07 | 2026-10-09 | 2026-10-11 | 2027-01-05 |  | 2 | 0.84 | 8.6 | 36.2796 | 1872.0284 | 0.2297 | 218.0702 |  | 73
6-02 | ONY | 1194431_SP27 | Tee |  | 62315014 |  |  | 329 | 0 | 329 | 35.0933 | 2026-10-07 | 2026-10-05 | 2026-10-07 | 2026-10-10 | 2026-10-12 | 2026-10-29 |  | 0.5 | 1.28 | 7 | 36.2796 | 249.9893 | 1.3161 | 35.7771 |  | 16
6-02 | ONY | 1194431_SP27 | Tee |  | 62330730, 732, 735, 739 |  |  | 2611 | 0 | 2611 | 278.5067 | 2026-10-10 | 2026-10-06 | 2026-10-08 | 2026-10-15 | 2026-10-17 | 2026-11-05 |  | 1 | 1.28 | 8.6 | 36.2796 | 614.2593 | 4.2506 | 71.5543 |  | 18
6-02 | ONY | 1194431_SP27 | Tee |  | 62326898, 440 |  |  | 271 | 0 | 271 | 28.9067 | 2026-10-10 | 2026-10-10 | 2026-10-13 | 2026-10-15 | 2026-10-17 | 2026-11-26 |  | 1.2 | 1.28 | 8.6 | 36.2796 | 737.1112 | 0.36765 | 85.8652 |  | 36
6-02 | ONY | 1194431_SP27 | Tee |  | 62330583, 585, 589, 590, 439, 441, 443, 445 |  |  | 3087 | 0 | 3087 | 329.28 | 2026-11-10 | 2026-10-10 | 2026-10-13 | 2026-10-20 | 2026-10-22 | 2026-12-03 |  | 1.4 | 1.28 | 8.6 | 36.2796 | 859.963 | 3.5897 | 100.176 |  | 38
6-02 | ONY | 1194431_SP27 | Tee |  | 62326668, 12.24 |  |  | 717 | 0 | 717 | 76.48 | 2026-11-03 | 2026-10-15 | 2026-10-17 | 2026-10-21 | 2026-10-23 | 2026-12-24 |  | 1.6 | 1.28 | 8.6 | 36.2796 | 982.8149 | 0.72954 | 114.4869 |  | 55
6-02 | ONY | 1194431_SP27 | Tee |  | 62330544, 548, 552, 556, 12.31 |  |  | 2253 | 0 | 2253 | 240.32 | 2026-11-03 | 2026-10-16 | 2026-10-19 | 2026-10-23 | 2026-10-25 | 2026-12-31 |  | 1.8 | 1.28 | 8.6 | 36.2796 | 1105.6668 | 2.0377 | 128.7977 |  | 58
6-02 | ONY | 1194431_SP27 | Tee |  | 62326618, 01.21 |  |  | 475 | 0 | 475 | 50.6667 | 2026-11-03 | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-10-25 | 2027-01-21 |  | 1.8 | 1.28 | 8.6 | 36.2796 | 1105.6668 | 0.42961 | 128.7977 |  | 75
6-02 | ONY | 1194431_SP27 | Tee |  | 01.28 |  |  | 641 | 0 | 641 | 68.3733 | 2026-11-30 | 2026-10-19 | 2026-10-21 | 2026-10-24 | 2026-10-26 | 2027-01-28 |  | 1.8 | 1.28 | 8.6 | 36.2796 | 1105.6668 | 0.57974 | 128.7977 |  | 80
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 716 | 0 | 716 | 72.7933 | 2026-11-05 | 2026-10-20 | 2026-10-22 | 2026-10-28 | 2026-10-30 | 2026-11-30 |  | 0.5 | 1.22 | 7 | 36.2796 | 262.2838 | 2.7299 | 37.5367 |  | 28
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 1500 | 0 | 1500 | 152.5 | 2026-11-05 | 2026-10-23 | 2026-10-26 | 2026-10-30 | 2026-11-01 | 2026-11-30 |  | 1 | 1.22 | 8.6 | 36.2796 | 644.4688 | 2.3275 | 75.0734 |  | 26
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 2500 | 0 | 2500 | 254.1667 | 2026-11-05 | 2026-10-26 | 2026-10-28 | 2026-11-04 | 2026-11-06 | 2026-11-30 |  | 1.1 | 1.22 | 8.6 | 36.2796 | 708.9157 | 3.5265 | 82.5807 |  | 22
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 3500 | 0 | 3500 | 355.8333 | 2026-11-05 | 2026-10-30 | 2026-11-02 | 2026-11-10 | 2026-11-12 | 2026-11-30 |  | 1.2 | 1.22 | 8.6 | 36.2796 | 773.3625 | 4.5257 | 90.088 |  | 17
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 4500 | 0 | 4500 | 457.5 | 2026-11-05 | 2026-11-05 | 2026-11-07 | 2026-11-16 | 2026-11-18 | 2026-11-30 |  | 1.4 | 1.22 | 8.6 | 36.2796 | 902.2563 | 4.9875 | 105.1027 |  | 12
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 5000 | 0 | 5000 | 508.3333 | 2026-11-05 | 2026-11-11 | 2026-11-13 | 2026-11-21 | 2026-11-23 | 2026-12-07 |  | 1.6 | 1.22 | 8.6 | 36.2796 | 1031.1501 | 4.849 | 120.1174 |  | 13
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 7516 | 0 | 7516 | 764.1267 | 2026-11-05 | 2026-11-17 | 2026-11-19 | 2026-11-28 | 2026-11-30 | 2026-12-07 |  | 1.8 | 1.22 | 8.6 | 36.2796 | 1160.0438 | 6.4791 | 135.1321 |  | 7
2026-04-16
6-03 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08 |  |  | 29699 | 29699 | 0 | 2598.6625 | 2026-05-04 | 2026-04-11 | 2026-04-14 | 2026-05-15 | 2026-05-20 | 2026-07-23 |  | 1.6453 | 1.05 | 9.1703 | 35.9036 | 1300.1298 | 22.8431 | 142.0323 |  | 56
6-03 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 19159 | 19159 | 0 | 1676.4125 | 2026-05-23 | 2026-05-09 | 2026-05-12 | 2026-06-04 | 2026-06-09 | 2026-07-02 |  | 1.6134 | 1.05 | 9.1023 | 35.7343 | 1259.5162 | 15.2114 | 138.6222 |  | 23
6-03 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 28598 | 28598 | 0 | 3312.6017 | 2026-06-03 | 2026-05-29 | 2026-06-02 | 2026-07-08 | 2026-07-10 | 2026-07-09 |  | 1.734 | 1.39 | 9.5107 | 33.6617 | 1006.3981 | 28.4162 | 106.0086 |  | 1
6-03 | ONY | 910047_HO26DIS | Pajama |  | all po |  |  | 11308 | 11308 | 0 | 1338.1133 | 2026-07-06 | 2026-07-03 | 2026-07-06 | 2026-07-21 | 2026-07-23 | 2026-08-06 |  | 1.8663 | 1.42 | 8.4758 | 36.2794 | 1018.4268 | 11.1034 | 120.3737 |  | 14
6-03 | HLF | CPW264TL38 | Tee | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 22323 | 22323 | 0 | 1674.225 | 2026-07-10 | 2026-07-13 | 2026-07-18 | 2026-08-18 | 2026-08-20 | 2026-08-21 |  | 1.3631 | 0.9 | 7.5879 | 37.546 | 1087.3719 | 20.5293 | 143.5626 |  | 3
6-03 | SMA | ST841_FA26 | Tee |  | 1333150_MAR |  |  | 2100 | 2100 | 0 | 304.5 | 2026-07-23 | 2026-08-11 | 2026-08-13 | 2026-08-28 | 2026-08-30 | 2026-08-20 |  | 0.68621 | 1.74 | 8.1658 | 36.7324 | 298.0922 | 7.0448 | 36.571 |  | -7
6-03 | SMA | ST841_FA26 | Tee |  | 1347534_APR_1 |  |  | 5132 | 3510 | 1622 | 744.14 | 2026-07-23 | 2026-08-21 | 2026-08-26 | 2026-09-09 | 2026-09-11 | 2026-09-19 |  | 1.35 | 1.74 | 9 | 37.3361 | 656.9857 | 7.8114 | 73.13 |  | 8
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 728 | 0 | 728 | 59.4533 | 2026-09-07 | 2026-09-03 | 2026-09-07 | 2026-09-11 | 2026-09-16 | 2026-10-01 |  | 0.5 | 0.98 | 7 | 37.3361 | 336.0245 | 2.1665 | 48.0901 |  | 16
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 1500 | 0 | 1500 | 122.5 | 2026-09-07 | 2026-09-07 | 2026-09-09 | 2026-09-15 | 2026-09-20 | 2026-10-01 |  | 1 | 0.98 | 9 | 37.3361 | 864.0629 | 1.736 | 96.1801 |  | 14
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 2700 | 0 | 2700 | 220.5 | 2026-09-07 | 2026-09-09 | 2026-09-11 | 2026-09-18 | 2026-09-23 | 2026-10-01 |  | 1.2 | 0.98 | 8.6 | 37.3361 | 990.7921 | 2.7251 | 115.4161 |  | 11
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62239979, 378, 565, 268, 269 |  |  | 1503 | 0 | 1503 | 122.745 | 2026-09-07 | 2026-09-14 | 2026-09-16 | 2026-09-19 | 2026-09-24 | 2026-10-08 |  | 1.4 | 0.98 | 8.6 | 37.3361 | 1155.9241 | 1.3003 | 134.6522 |  | 16
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 5000 | 0 | 5000 | 408.3333 | 2026-09-07 | 2026-09-15 | 2026-09-17 | 2026-09-24 | 2026-09-29 | 2026-10-15 |  | 1.6 | 0.98 | 8.6 | 37.3361 | 1321.0561 | 3.7849 | 153.8882 |  | 18
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 19966 | 0 | 19966 | 1630.5567 | 2026-09-07 | 2026-09-19 | 2026-09-22 | 2026-10-09 | 2026-10-14 | 2026-10-15 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 13.4344 | 173.1242 |  | 5
6-03 | ONY | 1195255_SP27 | Tee |  | 62345060 |  |  | 744 | 0 | 744 | 40.92 | 2026-10-07 | 2026-10-05 | 2026-10-07 | 2026-10-10 | 2026-10-12 | 2026-11-04 |  | 0.5 | 0.66 | 7 | 37.3361 | 498.9454 | 1.4911 | 71.4064 |  | 21
6-03 | ONY | 1195255_SP27 | Tee |  | 62345060 |  |  | 2000 | 0 | 2000 | 110 | 2026-10-07 | 2026-10-06 | 2026-10-08 | 2026-10-13 | 2026-10-15 | 2026-11-04 |  | 1 | 0.66 | 8.6 | 37.3361 | 1225.9801 | 1.6313 | 142.8129 |  | 19
6-03 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 3370 | 0 | 3370 | 185.35 | 2026-10-07 | 2026-10-08 | 2026-10-10 | 2026-10-15 | 2026-10-17 | 2026-11-05 |  | 1.1 | 0.66 | 8.6 | 37.3361 | 1348.5781 | 2.4989 | 157.0942 |  | 18
6-03 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 4000 | 0 | 4000 | 220 | 2026-10-07 | 2026-10-10 | 2026-10-13 | 2026-10-19 | 2026-10-21 | 2026-11-05 |  | 1.2 | 0.66 | 8.6 | 37.3361 | 1471.1761 | 2.7189 | 171.3755 |  | 15
6-03 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 4000 | 0 | 4000 | 220 | 2026-10-07 | 2026-10-14 | 2026-10-16 | 2026-10-21 | 2026-10-23 | 2026-11-05 |  | 1.4 | 0.66 | 8.6 | 37.3361 | 1716.3722 | 2.3305 | 199.938 |  | 13
6-03 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 4000 | 0 | 4000 | 220 | 2026-10-07 | 2026-10-16 | 2026-10-19 | 2026-10-23 | 2026-10-25 | 2026-11-05 |  | 1.6 | 0.66 | 8.6 | 37.3361 | 1961.5682 | 2.0392 | 228.5006 |  | 11
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 11.05 |  |  | 936 | 0 | 936 | 76.44 | 2026-10-10 | 2026-10-19 | 2026-10-21 | 2026-10-24 | 2026-10-29 | 2026-11-05 |  | 1 | 0.98 | 7 | 37.3361 | 672.0489 | 1.3928 | 96.1801 |  | 10
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 11.05 |  |  | 1500 | 0 | 1500 | 122.5 | 2026-10-10 | 2026-10-20 | 2026-10-22 | 2026-10-27 | 2026-11-01 | 2026-11-05 |  | 1.2 | 0.98 | 8.6 | 37.3361 | 990.7921 | 1.5139 | 115.4161 |  | 8
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 11.05 |  |  | 2500 | 0 | 2500 | 204.1667 | 2026-10-10 | 2026-10-22 | 2026-10-24 | 2026-10-29 | 2026-11-03 | 2026-11-05 |  | 1.4 | 0.98 | 8.6 | 37.3361 | 1155.9241 | 2.1628 | 134.6522 |  | 6
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 11.05 |  |  | 4000 | 0 | 4000 | 326.6667 | 2026-10-10 | 2026-10-24 | 2026-10-27 | 2026-11-02 | 2026-11-07 | 2026-11-05 |  | 1.6 | 0.98 | 8.6 | 37.3361 | 1321.0561 | 3.0279 | 153.8882 |  | 3
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.03 |  |  | 3099 | 0 | 3099 | 253.085 | 2026-11-07 | 2026-10-28 | 2026-10-30 | 2026-11-04 | 2026-11-09 | 2026-12-03 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 2.0852 | 173.1242 |  | 25
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.10 |  |  | 100 | 0 | 100 | 8.1667 | 2026-11-07 | 2026-10-30 | 2026-11-02 | 2026-11-04 | 2026-11-09 | 2026-12-10 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 0.067286 | 173.1242 |  | 31
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 900 | 0 | 900 | 73.5 | 2026-11-07 | 2026-10-30 | 2026-11-02 | 2026-11-05 | 2026-11-10 | 2026-12-31 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 0.60558 | 173.1242 |  | 47
6-03 | ONY | 1195255_SP27 | Tee |  | 62344872 |  |  | 484 | 0 | 484 | 26.62 | 2026-10-07 | 2026-10-31 | 2026-11-03 | 2026-11-05 | 2026-11-07 | 2026-11-11 |  | 1 | 0.66 | 7 | 37.3361 | 997.8908 | 0.48502 | 142.8129 |  | 5
6-03 | ONY | 1195255_SP27 | Tee |  | 62323334, 336, 338, 339, 843, 844 |  |  | 1576 | 0 | 1576 | 86.68 | 2026-10-07 | 2026-10-31 | 2026-11-03 | 2026-11-06 | 2026-11-08 | 2026-11-12 |  | 1.2 | 0.66 | 8.6 | 37.3361 | 1471.1761 | 1.0713 | 171.3755 |  | 5
6-03 | ONY | 1195255_SP27 | Tee |  | 62323334, 336, 338, 339, 843, 844 |  |  | 2500 | 0 | 2500 | 137.5 | 2026-10-07 | 2026-11-02 | 2026-11-04 | 2026-11-07 | 2026-11-09 | 2026-11-12 |  | 1.4 | 0.66 | 8.6 | 37.3361 | 1716.3722 | 1.4566 | 199.938 |  | 4
6-03 | ONY | 1195255_SP27 | Tee |  | 62323334, 336, 338, 339, 843, 844 |  |  | 3500 | 0 | 3500 | 192.5 | 2026-10-07 | 2026-11-03 | 2026-11-05 | 2026-11-10 | 2026-11-12 | 2026-11-12 |  | 1.6 | 0.66 | 8.6 | 37.3361 | 1961.5682 | 1.7843 | 228.5006 |  | 2
6-03 | ONY | 1195255_SP27 | Tee |  | 62323334, 336, 338, 339, 843, 844 |  |  | 6000 | 0 | 6000 | 330 | 2026-10-07 | 2026-11-05 | 2026-11-07 | 2026-11-13 | 2026-11-15 | 2026-11-12 |  | 1.8 | 0.66 | 8.6 | 37.3361 | 2206.7642 | 2.7189 | 257.0632 |  | -3
6-03 | ONY | 1195255_SP27 | Tee |  | 62323824, 861 |  |  | 11020 | 0 | 11020 | 606.1 | 2026-10-07 | 2026-11-09 | 2026-11-11 | 2026-11-19 | 2026-11-21 | 2026-12-03 |  | 1.8 | 0.66 | 8.6 | 37.3361 | 2206.7642 | 4.9937 | 257.0632 |  | 12
6-03 | ONY | 1195255_SP27 | Tee |  | 62323388, 390, 392, 394, 463, 466, 468, 469, 826, 827, 862, 863 |  |  | 30372 | 0 | 30372 | 1670.46 | 2026-10-07 | 2026-11-14 | 2026-11-17 | 2026-12-05 | 2026-12-07 | 2026-12-10 |  | 1.8 | 0.66 | 8.6 | 36.8624 | 2178.7713 | 13.94 | 253.8023 |  | 4
6-03 | ONY | 1195255_SP27 | Tee |  | 12.31 |  |  | 732 | 0 | 732 | 40.26 | 2026-10-07 | 2026-12-01 | 2026-12-03 | 2026-12-05 | 2026-12-07 | 2026-12-31 |  | 1.8 | 0.66 | 8.6 | 36.8624 | 2178.7713 | 0.33597 | 253.8023 |  | 21
6-03 | ONY | 1195255_SP27 | Tee |  | 01.07 |  |  | 1709 | 0 | 1709 | 93.995 | 2026-10-07 | 2026-12-01 | 2026-12-03 | 2026-12-07 | 2026-12-09 | 2027-01-07 |  | 1.8 | 0.66 | 8.6 | 36.8624 | 2178.7713 | 0.78439 | 253.8023 |  | 25
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-12-02 | 2026-12-04 | 2026-12-09 | 2026-12-14 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 36.8624 | 353.3986 | 2.3062 | 50.5766 |  | 13
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-12-04 | 2026-12-07 | 2026-12-11 | 2026-12-16 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 36.8624 | 868.3509 | 1.7274 | 101.1531 |  | 11
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-12-07 | 2026-12-09 | 2026-12-15 | 2026-12-20 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 36.8624 | 955.186 | 2.6173 | 111.2684 |  | 8
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-10 | 2026-12-12 | 2026-12-18 | 2026-12-23 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 36.8624 | 1042.021 | 2.879 | 121.3837 |  | 5
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 3450 | 0 | 3450 | 264.5 | 2026-12-07 | 2026-12-14 | 2026-12-16 | 2026-12-22 | 2026-12-27 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 36.8624 | 1128.8561 | 3.0562 | 131.499 |  | 7
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4441 | 0 | 4441 | 340.4767 | 2026-12-07 | 2026-12-17 | 2026-12-19 | 2026-12-28 | 2027-01-02 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 36.8624 | 1215.6912 | 3.6531 | 141.6143 |  | 3
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4540 | 0 | 4540 | 348.0667 | 2026-12-07 | 2026-12-22 | 2026-12-24 | 2026-12-31 | 2027-01-05 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 3.4855 | 151.7297 |  | 0
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-26 | 2026-12-29 | 2027-01-02 | 2027-01-07 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 1.4771 | 151.7297 |  | 10
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-28 | 2026-12-30 | 2027-01-09 | 2027-01-14 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 5.9853 | 151.7297 |  | 10
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-05 | 2027-01-07 | 2027-01-15 | 2027-01-20 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 5.074 | 151.7297 |  | 11
2026-04-14
6-04 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 26479 | 26479 | 0 | 2316.9125 | 2026-04-25 | 2026-04-09 | 2026-04-11 | 2026-05-12 | 2026-05-17 | 2026-06-04 |  | 1.489 | 1.05 | 8.8333 | 36.727 | 1159.316 | 22.8402 | 131.4811 |  | 17
6-04 | ONY | 915810_FA26 | Tee |  | all po |  |  | 6456 | 6456 | 0 | 634.84 | 2026-05-15 | 2026-05-07 | 2026-05-09 | 2026-05-26 | 2026-05-28 | 2026-06-11 |  | 0.8934 | 1.18 | 8.7965 | 36.3618 | 610.2657 | 10.579 | 69.5009 |  | 12
6-04 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 18832 | 18832 | 0 | 2181.3733 | 2026-06-03 | 2026-05-21 | 2026-05-23 | 2026-06-25 | 2026-06-27 | 2026-07-09 |  | 1.4109 | 1.39 | 9.1249 | 34.9781 | 816.4257 | 23.0664 | 89.6341 |  | 12
6-04 | ONY | 915810_FA26 | Tee |  | all po |  |  | 3182 | 3182 | 0 | 312.8967 | 2026-06-04 | 2026-06-20 | 2026-06-23 | 2026-07-01 | 2026-07-03 | 2026-07-09 |  | 0.99489 | 1.18 | 7.7074 | 36.4515 | 596.92 | 5.3307 | 77.5873 |  | 7
6-04 | ONY | 766362_HO26 | Pull On Pants |  | all po Juli, Agustus |  |  | 24434 | 24434 | 0 | 1751.1033 | 2026-07-09 | 2026-06-26 | 2026-06-29 | 2026-07-24 | 2026-07-26 | 2026-08-06 |  | 1.3668 | 0.86 | 8.2229 | 37.6497 | 1239.9326 | 19.7059 | 151.0617 |  | 11
6-04 | HLF | CPM263TL32_26Q4 | Tee | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 12021 | 12021 | 0 | 901.575 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-08-06 | 2026-08-08 | 2026-08-21 |  | 1.3542 | 0.9 | 7.4953 | 37.7324 | 1072.3844 | 11.2096 | 143.3328 |  | 10
6-04 | ONY | 766362_HO26 | Pull On Pants |  | 62071071, 222 |  |  | 421 | 421 | 0 | 30.1717 | 2026-07-17 | 2026-08-01 | 2026-08-04 | 2026-08-07 | 2026-08-09 | 2026-09-17 |  | 0.75413 | 0.86 | 8 | 38 | 671.7728 | 0.6267 | 84.123 |  | 27
6-04 | ONY | 766362_HO26 | Pull On Pants |  | 62152234, 324, 330, 335, 339 |  |  | 2202 | 2202 | 0 | 157.81 | 2026-07-30 | 2026-08-03 | 2026-08-05 | 2026-08-11 | 2026-08-13 | 2026-09-24 |  | 1.2672 | 0.86 | 8 | 38 | 1128.7677 | 1.9508 | 141.3504 |  | 31
6-04 | ONY | 766362_HO26 | Pull On Pants |  | 62037086 |  |  | 200 | 200 | 0 | 14.3333 | 2026-08-18 | 2026-08-05 | 2026-08-07 | 2026-08-11 | 2026-08-13 | 2026-09-30 |  | 1.0496 | 0.86 | 8 | 38 | 935.0164 | 0.2139 | 117.0878 |  | 36
6-04 | ONY | 766362_HO26 | Pull On Pants |  | 62151044, 781 |  |  | 1044 | 1044 | 0 | 74.82 | 2026-07-17 | 2026-08-05 | 2026-08-07 | 2026-08-12 | 2026-08-14 | 2026-10-07 |  | 1.0897 | 0.86 | 8 | 38 | 970.7113 | 1.0755 | 121.5577 |  | 41
6-04 | ONY | 766362_HO26 | Pull On Pants |  | 62190888 |  |  | 133 | 133 | 0 | 9.5317 | 2026-08-04 | 2026-08-06 | 2026-08-10 | 2026-08-12 | 2026-08-14 | 2026-10-08 |  | 0.84497 | 0.86 | 8 | 38 | 752.6882 | 0.1767 | 94.2557 |  | 42
6-04 | ONY | 766362_HO26 | Pull On Pants |  | 62037064, 045 |  |  | 790 | 790 | 0 | 56.6167 | 2026-08-18 | 2026-08-06 | 2026-08-10 | 2026-08-13 | 2026-08-15 | 2026-10-14 |  | 0.93976 | 0.86 | 8 | 38 | 837.1304 | 0.9437 | 104.83 |  | 46
6-04 | ONY | 766362_HO26 | Pull On Pants |  | 62152216, 219 |  |  | 703 | 703 | 0 | 50.3817 | 2026-08-04 | 2026-08-07 | 2026-08-11 | 2026-08-14 | 2026-08-16 | 2026-10-15 |  | 1.2774 | 0.86 | 8 | 38 | 1137.9087 | 0.6178 | 142.4951 |  | 46
6-04 | ONY | 766362_HO26 | Pull On Pants |  | 62058496 |  |  | 400 | 400 | 0 | 28.6667 | 2026-08-18 | 2026-08-10 | 2026-08-12 | 2026-08-18 | 2026-08-20 | 2026-10-21 |  | 0.48835 | 0.86 | 8 | 38 | 435.019 | 0.9195 | 54.4754 |  | 50
6-04 | ONY | 766362_HO26 | Pull On Pants |  | 62047531, 251, 996, 358, 360, 365, 368 |  |  | 300 | 300 | 0 | 21.5 | 2026-08-04 | 2026-08-11 | 2026-08-13 | 2026-08-18 | 2026-08-20 | 2026-10-29 |  | 1.2416 | 0.86 | 8 | 37.2912 | 1085.3837 | 0.2764 | 135.9176 |  | 57
6-04 | ONY | 766362_HO26 | Pull On Pants |  | 62047450, 452, 453, 532, 252, 337, 343, 344, 346, 351, 354, 358, 363, 365, 368, 370, 371 |  |  | 7510 | 7510 | 0 | 538.2167 | 2026-08-18 | 2026-08-11 | 2026-08-13 | 2026-08-26 | 2026-08-28 | 2026-11-05 |  | 1.6879 | 0.86 | 8.2216 | 37.8353 | 1538.5247 | 4.8813 | 187.4686 |  | 58
6-04 | ONY | 766362_HO26 | Pull On Pants |  | 62047451, 533, 253, 340, 349, 360, 369 |  |  | 4965 | 4965 | 0 | 355.825 | 2026-08-18 | 2026-08-19 | 2026-08-21 | 2026-08-31 | 2026-09-02 | 2026-11-12 |  | 1.693 | 0.86 | 9 | 37.9987 | 1696.5661 | 2.9265 | 188.8473 |  | 61
6-04 | ONY | 766362_HO26 | Pull On Pants |  | 62165996 |  |  | 3079 | 3079 | 0 | 220.6617 | 2026-08-18 | 2026-08-24 | 2026-08-27 | 2026-09-02 | 2026-09-04 | 2026-12-03 |  | 1.5754 | 0.86 | 9 | 37.4959 | 1557.8043 | 1.9765 | 173.4015 |  | 77
6-04 | ONY | 766362_HO26 | Pull On Pants |  | 62165997 |  |  | 3461 | 3461 | 0 | 248.0383 | 2026-08-18 | 2026-08-27 | 2026-08-31 | 2026-09-04 | 2026-09-06 | 2026-12-10 |  | 1.6679 | 0.86 | 9 | 38 | 1671.4962 | 2.0706 | 186.0567 |  | 81
6-04 | ONY | 766362_HO26 | Pull On Pants |  | 62165998 |  |  | 2467 | 1027 | 1440 | 176.8017 | 2026-08-18 | 2026-08-31 | 2026-09-02 | 2026-09-07 | 2026-09-09 | 2026-12-17 |  | 1.7 | 0.86 | 9 | 38 | 1703.6372 | 1.4481 | 189.6344 |  | 86
6-04 | ONY | 766362_V1 | Pull On Pants |  | 10.28 |  |  | 855 | 476 | 379 | 61.275 | 2026-05-22 | 2026-09-01 | 2026-09-03 | 2026-09-08 | 2026-09-10 | 2026-10-28 |  | 1.7 | 0.86 | 9 | 38 | 1703.6372 | 0.50187 | 189.6344 |  | 42
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004922_T1_W |  |  | 720 | 0 | 720 | 63.6 | 2026-08-24 | 2026-08-28 | 2026-09-04 | 2026-09-10 | 2026-09-12 | 2026-10-01 |  | 0.5 | 1.06 | 7 | 38 | 316.1887 | 2.2771 | 45.2513 |  | 17
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 1500 | 0 | 1500 | 132.5 | 2026-08-24 | 2026-09-01 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 2026-10-08 |  | 1 | 1.06 | 8.6 | 38 | 776.9208 | 1.9307 | 90.5025 |  | 21
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 2500 | 0 | 2500 | 220.8333 | 2026-08-24 | 2026-09-03 | 2026-09-10 | 2026-09-17 | 2026-09-19 | 2026-10-08 |  | 1.1 | 1.06 | 8.6 | 38 | 854.6128 | 2.9253 | 99.5528 |  | 18
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 3500 | 0 | 3500 | 309.1667 | 2026-08-24 | 2026-09-08 | 2026-09-15 | 2026-09-22 | 2026-09-24 | 2026-10-08 |  | 1.2 | 1.06 | 8.6 | 38 | 932.3049 | 3.7541 | 108.603 |  | 14
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 3500 | 0 | 3500 | 309.1667 | 2026-08-24 | 2026-09-14 | 2026-09-19 | 2026-09-25 | 2026-09-27 | 2026-10-08 |  | 1.4 | 1.06 | 8.6 | 38 | 1087.6891 | 3.2178 | 126.7035 |  | 11
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 3999 | 0 | 3999 | 353.245 | 2026-08-24 | 2026-09-17 | 2026-09-23 | 2026-09-29 | 2026-10-01 | 2026-10-08 |  | 1.6 | 1.06 | 8.6 | 38 | 1243.0732 | 3.217 | 144.804 |  | 8
6-04 | ONY | 766362_V1 | Pull On Pants |  | 10.28 |  |  | 1118 | 0 | 1118 | 80.1233 | 2026-05-22 | 2026-09-24 | 2026-09-26 | 2026-10-02 | 2026-10-04 | 2026-10-28 |  | 0.5 | 0.86 | 7 | 38 | 389.7209 | 2.8687 | 55.7748 |  | 22
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62215028, 029, 030, 031 |  |  | 1850 | 0 | 1850 | 132.5833 | 2026-05-22 | 2026-09-28 | 2026-09-30 | 2026-10-05 | 2026-10-07 | 2026-10-29 |  | 1 | 0.86 | 8.6 | 38 | 957.6 | 1.9319 | 111.5496 |  | 21
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62215028, 029, 030, 031 |  |  | 2000 | 0 | 2000 | 143.3333 | 2026-05-22 | 2026-09-30 | 2026-10-02 | 2026-10-07 | 2026-10-09 | 2026-10-29 |  | 1.2 | 0.86 | 8.6 | 38 | 1149.12 | 1.7405 | 133.8596 |  | 19
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62047539, 028, 030, 031 |  |  | 3467 | 0 | 3467 | 248.4683 | 2026-05-22 | 2026-10-02 | 2026-10-05 | 2026-10-10 | 2026-10-12 | 2026-11-05 |  | 1.4 | 0.86 | 8.6 | 38 | 1340.64 | 2.5861 | 156.1695 |  | 22
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62047539, 028, 030, 031 |  |  | 4500 | 0 | 4500 | 322.5 | 2026-05-22 | 2026-10-06 | 2026-10-08 | 2026-10-14 | 2026-10-16 | 2026-11-05 |  | 1.6 | 0.86 | 8.6 | 38 | 1532.16 | 2.937 | 178.4794 |  | 19
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62047540, 029 |  |  | 4726 | 0 | 4726 | 338.6967 | 2026-05-22 | 2026-10-09 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 2026-11-12 |  | 1.7 | 0.86 | 8.6 | 38 | 1627.92 | 2.9031 | 189.6344 |  | 22
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 960 | 0 | 960 | 25.6 | 2026-10-12 | 2026-10-13 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 2026-11-02 |  | 0.5 | 0.32 | 7 | 38 | 1047.375 | 0.91658 | 149.8948 |  | 12
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 1500 | 0 | 1500 | 40 | 2026-10-12 | 2026-10-14 | 2026-10-16 | 2026-10-20 | 2026-10-22 | 2026-11-02 |  | 1 | 0.32 | 8.6 | 38 | 2573.55 | 0.58285 | 299.7896 |  | 11
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 2500 | 0 | 2500 | 66.6667 | 2026-10-12 | 2026-10-15 | 2026-10-17 | 2026-10-21 | 2026-10-23 | 2026-11-02 |  | 1.1 | 0.32 | 8.6 | 38 | 2830.905 | 0.88311 | 329.7686 |  | 10
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 3500 | 0 | 3500 | 93.3333 | 2026-10-12 | 2026-10-16 | 2026-10-19 | 2026-10-22 | 2026-10-24 | 2026-11-02 |  | 1.2 | 0.32 | 8.6 | 38 | 3088.26 | 1.1333 | 359.7475 |  | 9
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 4500 | 0 | 4500 | 120 | 2026-10-12 | 2026-10-17 | 2026-10-20 | 2026-10-23 | 2026-10-25 | 2026-11-02 |  | 1.3 | 0.32 | 8.6 | 38 | 3345.615 | 1.345 | 389.7265 |  | 8
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0130_W |  |  | 1044 | 0 | 1044 | 27.84 | 2026-10-20 | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-10-25 | 2026-11-11 |  | 1.4 | 0.32 | 8.6 | 38 | 3602.97 | 0.28976 | 419.7055 |  | 16
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 5000 | 0 | 5000 | 133.3333 | 2026-10-12 | 2026-10-19 | 2026-10-21 | 2026-10-24 | 2026-10-26 | 2026-11-12 |  | 1.6 | 0.32 | 8.6 | 38 | 4117.68 | 1.2143 | 479.6634 |  | 16
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 7000 | 0 | 7000 | 186.6667 | 2026-10-12 | 2026-10-20 | 2026-10-22 | 2026-10-27 | 2026-10-29 | 2026-11-12 |  | 1.8 | 0.32 | 8.6 | 38 | 4632.39 | 1.5111 | 539.6213 |  | 14
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 33180 | 0 | 33180 | 884.8 | 2026-10-12 | 2026-10-22 | 2026-10-24 | 2026-11-03 | 2026-11-05 | 2026-11-12 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 6.4463 | 599.5792 |  | 8
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0213_W |  |  | 18216 | 0 | 18216 | 485.76 | 2026-10-20 | 2026-10-29 | 2026-10-31 | 2026-11-07 | 2026-11-09 | 2026-11-25 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 3.5391 | 599.5792 |  | 15
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0220_W |  |  | 17784 | 0 | 17784 | 474.24 | 2026-10-27 | 2026-11-03 | 2026-11-05 | 2026-11-11 | 2026-11-13 | 2026-12-02 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 3.4551 | 599.5792 |  | 18
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0227_W |  |  | 17784 | 0 | 17784 | 474.24 | 2026-10-27 | 2026-11-06 | 2026-11-09 | 2026-11-14 | 2026-11-16 | 2026-12-09 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 3.4551 | 599.5792 |  | 21
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0306_W |  |  | 17784 | 0 | 17784 | 474.24 | 2026-10-27 | 2026-11-10 | 2026-11-12 | 2026-11-18 | 2026-11-20 | 2026-12-16 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 3.4551 | 599.5792 |  | 24
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0313_W |  |  | 17784 | 0 | 17784 | 474.24 | 2026-10-27 | 2026-11-13 | 2026-11-16 | 2026-11-21 | 2026-11-23 | 2026-12-23 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 3.4551 | 599.5792 |  | 27
6-04 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-11-17 | 2026-11-19 | 2026-11-24 | 2026-11-29 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 38 | 364.3043 | 2.2371 | 52.1373 |  | 26
6-04 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-11-19 | 2026-11-21 | 2026-11-26 | 2026-12-01 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 38 | 895.1478 | 1.6757 | 104.2747 |  | 24
6-04 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-11-21 | 2026-11-24 | 2026-11-30 | 2026-12-05 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 38 | 984.6626 | 2.5389 | 114.7021 |  | 21
6-04 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-11-25 | 2026-11-27 | 2026-12-03 | 2026-12-08 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 38 | 1074.1774 | 2.7928 | 125.1296 |  | 18
6-04 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4941 | 0 | 4941 | 378.81 | 2026-12-07 | 2026-11-28 | 2026-12-01 | 2026-12-08 | 2026-12-13 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 38 | 1163.6922 | 4.246 | 135.557 |  | 19
6-04 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-12-07 | 2026-12-03 | 2026-12-05 | 2026-12-12 | 2026-12-17 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 38 | 1253.207 | 3.9898 | 145.9845 |  | 15
6-04 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 7550 | 0 | 7550 | 578.8333 | 2026-12-07 | 2026-12-08 | 2026-12-10 | 2026-12-19 | 2026-12-24 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 5.6229 | 156.412 |  | 9
6-04 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-15 | 2026-12-17 | 2026-12-21 | 2026-12-26 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 1.4329 | 156.412 |  | 19
6-04 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-16 | 2026-12-18 | 2026-12-29 | 2027-01-03 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 5.8061 | 156.412 |  | 19
6-04 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2026-12-23 | 2026-12-26 | 2027-01-05 | 2027-01-10 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 4.9221 | 156.412 |  | 20
2026-04-01
6-05 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08 |  |  | 56118 | 56118 | 0 | 4910.325 | 2026-05-07 | 2026-03-27 | 2026-03-30 | 2026-05-28 | 2026-06-02 | 2026-07-30 |  | 1.6939 | 1.05 | 8.9946 | 34.4529 | 1259.8102 | 44.5448 | 140.3152 |  | 52
6-05 | WMT | HQ263487_FA26 | Pull On Pants |  | all po |  |  | 20277 | 20277 | 0 | 1436.2875 | 2026-05-21 | 2026-05-22 | 2026-05-25 | 2026-06-17 | 2026-06-19 | 2026-06-27 |  | 1.4761 | 0.85 | 9.1873 | 32.7131 | 1315.2706 | 15.4166 | 143.4206 |  | 9
6-05 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 31058 | 31058 | 0 | 2717.575 | 2026-05-26 | 2026-06-11 | 2026-06-13 | 2026-07-13 | 2026-07-18 | 2026-07-16 |  | 1.7623 | 1.05 | 9.1485 | 36.1574 | 1399.0404 | 22.1995 | 153.2011 |  | 3
6-05 | TGT | 5GK4L2_C426 | Jumper |  | all po |  |  | 2892 | 2892 | 0 | 383.19 | 2026-07-03 | 2026-07-08 | 2026-07-10 | 2026-07-21 | 2026-07-23 | 2026-08-21 |  | 0.91766 | 1.59 | 7.5859 | 35.6461 | 393.2819 | 7.3535 | 51.9374 |  | 24
6-05 | ONY | 1184404_HO26 | Tee |  | all po |  |  | 5350 | 5350 | 0 | 347.75 | 2026-07-13 | 2026-07-16 | 2026-07-18 | 2026-07-30 | 2026-08-01 | 2026-08-13 |  | 0.85133 | 0.78 | 6.9853 | 34.9478 | 671.4355 | 7.968 | 96.2951 |  | 11
6-05 | HLF | CPW264TL38 | Tee | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 17942 | 17942 | 0 | 1345.65 | 2026-07-10 | 2026-07-22 | 2026-07-28 | 2026-08-20 | 2026-08-22 | 2026-08-21 |  | 1.5414 | 0.9 | 7.746 | 34.9112 | 1167.0888 | 15.3733 | 150.9414 |  | 1
6-05 | SMA | LPST840 | Pull On Pants |  | 1352772, _AH |  |  | 4836 | 4836 | 0 | 596.44 | 2026-08-18 | 2026-08-13 | 2026-08-18 | 2026-09-02 | 2026-09-04 | 2026-09-22 |  | 1.1327 | 1.48 | 8.586 | 35.7551 | 592.0812 | 8.1678 | 69.0835 |  | 15
6-05 | SMA | LPST840 | Pull On Pants |  | 1354810_SS, _AH |  |  | 79 | 79 | 0 | 9.7433 | 2026-08-18 | 2026-08-27 | 2026-08-31 | 2026-09-02 | 2026-09-04 | 2026-09-23 |  | 0.32267 | 1.48 | 9 | 36 | 178.0081 | 0.4438 | 19.8143 |  | 16
6-05 | SMA | LPST840 | Pull On Pants |  | 1352773, _AH |  |  | 3544 | 1820 | 1724 | 437.0933 | 2026-08-24 | 2026-08-27 | 2026-08-31 | 2026-09-08 | 2026-09-10 | 2026-10-02 |  | 1.67 | 1.48 | 9 | 34.9478 | 894.3719 | 3.9626 | 99.5539 |  | 20
6-05 | TGT | 5GK4L2_C127 | Jumper |  | 10002064559_0110 |  |  | 500 | 0 | 500 | 66.25 | 2026-09-10 | 2026-09-02 | 2026-09-04 | 2026-09-11 | 2026-09-13 | 2026-10-10 |  | 0.5 | 1.59 | 7 | 35 | 194.1509 | 2.5753 | 27.7859 |  | 24
6-05 | TGT | 5GK4L2_C127 | Jumper |  | 10002064559_0110 |  |  | 650 | 0 | 650 | 86.125 | 2026-09-10 | 2026-09-07 | 2026-09-09 | 2026-09-15 | 2026-09-17 | 2026-10-10 |  | 0.8 | 1.59 | 8.6 | 35 | 381.6453 | 1.7032 | 44.4574 |  | 22
6-05 | TGT | 5GK4L2_C127 | Jumper |  | 10002064559_0110 |  |  | 1766 | 0 | 1766 | 233.995 | 2026-09-10 | 2026-09-09 | 2026-09-11 | 2026-09-19 | 2026-09-21 | 2026-10-10 |  | 1 | 1.59 | 8.6 | 35 | 477.0566 | 3.7019 | 55.5717 |  | 18
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 795 | 0 | 795 | 113.95 | 2026-09-21 | 2026-09-10 | 2026-09-17 | 2026-09-24 | 2026-09-26 | 2026-11-02 |  | 0.5 | 1.72 | 7 | 35 | 179.4767 | 4.4295 | 25.6858 |  | 33
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 1500 | 0 | 1500 | 215 | 2026-09-21 | 2026-09-16 | 2026-09-22 | 2026-09-28 | 2026-09-30 | 2026-11-02 |  | 1 | 1.72 | 8.6 | 35 | 441 | 3.4014 | 51.3715 |  | 30
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 2500 | 0 | 2500 | 358.3333 | 2026-09-21 | 2026-09-19 | 2026-09-25 | 2026-10-03 | 2026-10-05 | 2026-11-02 |  | 1.1 | 1.72 | 8.6 | 35 | 485.1 | 5.1536 | 56.5087 |  | 25
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 3000 | 0 | 3000 | 430 | 2026-09-21 | 2026-09-25 | 2026-10-01 | 2026-10-10 | 2026-10-12 | 2026-11-02 |  | 1.2 | 1.72 | 8.6 | 35 | 529.2 | 5.6689 | 61.6458 |  | 19
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 3200 | 0 | 3200 | 458.6667 | 2026-09-21 | 2026-10-02 | 2026-10-08 | 2026-10-16 | 2026-10-18 | 2026-11-02 |  | 1.4 | 1.72 | 8.6 | 35 | 617.4 | 5.183 | 71.9202 |  | 14
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 6000 | 0 | 6000 | 860 | 2026-09-21 | 2026-10-08 | 2026-10-14 | 2026-10-27 | 2026-10-29 | 2026-11-02 |  | 1.5 | 1.72 | 8.6 | 35 | 661.5 | 9.0703 | 77.0573 |  | 5
6-05 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 750 | 0 | 750 | 55.625 | 2026-10-23 | 2026-10-22 | 2026-10-24 | 2026-10-29 | 2026-10-31 | 2026-11-19 |  | 0.5 | 0.89 | 7 | 35 | 346.8539 | 2.1623 | 49.6399 |  | 18
6-05 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 1500 | 0 | 1500 | 111.25 | 2026-10-23 | 2026-10-24 | 2026-10-27 | 2026-10-31 | 2026-11-02 | 2026-11-19 |  | 1 | 0.89 | 8.6 | 35 | 852.2697 | 1.76 | 99.2798 |  | 16
6-05 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 2250 | 0 | 2250 | 166.875 | 2026-10-23 | 2026-10-27 | 2026-10-29 | 2026-11-03 | 2026-11-05 | 2026-11-19 |  | 1.1 | 0.89 | 8.6 | 35 | 937.4966 | 2.4 | 109.2078 |  | 14
6-05 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 2500 | 0 | 2500 | 185.4167 | 2026-10-23 | 2026-10-29 | 2026-10-31 | 2026-11-05 | 2026-11-07 | 2026-11-19 |  | 1.2 | 0.89 | 8.6 | 35 | 1022.7236 | 2.4445 | 119.1358 |  | 12
6-05 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 3750 | 0 | 3750 | 278.125 | 2026-10-23 | 2026-10-31 | 2026-11-03 | 2026-11-09 | 2026-11-11 | 2026-11-19 |  | 1.3 | 0.89 | 8.6 | 35 | 1107.9506 | 3.3846 | 129.0638 |  | 9
6-05 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041432_US_OS |  |  | 3625 | 0 | 3625 | 268.8542 | 2026-10-30 | 2026-11-04 | 2026-11-06 | 2026-11-12 | 2026-11-14 | 2026-11-26 |  | 1.4 | 0.89 | 8.6 | 35 | 1193.1775 | 3.0381 | 138.9918 |  | 12
6-05 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041432_US_OS |  |  | 9000 | 0 | 9000 | 667.5 | 2026-10-30 | 2026-11-07 | 2026-11-10 | 2026-11-20 | 2026-11-22 | 2026-11-26 |  | 1.5 | 0.89 | 8.6 | 35 | 1278.4045 | 7.04 | 148.9197 |  | 5
6-05 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 728 | 0 | 728 | 57.0267 | 2026-11-09 | 2026-11-12 | 2026-11-18 | 2026-11-23 | 2026-11-25 | 2026-12-03 |  | 0.5 | 0.94 | 7 | 35 | 328.4043 | 2.2168 | 46.9995 |  | 9
6-05 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 1500 | 0 | 1500 | 117.5 | 2026-11-09 | 2026-11-14 | 2026-11-20 | 2026-11-25 | 2026-11-27 | 2026-12-03 |  | 1 | 0.94 | 8.6 | 35 | 806.9362 | 1.8589 | 93.999 |  | 7
6-05 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 1500 | 0 | 1500 | 117.5 | 2026-11-09 | 2026-11-17 | 2026-11-23 | 2026-11-27 | 2026-11-29 | 2026-12-03 |  | 1.1 | 0.94 | 8.6 | 35 | 887.6298 | 1.6899 | 103.3989 |  | 5
6-05 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 2500 | 0 | 2500 | 195.8333 | 2026-11-09 | 2026-11-19 | 2026-11-25 | 2026-12-01 | 2026-12-03 | 2026-12-10 |  | 1.2 | 0.94 | 8.6 | 35 | 968.3234 | 2.5818 | 112.7988 |  | 8
6-05 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1210, 4500041655_BJSHVS_1210, 4500041655_BJSHVS_HTR_1210, 4500041657_HTR_1210 |  |  | 3500 | 0 | 3500 | 274.1667 | 2026-11-09 | 2026-11-23 | 2026-11-28 | 2026-12-04 | 2026-12-06 | 2026-12-10 |  | 1.4 | 0.94 | 8.6 | 35 | 1129.7106 | 3.0981 | 131.5986 |  | 5
2026-04-12
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08 |  |  | 24866 | 24866 | 0 | 2175.775 | 2026-04-13 | 2026-04-08 | 2026-04-10 | 2026-05-06 | 2026-05-11 | 2026-06-25 |  | 1.592 | 1.05 | 8.7258 | 36.5651 | 1219.0291 | 20.3982 | 139.9557 |  | 39
6-06 | ONY | 890955_FA26 | Pull On Pants |  | all po |  |  | 7023 | 7023 | 0 | 550.135 | 2026-04-30 | 2026-04-30 | 2026-05-04 | 2026-05-15 | 2026-05-17 | 2026-06-04 |  | 1.2371 | 0.94 | 8.5835 | 36.7291 | 1045.603 | 6.7167 | 122.0354 |  | 15
6-06 | ONY | 905200_FA26 | Pull On Pants |  | all po |  |  | 26558 | 26558 | 0 | 2478.7467 | 2026-05-02 | 2026-05-09 | 2026-05-12 | 2026-06-17 | 2026-06-19 | 2026-06-11 |  | 1.3726 | 1.12 | 9.4741 | 36.0936 | 1056.0642 | 25.1481 | 111.6698 |  | -6
6-06 | ONY | 890955_FA26 | Pull On Pants |  | all po |  |  | 3293 | 3293 | 0 | 257.9517 | 2026-04-13 | 2026-06-11 | 2026-06-13 | 2026-06-20 | 2026-06-22 | 2026-07-16 |  | 1.2036 | 0.94 | 9.4007 | 36.6757 | 1112.5004 | 2.96 | 118.5556 |  | 22
6-06 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 25055 | 25055 | 0 | 2192.3125 | 2026-05-26 | 2026-06-15 | 2026-06-18 | 2026-07-10 | 2026-07-15 | 2026-07-16 |  | 1.9617 | 1.05 | 9.4584 | 33.9307 | 1510.9939 | 16.5818 | 160.0393 |  | 5
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 29241 | 29241 | 0 | 2558.5875 | 2026-06-23 | 2026-07-06 | 2026-07-08 | 2026-08-04 | 2026-08-09 | 2026-09-17 |  | 1.9966 | 1.05 | 8.2272 | 36.0033 | 1419.4044 | 20.6009 | 172.8375 |  | 30
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 38318 | 36843 | 1475 | 3352.825 | 2026-08-01 | 2026-07-30 | 2026-08-01 | 2026-09-07 | 2026-09-12 | 2026-10-15 |  | 2.19 | 1.05 | 9 | 36.8624 | 1743.7409 | 21.9746 | 194.0984 |  | 32
6-06 | ONY | 777362_HO26_GLD | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 62212924, 927, 931, 933 |  |  | 6000 | 0 | 6000 | 525 | 2026-08-29 | 2026-09-01 | 2026-09-03 | 2026-09-10 | 2026-09-15 | 2026-09-24 |  | 2.2 | 1.05 | 9 | 36.8624 | 1751.7031 | 3.4252 | 194.9847 |  | 11
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 38498 | 0 | 38498 | 3368.575 | 2026-08-01 | 2026-09-04 | 2026-09-08 | 2026-10-08 | 2026-10-13 | 2026-10-15 |  | 2.2 | 1.05 | 8.6 | 36.8624 | 1673.8497 | 22.9997 | 194.9847 |  | 6
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 11.12 |  |  | 7964 | 0 | 7964 | 696.85 | 2026-08-18 | 2026-10-03 | 2026-10-06 | 2026-10-14 | 2026-10-19 | 2026-11-12 |  | 2.2 | 1.05 | 8.6 | 36.8624 | 1673.8497 | 4.7579 | 194.9847 |  | 25
6-06 | ONY | 777362_V2 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 11.12 |  |  | 9276 | 0 | 9276 | 811.65 | 2026-10-08 | 2026-10-09 | 2026-10-12 | 2026-10-21 | 2026-10-26 | 2026-11-12 |  | 2.2 | 1.05 | 8.6 | 36.8624 | 1673.8497 | 5.5417 | 194.9847 |  | 19
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 720 | 0 | 720 | 43.2 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-23 | 2026-10-25 | 2026-11-06 |  | 0.5 | 0.72 | 7 | 36.8624 | 451.5649 | 1.5945 | 64.6256 |  | 12
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 1500 | 0 | 1500 | 90 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 2026-10-24 | 2026-10-26 | 2026-11-06 |  | 1 | 0.72 | 8.6 | 36.8624 | 1109.5594 | 1.3519 | 129.2512 |  | 11
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 2500 | 0 | 2500 | 150 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-10-27 | 2026-10-29 | 2026-11-06 |  | 1.2 | 0.72 | 8.6 | 36.8624 | 1331.4713 | 1.8776 | 155.1014 |  | 9
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 3500 | 0 | 3500 | 210 | 2026-10-15 | 2026-10-22 | 2026-10-24 | 2026-10-29 | 2026-10-31 | 2026-11-06 |  | 1.4 | 0.72 | 8.6 | 36.8624 | 1553.3832 | 2.2531 | 180.9517 |  | 7
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 5000 | 0 | 5000 | 300 | 2026-10-15 | 2026-10-24 | 2026-10-27 | 2026-11-02 | 2026-11-04 | 2026-11-06 |  | 1.6 | 0.72 | 8.6 | 36.8624 | 1775.2951 | 2.8164 | 206.8019 |  | 4
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 5000 | 0 | 5000 | 300 | 2026-10-15 | 2026-10-28 | 2026-10-30 | 2026-11-05 | 2026-11-07 | 2026-11-06 |  | 1.8 | 0.72 | 8.6 | 36.8624 | 1997.207 | 2.5035 | 232.6521 |  | 1
6-06 | ONY | 777362_V2 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 12.03 |  |  | 647 | 0 | 647 | 56.6125 | 2026-08-27 | 2026-10-31 | 2026-11-03 | 2026-11-06 | 2026-11-11 | 2026-12-03 |  | 1 | 1.05 | 7 | 36.8624 | 619.289 | 1.0447 | 88.6294 |  | 23
6-06 | ONY | 777362_V2 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 12.03 |  |  | 1500 | 0 | 1500 | 131.25 | 2026-08-27 | 2026-11-02 | 2026-11-04 | 2026-11-09 | 2026-11-14 | 2026-12-03 |  | 1.3 | 1.05 | 8.6 | 36.8624 | 989.093 | 1.5165 | 115.2182 |  | 21
6-06 | ONY | 777362_V2 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 12.03 |  |  | 2500 | 0 | 2500 | 218.75 | 2026-08-27 | 2026-11-04 | 2026-11-06 | 2026-11-11 | 2026-11-16 | 2026-12-03 |  | 1.5 | 1.05 | 8.6 | 36.8624 | 1141.2611 | 2.1906 | 132.9441 |  | 19
6-06 | ONY | 777362_V2 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 12.03 |  |  | 3500 | 0 | 3500 | 306.25 | 2026-08-27 | 2026-11-06 | 2026-11-09 | 2026-11-14 | 2026-11-19 | 2026-12-03 |  | 1.6 | 1.05 | 8.6 | 36.8624 | 1217.3452 | 2.8751 | 141.807 |  | 16
6-06 | ONY | 777362_V2 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 12.03 |  |  | 4000 | 0 | 4000 | 350 | 2026-10-08 | 2026-11-10 | 2026-11-12 | 2026-11-18 | 2026-11-23 | 2026-12-03 |  | 1.8 | 1.05 | 8.6 | 36.8624 | 1369.5134 | 2.9207 | 159.5329 |  | 13
6-06 | ONY | 777362_V2 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 12.03 |  |  | 4500 | 0 | 4500 | 393.75 | 2026-10-08 | 2026-11-13 | 2026-11-16 | 2026-11-21 | 2026-11-26 | 2026-12-03 |  | 2 | 1.05 | 8.6 | 36.8624 | 1521.6815 | 2.9573 | 177.2588 |  | 10
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 12.10 |  |  | 9196 | 0 | 9196 | 804.65 | 2026-08-20 | 2026-11-17 | 2026-11-19 | 2026-11-27 | 2026-12-02 | 2026-12-10 |  | 2.2 | 1.05 | 8.6 | 36.8624 | 1673.8497 | 5.4939 | 194.9847 |  | 11
2026-06-06
6-07 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 24374 | 24374 | 0 | 2823.3217 | 2026-06-03 | 2026-06-02 | 2026-06-04 | 2026-07-10 | 2026-07-12 | 2026-07-09 |  | 1.4647 | 1.39 | 9.211 | 35.496 | 868.1993 | 28.0742 | 94.4264 |  | -3
6-07 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08 |  |  | 11906 | 11906 | 0 | 1041.775 | 2026-05-07 | 2026-07-06 | 2026-07-08 | 2026-07-24 | 2026-07-29 | 2026-07-30 |  | 1.5471 | 1.05 | 8.2762 | 33.6826 | 1035.0792 | 11.5025 | 125.2931 |  | 5
6-07 | HLF | CPM263PA05_26Q4 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 17364 | 17364 | 0 | 1750.87 | 2026-07-10 | 2026-07-16 | 2026-07-22 | 2026-08-26 | 2026-08-28 | 2026-08-21 |  | 1.304 | 1.21 | 7.6793 | 36.2259 | 755.5279 | 22.9826 | 98.5623 |  | -4
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014226_TRN |  |  | 2160 | 2160 | 0 | 129.6 | 2026-08-15 | 2026-08-13 | 2026-08-21 | 2026-08-28 | 2026-08-30 | 2026-10-01 |  | 0.88104 | 0.72 | 8 | 36.1737 | 892.3775 | 2.4205 | 111.7483 |  | 26
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002008674_SET |  |  | 13794 | 11594 | 2200 | 827.64 | 2026-08-24 | 2026-08-18 | 2026-08-26 | 2026-09-08 | 2026-09-10 | 2026-10-08 |  | 1.6 | 0.72 | 9 | 37 | 1864.8 | 7.397 | 207.5736 |  | 25
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014233 |  |  | 5496 | 0 | 5496 | 329.76 | 2026-08-22 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-13 | 2026-10-12 |  | 1.8 | 0.72 | 9 | 37 | 2097.9 | 2.6198 | 233.5203 |  | 25
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014232 |  |  | 7296 | 0 | 7296 | 437.76 | 2026-08-18 | 2026-09-02 | 2026-09-09 | 2026-09-16 | 2026-09-18 | 2026-10-24 |  | 2 | 0.72 | 8.6 | 37 | 2227.4 | 3.2756 | 259.467 |  | 33
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014238 |  |  | 4536 | 0 | 4536 | 272.16 | 2026-08-22 | 2026-09-07 | 2026-09-14 | 2026-09-18 | 2026-09-20 | 2026-10-26 |  | 2 | 0.72 | 8.6 | 37 | 2227.4 | 2.0365 | 259.467 |  | 32
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014236, 0201_LIVERPOOL |  |  | 6660 | 0 | 6660 | 399.6 | 2026-08-24 | 2026-09-09 | 2026-09-16 | 2026-09-22 | 2026-09-24 | 2026-11-07 |  | 2 | 0.72 | 8.6 | 37 | 2227.4 | 2.99 | 259.467 |  | 40
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014237 |  |  | 3624 | 0 | 3624 | 217.44 | 2026-08-29 | 2026-09-14 | 2026-09-19 | 2026-09-24 | 2026-09-26 | 2026-11-09 |  | 2 | 0.72 | 8.6 | 37 | 2227.4 | 1.627 | 259.467 |  | 39
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014235 |  |  | 4872 | 0 | 4872 | 292.32 | 2026-08-29 | 2026-09-16 | 2026-09-22 | 2026-09-26 | 2026-09-28 | 2026-11-21 |  | 2 | 0.72 | 8.6 | 37 | 2227.4 | 2.1873 | 259.467 |  | 48
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014240 |  |  | 3624 | 0 | 3624 | 217.44 | 2026-09-05 | 2026-09-18 | 2026-09-24 | 2026-09-29 | 2026-10-01 | 2026-11-23 |  | 2 | 0.72 | 8.6 | 37 | 2227.4 | 1.627 | 259.467 |  | 47
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014239 |  |  | 4872 | 0 | 4872 | 292.32 | 2026-09-05 | 2026-09-21 | 2026-09-26 | 2026-10-01 | 2026-10-03 | 2026-12-05 |  | 2 | 0.72 | 8.6 | 37 | 2227.4 | 2.1873 | 259.467 |  | 56
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 0301_GLAM |  |  | 477 | 0 | 477 | 28.62 | 2026-09-05 | 2026-09-23 | 2026-09-29 | 2026-10-01 | 2026-10-03 | 2027-01-05 |  | 2 | 0.72 | 8.6 | 37 | 2227.4 | 0.21415 | 259.467 |  | 80
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0214_E |  |  | 751 | 0 | 751 | 57.5767 | 2026-10-17 | 2026-09-26 | 2026-09-29 | 2026-10-03 | 2026-10-05 | 2026-11-16 |  | 0.5 | 0.92 | 7 | 37.461 | 359.1372 | 2.0911 | 51.3978 |  | 37
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0214_E |  |  | 1500 | 0 | 1500 | 115 | 2026-10-17 | 2026-09-29 | 2026-10-01 | 2026-10-06 | 2026-10-08 | 2026-11-16 |  | 1 | 0.92 | 8.6 | 37.461 | 882.4513 | 1.6998 | 102.7957 |  | 35
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0214_E |  |  | 3200 | 0 | 3200 | 245.3333 | 2026-10-17 | 2026-10-01 | 2026-10-03 | 2026-10-09 | 2026-10-11 | 2026-11-16 |  | 1.1 | 0.92 | 8.6 | 37.461 | 970.6965 | 3.2966 | 113.0752 |  | 32
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_E |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-10-24 | 2026-10-05 | 2026-10-07 | 2026-10-15 | 2026-10-17 | 2026-11-23 |  | 1.2 | 0.92 | 8.6 | 37.461 | 1058.9416 | 4.7217 | 123.3548 |  | 33
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_E |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-10-24 | 2026-10-10 | 2026-10-13 | 2026-10-20 | 2026-10-22 | 2026-11-23 |  | 1.4 | 0.92 | 8.6 | 37.461 | 1235.4319 | 4.0472 | 143.9139 |  | 29
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_E |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-10-24 | 2026-10-15 | 2026-10-17 | 2026-10-24 | 2026-10-26 | 2026-11-23 |  | 1.6 | 0.92 | 8.6 | 37.461 | 1411.9221 | 3.5413 | 164.473 |  | 25
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_E |  |  | 6812 | 0 | 6812 | 522.2533 | 2026-10-24 | 2026-10-20 | 2026-10-22 | 2026-10-29 | 2026-10-31 | 2026-11-23 |  | 1.8 | 0.92 | 8.6 | 37.461 | 1588.4124 | 4.2886 | 185.0322 |  | 21
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_W |  |  | 16360 | 0 | 16360 | 1254.2667 | 2026-10-31 | 2026-10-24 | 2026-10-27 | 2026-11-09 | 2026-11-11 | 2026-12-03 |  | 2 | 0.92 | 8.6 | 37.461 | 1764.9027 | 9.2696 | 205.5913 |  | 21
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0307_E |  |  | 10904 | 0 | 10904 | 835.9733 | 2026-10-31 | 2026-11-04 | 2026-11-06 | 2026-11-16 | 2026-11-18 | 2026-12-07 |  | 2 | 0.92 | 8.6 | 37.461 | 1764.9027 | 6.1782 | 205.5913 |  | 18
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0307_W |  |  | 13634 | 0 | 13634 | 1045.2733 | 2026-10-31 | 2026-11-11 | 2026-11-13 | 2026-11-25 | 2026-11-27 | 2026-12-17 |  | 2 | 0.92 | 8.6 | 37.461 | 1764.9027 | 7.7251 | 205.5913 |  | 19
2026-04-22
6-08 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08 |  |  | 43947 | 43947 | 0 | 3845.3625 | 2026-05-07 | 2026-04-17 | 2026-04-20 | 2026-06-02 | 2026-06-07 | 2026-07-30 |  | 1.6982 | 1.05 | 9.3938 | 37.476 | 1434.8257 | 30.6288 | 153.0167 |  | 49
6-08 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 7260 | 7260 | 0 | 635.25 | 2026-05-26 | 2026-05-26 | 2026-05-29 | 2026-06-09 | 2026-06-14 | 2026-07-09 |  | 1.6754 | 1.05 | 8.7363 | 37.2525 | 1308.6032 | 5.5479 | 150.0591 |  | 25
6-08 | ONY | 766362_V1 | Pull On Pants |  | all po Juni, Juli, Agustus |  |  | 39555 | 39555 | 0 | 2834.775 | 2026-05-11 | 2026-06-04 | 2026-06-06 | 2026-07-13 | 2026-07-15 | 2026-07-09 |  | 1.4081 | 0.86 | 9.3671 | 37.1994 | 1437.6838 | 27.513 | 153.7592 |  | -5
6-08 | ONY | 766362_V1 | Pull On Pants |  | 10.08 |  |  | 1527 | 1527 | 0 | 109.435 | 2026-05-22 | 2026-07-08 | 2026-07-10 | 2026-07-14 | 2026-07-16 | 2026-10-08 |  | 1.6514 | 0.86 | 6.2222 | 37.1962 | 1119.9118 | 1.3635 | 180.3113 |  | 66
6-08 | ONY | 766362_HO26 | Pull On Pants |  | all po Juli, Agustus |  |  | 33157 | 33157 | 0 | 2376.2517 | 2026-07-17 | 2026-07-09 | 2026-07-11 | 2026-08-07 | 2026-08-09 | 2026-08-27 |  | 1.7579 | 0.86 | 7.9801 | 38.0045 | 1562.2267 | 21.2242 | 196.1193 |  | 12
6-08 | ONY | 766362_HO26 | Pull On Pants |  | 62077258 |  |  | 264 | 264 | 0 | 18.92 | 2026-08-04 | 2026-08-03 | 2026-08-05 | 2026-08-07 | 2026-08-09 | 2026-09-02 |  | 1.0868 | 0.86 | 8 | 38 | 968.0968 | 0.2727 | 121.2303 |  | 16
6-08 | ONY | 766362_HO26 | Pull On Pants |  | 62047477, 478, 479, 480 |  |  | 1311 | 1311 | 0 | 93.955 | 2026-07-17 | 2026-08-03 | 2026-08-05 | 2026-08-10 | 2026-08-12 | 2026-09-03 |  | 1.3152 | 0.86 | 8 | 37.6439 | 1160.5879 | 1.1296 | 145.3351 |  | 16
6-08 | ONY | 766362_HO26 | Pull On Pants |  | 62071071, 222 |  |  | 421 | 421 | 0 | 30.1717 | 2026-07-30 | 2026-08-04 | 2026-08-06 | 2026-08-10 | 2026-08-12 | 2026-09-17 |  | 1.04 | 0.86 | 8 | 37 | 902.0784 | 0.4667 | 112.9631 |  | 26
6-08 | ONY | 766362_HO26 | Pull On Pants |  | 62152234, 324, 330, 335, 339 |  |  | 2202 | 2202 | 0 | 157.81 | 2026-08-18 | 2026-08-04 | 2026-08-06 | 2026-08-12 | 2026-08-14 | 2026-09-24 |  | 1.4435 | 0.86 | 8 | 36.5861 | 1237.9827 | 1.7787 | 155.0269 |  | 30
6-08 | ONY | 766362_HO26 | Pull On Pants |  | 62037086 |  |  | 200 | 200 | 0 | 14.3333 | 2026-07-17 | 2026-08-06 | 2026-08-10 | 2026-08-12 | 2026-08-14 | 2026-09-30 |  | 1.2307 | 0.86 | 8 | 34 | 980.873 | 0.2039 | 122.8302 |  | 35
6-08 | ONY | 766362_HO26 | Pull On Pants |  | 62047531, 251, 996, 358, 360, 365, 368 |  |  | 3379 | 3379 | 0 | 242.1617 | 2026-08-04 | 2026-08-06 | 2026-08-10 | 2026-08-18 | 2026-08-20 | 2026-10-29 |  | 1.5214 | 0.86 | 8 | 35.7629 | 1275.4313 | 2.6493 | 159.7164 |  | 57
6-08 | ONY | 766362_HO26 | Pull On Pants |  | 62047450, 452, 453, 532, 252, 337, 343, 344, 346, 351, 354, 358, 363, 365, 368, 370, 371 |  |  | 2835 | 2835 | 0 | 203.175 | 2026-08-04 | 2026-08-11 | 2026-08-13 | 2026-08-20 | 2026-08-22 | 2026-11-05 |  | 1.7685 | 0.86 | 8 | 37.6509 | 1560.8655 | 1.8163 | 195.46 |  | 61
6-08 | ONY | 766362_V1 | Pull On Pants |  | 10.08 |  |  | 9022 | 9022 | 0 | 646.5767 | 2026-05-22 | 2026-08-13 | 2026-08-18 | 2026-08-28 | 2026-08-30 | 2026-10-08 |  | 1.7868 | 0.86 | 8.3731 | 38.0795 | 1669.3807 | 5.4044 | 199.7333 |  | 32
6-08 | ONY | 766362_V1 | Pull On Pants |  | 10.28 |  |  | 5346 | 5290 | 56 | 383.13 | 2026-05-22 | 2026-08-21 | 2026-08-26 | 2026-09-02 | 2026-09-04 | 2026-10-28 |  | 1.8 | 0.86 | 9 | 37.8178 | 1795.2007 | 2.9779 | 199.8264 |  | 46
6-08 | SMA | PST840 | Pull On Pants |  | 1352813, _AH |  |  | 808 | 446 | 362 | 109.7533 | 2026-08-18 | 2026-08-27 | 2026-08-31 | 2026-09-07 | 2026-09-09 | 2026-09-22 |  | 0.69 | 1.63 | 7 | 38 | 283.7551 | 2.8475 | 40.6095 |  | 12
6-08 | SMA | PST840 | Pull On Pants |  | 1352813, _AH |  |  | 1500 | 0 | 1500 | 203.75 | 2026-08-18 | 2026-09-01 | 2026-09-03 | 2026-09-10 | 2026-09-12 | 2026-09-22 |  | 1 | 1.63 | 9 | 38 | 528.7362 | 2.837 | 58.8544 |  | 9
6-08 | SMA | PST840 | Pull On Pants |  | 1352813, _AH |  |  | 1900 | 0 | 1900 | 258.0833 | 2026-08-18 | 2026-09-04 | 2026-09-08 | 2026-09-15 | 2026-09-17 | 2026-09-22 |  | 1.1 | 1.63 | 9 | 38 | 581.6098 | 3.2668 | 64.7398 |  | 6
6-08 | SMA | PST840 | Pull On Pants |  | 1354809_SS, _AH |  |  | 79 | 0 | 79 | 10.7308 | 2026-08-18 | 2026-09-09 | 2026-09-11 | 2026-09-15 | 2026-09-17 | 2026-09-23 |  | 1.2 | 1.63 | 8.6 | 38 | 606.2842 | 0.1303 | 70.6253 |  | 7
6-08 | SMA | PST840 | Pull On Pants |  | 1352814, _AH |  |  | 2500 | 0 | 2500 | 339.5833 | 2026-08-24 | 2026-09-09 | 2026-09-11 | 2026-09-19 | 2026-09-21 | 2026-10-02 |  | 1.2 | 1.63 | 8.6 | 38 | 606.2842 | 4.1235 | 70.6253 |  | 11
6-08 | SMA | PST840 | Pull On Pants |  | 1352814, _AH |  |  | 3938 | 0 | 3938 | 534.9117 | 2026-08-24 | 2026-09-15 | 2026-09-17 | 2026-09-26 | 2026-09-28 | 2026-10-02 |  | 1.3 | 1.63 | 8.6 | 38 | 656.8079 | 5.9957 | 76.5107 |  | 5
6-08 | SMA | PST840 | Pull On Pants |  | 1352815, _AH |  |  | 4376 | 0 | 4376 | 594.4067 | 2026-09-14 | 2026-09-22 | 2026-09-24 | 2026-10-03 | 2026-10-05 | 2026-11-02 |  | 1.4 | 1.63 | 8.6 | 38 | 707.3315 | 6.1866 | 82.3962 |  | 25
6-08 | SMA | PST840 | Pull On Pants |  | 1352815, _AH |  |  | 5500 | 0 | 5500 | 747.0833 | 2026-09-14 | 2026-09-29 | 2026-10-01 | 2026-10-12 | 2026-10-14 | 2026-11-02 |  | 1.5 | 1.63 | 8.6 | 38 | 757.8552 | 7.2573 | 88.2816 |  | 18
6-08 | SMA | PST840 | Pull On Pants |  | 1352816, _AH |  |  | 2500 | 0 | 2500 | 339.5833 | 2026-09-14 | 2026-10-07 | 2026-10-09 | 2026-10-15 | 2026-10-17 | 2026-12-03 |  | 1.5 | 1.63 | 8.6 | 38 | 757.8552 | 3.2988 | 88.2816 |  | 42
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 1140 | 0 | 1140 | 28.5 | 2026-10-13 | 2026-10-10 | 2026-10-13 | 2026-10-16 | 2026-10-18 | 2026-11-14 |  | 0.5 | 0.3 | 7 | 37.8178 | 1111.8424 | 1.0253 | 159.1211 |  | 25
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 2500 | 0 | 2500 | 62.5 | 2026-10-13 | 2026-10-12 | 2026-10-14 | 2026-10-17 | 2026-10-19 | 2026-11-14 |  | 1 | 0.3 | 8.6 | 37.8178 | 2731.9557 | 0.9151 | 318.2421 |  | 24
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 3500 | 0 | 3500 | 87.5 | 2026-10-13 | 2026-10-13 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 2026-11-14 |  | 1.2 | 0.3 | 8.6 | 37.8178 | 3278.3468 | 1.0676 | 381.8905 |  | 23
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 5000 | 0 | 5000 | 125 | 2026-10-13 | 2026-10-14 | 2026-10-16 | 2026-10-20 | 2026-10-22 | 2026-11-14 |  | 1.4 | 0.3 | 8.6 | 37.8178 | 3824.738 | 1.3073 | 445.5389 |  | 22
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 10000 | 0 | 10000 | 250 | 2026-10-13 | 2026-10-15 | 2026-10-17 | 2026-10-22 | 2026-10-24 | 2026-11-14 |  | 1.6 | 0.3 | 8.6 | 37.8178 | 4371.1291 | 2.2877 | 509.1874 |  | 20
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 10000 | 0 | 10000 | 250 | 2026-10-13 | 2026-10-17 | 2026-10-20 | 2026-10-24 | 2026-10-26 | 2026-11-14 |  | 1.8 | 0.3 | 8.6 | 37.8178 | 4917.5203 | 2.0335 | 572.8358 |  | 18
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 84140 | 0 | 84140 | 2103.5 | 2026-10-13 | 2026-10-20 | 2026-10-22 | 2026-11-11 | 2026-11-13 | 2026-11-14 |  | 2 | 0.3 | 8.6 | 37.8178 | 5463.9114 | 15.3992 | 636.4842 |  | 3
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0130_TRN |  |  | 2088 | 0 | 2088 | 52.2 | 2026-10-27 | 2026-11-06 | 2026-11-09 | 2026-11-11 | 2026-11-13 | 2026-11-18 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 0.3474 | 700.1326 |  | 6
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0213_BA |  |  | 18216 | 0 | 18216 | 455.4 | 2026-10-27 | 2026-11-06 | 2026-11-09 | 2026-11-14 | 2026-11-16 | 2026-12-03 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 3.0308 | 700.1326 |  | 16
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0220_BA |  |  | 17784 | 0 | 17784 | 444.6 | 2026-10-27 | 2026-11-10 | 2026-11-12 | 2026-11-18 | 2026-11-20 | 2026-12-09 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 2.9589 | 700.1326 |  | 18
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0227_BA |  |  | 17784 | 0 | 17784 | 444.6 | 2026-10-27 | 2026-11-13 | 2026-11-16 | 2026-11-21 | 2026-11-23 | 2026-12-16 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 2.9589 | 700.1326 |  | 21
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0306_BA |  |  | 17784 | 0 | 17784 | 444.6 | 2026-10-27 | 2026-11-17 | 2026-11-19 | 2026-11-25 | 2026-11-27 | 2026-12-23 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 2.9589 | 700.1326 |  | 24
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0313_BA |  |  | 17784 | 0 | 17784 | 444.6 | 2026-10-27 | 2026-11-20 | 2026-11-23 | 2026-11-28 | 2026-11-30 | 2026-12-30 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 2.9589 | 700.1326 |  | 26
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-11-24 | 2026-11-26 | 2026-12-01 | 2026-12-06 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 37.8178 | 362.5573 | 2.2479 | 51.8873 |  | 20
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-11-26 | 2026-11-28 | 2026-12-03 | 2026-12-08 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 37.8178 | 890.8551 | 1.6838 | 103.7746 |  | 18
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-11-28 | 2026-12-01 | 2026-12-07 | 2026-12-12 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 37.8178 | 979.9406 | 2.5512 | 114.1521 |  | 15
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-02 | 2026-12-04 | 2026-12-10 | 2026-12-15 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 37.8178 | 1069.0261 | 2.8063 | 124.5295 |  | 12
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4941 | 0 | 4941 | 378.81 | 2026-12-07 | 2026-12-05 | 2026-12-08 | 2026-12-15 | 2026-12-20 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 37.8178 | 1158.1117 | 4.2664 | 134.907 |  | 13
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-12-07 | 2026-12-10 | 2026-12-12 | 2026-12-19 | 2026-12-24 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 37.8178 | 1247.1972 | 4.009 | 145.2844 |  | 9
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 10050 | 0 | 10050 | 770.5 | 2026-12-07 | 2026-12-15 | 2026-12-17 | 2026-12-30 | 2027-01-04 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 7.5209 | 155.6619 |  | 1
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-24 | 2026-12-28 | 2026-12-31 | 2027-01-05 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 1.4398 | 155.6619 |  | 11
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-26 | 2026-12-29 | 2027-01-08 | 2027-01-13 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 5.8341 | 155.6619 |  | 11
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-04 | 2027-01-06 | 2027-01-14 | 2027-01-19 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 4.9458 | 155.6619 |  | 12
2026-05-20
6-09 | TGT | G9M018_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 65630 | 65630 | 0 | 4648.7917 | 2026-05-25 | 2026-05-11 | 2026-05-18 | 2026-07-04 | 2026-07-06 | 2026-07-11 |  | 1.8566 | 0.85 | 9.5019 | 35.1267 | 1837.1199 | 35.7244 | 193.6912 |  | 6
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874451_BA_E |  |  | 171876 | 171876 | 0 | 3151.06 | 2026-06-27 | 2026-06-26 | 2026-07-02 | 2026-07-25 | 2026-07-27 | 2026-08-05 |  | 2.8155 | 0.22 | 8.2809 | 35.8848 | 9583.592 | 17.9344 | 1159.3956 |  | 9
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874422_TRN_W |  |  | 8820 | 8820 | 0 | 161.7 | 2026-06-27 | 2026-07-17 | 2026-07-23 | 2026-07-27 | 2026-07-29 | 2026-08-13 |  | 2.8082 | 0.22 | 5.7423 | 36.7474 | 6787.7449 | 1.2994 | 1184.1877 |  | 14
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874468_BA_E |  |  | 50484 | 50484 | 0 | 925.54 | 2026-06-27 | 2026-07-18 | 2026-07-24 | 2026-08-01 | 2026-08-03 | 2026-08-19 |  | 3.106 | 0.22 | 7.8623 | 36.816 | 10298.4392 | 4.9021 | 1312.2127 |  | 12
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874454_BA_E |  |  | 43596 | 43596 | 0 | 799.26 | 2026-07-04 | 2026-07-24 | 2026-07-30 | 2026-08-06 | 2026-08-08 | 2026-08-26 |  | 3.1127 | 0.22 | 7.4905 | 36.8263 | 9835.3064 | 4.4326 | 1315.3963 |  | 12
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874439_BA_E |  |  | 107016 | 107016 | 0 | 1961.96 | 2026-07-01 | 2026-07-29 | 2026-08-04 | 2026-08-21 | 2026-08-23 | 2026-09-02 |  | 3.0576 | 0.22 | 8.0034 | 36.8072 | 10317.1778 | 10.3726 | 1291.4271 |  | 7
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874453_BA_E |  |  | 42420 | 42420 | 0 | 777.7 | 2026-07-11 | 2026-08-11 | 2026-08-19 | 2026-08-28 | 2026-08-30 | 2026-09-09 |  | 3.1215 | 0.22 | 9 | 36.5448 | 11760.1408 | 3.6071 | 1309.0386 |  | 8
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874469_BA_E |  |  | 28896 | 28896 | 0 | 529.76 | 2026-07-08 | 2026-08-18 | 2026-08-26 | 2026-09-01 | 2026-09-03 | 2026-10-07 |  | 3.1561 | 0.22 | 9 | 36.41 | 11846.5069 | 2.4392 | 1318.6521 |  | 29
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874471_BA_E |  |  | 55356 | 34575 | 20781 | 1014.86 | 2026-07-11 | 2026-08-20 | 2026-08-28 | 2026-09-08 | 2026-09-10 | 2026-10-14 |  | 2.9 | 0.22 | 9 | 36.8261 | 11009.6528 | 5.028 | 1225.5007 |  | 30
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874444_BA_E |  |  | 49392 | 0 | 49392 | 905.52 | 2026-07-11 | 2026-08-28 | 2026-09-04 | 2026-09-14 | 2026-09-16 | 2026-10-21 |  | 2.9 | 0.22 | 9 | 36.8261 | 11009.6528 | 4.4862 | 1225.5007 |  | 32
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874473_BA_E |  |  | 49560 | 0 | 49560 | 908.6 | 2026-07-11 | 2026-09-03 | 2026-09-10 | 2026-09-19 | 2026-09-21 | 2026-11-04 |  | 2.9 | 0.22 | 8.6 | 36.8261 | 10520.3349 | 4.7109 | 1225.5007 |  | 39
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021697_T1 |  |  | 704 | 0 | 704 | 69.8133 | 2026-09-08 | 2026-09-15 | 2026-09-17 | 2026-09-23 | 2026-09-25 | 2026-10-22 |  | 0.5 | 1.19 | 7 | 36.8261 | 272.9461 | 2.5793 | 39.0626 |  | 25
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021697_T1 |  |  | 1800 | 0 | 1800 | 178.5 | 2026-09-08 | 2026-09-18 | 2026-09-21 | 2026-09-26 | 2026-09-28 | 2026-10-22 |  | 1 | 1.19 | 8.6 | 36.8261 | 670.6675 | 2.6839 | 78.1252 |  | 22
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 2666 | 0 | 2666 | 264.3783 | 2026-09-08 | 2026-09-22 | 2026-09-24 | 2026-10-01 | 2026-10-03 | 2026-10-29 |  | 1.1 | 1.19 | 8.6 | 36.8261 | 737.7343 | 3.6138 | 85.9377 |  | 24
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 3000 | 0 | 3000 | 297.5 | 2026-09-08 | 2026-09-26 | 2026-09-29 | 2026-10-06 | 2026-10-08 | 2026-10-29 |  | 1.2 | 1.19 | 8.6 | 36.8261 | 804.801 | 3.7276 | 93.7503 |  | 20
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 3500 | 0 | 3500 | 347.0833 | 2026-09-08 | 2026-10-01 | 2026-10-03 | 2026-10-10 | 2026-10-12 | 2026-10-29 |  | 1.4 | 1.19 | 8.6 | 36.8261 | 938.9346 | 3.7276 | 109.3753 |  | 16
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021703 |  |  | 4440 | 0 | 4440 | 440.3 | 2026-09-08 | 2026-10-06 | 2026-10-08 | 2026-10-15 | 2026-10-17 | 2026-11-18 |  | 1.6 | 1.19 | 8.6 | 36.8261 | 1073.0681 | 4.1377 | 125.0004 |  | 29
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021703 |  |  | 5000 | 0 | 5000 | 495.8333 | 2026-09-08 | 2026-10-10 | 2026-10-13 | 2026-10-20 | 2026-10-22 | 2026-11-18 |  | 1.8 | 1.19 | 8.6 | 36.8261 | 1207.2016 | 4.1418 | 140.6254 |  | 25
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021702 |  |  | 12160 | 0 | 12160 | 1205.8667 | 2026-09-08 | 2026-10-15 | 2026-10-17 | 2026-10-31 | 2026-11-02 | 2026-12-02 |  | 1.8 | 1.19 | 8.6 | 36.8261 | 1207.2016 | 10.0729 | 140.6254 |  | 27
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021705, 0301_GLAM |  |  | 9584 | 0 | 9584 | 950.4133 | 2026-09-08 | 2026-10-27 | 2026-10-29 | 2026-11-10 | 2026-11-12 | 2026-12-16 |  | 1.8 | 1.19 | 8.6 | 36.8261 | 1207.2016 | 7.939 | 140.6254 |  | 31
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0130_TRN |  |  | 2940 | 0 | 2940 | 53.9 | 2026-10-13 | 2026-11-02 | 2026-11-07 | 2026-11-12 | 2026-11-14 | 2026-11-18 |  | 0.5 | 0.22 | 7 | 36.8261 | 1476.3902 | 1.9913 | 211.2932 |  | 5
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0206_BA |  |  | 10000 | 0 | 10000 | 183.3333 | 2026-10-13 | 2026-11-04 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 2026-11-25 |  | 1 | 0.22 | 8.6 | 36.8261 | 3627.7017 | 2.7566 | 422.5864 |  | 8
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0206_BA |  |  | 15000 | 0 | 15000 | 275 | 2026-10-13 | 2026-11-07 | 2026-11-13 | 2026-11-19 | 2026-11-21 | 2026-11-25 |  | 1.5 | 0.22 | 8.6 | 36.8261 | 5441.5525 | 2.7566 | 633.8797 |  | 5
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0206_BA |  |  | 17244 | 0 | 17244 | 316.14 | 2026-10-13 | 2026-11-11 | 2026-11-17 | 2026-11-21 | 2026-11-23 | 2026-11-25 |  | 2 | 0.22 | 8.6 | 36.8261 | 7255.4034 | 2.3767 | 845.1729 |  | 3
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0206_BA |  |  | 20000 | 0 | 20000 | 366.6667 | 2026-10-13 | 2026-11-13 | 2026-11-19 | 2026-11-24 | 2026-11-26 | 2026-11-25 |  | 2.5 | 0.22 | 8.6 | 36.8261 | 9069.2542 | 2.2053 | 1056.4661 |  | 1
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0213_BA |  |  | 16548 | 0 | 16548 | 303.38 | 2026-10-13 | 2026-11-16 | 2026-11-21 | 2026-11-26 | 2026-11-28 | 2026-12-02 |  | 2.7 | 0.22 | 8.6 | 36.8261 | 9794.7946 | 1.6895 | 1140.9834 |  | 5
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0220_BA |  |  | 16548 | 0 | 16548 | 303.38 | 2026-10-27 | 2026-11-18 | 2026-11-24 | 2026-11-28 | 2026-11-30 | 2026-12-09 |  | 2.8 | 0.22 | 8.6 | 36.8261 | 10157.5647 | 1.6291 | 1183.242 |  | 9
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0227_BA |  |  | 16548 | 0 | 16548 | 303.38 | 2026-10-27 | 2026-11-20 | 2026-11-26 | 2026-12-01 | 2026-12-03 | 2026-12-16 |  | 2.9 | 0.22 | 8.6 | 36.8261 | 10520.3349 | 1.573 | 1225.5007 |  | 13
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0306_BA |  |  | 16548 | 0 | 16548 | 303.38 | 2026-10-27 | 2026-11-23 | 2026-11-28 | 2026-12-03 | 2026-12-05 | 2026-12-23 |  | 2.9 | 0.22 | 8.6 | 36.8261 | 10520.3349 | 1.573 | 1225.5007 |  | 17
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0313_BA |  |  | 16548 | 0 | 16548 | 303.38 | 2026-10-27 | 2026-11-25 | 2026-12-01 | 2026-12-05 | 2026-12-07 | 2026-12-30 |  | 2.9 | 0.22 | 8.6 | 36.8261 | 10520.3349 | 1.573 | 1225.5007 |  | 20
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-12-01 | 2026-12-03 | 2026-12-08 | 2026-12-13 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 36.8261 | 353.0498 | 2.3085 | 50.5266 |  | 14
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-12-03 | 2026-12-05 | 2026-12-10 | 2026-12-15 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 36.8261 | 867.4939 | 1.7291 | 101.0533 |  | 12
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-12-05 | 2026-12-08 | 2026-12-14 | 2026-12-19 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 36.8261 | 954.2433 | 2.6199 | 111.1586 |  | 9
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-09 | 2026-12-11 | 2026-12-17 | 2026-12-22 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 36.8261 | 1040.9927 | 2.8819 | 121.2639 |  | 6
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4041 | 0 | 4041 | 309.81 | 2026-12-07 | 2026-12-12 | 2026-12-15 | 2026-12-22 | 2026-12-27 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 36.8261 | 1127.742 | 3.5833 | 131.3693 |  | 7
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4000 | 0 | 4000 | 306.6667 | 2026-12-07 | 2026-12-17 | 2026-12-19 | 2026-12-26 | 2026-12-31 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 36.8261 | 1214.4914 | 3.2936 | 141.4746 |  | 4
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4000 | 0 | 4000 | 306.6667 | 2026-12-07 | 2026-12-21 | 2026-12-23 | 2026-12-30 | 2027-01-04 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 36.8261 | 1301.2408 | 3.074 | 151.5799 |  | 1
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-24 | 2026-12-28 | 2026-12-31 | 2027-01-05 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 36.8261 | 1301.2408 | 1.4786 | 151.5799 |  | 11
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-26 | 2026-12-29 | 2027-01-08 | 2027-01-13 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 36.8261 | 1301.2408 | 5.9912 | 151.5799 |  | 11
6-09 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-04 | 2027-01-06 | 2027-01-14 | 2027-01-19 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 36.8261 | 1301.2408 | 5.079 | 151.5799 |  | 12
2026-04-16
6-10 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 15160 | 15160 | 0 | 1326.5 | 2026-04-25 | 2026-04-11 | 2026-04-14 | 2026-05-04 | 2026-05-09 | 2026-06-04 |  | 1.4219 | 1.05 | 8.5757 | 37.7094 | 1103.5488 | 13.7375 | 128.9159 |  | 24
6-10 | ONY | 962148_FA26 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | all po |  |  | 4540 | 4540 | 0 | 211.8667 | 2026-04-15 | 2026-04-28 | 2026-04-30 | 2026-05-08 | 2026-05-10 | 2026-08-06 |  | 0.88245 | 0.56 | 8.0175 | 38 | 1209.8277 | 3.7526 | 151.1709 |  | 73
6-10 | ONY | 905200_FA26 | Pull On Pants |  | all po |  |  | 57498 | 57498 | 0 | 5366.48 | 2026-05-15 | 2026-05-04 | 2026-05-06 | 2026-07-13 | 2026-07-15 | 2026-07-16 |  | 1.4275 | 1.12 | 9.3511 | 36.6522 | 1100.8636 | 52.2299 | 117.9376 |  | 3
6-10 | TGT | X25413_C426 | Pull On Pants |  | all po |  |  | 3123 | 3123 | 0 | 379.965 | 2026-07-06 | 2026-07-08 | 2026-07-10 | 2026-07-18 | 2026-07-20 | 2026-08-15 |  | 1.2038 | 1.46 | 7.7928 | 35.9876 | 582.7032 | 5.3595 | 74.9092 |  | 22
6-10 | ONY | 826369_HO26 | Pull On Pants |  | all po |  |  | 2235 | 2235 | 0 | 167.625 | 2026-07-13 | 2026-07-14 | 2026-07-16 | 2026-07-23 | 2026-07-25 | 2026-08-13 |  | 0.82751 | 0.9 | 7.2576 | 37.0282 | 622.6666 | 3.5894 | 85.9499 |  | 17
6-10 | ONY | 1184403_HO26 | Pull On Pants |  | all po |  |  | 7414 | 7414 | 0 | 716.6867 | 2026-07-13 | 2026-07-18 | 2026-07-21 | 2026-08-07 | 2026-08-09 | 2026-08-20 |  | 0.95783 | 1.16 | 7.2192 | 37.4439 | 562.4717 | 13.1811 | 78.0539 |  | 8
6-10 | ONY | 1182719_HO26 | Skorts |  | all po |  |  | 23350 | 23350 | 0 | 1148.0417 | 2026-07-11 | 2026-08-03 | 2026-08-05 | 2026-08-31 | 2026-09-02 | 2026-08-27 |  | 1.2859 | 0.59 | 8 | 37.7782 | 1659.9607 | 14.0666 | 207.8692 |  | -4
6-10 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 12523 | 9564 | 2959 | 553.0992 | 2026-08-06 | 2026-08-24 | 2026-08-27 | 2026-09-08 | 2026-09-10 | 2026-09-17 |  | 1.37 | 0.53 | 9 | 38 | 2227.7751 | 5.6213 | 247.9769 |  | 7
6-10 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 5500 | 0 | 5500 | 242.9167 | 2026-08-06 | 2026-09-02 | 2026-09-04 | 2026-09-10 | 2026-09-12 | 2026-09-17 |  | 1.4 | 0.53 | 9 | 38 | 2276.5585 | 2.4159 | 253.4071 |  | 5
6-10 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 12074 | 0 | 12074 | 533.2683 | 2026-08-06 | 2026-09-04 | 2026-09-08 | 2026-09-17 | 2026-09-19 | 2026-09-17 |  | 1.5 | 0.53 | 8.6 | 38 | 2330.7623 | 5.1803 | 271.5076 |  | 0
6-10 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016283, 292, 296 |  |  | 4000 | 0 | 4000 | 176.6667 | 2026-08-06 | 2026-09-11 | 2026-09-15 | 2026-09-19 | 2026-09-21 | 2026-10-15 |  | 1.5 | 0.53 | 8.6 | 38 | 2330.7623 | 1.7162 | 271.5076 |  | 22
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 728 | 0 | 728 | 59.4533 | 2026-09-07 | 2026-09-15 | 2026-09-17 | 2026-09-22 | 2026-09-27 | 2026-10-01 |  | 0.5 | 0.98 | 7 | 38 | 342 | 2.1287 | 48.9452 |  | 8
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 1500 | 0 | 1500 | 122.5 | 2026-09-07 | 2026-09-17 | 2026-09-19 | 2026-09-24 | 2026-09-29 | 2026-10-01 |  | 1 | 0.98 | 8.6 | 38 | 840.3429 | 1.785 | 97.8905 |  | 6
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 2700 | 0 | 2700 | 220.5 | 2026-09-07 | 2026-09-19 | 2026-09-22 | 2026-09-28 | 2026-10-03 | 2026-10-01 |  | 1.2 | 0.98 | 8.6 | 38 | 1008.4114 | 2.6775 | 117.4686 |  | 3
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62239979, 378, 565, 268, 269 |  |  | 1503 | 0 | 1503 | 122.745 | 2026-09-07 | 2026-09-23 | 2026-09-25 | 2026-09-29 | 2026-10-04 | 2026-10-08 |  | 1.4 | 0.98 | 8.6 | 38 | 1176.48 | 1.2775 | 137.0467 |  | 8
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 4500 | 0 | 4500 | 367.5 | 2026-09-07 | 2026-09-24 | 2026-09-26 | 2026-10-02 | 2026-10-07 | 2026-10-15 |  | 1.6 | 0.98 | 8.6 | 38 | 1344.5486 | 3.3468 | 156.6248 |  | 11
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 6250 | 0 | 6250 | 510.4167 | 2026-09-07 | 2026-09-28 | 2026-09-30 | 2026-10-07 | 2026-10-12 | 2026-10-15 |  | 1.8 | 0.98 | 8.6 | 38 | 1512.6171 | 4.1319 | 176.2029 |  | 7
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 960 | 0 | 960 | 25.6 | 2026-10-12 | 2026-10-02 | 2026-10-05 | 2026-10-08 | 2026-10-10 | 2026-11-02 |  | 0.5 | 0.32 | 7 | 38 | 1047.375 | 0.91658 | 149.8948 |  | 21
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 1500 | 0 | 1500 | 40 | 2026-10-12 | 2026-10-03 | 2026-10-06 | 2026-10-09 | 2026-10-11 | 2026-11-02 |  | 1 | 0.32 | 8.6 | 38 | 2573.55 | 0.58285 | 299.7896 |  | 20
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 2500 | 0 | 2500 | 66.6667 | 2026-10-12 | 2026-10-05 | 2026-10-07 | 2026-10-10 | 2026-10-12 | 2026-11-02 |  | 1.1 | 0.32 | 8.6 | 38 | 2830.905 | 0.88311 | 329.7686 |  | 19
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 3500 | 0 | 3500 | 93.3333 | 2026-10-12 | 2026-10-06 | 2026-10-08 | 2026-10-12 | 2026-10-14 | 2026-11-02 |  | 1.2 | 0.32 | 8.6 | 38 | 3088.26 | 1.1333 | 359.7475 |  | 18
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 4500 | 0 | 4500 | 120 | 2026-10-12 | 2026-10-07 | 2026-10-09 | 2026-10-13 | 2026-10-15 | 2026-11-02 |  | 1.3 | 0.32 | 8.6 | 38 | 3345.615 | 1.345 | 389.7265 |  | 17
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0130_W |  |  | 1044 | 0 | 1044 | 27.84 | 2026-10-20 | 2026-10-08 | 2026-10-10 | 2026-10-13 | 2026-10-15 | 2026-11-11 |  | 1.4 | 0.32 | 8.6 | 38 | 3602.97 | 0.28976 | 419.7055 |  | 25
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 5000 | 0 | 5000 | 133.3333 | 2026-10-12 | 2026-10-08 | 2026-10-10 | 2026-10-14 | 2026-10-16 | 2026-11-12 |  | 1.6 | 0.32 | 8.6 | 38 | 4117.68 | 1.2143 | 479.6634 |  | 25
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 7000 | 0 | 7000 | 186.6667 | 2026-10-12 | 2026-10-09 | 2026-10-12 | 2026-10-16 | 2026-10-18 | 2026-11-12 |  | 1.8 | 0.32 | 8.6 | 38 | 4632.39 | 1.5111 | 539.6213 |  | 23
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 33180 | 0 | 33180 | 884.8 | 2026-10-12 | 2026-10-12 | 2026-10-14 | 2026-10-23 | 2026-10-25 | 2026-11-12 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 6.4463 | 599.5792 |  | 17
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_W |  |  | 860 | 0 | 860 | 65.9333 | 2026-10-31 | 2026-10-19 | 2026-10-21 | 2026-10-26 | 2026-10-28 | 2026-12-03 |  | 0.5 | 0.92 | 7 | 38 | 364.3043 | 2.3607 | 52.1373 |  | 33
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_W |  |  | 1500 | 0 | 1500 | 115 | 2026-10-31 | 2026-10-21 | 2026-10-23 | 2026-10-28 | 2026-10-30 | 2026-12-03 |  | 1 | 0.92 | 8.6 | 38 | 895.1478 | 1.6757 | 104.2747 |  | 31
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_W |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-10-31 | 2026-10-23 | 2026-10-26 | 2026-10-31 | 2026-11-02 | 2026-12-03 |  | 1.1 | 0.92 | 8.6 | 38 | 984.6626 | 2.5389 | 114.7021 |  | 28
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_W |  |  | 3000 | 0 | 3000 | 230 | 2026-10-31 | 2026-10-27 | 2026-10-29 | 2026-11-04 | 2026-11-06 | 2026-12-03 |  | 1.2 | 0.92 | 8.6 | 38 | 1074.1774 | 2.7928 | 125.1296 |  | 25
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_W |  |  | 4000 | 0 | 4000 | 306.6667 | 2026-10-31 | 2026-10-30 | 2026-11-02 | 2026-11-07 | 2026-11-09 | 2026-12-03 |  | 1.4 | 0.92 | 8.6 | 38 | 1253.207 | 3.1918 | 145.9845 |  | 22
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0221_W |  |  | 4500 | 0 | 4500 | 345 | 2026-10-31 | 2026-11-03 | 2026-11-05 | 2026-11-11 | 2026-11-13 | 2026-12-03 |  | 1.6 | 0.92 | 8.6 | 38 | 1432.2365 | 3.1419 | 166.8394 |  | 19
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0307_E |  |  | 10904 | 0 | 10904 | 835.9733 | 2026-10-31 | 2026-11-06 | 2026-11-09 | 2026-11-19 | 2026-11-21 | 2026-12-07 |  | 1.8 | 0.92 | 8.6 | 38 | 1611.2661 | 6.7673 | 187.6944 |  | 15
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0307_W |  |  | 13634 | 0 | 13634 | 1045.2733 | 2026-10-31 | 2026-11-14 | 2026-11-17 | 2026-11-28 | 2026-11-30 | 2026-12-17 |  | 2 | 0.92 | 8.6 | 38 | 1790.2957 | 7.6155 | 208.5493 |  | 16
2026-05-21
6-11 | TGT | MRLPMM_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 98283 | 98283 | 0 | 7371.225 | 2026-06-08 | 2026-05-12 | 2026-05-19 | 2026-08-06 | 2026-08-08 | 2026-08-22 |  | 2.1566 | 0.9 | 8.7955 | 29.273 | 1554.7148 | 63.2161 | 177.0823 |  | 10
6-11 | ONY | 1182719_HO26 | Skorts |  | all po |  |  | 17407 | 17407 | 0 | 855.8442 | 2026-07-11 | 2026-08-01 | 2026-08-04 | 2026-08-28 | 2026-08-30 | 2026-08-27 |  | 1.242 | 0.59 | 8 | 30.358 | 1288.3006 | 13.5116 | 161.328 |  | -3
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004922_T1_W |  |  | 720 | 720 | 0 | 63.6 | 2026-08-24 | 2026-08-18 | 2026-08-26 | 2026-08-31 | 2026-09-02 | 2026-10-01 |  | 0.88836 | 1.06 | 8 | 29.4464 | 497.5125 | 1.4472 | 62.3012 |  | 25
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 7500 | 5062 | 2438 | 662.5 | 2026-08-24 | 2026-08-19 | 2026-08-27 | 2026-09-09 | 2026-09-11 | 2026-10-08 |  | 1.74 | 1.06 | 9 | 30 | 1116.883 | 6.7151 | 124.3219 |  | 24
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 4500 | 0 | 4500 | 397.5 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-15 | 2026-09-17 | 2026-10-08 |  | 1.8 | 1.06 | 8.6 | 30 | 1104.0453 | 4.0759 | 128.6089 |  | 20
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 8999 | 0 | 8999 | 794.9117 | 2026-08-24 | 2026-09-04 | 2026-09-11 | 2026-09-23 | 2026-09-25 | 2026-10-08 |  | 2 | 1.06 | 8.6 | 30 | 1226.717 | 7.3358 | 142.8987 |  | 13
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004937_BA_E |  |  | 6792 | 0 | 6792 | 599.96 | 2026-09-10 | 2026-09-15 | 2026-09-21 | 2026-09-30 | 2026-10-02 | 2026-10-12 |  | 2 | 1.06 | 8.6 | 30 | 1226.717 | 5.5367 | 142.8987 |  | 10
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004936_BA_E |  |  | 7078 | 0 | 7078 | 625.2233 | 2026-08-29 | 2026-09-22 | 2026-09-28 | 2026-10-07 | 2026-10-09 | 2026-10-24 |  | 2 | 1.06 | 8.6 | 30 | 1226.717 | 5.7699 | 142.8987 |  | 15
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004947_BA_E |  |  | 6792 | 0 | 6792 | 599.96 | 2026-09-05 | 2026-09-29 | 2026-10-05 | 2026-10-14 | 2026-10-16 | 2026-10-26 |  | 2 | 1.06 | 8.6 | 30 | 1226.717 | 5.5367 | 142.8987 |  | 10
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004946_BA_E |  |  | 9078 | 0 | 9078 | 801.89 | 2026-09-05 | 2026-10-06 | 2026-10-12 | 2026-10-22 | 2026-10-24 | 2026-11-07 |  | 2 | 1.06 | 8.6 | 30 | 1226.717 | 7.4002 | 142.8987 |  | 14
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004950_BA_E |  |  | 3792 | 0 | 3792 | 334.96 | 2026-09-05 | 2026-10-14 | 2026-10-20 | 2026-10-26 | 2026-10-28 | 2026-11-09 |  | 2 | 1.06 | 8.6 | 30 | 1226.717 | 3.0912 | 142.8987 |  | 12
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004948_BA_E |  |  | 9078 | 0 | 9078 | 801.89 | 2026-09-05 | 2026-10-17 | 2026-10-23 | 2026-11-03 | 2026-11-05 | 2026-11-21 |  | 2 | 1.06 | 8.6 | 30 | 1226.717 | 7.4002 | 142.8987 |  | 16
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004939_BA_E |  |  | 4792 | 0 | 4792 | 423.2933 | 2026-09-05 | 2026-10-26 | 2026-10-31 | 2026-11-07 | 2026-11-09 | 2026-11-23 |  | 2 | 1.06 | 8.6 | 30 | 1226.717 | 3.9064 | 142.8987 |  | 13
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004938_BA_E, LIVERPOOL_C127 |  |  | 16928 | 0 | 16928 | 1495.3067 | 2026-09-05 | 2026-10-30 | 2026-11-05 | 2026-11-24 | 2026-11-26 | 2026-12-05 |  | 2 | 1.06 | 8.6 | 30 | 1226.717 | 13.7994 | 142.8987 |  | 10
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | GLAM |  |  | 647 | 0 | 647 | 57.1517 | 2026-09-19 | 2026-11-16 | 2026-11-21 | 2026-11-25 | 2026-11-27 | 2027-01-05 |  | 2 | 1.06 | 8.6 | 30 | 1226.717 | 0.52742 | 142.8987 |  | 33
6-11 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-11-20 | 2026-11-23 | 2026-11-28 | 2026-12-03 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 30 | 287.6087 | 2.8337 | 41.161 |  | 22
6-11 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-11-24 | 2026-11-26 | 2026-12-01 | 2026-12-06 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 30 | 706.6957 | 2.1226 | 82.3221 |  | 20
6-11 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-11-26 | 2026-11-28 | 2026-12-04 | 2026-12-09 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 30 | 777.3652 | 3.216 | 90.5543 |  | 17
6-11 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2026-12-09 | 2026-12-14 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 30 | 848.0348 | 3.5376 | 98.7865 |  | 13
6-11 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4041 | 0 | 4041 | 309.81 | 2026-12-07 | 2026-12-04 | 2026-12-07 | 2026-12-14 | 2026-12-19 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 30 | 918.7043 | 4.3986 | 107.0187 |  | 14
6-11 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4550 | 0 | 4550 | 348.8333 | 2026-12-07 | 2026-12-09 | 2026-12-11 | 2026-12-19 | 2026-12-24 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 30 | 989.3739 | 4.5989 | 115.2509 |  | 9
6-11 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-15 | 2026-12-17 | 2026-12-22 | 2026-12-27 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 30 | 1060.0435 | 1.815 | 123.4831 |  | 18
6-11 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-17 | 2026-12-19 | 2026-12-31 | 2027-01-05 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 30 | 1060.0435 | 7.3544 | 123.4831 |  | 17
6-11 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2026-12-26 | 2026-12-29 | 2027-01-08 | 2027-01-13 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 30 | 1060.0435 | 6.2346 | 123.4831 |  | 17
2026-04-23
6-12 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08 |  |  | 36158 | 36158 | 0 | 3163.825 | 2026-05-04 | 2026-04-18 | 2026-04-21 | 2026-05-26 | 2026-05-31 | 2026-07-23 |  | 1.6893 | 1.05 | 9.1441 | 37.1237 | 1376.3212 | 26.2715 | 150.7858 |  | 47
6-12 | ONY | 907938_FA26 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | all po |  |  | 1178 | 1178 | 0 | 89.3317 | 2026-05-07 | 2026-05-21 | 2026-05-23 | 2026-05-29 | 2026-05-31 | 2026-06-11 |  | 0.65017 | 0.91 | 7.881 | 35.392 | 502.1956 | 2.3457 | 63.837 |  | 10
6-12 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 31999 | 31999 | 0 | 3706.5508 | 2026-06-03 | 2026-05-23 | 2026-05-26 | 2026-07-09 | 2026-07-11 | 2026-07-09 |  | 1.5521 | 1.39 | 9.4353 | 36.0815 | 957.9881 | 33.4023 | 101.7153 |  | 0
6-12 | ONY | 910047_HO26DIS | Pajama |  | all po |  |  | 27677 | 27677 | 0 | 3275.1117 | 2026-07-06 | 2026-07-04 | 2026-07-07 | 2026-08-13 | 2026-08-15 | 2026-09-03 |  | 1.7232 | 1.42 | 8.2028 | 37.8066 | 948.3748 | 29.1836 | 115.8242 |  | 13
6-12 | TGT | X25413_C426 | Pull On Pants |  | all po |  |  | 3075 | 3075 | 0 | 374.125 | 2026-07-06 | 2026-08-07 | 2026-08-11 | 2026-08-26 | 2026-08-28 | 2026-09-01 |  | 0.88558 | 1.46 | 8 | 37.3443 | 456.6583 | 6.7337 | 57.1852 |  | 4
6-12 | KOH | ZC6HY000 | Gown |  | 16439999, 00, 001 |  |  | 17914 | 11369 | 6545 | 985.27 | 2026-07-30 | 2026-08-19 | 2026-08-21 | 2026-09-11 | 2026-09-13 | 2026-09-28 |  | 1.11 | 0.66 | 9 | 38.2541 | 1459.1493 | 12.277 | 162.4201 |  | 13
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021697_T1 |  |  | 704 | 0 | 704 | 69.8133 | 2026-09-08 | 2026-09-07 | 2026-09-09 | 2026-09-15 | 2026-09-17 | 2026-10-22 |  | 0.5 | 1.19 | 7 | 38.2541 | 283.5302 | 2.483 | 40.5773 |  | 32
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021697_T1 |  |  | 1800 | 0 | 1800 | 178.5 | 2026-09-08 | 2026-09-09 | 2026-09-11 | 2026-09-18 | 2026-09-20 | 2026-10-22 |  | 1 | 1.19 | 8.6 | 38.2541 | 696.6741 | 2.5837 | 81.1547 |  | 29
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 2666 | 0 | 2666 | 264.3783 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 2026-09-22 | 2026-09-24 | 2026-10-29 |  | 1.1 | 1.19 | 8.6 | 38.2541 | 766.3415 | 3.4789 | 89.2702 |  | 32
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 3000 | 0 | 3000 | 297.5 | 2026-09-08 | 2026-09-17 | 2026-09-19 | 2026-09-26 | 2026-09-28 | 2026-10-29 |  | 1.2 | 1.19 | 8.6 | 38.2541 | 836.0089 | 3.5885 | 97.3856 |  | 28
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 3500 | 0 | 3500 | 347.0833 | 2026-09-08 | 2026-09-22 | 2026-09-24 | 2026-10-01 | 2026-10-03 | 2026-10-29 |  | 1.4 | 1.19 | 8.6 | 38.2541 | 975.3438 | 3.5885 | 113.6166 |  | 24
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021703 |  |  | 3440 | 0 | 3440 | 341.1333 | 2026-09-08 | 2026-09-26 | 2026-09-29 | 2026-10-05 | 2026-10-07 | 2026-11-18 |  | 1.6 | 1.19 | 8.6 | 38.2541 | 1114.6786 | 3.0861 | 129.8475 |  | 38
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021703 |  |  | 4500 | 0 | 4500 | 446.25 | 2026-09-08 | 2026-09-30 | 2026-10-02 | 2026-10-09 | 2026-10-11 | 2026-11-18 |  | 1.8 | 1.19 | 8.6 | 38.2541 | 1254.0134 | 3.5885 | 146.0785 |  | 34
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021702 |  |  | 10160 | 0 | 10160 | 1007.5333 | 2026-09-08 | 2026-10-05 | 2026-10-07 | 2026-10-19 | 2026-10-21 | 2026-12-02 |  | 1.8 | 1.19 | 8.6 | 38.2541 | 1254.0134 | 8.102 | 146.0785 |  | 38
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021705, 0301_GLAM |  |  | 9300 | 0 | 9300 | 922.25 | 2026-09-08 | 2026-10-14 | 2026-10-16 | 2026-10-27 | 2026-10-29 | 2026-12-16 |  | 1.8 | 1.19 | 8.6 | 38.2541 | 1254.0134 | 7.4162 | 146.0785 |  | 43
6-12 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 750 | 0 | 750 | 55.625 | 2026-10-23 | 2026-10-22 | 2026-10-24 | 2026-10-29 | 2026-10-31 | 2026-11-19 |  | 0.5 | 0.89 | 7 | 38.2541 | 379.1021 | 1.9784 | 54.2551 |  | 18
6-12 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 1500 | 0 | 1500 | 111.25 | 2026-10-23 | 2026-10-24 | 2026-10-27 | 2026-10-31 | 2026-11-02 | 2026-11-19 |  | 1 | 0.89 | 8.6 | 38.2541 | 931.5081 | 1.6103 | 108.5102 |  | 16
6-12 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 2250 | 0 | 2250 | 166.875 | 2026-10-23 | 2026-10-27 | 2026-10-29 | 2026-11-03 | 2026-11-05 | 2026-11-19 |  | 1.1 | 0.89 | 8.6 | 38.2541 | 1024.6589 | 2.1959 | 119.3612 |  | 14
6-12 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 3000 | 0 | 3000 | 222.5 | 2026-10-23 | 2026-10-29 | 2026-10-31 | 2026-11-06 | 2026-11-08 | 2026-11-19 |  | 1.2 | 0.89 | 8.6 | 38.2541 | 1117.8097 | 2.6838 | 130.2123 |  | 11
6-12 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 3500 | 0 | 3500 | 259.5833 | 2026-10-23 | 2026-11-02 | 2026-11-04 | 2026-11-10 | 2026-11-12 | 2026-11-19 |  | 1.3 | 0.89 | 8.6 | 38.2541 | 1210.9605 | 2.8903 | 141.0633 |  | 8
6-12 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 4500 | 0 | 4500 | 333.75 | 2026-10-23 | 2026-11-05 | 2026-11-07 | 2026-11-13 | 2026-11-15 | 2026-11-19 |  | 1.4 | 0.89 | 8.6 | 38.2541 | 1304.1113 | 3.4506 | 151.9143 |  | 5
6-12 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 5502 | 0 | 5502 | 408.065 | 2026-10-23 | 2026-11-09 | 2026-11-11 | 2026-11-18 | 2026-11-20 | 2026-11-19 |  | 1.5 | 0.89 | 8.6 | 38.2541 | 1397.2621 | 3.9377 | 162.7653 |  | 1
6-12 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041432_US_OS |  |  | 5625 | 0 | 5625 | 417.1875 | 2026-10-30 | 2026-11-13 | 2026-11-16 | 2026-11-23 | 2026-11-25 | 2026-11-26 |  | 1.5 | 0.89 | 8.6 | 38.2541 | 1397.2621 | 4.0257 | 162.7653 |  | 3
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021705, 0301_GLAM |  |  | 784 | 0 | 784 | 77.7467 | 2026-09-08 | 2026-11-18 | 2026-11-20 | 2026-11-26 | 2026-11-28 | 2026-12-16 |  | 0.5 | 1.19 | 7 | 38.2541 | 283.5302 | 2.7651 | 40.5773 |  | 17
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021705, 0301_GLAM |  |  | 1500 | 0 | 1500 | 148.75 | 2026-09-08 | 2026-11-21 | 2026-11-24 | 2026-11-28 | 2026-11-30 | 2026-12-16 |  | 1 | 1.19 | 8.6 | 38.2541 | 696.6741 | 2.1531 | 81.1547 |  | 15
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021705, 0301_GLAM |  |  | 2000 | 0 | 2000 | 198.3333 | 2026-09-08 | 2026-11-24 | 2026-11-26 | 2026-12-01 | 2026-12-03 | 2026-12-16 |  | 1.2 | 1.19 | 8.6 | 38.2541 | 836.0089 | 2.3923 | 97.3856 |  | 13
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021704 |  |  | 3320 | 0 | 3320 | 329.2333 | 2026-09-15 | 2026-11-26 | 2026-11-28 | 2026-12-04 | 2026-12-06 | 2026-12-30 |  | 1.4 | 1.19 | 8.6 | 38.2541 | 975.3438 | 3.4039 | 113.6166 |  | 21
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021704 |  |  | 5000 | 0 | 5000 | 495.8333 | 2026-09-15 | 2026-11-30 | 2026-12-02 | 2026-12-09 | 2026-12-11 | 2026-12-30 |  | 1.6 | 1.19 | 8.6 | 38.2541 | 1114.6786 | 4.4856 | 129.8475 |  | 17
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021704 |  |  | 14000 | 0 | 14000 | 1388.3333 | 2026-09-15 | 2026-12-04 | 2026-12-07 | 2026-12-22 | 2026-12-24 | 2026-12-30 |  | 1.8 | 1.19 | 8.6 | 38.2541 | 1254.0134 | 11.1642 | 146.0785 |  | 6
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021707 |  |  | 22320 | 0 | 22320 | 2213.4 | 2026-11-16 | 2026-12-17 | 2026-12-19 | 2027-01-14 | 2027-01-16 | 2027-01-13 |  | 1.8 | 1.19 | 8.6 | 38.2541 | 1254.0134 | 17.7989 | 146.0785 |  | -3
2026-07-01
6-13 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 15589 | 15589 | 0 | 1364.0375 | 2026-05-26 | 2026-06-26 | 2026-06-29 | 2026-07-16 | 2026-07-21 | 2026-07-30 |  | 1.5565 | 1.05 | 9.3933 | 34.0142 | 1193.554 | 13.061 | 127.2931 |  | 12
6-13 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08 |  |  | 10000 | 10000 | 0 | 875 | 2026-06-23 | 2026-07-11 | 2026-07-14 | 2026-07-27 | 2026-08-01 | 2026-08-20 |  | 1.7463 | 1.05 | 7.9762 | 33.0413 | 1104.5568 | 9.0534 | 138.7318 |  | 18
6-13 | ONY | 1182723_HO26 | Skorts |  | all po |  |  | 32276 | 32276 | 0 | 2447.5967 | 2026-07-14 | 2026-07-22 | 2026-07-24 | 2026-09-03 | 2026-09-05 | 2026-10-01 |  | 1.5586 | 0.91 | 7.8718 | 34.6897 | 1178.6229 | 27.3845 | 149.9965 |  | 22
6-13 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 5749 | 3388 | 2361 | 253.9142 | 2026-08-06 | 2026-08-28 | 2026-09-01 | 2026-09-08 | 2026-09-10 | 2026-09-17 |  | 1.17 | 0.53 | 9 | 35 | 1752.3509 | 3.2807 | 195.0568 |  | 7
6-13 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 3348 | 0 | 3348 | 147.87 | 2026-08-06 | 2026-09-02 | 2026-09-04 | 2026-09-10 | 2026-09-12 | 2026-09-17 |  | 1.3 | 0.53 | 9 | 35 | 1947.0566 | 1.7195 | 216.7297 |  | 5
6-13 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 3500 | 0 | 3500 | 154.5833 | 2026-08-06 | 2026-09-04 | 2026-09-08 | 2026-09-14 | 2026-09-16 | 2026-09-17 |  | 1.4 | 0.53 | 8.6 | 35 | 2003.6377 | 1.7468 | 233.4013 |  | 3
6-13 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 6250 | 0 | 6250 | 276.0417 | 2026-08-06 | 2026-09-08 | 2026-09-10 | 2026-09-17 | 2026-09-19 | 2026-09-17 |  | 1.5 | 0.53 | 8.6 | 35 | 2146.7547 | 2.9114 | 250.0728 |  | 0
6-13 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016283, 292, 296 |  |  | 17338 | 0 | 17338 | 765.7617 | 2026-08-06 | 2026-09-11 | 2026-09-15 | 2026-09-26 | 2026-09-28 | 2026-10-15 |  | 1.5 | 0.53 | 8.6 | 35 | 2146.7547 | 8.0764 | 250.0728 |  | 16
6-13 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016287 |  |  | 7319 | 0 | 7319 | 323.2558 | 2026-08-06 | 2026-09-22 | 2026-09-24 | 2026-09-30 | 2026-10-02 | 2026-11-12 |  | 1.5 | 0.53 | 8.6 | 35 | 2146.7547 | 3.4093 | 250.0728 |  | 37
6-13 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021697_T1 |  |  | 704 | 0 | 704 | 69.8133 | 2026-09-08 | 2026-09-25 | 2026-09-28 | 2026-10-03 | 2026-10-05 | 2026-10-22 |  | 0.5 | 1.19 | 7 | 35 | 259.4118 | 2.7138 | 37.1256 |  | 16
6-13 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021697_T1 |  |  | 1800 | 0 | 1800 | 178.5 | 2026-09-08 | 2026-09-29 | 2026-10-01 | 2026-10-07 | 2026-10-09 | 2026-10-22 |  | 1 | 1.19 | 8.6 | 35 | 637.4118 | 2.8239 | 74.2513 |  | 13
6-13 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 2666 | 0 | 2666 | 264.3783 | 2026-09-08 | 2026-10-02 | 2026-10-05 | 2026-10-12 | 2026-10-14 | 2026-10-29 |  | 1.1 | 1.19 | 8.6 | 35 | 701.1529 | 3.8023 | 81.6764 |  | 15
6-13 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 3000 | 0 | 3000 | 297.5 | 2026-09-08 | 2026-10-07 | 2026-10-09 | 2026-10-16 | 2026-10-18 | 2026-10-29 |  | 1.2 | 1.19 | 8.6 | 35 | 764.8941 | 3.9221 | 89.1016 |  | 11
6-13 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 3500 | 0 | 3500 | 347.0833 | 2026-09-08 | 2026-10-12 | 2026-10-14 | 2026-10-21 | 2026-10-23 | 2026-10-29 |  | 1.4 | 1.19 | 8.6 | 35 | 892.3765 | 3.9221 | 103.9518 |  | 7
6-13 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021703 |  |  | 4940 | 0 | 4940 | 489.8833 | 2026-09-08 | 2026-10-16 | 2026-10-19 | 2026-10-27 | 2026-10-29 | 2026-11-18 |  | 1.6 | 1.19 | 8.6 | 35 | 1019.8588 | 4.8438 | 118.8021 |  | 19
6-13 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 750 | 0 | 750 | 55.625 | 2026-10-23 | 2026-10-22 | 2026-10-24 | 2026-10-29 | 2026-10-31 | 2026-11-19 |  | 0.5 | 0.89 | 7 | 35 | 346.8539 | 2.1623 | 49.6399 |  | 18
6-13 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 1500 | 0 | 1500 | 111.25 | 2026-10-23 | 2026-10-24 | 2026-10-27 | 2026-10-31 | 2026-11-02 | 2026-11-19 |  | 1 | 0.89 | 8.6 | 35 | 852.2697 | 1.76 | 99.2798 |  | 16
6-13 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 2250 | 0 | 2250 | 166.875 | 2026-10-23 | 2026-10-27 | 2026-10-29 | 2026-11-03 | 2026-11-05 | 2026-11-19 |  | 1.1 | 0.89 | 8.6 | 35 | 937.4966 | 2.4 | 109.2078 |  | 14
6-13 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 3000 | 0 | 3000 | 222.5 | 2026-10-23 | 2026-10-29 | 2026-10-31 | 2026-11-06 | 2026-11-08 | 2026-11-19 |  | 1.2 | 0.89 | 8.6 | 35 | 1022.7236 | 2.9333 | 119.1358 |  | 11
6-13 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 3500 | 0 | 3500 | 259.5833 | 2026-10-23 | 2026-11-02 | 2026-11-04 | 2026-11-10 | 2026-11-12 | 2026-11-19 |  | 1.3 | 0.89 | 8.6 | 35 | 1107.9506 | 3.159 | 129.0638 |  | 8
6-13 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 4000 | 0 | 4000 | 296.6667 | 2026-10-23 | 2026-11-05 | 2026-11-07 | 2026-11-13 | 2026-11-15 | 2026-11-19 |  | 1.4 | 0.89 | 8.6 | 35 | 1193.1775 | 3.3524 | 138.9918 |  | 5
6-13 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 4752 | 0 | 4752 | 352.44 | 2026-10-23 | 2026-11-09 | 2026-11-11 | 2026-11-18 | 2026-11-20 | 2026-11-19 |  | 1.5 | 0.89 | 8.6 | 35 | 1278.4045 | 3.7171 | 148.9197 |  | 1
6-13 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041432_US_OS |  |  | 7625 | 0 | 7625 | 565.5208 | 2026-10-30 | 2026-11-13 | 2026-11-16 | 2026-11-25 | 2026-11-27 | 2026-11-26 |  | 1.5 | 0.89 | 8.6 | 35 | 1278.4045 | 5.9645 | 148.9197 |  | 1
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-11-20 | 2026-11-23 | 2026-11-27 | 2026-12-02 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 35 | 335.5435 | 2.4289 | 48.0212 |  | 23
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-11-23 | 2026-11-25 | 2026-11-30 | 2026-12-05 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 35 | 824.4783 | 1.8193 | 96.0424 |  | 21
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-11-25 | 2026-11-27 | 2026-12-03 | 2026-12-08 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 35 | 906.9261 | 2.7566 | 105.6467 |  | 18
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-11-28 | 2026-12-01 | 2026-12-07 | 2026-12-12 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 35 | 989.3739 | 3.0322 | 115.2509 |  | 15
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4441 | 0 | 4441 | 340.4767 | 2026-12-07 | 2026-12-02 | 2026-12-04 | 2026-12-11 | 2026-12-16 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 35 | 1071.8217 | 4.1434 | 124.8552 |  | 16
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-12-07 | 2026-12-07 | 2026-12-09 | 2026-12-16 | 2026-12-21 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 35 | 1154.2696 | 4.3317 | 134.4594 |  | 12
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 13550 | 0 | 13550 | 1038.8333 | 2026-12-07 | 2026-12-11 | 2026-12-14 | 2026-12-30 | 2027-01-04 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 35 | 1236.7174 | 10.9564 | 144.0637 |  | 1
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-24 | 2026-12-28 | 2027-01-02 | 2027-01-07 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 35 | 1236.7174 | 1.5557 | 144.0637 |  | 10
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-28 | 2026-12-30 | 2027-01-09 | 2027-01-14 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 35 | 1236.7174 | 6.3038 | 144.0637 |  | 10
6-13 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-05 | 2027-01-07 | 2027-01-15 | 2027-01-20 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 35 | 1236.7174 | 5.344 | 144.0637 |  | 11
2026-06-02
6-14 | TGT | MRLPMM_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 41982 | 41982 | 0 | 3148.65 | 2026-05-26 | 2026-05-22 | 2026-05-29 | 2026-07-02 | 2026-07-04 | 2026-07-25 |  | 1.9917 | 0.9 | 9.4588 | 31.818 | 1678.4133 | 25.0129 | 177.7655 |  | 20
6-14 | TGT | G9M018_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 67974 | 67974 | 0 | 4814.825 | 2026-06-25 | 2026-06-24 | 2026-06-30 | 2026-08-20 | 2026-08-22 | 2026-08-22 |  | 1.8952 | 0.85 | 8.5318 | 36.0905 | 1730.0941 | 39.2892 | 203.1487 |  | 1
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 10002039574, 76, 78 |  |  | 10452 | 7205 | 3247 | 1315.21 | 2026-08-22 | 2026-08-13 | 2026-08-18 | 2026-09-10 | 2026-09-12 | 2026-10-05 |  | 1.45 | 1.51 | 9 | 35.1606 | 765.7562 | 13.6493 | 85.2374 |  | 20
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 10002039579 |  |  | 4176 | 0 | 4176 | 525.48 | 2026-08-22 | 2026-09-04 | 2026-09-08 | 2026-09-18 | 2026-09-20 | 2026-11-16 |  | 1.5 | 1.51 | 8.6 | 35.1606 | 756.9544 | 5.5168 | 88.1767 |  | 50
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 10002039580 |  |  | 4176 | 0 | 4176 | 525.48 | 2026-08-22 | 2026-09-14 | 2026-09-16 | 2026-09-25 | 2026-09-27 | 2026-11-30 |  | 1.5 | 1.51 | 8.6 | 35.1606 | 756.9544 | 5.5168 | 88.1767 |  | 56
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 10002039581 |  |  | 4176 | 0 | 4176 | 525.48 | 2026-08-22 | 2026-09-21 | 2026-09-23 | 2026-10-02 | 2026-10-04 | 2026-12-14 |  | 1.5 | 1.51 | 8.6 | 35.1606 | 756.9544 | 5.5168 | 88.1767 |  | 62
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 0301_GLAM |  |  | 451 | 0 | 451 | 56.7508 | 2026-08-22 | 2026-09-28 | 2026-09-30 | 2026-10-03 | 2026-10-05 | 2026-12-16 |  | 1.5 | 1.51 | 8.6 | 35.1606 | 756.9544 | 0.59581 | 88.1767 |  | 63
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 10002039582 |  |  | 3036 | 0 | 3036 | 382.03 | 2026-08-22 | 2026-09-29 | 2026-10-01 | 2026-10-08 | 2026-10-10 | 2026-12-28 |  | 1.5 | 1.51 | 8.6 | 35.1606 | 756.9544 | 4.0108 | 88.1767 |  | 68
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 740 | 0 | 740 | 45.0167 | 2026-10-15 | 2026-10-03 | 2026-10-06 | 2026-10-10 | 2026-10-12 | 2026-11-06 |  | 0.5 | 0.73 | 7 | 35.1606 | 424.8172 | 1.7419 | 60.7976 |  | 23
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 1500 | 0 | 1500 | 91.25 | 2026-10-15 | 2026-10-06 | 2026-10-08 | 2026-10-12 | 2026-10-14 | 2026-10-29 |  | 1 | 0.73 | 8.6 | 35.1606 | 1043.8366 | 1.437 | 121.5952 |  | 15
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 2500 | 0 | 2500 | 152.0833 | 2026-10-15 | 2026-10-07 | 2026-10-09 | 2026-10-14 | 2026-10-16 | 2026-10-29 |  | 1.2 | 0.73 | 8.6 | 35.1606 | 1252.604 | 1.9958 | 145.9143 |  | 13
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 3500 | 0 | 3500 | 212.9167 | 2026-10-15 | 2026-10-09 | 2026-10-12 | 2026-10-16 | 2026-10-18 | 2026-10-29 |  | 1.4 | 0.73 | 8.6 | 35.1606 | 1461.3713 | 2.395 | 170.2333 |  | 11
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 5000 | 0 | 5000 | 304.1667 | 2026-10-15 | 2026-10-12 | 2026-10-14 | 2026-10-20 | 2026-10-22 | 2026-11-09 |  | 1.6 | 0.73 | 8.6 | 35.1606 | 1670.1386 | 2.9938 | 194.5524 |  | 17
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 5000 | 0 | 5000 | 304.1667 | 2026-10-15 | 2026-10-15 | 2026-10-17 | 2026-10-23 | 2026-10-25 | 2026-11-23 |  | 1.8 | 0.73 | 8.6 | 35.1606 | 1878.9059 | 2.6611 | 218.8714 |  | 26
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 16000 | 0 | 16000 | 973.3333 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 2026-11-02 | 2026-11-04 | 2026-12-07 |  | 2 | 0.73 | 8.6 | 35.1606 | 2087.6733 | 7.664 | 243.1904 |  | 30
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 716 | 0 | 716 | 72.7933 | 2026-11-05 | 2026-10-28 | 2026-10-30 | 2026-11-05 | 2026-11-07 | 2026-11-30 |  | 0.5 | 1.22 | 7 | 35.1606 | 254.1939 | 2.8167 | 36.3789 |  | 21
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 1500 | 0 | 1500 | 152.5 | 2026-11-05 | 2026-10-31 | 2026-11-03 | 2026-11-07 | 2026-11-09 | 2026-11-30 |  | 1 | 1.22 | 8.6 | 35.1606 | 624.5908 | 2.4016 | 72.7578 |  | 19
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 2500 | 0 | 2500 | 254.1667 | 2026-11-05 | 2026-11-03 | 2026-11-05 | 2026-11-12 | 2026-11-14 | 2026-11-30 |  | 1.1 | 1.22 | 8.6 | 35.1606 | 687.0498 | 3.6387 | 80.0336 |  | 15
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 3500 | 0 | 3500 | 355.8333 | 2026-11-05 | 2026-11-07 | 2026-11-10 | 2026-11-18 | 2026-11-20 | 2026-11-30 |  | 1.2 | 1.22 | 8.6 | 35.1606 | 749.5089 | 4.6697 | 87.3094 |  | 10
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 4500 | 0 | 4500 | 457.5 | 2026-11-05 | 2026-11-13 | 2026-11-16 | 2026-11-24 | 2026-11-26 | 2026-11-30 |  | 1.4 | 1.22 | 8.6 | 35.1606 | 874.4271 | 5.1462 | 101.8609 |  | 5
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 4000 | 0 | 4000 | 406.6667 | 2026-11-05 | 2026-11-19 | 2026-11-21 | 2026-11-28 | 2026-11-30 | 2026-12-07 |  | 1.6 | 1.22 | 8.6 | 35.1606 | 999.3452 | 4.0026 | 116.4125 |  | 7
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 5016 | 0 | 5016 | 509.96 | 2026-11-05 | 2026-11-24 | 2026-11-26 | 2026-12-03 | 2026-12-05 | 2026-12-07 |  | 1.8 | 1.22 | 8.6 | 35.1606 | 1124.2634 | 4.4616 | 130.964 |  | 3
2026-06-08
6-15 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 12675 | 12675 | 0 | 1468.1875 | 2026-06-03 | 2026-06-03 | 2026-06-05 | 2026-06-25 | 2026-06-27 | 2026-07-09 |  | 1.4468 | 1.39 | 9.1261 | 37.5708 | 899.3507 | 14.0935 | 98.7251 |  | 12
6-15 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 24345 | 24345 | 0 | 2130.1875 | 2026-05-26 | 2026-06-20 | 2026-06-23 | 2026-07-14 | 2026-07-19 | 2026-07-30 |  | 1.8746 | 1.05 | 9.3739 | 36.7685 | 1550.6758 | 15.6996 | 165.723 |  | 14
6-15 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08 |  |  | 5783 | 5783 | 0 | 506.0125 | 2026-06-23 | 2026-07-09 | 2026-07-11 | 2026-07-20 | 2026-07-25 | 2026-08-20 |  | 1.6985 | 1.05 | 7.855 | 37.8144 | 1210.7956 | 4.7762 | 154.4219 |  | 24
6-15 | HLF | CPM263TL32_26Q4 | Tee | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 25311 | 25311 | 0 | 1898.325 | 2026-07-10 | 2026-07-11 | 2026-07-17 | 2026-08-18 | 2026-08-20 | 2026-08-21 |  | 1.4303 | 0.9 | 7.6394 | 37.2943 | 1140.9978 | 22.1832 | 149.6259 |  | 3
6-15 | SMA | LPST840 | Pull On Pants |  | 1352772, _AH |  |  | 4836 | 4836 | 0 | 596.44 | 2026-08-18 | 2026-08-11 | 2026-08-13 | 2026-08-31 | 2026-09-02 | 2026-09-22 |  | 1.1218 | 1.48 | 8.4698 | 37.5236 | 607.0652 | 7.9662 | 71.8036 |  | 17
6-15 | SMA | LPST840 | Pull On Pants |  | 1354810_SS, _AH |  |  | 79 | 79 | 0 | 9.7433 | 2026-08-18 | 2026-08-24 | 2026-08-27 | 2026-08-31 | 2026-09-02 | 2026-09-23 |  | 0.32977 | 1.48 | 9 | 37 | 186.9822 | 0.4225 | 20.8133 |  | 18
6-15 | SMA | LPST840 | Pull On Pants |  | 1352773, _AH |  |  | 5500 | 2525 | 2975 | 678.3333 | 2026-08-24 | 2026-08-24 | 2026-08-27 | 2026-09-10 | 2026-09-12 | 2026-10-02 |  | 1.24 | 1.48 | 9 | 37 | 703.08 | 7.8227 | 78.2609 |  | 18
6-15 | SMA | PST840 | Pull On Pants |  | 1352813, _AH |  |  | 1000 | 0 | 1000 | 135.8333 | 2026-08-18 | 2026-09-04 | 2026-09-08 | 2026-09-11 | 2026-09-13 | 2026-09-22 |  | 1.6 | 1.63 | 8.0254 | 36.6361 | 727.297 | 1.375 | 90.7872 |  | 8
6-15 | SMA | LPST840 | Pull On Pants |  | 1352773, _AH |  |  | 2284 | 0 | 2284 | 281.6933 | 2026-08-24 | 2026-09-07 | 2026-09-09 | 2026-09-16 | 2026-09-18 | 2026-10-02 |  | 1.43 | 1.48 | 9 | 37 | 810.81 | 2.8169 | 90.2525 |  | 14
6-15 | SMA | LPST840 | Pull On Pants |  | 1352774, _AH |  |  | 7368 | 0 | 7368 | 908.72 | 2026-09-14 | 2026-09-10 | 2026-09-14 | 2026-09-25 | 2026-09-27 | 2026-11-02 |  | 1.6 | 1.48 | 8.6 | 37 | 866.88 | 8.4994 | 100.9818 |  | 32
6-15 | SMA | PST840 | Pull On Pants |  | 1352814, _AH |  |  | 2000 | 0 | 2000 | 271.6667 | 2026-08-24 | 2026-09-21 | 2026-09-23 | 2026-09-29 | 2026-10-01 | 2026-11-02 |  | 1.6 | 1.63 | 8.6 | 37 | 787.1058 | 2.541 | 91.689 |  | 29
6-15 | SMA | PST840 | Pull On Pants |  | 1352816, _AH |  |  | 5132 | 0 | 5132 | 697.0967 | 2026-10-05 | 2026-09-24 | 2026-09-26 | 2026-10-06 | 2026-10-08 | 2026-12-03 |  | 1.6 | 1.63 | 8.6 | 37.461 | 796.9131 | 6.4398 | 92.8314 |  | 50
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 732 | 0 | 732 | 102.48 | 2026-09-12 | 2026-09-28 | 2026-10-03 | 2026-10-10 | 2026-10-12 | 2026-10-29 |  | 0.5 | 1.68 | 7 | 37 | 194.25 | 3.7683 | 27.8 |  | 16
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 1500 | 0 | 1500 | 210 | 2026-09-12 | 2026-10-02 | 2026-10-08 | 2026-10-14 | 2026-10-16 | 2026-10-29 |  | 1 | 1.68 | 8.6 | 37 | 477.3 | 3.1427 | 55.6001 |  | 13
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 2000 | 0 | 2000 | 280 | 2026-09-12 | 2026-10-06 | 2026-10-12 | 2026-10-19 | 2026-10-21 | 2026-10-29 |  | 1.1 | 1.68 | 8.6 | 37 | 525.03 | 3.8093 | 61.1601 |  | 9
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 2500 | 0 | 2500 | 350 | 2026-09-12 | 2026-10-10 | 2026-10-16 | 2026-10-23 | 2026-10-25 | 2026-10-29 |  | 1.2 | 1.68 | 8.6 | 37 | 572.76 | 4.3648 | 66.7201 |  | 5
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 3000 | 0 | 3000 | 420 | 2026-09-12 | 2026-10-15 | 2026-10-21 | 2026-10-28 | 2026-10-30 | 2026-10-29 |  | 1.4 | 1.68 | 8.6 | 37 | 668.22 | 4.4895 | 77.8401 |  | 1
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0130 |  |  | 4332 | 0 | 4332 | 606.48 | 2026-10-03 | 2026-10-20 | 2026-10-26 | 2026-11-04 | 2026-11-06 | 2026-11-09 |  | 1.5 | 1.68 | 8.6 | 37 | 715.95 | 6.0507 | 83.4001 |  | 4
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0213 |  |  | 4000 | 0 | 4000 | 560 | 2026-10-17 | 2026-10-27 | 2026-11-02 | 2026-11-10 | 2026-11-12 | 2026-11-23 |  | 1.6 | 1.68 | 8.6 | 37 | 763.68 | 5.2378 | 88.9601 |  | 11
6-15 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 716 | 0 | 716 | 72.7933 | 2026-11-05 | 2026-11-05 | 2026-11-07 | 2026-11-13 | 2026-11-15 | 2026-11-30 |  | 0.5 | 1.22 | 7 | 37 | 267.4918 | 2.6767 | 38.282 |  | 14
6-15 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 1500 | 0 | 1500 | 152.5 | 2026-11-05 | 2026-11-09 | 2026-11-11 | 2026-11-16 | 2026-11-18 | 2026-11-30 |  | 1 | 1.22 | 8.6 | 37 | 657.2656 | 2.2822 | 76.564 |  | 12
6-15 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 2500 | 0 | 2500 | 254.1667 | 2026-11-05 | 2026-11-11 | 2026-11-13 | 2026-11-19 | 2026-11-21 | 2026-11-30 |  | 1.1 | 1.22 | 8.6 | 37 | 722.9921 | 3.4579 | 84.2204 |  | 9
6-15 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 2900 | 0 | 2900 | 294.8333 | 2026-11-05 | 2026-11-14 | 2026-11-17 | 2026-11-24 | 2026-11-26 | 2026-11-30 |  | 1.2 | 1.22 | 8.6 | 37 | 788.7187 | 3.6768 | 91.8769 |  | 5
6-15 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 4000 | 0 | 4000 | 406.6667 | 2026-11-05 | 2026-11-19 | 2026-11-21 | 2026-11-28 | 2026-11-30 | 2026-12-07 |  | 1.4 | 1.22 | 8.6 | 37 | 920.1718 | 4.347 | 107.1897 |  | 7
6-15 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 7516 | 0 | 7516 | 764.1267 | 2026-11-05 | 2026-11-24 | 2026-11-26 | 2026-12-07 | 2026-12-09 | 2026-12-07 |  | 1.6 | 1.22 | 8.6 | 37 | 1051.6249 | 7.147 | 122.5025 |  | 0
2026-04-11
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 55281 | 55281 | 0 | 4837.0875 | 2026-05-07 | 2026-04-07 | 2026-04-09 | 2026-05-30 | 2026-06-04 | 2026-07-30 |  | 1.7381 | 1.05 | 9.2232 | 36.7546 | 1414.0742 | 39.0934 | 153.5931 |  | 50
6-16 | TGT | G917K0_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 43173 | 43173 | 0 | 4497.1875 | 2026-05-26 | 2026-05-21 | 2026-05-28 | 2026-07-11 | 2026-07-13 | 2026-07-25 |  | 1.8617 | 1.25 | 9.2646 | 36.899 | 1283.0131 | 33.6497 | 138.7353 |  | 12
6-16 | TGT | G9M018_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 41073 | 41073 | 0 | 2909.3375 | 2026-06-25 | 2026-07-03 | 2026-07-09 | 2026-08-07 | 2026-08-09 | 2026-08-22 |  | 1.9856 | 0.85 | 8.0933 | 37.783 | 1800.1043 | 22.817 | 222.8196 |  | 9
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 3586 | 3586 | 0 | 313.775 | 2026-06-23 | 2026-08-03 | 2026-08-05 | 2026-08-12 | 2026-08-17 | 2026-09-24 |  | 1.5382 | 1.05 | 8 | 37.0838 | 1095.2295 | 3.2742 | 137.1506 |  | 30
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 33087 | 24145 | 8942 | 2895.1125 | 2026-08-20 | 2026-08-06 | 2026-08-10 | 2026-09-11 | 2026-09-16 | 2026-10-15 |  | 2.04 | 1.05 | 9 | 38 | 1674.432 | 19.7601 | 186.3835 |  | 28
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 28491 | 0 | 28491 | 2492.9625 | 2026-08-20 | 2026-09-07 | 2026-09-09 | 2026-10-03 | 2026-10-08 | 2026-10-15 |  | 2 | 1.05 | 8.6 | 38 | 1568.64 | 18.1629 | 182.7289 |  | 10
6-16 | ONY | 1194585_HO26_NB | Pull On Pants | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); Normal Garment Wash 清水洗/普通水洗; | 62242721, 726, 728, 729, 837, 838, 839 |  |  | 490 | 0 | 490 | 33.8917 | 2026-09-10 | 2026-09-25 | 2026-10-01 | 2026-10-05 | 2026-10-10 | 2026-10-08 |  | 0.5 | 0.83 | 7 | 38 | 403.8072 | 1.2135 | 57.7908 |  | 3
6-16 | ONY | 1194585_HO26_NB | Pull On Pants | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); Normal Garment Wash 清水洗/普通水洗; | 62242721, 726, 728, 729, 837, 838, 839 |  |  | 1000 | 0 | 1000 | 69.1667 | 2026-09-10 | 2026-09-26 | 2026-10-02 | 2026-10-06 | 2026-10-11 | 2026-10-08 |  | 1 | 0.83 | 8.6 | 38 | 992.212 | 1.0078 | 115.5815 |  | 2
6-16 | ONY | 1194585_HO26_NB | Pull On Pants | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); Normal Garment Wash 清水洗/普通水洗; | 62242165, 169, 172, 174 |  |  | 1510 | 0 | 1510 | 104.4417 | 2026-09-10 | 2026-09-28 | 2026-10-03 | 2026-10-08 | 2026-10-13 | 2026-10-29 |  | 1 | 0.83 | 8.6 | 38 | 992.212 | 1.5219 | 115.5815 |  | 18
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62385693 |  |  | 610 | 0 | 610 | 37.1083 | 2026-10-09 | 2026-09-30 | 2026-10-06 | 2026-10-09 | 2026-10-11 | 2026-10-28 |  | 0.5 | 0.73 | 7 | 38 | 459.1233 | 1.3286 | 65.7073 |  | 16
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62385693 |  |  | 1500 | 0 | 1500 | 91.25 | 2026-10-09 | 2026-10-01 | 2026-10-07 | 2026-10-10 | 2026-10-12 | 2026-10-28 |  | 1 | 0.73 | 8.6 | 38 | 1128.1315 | 1.3296 | 131.4146 |  | 15
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62377531, 116, 287 |  |  | 3099 | 0 | 3099 | 188.5225 | 2026-10-09 | 2026-10-02 | 2026-10-08 | 2026-10-13 | 2026-10-15 | 2026-10-29 |  | 1.1 | 0.73 | 8.6 | 38 | 1240.9447 | 2.4973 | 144.5561 |  | 14
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62385611 |  |  | 480 | 0 | 480 | 29.2 | 2026-10-09 | 2026-10-05 | 2026-10-10 | 2026-10-13 | 2026-10-15 | 2026-11-04 |  | 1.2 | 0.73 | 8.6 | 38 | 1353.7578 | 0.35457 | 157.6976 |  | 19
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62379119, 121, 451, 452, 453, 454 |  |  | 4426 | 0 | 4426 | 269.2483 | 2026-10-09 | 2026-10-05 | 2026-10-10 | 2026-10-16 | 2026-10-18 | 2026-11-05 |  | 1.4 | 0.73 | 8.6 | 38 | 1579.3841 | 2.8024 | 183.9805 |  | 17
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62379119, 121, 451, 452, 453, 454 |  |  | 7000 | 0 | 7000 | 425.8333 | 2026-10-09 | 2026-10-08 | 2026-10-14 | 2026-10-21 | 2026-10-23 | 2026-11-05 |  | 1.6 | 0.73 | 8.6 | 38 | 1805.0104 | 3.8781 | 210.2634 |  | 13
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62377481, 168, 252 |  |  | 2079 | 0 | 2079 | 126.4725 | 2026-11-04 | 2026-10-13 | 2026-10-19 | 2026-10-22 | 2026-10-24 | 2026-11-26 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 1.0238 | 236.5463 |  | 30
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62383169, 171, 483, 485, 487, 489 |  |  | 10557 | 0 | 10557 | 642.2175 | 2026-11-04 | 2026-10-14 | 2026-10-20 | 2026-10-28 | 2026-10-30 | 2026-12-03 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 5.1989 | 236.5463 |  | 31
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 12.24 |  |  | 1889 | 0 | 1889 | 114.9142 | 2026-12-04 | 2026-10-20 | 2026-10-26 | 2026-10-29 | 2026-10-31 | 2026-12-24 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 0.93025 | 236.5463 |  | 48
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 12.31 |  |  | 3707 | 0 | 3707 | 225.5092 | 2026-12-04 | 2026-10-21 | 2026-10-27 | 2026-10-31 | 2026-11-02 | 2026-12-31 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 1.8255 | 236.5463 |  | 51
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 01.21 |  |  | 1614 | 0 | 1614 | 98.185 | 2026-12-04 | 2026-10-23 | 2026-10-29 | 2026-11-02 | 2026-11-04 | 2027-01-21 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 0.79482 | 236.5463 |  | 67
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 01.28 |  |  | 3066 | 0 | 3066 | 186.515 | 2026-12-04 | 2026-10-24 | 2026-10-30 | 2026-11-04 | 2026-11-06 | 2027-01-28 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 1.5099 | 236.5463 |  | 71
6-16 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 728 | 0 | 728 | 57.0267 | 2026-11-09 | 2026-10-27 | 2026-11-02 | 2026-11-06 | 2026-11-08 | 2026-12-03 |  | 0.5 | 0.94 | 7 | 38 | 356.5532 | 2.0418 | 51.028 |  | 23
6-16 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 1500 | 0 | 1500 | 117.5 | 2026-11-09 | 2026-10-29 | 2026-11-04 | 2026-11-09 | 2026-11-11 | 2026-12-03 |  | 1 | 0.94 | 8.6 | 38 | 876.1021 | 1.7121 | 102.056 |  | 21
6-16 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 2500 | 0 | 2500 | 195.8333 | 2026-11-09 | 2026-10-31 | 2026-11-06 | 2026-11-12 | 2026-11-14 | 2026-12-03 |  | 1.1 | 0.94 | 8.6 | 38 | 963.7123 | 2.5941 | 112.2616 |  | 18
6-16 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 3000 | 0 | 3000 | 235 | 2026-11-09 | 2026-11-04 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 2026-12-03 |  | 1.2 | 0.94 | 8.6 | 38 | 1051.3226 | 2.8535 | 122.4672 |  | 15
6-16 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 4372 | 0 | 4372 | 342.4733 | 2026-11-09 | 2026-11-07 | 2026-11-13 | 2026-11-20 | 2026-11-22 | 2026-12-03 |  | 1.4 | 0.94 | 8.6 | 38 | 1226.543 | 3.5645 | 142.8785 |  | 11
6-16 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1210, 4500041655_BJSHVS_1210, 4500041655_BJSHVS_HTR_1210, 4500041657_HTR_1210 |  |  | 4323 | 0 | 4323 | 338.635 | 2026-11-09 | 2026-11-12 | 2026-11-18 | 2026-11-24 | 2026-11-26 | 2026-12-10 |  | 1.6 | 0.94 | 8.6 | 38 | 1401.7634 | 3.084 | 163.2897 |  | 14
6-16 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1210, 4500041655_BJSHVS_1210, 4500041655_BJSHVS_HTR_1210, 4500041657_HTR_1210 |  |  | 7822 | 0 | 7822 | 612.7233 | 2026-11-09 | 2026-11-16 | 2026-11-21 | 2026-11-30 | 2026-12-02 | 2026-12-10 |  | 1.8 | 0.94 | 8.6 | 38 | 1576.9838 | 4.9601 | 183.7009 |  | 9
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-11-25 | 2026-11-27 | 2026-12-02 | 2026-12-07 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 38 | 364.3043 | 2.2371 | 52.1373 |  | 19
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-11-27 | 2026-11-30 | 2026-12-04 | 2026-12-09 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 38 | 895.1478 | 1.6757 | 104.2747 |  | 17
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2026-12-08 | 2026-12-13 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 38 | 984.6626 | 2.5389 | 114.7021 |  | 14
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-03 | 2026-12-05 | 2026-12-11 | 2026-12-16 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 38 | 1074.1774 | 2.7928 | 125.1296 |  | 11
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4941 | 0 | 4941 | 378.81 | 2026-12-07 | 2026-12-07 | 2026-12-09 | 2026-12-16 | 2026-12-21 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 38 | 1163.6922 | 4.246 | 135.557 |  | 12
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-12-07 | 2026-12-11 | 2026-12-14 | 2026-12-21 | 2026-12-26 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 38 | 1253.207 | 3.9898 | 145.9845 |  | 8
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 6550 | 0 | 6550 | 502.1667 | 2026-12-07 | 2026-12-16 | 2026-12-18 | 2026-12-28 | 2027-01-02 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 4.8782 | 156.412 |  | 3
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-22 | 2026-12-24 | 2026-12-29 | 2027-01-03 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 1.4329 | 156.412 |  | 13
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-23 | 2026-12-26 | 2027-01-06 | 2027-01-11 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 5.8061 | 156.412 |  | 13
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2026-12-31 | 2027-01-04 | 2027-01-12 | 2027-01-17 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 4.9221 | 156.412 |  | 14
2026-05-29
6-17 | TGT | G9M018_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 114421 | 114421 | 0 | 8104.8208 | 2026-06-25 | 2026-05-20 | 2026-05-26 | 2026-08-14 | 2026-08-16 | 2026-08-22 |  | 1.8494 | 0.85 | 9.0274 | 36.6846 | 1815.7792 | 63.0148 | 201.5045 |  | 4
6-17 | ONY | 1182430_HO26_HT | Pull On Pants |  | all po |  |  | 17242 | 17227 | 15 | 1120.73 | 2026-08-24 | 2026-08-10 | 2026-08-12 | 2026-09-02 | 2026-09-04 | 2026-10-15 |  | 1.4 | 0.78 | 9 | 38 | 1546.8923 | 11.1462 | 172.1869 |  | 35
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004922_T1_W |  |  | 720 | 720 | 0 | 63.6 | 2026-08-24 | 2026-08-21 | 2026-08-31 | 2026-09-03 | 2026-09-05 | 2026-10-01 |  | 0.87336 | 1.06 | 8 | 38 | 631.1914 | 1.1407 | 79.0412 |  | 22
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 1500 | 728 | 772 | 132.5 | 2026-08-24 | 2026-08-24 | 2026-09-01 | 2026-09-07 | 2026-09-09 | 2026-10-08 |  | 1 | 1.06 | 9 | 38 | 813.0566 | 1.8449 | 90.5025 |  | 26
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 2500 | 0 | 2500 | 220.8333 | 2026-08-24 | 2026-08-27 | 2026-09-03 | 2026-09-10 | 2026-09-12 | 2026-10-08 |  | 1.1 | 1.06 | 9 | 38 | 894.3623 | 2.7953 | 99.5528 |  | 23
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 3500 | 0 | 3500 | 309.1667 | 2026-08-24 | 2026-09-01 | 2026-09-08 | 2026-09-16 | 2026-09-18 | 2026-10-08 |  | 1.2 | 1.06 | 8.6 | 38 | 932.3049 | 3.7541 | 108.603 |  | 19
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 4500 | 0 | 4500 | 397.5 | 2026-08-24 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-23 | 2026-10-08 |  | 1.4 | 1.06 | 8.6 | 38 | 1087.6891 | 4.1372 | 126.7035 |  | 15
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 5999 | 0 | 5999 | 529.9117 | 2026-08-24 | 2026-09-11 | 2026-09-18 | 2026-09-26 | 2026-09-28 | 2026-10-08 |  | 1.6 | 1.06 | 8.6 | 38 | 1243.0732 | 4.8259 | 144.804 |  | 10
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004937_BA_E |  |  | 6792 | 0 | 6792 | 599.96 | 2026-09-10 | 2026-09-18 | 2026-09-24 | 2026-10-02 | 2026-10-04 | 2026-10-12 |  | 1.8 | 1.06 | 8.6 | 38 | 1398.4574 | 4.8568 | 162.9045 |  | 8
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004936_BA_E |  |  | 11078 | 0 | 11078 | 978.5567 | 2026-08-29 | 2026-09-24 | 2026-09-30 | 2026-10-10 | 2026-10-12 | 2026-10-24 |  | 2 | 1.06 | 8.6 | 38 | 1553.8415 | 7.1294 | 181.0051 |  | 12
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004947_BA_E |  |  | 6792 | 0 | 6792 | 599.96 | 2026-09-05 | 2026-10-02 | 2026-10-08 | 2026-10-15 | 2026-10-17 | 2026-10-26 |  | 2 | 1.06 | 8.6 | 38 | 1553.8415 | 4.3711 | 181.0051 |  | 9
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004946_BA_E |  |  | 9078 | 0 | 9078 | 801.89 | 2026-09-05 | 2026-10-07 | 2026-10-13 | 2026-10-22 | 2026-10-24 | 2026-11-07 |  | 2 | 1.06 | 8.6 | 38 | 1553.8415 | 5.8423 | 181.0051 |  | 14
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004950_BA_E |  |  | 9792 | 0 | 9792 | 864.96 | 2026-09-05 | 2026-10-14 | 2026-10-20 | 2026-10-29 | 2026-10-31 | 2026-11-09 |  | 2 | 1.06 | 8.6 | 38 | 1553.8415 | 6.3018 | 181.0051 |  | 9
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004948_BA_E |  |  | 9078 | 0 | 9078 | 801.89 | 2026-09-05 | 2026-10-21 | 2026-10-27 | 2026-11-05 | 2026-11-07 | 2026-11-21 |  | 2 | 1.06 | 8.6 | 38 | 1553.8415 | 5.8423 | 181.0051 |  | 14
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004939_BA_E |  |  | 8792 | 0 | 8792 | 776.6267 | 2026-09-05 | 2026-10-28 | 2026-11-03 | 2026-11-12 | 2026-11-14 | 2026-11-23 |  | 2 | 1.06 | 8.6 | 38 | 1553.8415 | 5.6582 | 181.0051 |  | 9
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004938_BA_E, LIVERPOOL_C127 |  |  | 2928 | 0 | 2928 | 258.64 | 2026-09-05 | 2026-11-04 | 2026-11-10 | 2026-11-14 | 2026-11-16 | 2026-12-05 |  | 2 | 1.06 | 8.6 | 38 | 1553.8415 | 1.8844 | 181.0051 |  | 18
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 728 | 0 | 728 | 57.0267 | 2026-11-09 | 2026-11-06 | 2026-11-12 | 2026-11-17 | 2026-11-19 | 2026-12-03 |  | 0.5 | 0.94 | 7 | 38 | 356.5532 | 2.0418 | 51.028 |  | 14
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 1500 | 0 | 1500 | 117.5 | 2026-11-09 | 2026-11-09 | 2026-11-14 | 2026-11-19 | 2026-11-21 | 2026-12-03 |  | 1 | 0.94 | 8.6 | 38 | 876.1021 | 1.7121 | 102.056 |  | 12
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 2500 | 0 | 2500 | 195.8333 | 2026-11-09 | 2026-11-11 | 2026-11-17 | 2026-11-23 | 2026-11-25 | 2026-12-03 |  | 1.1 | 0.94 | 8.6 | 38 | 963.7123 | 2.5941 | 112.2616 |  | 9
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 3000 | 0 | 3000 | 235 | 2026-11-09 | 2026-11-14 | 2026-11-20 | 2026-11-26 | 2026-11-28 | 2026-12-03 |  | 1.2 | 0.94 | 8.6 | 38 | 1051.3226 | 2.8535 | 122.4672 |  | 6
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 3500 | 0 | 3500 | 274.1667 | 2026-11-09 | 2026-11-18 | 2026-11-24 | 2026-11-30 | 2026-12-02 | 2026-12-03 |  | 1.4 | 0.94 | 8.6 | 38 | 1226.543 | 2.8535 | 142.8785 |  | 3
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1210, 4500041655_BJSHVS_1210, 4500041655_BJSHVS_HTR_1210, 4500041657_HTR_1210 |  |  | 4323 | 0 | 4323 | 338.635 | 2026-11-09 | 2026-11-21 | 2026-11-27 | 2026-12-03 | 2026-12-05 | 2026-12-10 |  | 1.6 | 0.94 | 8.6 | 38 | 1401.7634 | 3.084 | 163.2897 |  | 6
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1210, 4500041655_BJSHVS_1210, 4500041655_BJSHVS_HTR_1210, 4500041657_HTR_1210 |  |  | 5500 | 0 | 5500 | 430.8333 | 2026-11-09 | 2026-11-25 | 2026-12-01 | 2026-12-07 | 2026-12-09 | 2026-12-10 |  | 1.8 | 0.94 | 8.6 | 38 | 1576.9838 | 3.4877 | 183.7009 |  | 3
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-12-02 | 2026-12-04 | 2026-12-09 | 2026-12-14 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 38 | 364.3043 | 2.2371 | 52.1373 |  | 13
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-12-04 | 2026-12-07 | 2026-12-11 | 2026-12-16 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 38 | 895.1478 | 1.6757 | 104.2747 |  | 11
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-12-07 | 2026-12-09 | 2026-12-15 | 2026-12-20 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 38 | 984.6626 | 2.5389 | 114.7021 |  | 8
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-10 | 2026-12-12 | 2026-12-18 | 2026-12-23 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 38 | 1074.1774 | 2.7928 | 125.1296 |  | 5
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4941 | 0 | 4941 | 378.81 | 2026-12-07 | 2026-12-14 | 2026-12-16 | 2026-12-23 | 2026-12-28 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 38 | 1163.6922 | 4.246 | 135.557 |  | 6
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4550 | 0 | 4550 | 348.8333 | 2026-12-07 | 2026-12-18 | 2026-12-21 | 2026-12-29 | 2027-01-03 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 38 | 1253.207 | 3.6307 | 145.9845 |  | 2
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-23 | 2026-12-26 | 2026-12-30 | 2027-01-04 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 1.4329 | 156.412 |  | 12
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-24 | 2026-12-28 | 2027-01-07 | 2027-01-12 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 5.8061 | 156.412 |  | 12
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-02 | 2027-01-05 | 2027-01-13 | 2027-01-18 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 4.9221 | 156.412 |  | 13
2026-04-07
6-18 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08 |  |  | 58617 | 58617 | 0 | 5128.9875 | 2026-05-07 | 2026-04-01 | 2026-04-04 | 2026-05-25 | 2026-05-30 | 2026-07-30 |  | 1.8839 | 1.05 | 9.0947 | 36.6174 | 1505.6912 | 38.9303 | 165.8552 |  | 54
6-18 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 36668 | 36668 | 0 | 4247.3767 | 2026-06-03 | 2026-05-20 | 2026-05-22 | 2026-07-08 | 2026-07-10 | 2026-07-09 |  | 1.6867 | 1.39 | 9.4411 | 36.547 | 1055.0911 | 34.7534 | 111.9562 |  | 1
6-18 | ONY | 910047_HO26DIS | Pajama |  | all po |  |  | 38392 | 38392 | 0 | 4543.0533 | 2026-07-06 | 2026-07-03 | 2026-07-06 | 2026-08-19 | 2026-08-21 | 2026-09-03 |  | 2.054 | 1.42 | 8.2635 | 38.6602 | 1164.4988 | 32.9687 | 141.1757 |  | 10
6-18 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 2978 | 2978 | 0 | 260.575 | 2026-06-23 | 2026-08-12 | 2026-08-14 | 2026-08-21 | 2026-08-26 | 2026-10-15 |  | 1.7247 | 1.05 | 8.0143 | 37.9956 | 1260.476 | 2.3626 | 157.5616 |  | 42
6-18 | ONY | 910047_HO26DIS | Pajama |  | all po |  |  | 8515 | 8515 | 0 | 1007.6083 | 2026-07-06 | 2026-08-14 | 2026-08-19 | 2026-09-02 | 2026-09-04 | 2026-09-03 |  | 1.9776 | 1.42 | 8.5299 | 38.1355 | 1141.6509 | 7.4585 | 134.0827 |  | 1
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004914_T1_W |  |  | 2160 | 2160 | 0 | 140.4 | 2026-08-18 | 2026-08-21 | 2026-08-31 | 2026-09-04 | 2026-09-06 | 2026-10-01 |  | 1.294 | 0.78 | 8 | 38 | 1270.8633 | 1.6996 | 159.1444 |  | 21
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004915_SET_W |  |  | 2825 | 192 | 2633 | 183.625 | 2026-08-18 | 2026-08-26 | 2026-09-02 | 2026-09-08 | 2026-09-10 | 2026-10-08 |  | 1.2 | 0.78 | 9 | 38 | 1325.9077 | 2.1306 | 147.5887 |  | 25
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004915_SET_W |  |  | 4500 | 0 | 4500 | 292.5 | 2026-08-18 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-13 | 2026-10-08 |  | 1.4 | 0.78 | 9 | 38 | 1546.8923 | 2.9091 | 172.1869 |  | 22
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004915_SET_W |  |  | 5500 | 0 | 5500 | 357.5 | 2026-08-18 | 2026-09-02 | 2026-09-09 | 2026-09-16 | 2026-09-18 | 2026-10-08 |  | 1.6 | 0.78 | 8.6 | 38 | 1689.3046 | 3.2558 | 196.785 |  | 19
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004915_SET_W |  |  | 6000 | 0 | 6000 | 390 | 2026-08-18 | 2026-09-07 | 2026-09-14 | 2026-09-19 | 2026-09-21 | 2026-10-08 |  | 1.8 | 0.78 | 8.6 | 38 | 1900.4677 | 3.1571 | 221.3831 |  | 16
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004915_SET_W |  |  | 14000 | 0 | 14000 | 910 | 2026-08-18 | 2026-09-10 | 2026-09-17 | 2026-09-28 | 2026-09-30 | 2026-10-08 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 6.6299 | 245.9812 |  | 9
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004943_BA_E |  |  | 3816 | 0 | 3816 | 248.04 | 2026-08-18 | 2026-09-19 | 2026-09-25 | 2026-09-30 | 2026-10-02 | 2026-10-12 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.8071 | 245.9812 |  | 10
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004944_BA_W |  |  | 5064 | 0 | 5064 | 329.16 | 2026-08-18 | 2026-09-22 | 2026-09-28 | 2026-10-02 | 2026-10-04 | 2026-10-24 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 2.3981 | 245.9812 |  | 19
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004935_BA_E |  |  | 3132 | 0 | 3132 | 203.58 | 2026-08-18 | 2026-09-24 | 2026-09-30 | 2026-10-03 | 2026-10-05 | 2026-10-26 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.4832 | 245.9812 |  | 19
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004934_BA_W |  |  | 4200 | 0 | 4200 | 273 | 2026-08-24 | 2026-09-25 | 2026-10-01 | 2026-10-06 | 2026-10-08 | 2026-11-07 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.989 | 245.9812 |  | 28
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004949_BA_E |  |  | 2508 | 0 | 2508 | 163.02 | 2026-09-05 | 2026-09-28 | 2026-10-03 | 2026-10-07 | 2026-10-09 | 2026-11-09 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.1877 | 245.9812 |  | 28
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004945_BA_W |  |  | 3348 | 0 | 3348 | 217.62 | 2026-09-05 | 2026-09-29 | 2026-10-05 | 2026-10-09 | 2026-10-11 | 2026-11-21 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.5855 | 245.9812 |  | 37
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004942_BA_E |  |  | 2508 | 0 | 2508 | 163.02 | 2026-08-24 | 2026-10-01 | 2026-10-07 | 2026-10-10 | 2026-10-12 | 2026-11-23 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.1877 | 245.9812 |  | 37
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004941_BA_W, LIVERPOOL_C127 |  |  | 3848 | 0 | 3848 | 250.12 | 2026-08-29 | 2026-10-02 | 2026-10-08 | 2026-10-13 | 2026-10-15 | 2026-12-05 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.8223 | 245.9812 |  | 46
6-18 | TGT | 1KE9E9_SSLLC127 | Pajama |  | 1206 |  |  | 840 | 0 | 840 | 48.3 | 2026-10-15 | 2026-10-08 | 2026-10-10 | 2026-10-14 | 2026-10-16 | 2026-11-06 |  | 1.5 | 0.69 | 7 | 38 | 1457.2174 | 0.57644 | 208.5493 |  | 20
6-18 | TGT | 1KE9E9_SSLLC127 | Pajama |  | 1206 |  |  | 1500 | 0 | 1500 | 86.25 | 2026-10-15 | 2026-10-09 | 2026-10-12 | 2026-10-15 | 2026-10-17 | 2026-11-06 |  | 1.6 | 0.69 | 8.6 | 38 | 1909.6487 | 0.78548 | 222.4526 |  | 19
6-18 | TGT | 1KE9E9_SSLLC127 | Pajama |  | 1206 |  |  | 3500 | 0 | 3500 | 201.25 | 2026-10-15 | 2026-10-10 | 2026-10-13 | 2026-10-17 | 2026-10-19 | 2026-11-06 |  | 1.8 | 0.69 | 8.6 | 38 | 2148.3548 | 1.6292 | 250.2592 |  | 17
6-18 | TGT | 1KE9E9_SSLLC127 | Pajama |  | 1206 |  |  | 14000 | 0 | 14000 | 805 | 2026-10-15 | 2026-10-13 | 2026-10-15 | 2026-10-24 | 2026-10-26 | 2026-11-06 |  | 2 | 0.69 | 8.6 | 38 | 2387.0609 | 5.865 | 278.0657 |  | 11
6-18 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 720 | 0 | 720 | 43.2 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-10-26 | 2026-10-28 | 2026-11-06 |  | 1.5 | 0.72 | 7 | 38 | 1396.5 | 0.51557 | 199.8597 |  | 10
6-18 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 1500 | 0 | 1500 | 90 | 2026-10-15 | 2026-10-21 | 2026-10-23 | 2026-10-27 | 2026-10-29 | 2026-11-06 |  | 1.6 | 0.72 | 8.6 | 38 | 1830.08 | 0.81964 | 213.1837 |  | 9
6-18 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 3500 | 0 | 3500 | 210 | 2026-10-15 | 2026-10-22 | 2026-10-24 | 2026-10-29 | 2026-10-31 | 2026-11-06 |  | 1.8 | 0.72 | 8.6 | 38 | 2058.84 | 1.7 | 239.8317 |  | 7
6-18 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 6378 | 0 | 6378 | 382.68 | 2026-10-15 | 2026-10-24 | 2026-10-27 | 2026-11-02 | 2026-11-04 | 2026-11-06 |  | 2 | 0.72 | 8.6 | 38 | 2287.6 | 2.7881 | 266.4797 |  | 4
6-18 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 750 | 0 | 750 | 55.625 | 2026-10-23 | 2026-10-28 | 2026-10-30 | 2026-11-04 | 2026-11-06 | 2026-11-19 |  | 0.5 | 0.89 | 7 | 38 | 376.5843 | 1.9916 | 53.8948 |  | 13
6-18 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 1500 | 0 | 1500 | 111.25 | 2026-10-23 | 2026-10-30 | 2026-11-02 | 2026-11-06 | 2026-11-08 | 2026-11-19 |  | 1 | 0.89 | 8.6 | 38 | 925.3213 | 1.6211 | 107.7895 |  | 11
6-18 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 2250 | 0 | 2250 | 166.875 | 2026-10-23 | 2026-11-02 | 2026-11-04 | 2026-11-09 | 2026-11-11 | 2026-11-19 |  | 1.1 | 0.89 | 8.6 | 38 | 1017.8535 | 2.2105 | 118.5685 |  | 9
6-18 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 3000 | 0 | 3000 | 222.5 | 2026-10-23 | 2026-11-04 | 2026-11-06 | 2026-11-12 | 2026-11-14 | 2026-11-19 |  | 1.2 | 0.89 | 8.6 | 38 | 1110.3856 | 2.7018 | 129.3474 |  | 6
6-18 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041016_CA_PPK, 4500041031_US_OS, 4500041673_CA_PPK, 4500041035_US_PPK |  |  | 3000 | 0 | 3000 | 222.5 | 2026-10-23 | 2026-11-07 | 2026-11-10 | 2026-11-14 | 2026-11-16 | 2026-11-19 |  | 1.3 | 0.89 | 8.6 | 38 | 1202.9178 | 2.4939 | 140.1264 |  | 4
6-18 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041432_US_OS |  |  | 3625 | 0 | 3625 | 268.8542 | 2026-10-30 | 2026-11-10 | 2026-11-12 | 2026-11-18 | 2026-11-20 | 2026-11-26 |  | 1.4 | 0.89 | 8.6 | 38 | 1295.4499 | 2.7983 | 150.9053 |  | 7
6-18 | HLF | RDW271LE13 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; PNEUMATIC FLAT COOL + HEAT PRESS MACHINE FLIP HEAD WITH VACUUM(80cmX40cm) 氣動式平面冷熱壓機(80cmX40cm); | 4500041432_US_OS |  |  | 5000 | 0 | 5000 | 370.8333 | 2026-10-30 | 2026-11-13 | 2026-11-16 | 2026-11-23 | 2026-11-25 | 2026-11-26 |  | 1.5 | 0.89 | 8.6 | 38 | 1387.982 | 3.6024 | 161.6843 |  | 3
2026-06-04
6-19 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 30137 | 30137 | 0 | 3490.8692 | 2026-06-03 | 2026-05-29 | 2026-06-02 | 2026-07-10 | 2026-07-12 | 2026-07-09 |  | 1.6466 | 1.39 | 9.3862 | 35.7151 | 1000.7301 | 30.115 | 106.8093 |  | -3
6-19 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 17165 | 17165 | 0 | 1501.9375 | 2026-06-23 | 2026-07-06 | 2026-07-08 | 2026-07-27 | 2026-08-01 | 2026-09-17 |  | 1.8451 | 1.05 | 8.0928 | 35.1592 | 1260.0109 | 13.6229 | 155.977 |  | 37
6-19 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 176 | 176 | 0 | 15.4 | 2026-05-23 | 2026-07-22 | 2026-07-24 | 2026-07-27 | 2026-08-01 | 2026-07-30 |  | 1.3031 | 1.05 | 7.482 | 34.9354 | 817.4638 | 0.2153 | 109.4549 |  | 3
6-19 | ONY | 1182723_HO26 | Skorts |  | all po |  |  | 36303 | 36303 | 0 | 2752.9775 | 2026-07-14 | 2026-07-22 | 2026-07-24 | 2026-09-03 | 2026-09-05 | 2026-10-01 |  | 1.6289 | 0.91 | 7.9363 | 37.2893 | 1334.965 | 27.194 | 168.5127 |  | 22
6-19 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 4749 | 3566 | 1183 | 209.7475 | 2026-08-06 | 2026-08-28 | 2026-09-01 | 2026-09-07 | 2026-09-09 | 2026-09-17 |  | 1.24 | 0.53 | 9 | 38 | 2016.3804 | 2.3552 | 224.4463 |  | 8
6-19 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 3000 | 0 | 3000 | 132.5 | 2026-08-06 | 2026-09-01 | 2026-09-03 | 2026-09-08 | 2026-09-10 | 2026-09-17 |  | 1.3 | 0.53 | 9 | 38 | 2113.9472 | 1.4191 | 235.3066 |  | 7
6-19 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 3500 | 0 | 3500 | 154.5833 | 2026-08-06 | 2026-09-02 | 2026-09-04 | 2026-09-10 | 2026-09-12 | 2026-09-17 |  | 1.4 | 0.53 | 9 | 38 | 2276.5585 | 1.5374 | 253.4071 |  | 5
6-19 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 12024 | 0 | 12024 | 531.06 | 2026-08-06 | 2026-09-04 | 2026-09-08 | 2026-09-17 | 2026-09-19 | 2026-09-17 |  | 1.5 | 0.53 | 8.6 | 38 | 2330.7623 | 5.1588 | 271.5076 |  | 0
6-19 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016283, 292, 296 |  |  | 8000 | 0 | 8000 | 353.3333 | 2026-08-06 | 2026-09-11 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 2026-10-15 |  | 1.5 | 0.53 | 8.6 | 38 | 2330.7623 | 3.4324 | 271.5076 |  | 21
6-19 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 728 | 0 | 728 | 59.4533 | 2026-09-07 | 2026-09-16 | 2026-09-18 | 2026-09-23 | 2026-09-28 | 2026-10-01 |  | 0.5 | 0.98 | 7 | 38 | 342 | 2.1287 | 48.9452 |  | 7
6-19 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 1500 | 0 | 1500 | 122.5 | 2026-09-07 | 2026-09-18 | 2026-09-21 | 2026-09-25 | 2026-09-30 | 2026-10-01 |  | 1 | 0.98 | 8.6 | 38 | 840.3429 | 1.785 | 97.8905 |  | 5
6-19 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 2700 | 0 | 2700 | 220.5 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 2026-09-29 | 2026-10-04 | 2026-10-01 |  | 1.2 | 0.98 | 8.6 | 38 | 1008.4114 | 2.6775 | 117.4686 |  | 2
6-19 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62239979, 378, 565, 268, 269 |  |  | 1503 | 0 | 1503 | 122.745 | 2026-09-07 | 2026-09-24 | 2026-09-26 | 2026-09-30 | 2026-10-05 | 2026-10-08 |  | 1.4 | 0.98 | 8.6 | 38 | 1176.48 | 1.2775 | 137.0467 |  | 7
6-19 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 6500 | 0 | 6500 | 530.8333 | 2026-09-07 | 2026-09-25 | 2026-09-28 | 2026-10-06 | 2026-10-11 | 2026-10-15 |  | 1.6 | 0.98 | 8.6 | 38 | 1344.5486 | 4.8343 | 156.6248 |  | 8
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 732 | 0 | 732 | 102.48 | 2026-09-12 | 2026-09-28 | 2026-10-03 | 2026-10-10 | 2026-10-12 | 2026-10-29 |  | 0.5 | 1.68 | 7 | 38 | 199.5 | 3.6692 | 28.5514 |  | 16
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 1500 | 0 | 1500 | 210 | 2026-09-12 | 2026-10-02 | 2026-10-08 | 2026-10-14 | 2026-10-16 | 2026-10-29 |  | 1 | 1.68 | 8.6 | 38 | 490.2 | 3.06 | 57.1028 |  | 13
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 2500 | 0 | 2500 | 350 | 2026-09-12 | 2026-10-06 | 2026-10-12 | 2026-10-20 | 2026-10-22 | 2026-10-29 |  | 1.1 | 1.68 | 8.6 | 38 | 539.22 | 4.6363 | 62.8131 |  | 8
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 4600 | 0 | 4600 | 644 | 2026-09-12 | 2026-10-12 | 2026-10-17 | 2026-10-29 | 2026-10-31 | 2026-10-29 |  | 1.2 | 1.68 | 8.6 | 38 | 588.24 | 7.8199 | 68.5233 |  | 0
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0130 |  |  | 2000 | 0 | 2000 | 280 | 2026-10-03 | 2026-10-21 | 2026-10-27 | 2026-11-02 | 2026-11-04 | 2026-11-09 |  | 1.4 | 1.68 | 8.6 | 38 | 686.28 | 2.9143 | 79.9439 |  | 6
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0130 |  |  | 2332 | 0 | 2332 | 326.48 | 2026-10-03 | 2026-10-24 | 2026-10-30 | 2026-11-05 | 2026-11-07 | 2026-11-09 |  | 1.5 | 1.68 | 8.6 | 38 | 735.3 | 3.1715 | 85.6542 |  | 3
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0213 |  |  | 4000 | 0 | 4000 | 560 | 2026-10-17 | 2026-10-28 | 2026-11-03 | 2026-11-11 | 2026-11-13 | 2026-11-23 |  | 1.6 | 1.68 | 8.6 | 38 | 784.32 | 5.1 | 91.3645 |  | 10
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0227 |  |  | 6678 | 0 | 6678 | 934.92 | 2026-10-31 | 2026-11-03 | 2026-11-09 | 2026-11-20 | 2026-11-22 | 2026-12-07 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 7.5683 | 102.785 |  | 14
2026-04-15
6-20 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 138695 | 138695 | 0 | 12135.8125 | 2026-05-23 | 2026-04-10 | 2026-04-13 | 2026-07-21 | 2026-07-26 | 2026-07-30 |  | 2.1304 | 1.05 | 9.4002 | 37.0349 | 1779.9917 | 77.9189 | 189.6972 |  | 8
6-20 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08 |  |  | 770 | 770 | 0 | 67.375 | 2026-06-23 | 2026-07-16 | 2026-07-18 | 2026-07-22 | 2026-07-27 | 2026-08-20 |  | 2.0801 | 1.05 | 7.995 | 36 | 1436.8349 | 0.5359 | 180.0417 |  | 22
6-20 | HLF | CPM263PA81 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 31 | 31 | 0 | 2.7642 | 2026-05-23 | 2026-07-14 | 2026-07-20 | 2026-07-22 | 2026-07-24 | 2026-08-21 |  | 1.3516 | 1.07 | 8 | 37 | 942.2492 | 0.0329 | 117.9935 |  | 23
6-20 | HLF | CPM263PA05_26Q4 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 20835 | 20835 | 0 | 2100.8625 | 2026-07-10 | 2026-07-14 | 2026-07-20 | 2026-08-27 | 2026-08-29 | 2026-08-21 |  | 1.3551 | 1.21 | 7.7377 | 37.0102 | 808.2034 | 25.7794 | 104.6388 |  | -5
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025143 |  |  | 7812 | 7592 | 220 | 826.77 | 2026-08-18 | 2026-08-20 | 2026-08-24 | 2026-09-07 | 2026-09-09 | 2026-10-21 |  | 1.69 | 1.27 | 9 | 37 | 1116.6775 | 6.9958 | 124.299 |  | 37
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025140 |  |  | 96 | 0 | 96 | 10.16 | 2026-08-18 | 2026-09-01 | 2026-09-03 | 2026-09-07 | 2026-09-09 | 2026-10-22 |  | 1.8 | 1.27 | 9 | 37 | 1189.3606 | 0.080716 | 132.3895 |  | 38
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025142 |  |  | 4384 | 0 | 4384 | 463.9733 | 2026-08-18 | 2026-09-01 | 2026-09-03 | 2026-09-11 | 2026-09-13 | 2026-11-18 |  | 1.8 | 1.27 | 9 | 37 | 1189.3606 | 3.686 | 132.3895 |  | 57
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025142 |  |  | 5000 | 0 | 5000 | 529.1667 | 2026-08-18 | 2026-09-07 | 2026-09-09 | 2026-09-17 | 2026-09-19 | 2026-11-18 |  | 1.8 | 1.27 | 8.6 | 37 | 1136.5002 | 4.3995 | 132.3895 |  | 53
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025144 |  |  | 12504 | 0 | 12504 | 1323.34 | 2026-08-18 | 2026-09-11 | 2026-09-15 | 2026-09-30 | 2026-10-02 | 2026-12-16 |  | 1.8 | 1.27 | 8.6 | 37 | 1136.5002 | 11.0022 | 132.3895 |  | 66
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 795 | 0 | 795 | 113.95 | 2026-09-21 | 2026-09-22 | 2026-09-28 | 2026-10-05 | 2026-10-07 | 2026-11-02 |  | 0.5 | 1.72 | 7 | 37 | 189.7326 | 4.1901 | 27.1535 |  | 24
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 1400 | 0 | 1400 | 200.6667 | 2026-09-21 | 2026-09-26 | 2026-10-02 | 2026-10-08 | 2026-10-10 | 2026-11-02 |  | 1 | 1.72 | 8.6 | 37 | 466.2 | 3.003 | 54.3071 |  | 21
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 1500 | 0 | 1500 | 215 | 2026-09-21 | 2026-09-30 | 2026-10-06 | 2026-10-12 | 2026-10-14 | 2026-11-02 |  | 1.1 | 1.72 | 8.6 | 37 | 512.82 | 2.925 | 59.7378 |  | 18
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 2500 | 0 | 2500 | 358.3333 | 2026-09-21 | 2026-10-03 | 2026-10-09 | 2026-10-16 | 2026-10-18 | 2026-11-02 |  | 1.2 | 1.72 | 8.6 | 37 | 559.44 | 4.4688 | 65.1685 |  | 14
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 2795 | 0 | 2795 | 400.6167 | 2026-09-21 | 2026-10-08 | 2026-10-14 | 2026-10-21 | 2026-10-23 | 2026-11-02 |  | 1.4 | 1.72 | 8.6 | 37 | 652.68 | 4.2823 | 76.0299 |  | 10
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 5500 | 0 | 5500 | 788.3333 | 2026-09-21 | 2026-10-13 | 2026-10-19 | 2026-10-30 | 2026-11-01 | 2026-11-02 |  | 1.5 | 1.72 | 8.6 | 37 | 699.3 | 7.865 | 81.4606 |  | 2
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041497 |  |  | 5988 | 0 | 5988 | 858.28 | 2026-10-19 | 2026-10-22 | 2026-10-28 | 2026-11-09 | 2026-11-11 | 2026-11-16 |  | 1.6 | 1.72 | 8.6 | 37 | 745.92 | 8.0277 | 86.8913 |  | 6
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041486 |  |  | 6636 | 0 | 6636 | 951.16 | 2026-10-19 | 2026-10-31 | 2026-11-06 | 2026-11-18 | 2026-11-20 | 2026-11-30 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 7.9079 | 97.7527 |  | 10
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041480 |  |  | 11112 | 0 | 11112 | 1592.72 | 2026-11-02 | 2026-11-10 | 2026-11-16 | 2026-12-03 | 2026-12-05 | 2026-12-14 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 13.2418 | 97.7527 |  | 9
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0301_GLAM |  |  | 815 | 0 | 815 | 116.8167 | 2026-10-19 | 2026-11-25 | 2026-12-01 | 2026-12-04 | 2026-12-06 | 2026-12-16 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 0.97121 | 97.7527 |  | 10
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041498 |  |  | 5748 | 0 | 5748 | 823.88 | 2026-11-02 | 2026-11-26 | 2026-12-02 | 2026-12-12 | 2026-12-14 | 2026-12-28 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 6.8497 | 97.7527 |  | 12
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041488 |  |  | 1992 | 0 | 1992 | 285.52 | 2026-11-02 | 2026-12-04 | 2026-12-10 | 2026-12-15 | 2026-12-17 | 2027-01-11 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 2.3738 | 97.7527 |  | 21
DATA END |  |  |  |  | PLEASE DO NOT REMOVE THIS ROW. NEW DATA PLEASE INSERT ABOVE ↑
ORDER DATA FIRST |  |  |  |  | PLEASE DO NOT REMOVE THIS ROW. NEW DATA PLEASE INSERT BELOW ↓

## Holidays_Table
2025-01-01 | New Year's Day | 停工請C欄打勾"V"
2025-01-27 | Isra Mi'raj
2025-01-29 | Chinese New Year
2025-03-15 | Off
2025-03-22 | Off
2025-03-28 | Off
2025-03-29 | Hindu New Year
2025-03-31 | Eid Al-Fitr
2025-04-01 | Eid Al-Fitr
2025-04-02 | Eid Al-Fitr
2025-04-03 | Eid Al-Fitr
2025-04-04 | Eid Al-Fitr
2025-04-05 | Eid Al-Fitr
2025-04-07 | Off
2025-04-18 | Good Friday
2025-05-01 | World Labor Day
2025-05-12 | Waisak Day
2025-05-29 | Ascension Day of Jesus Christ
2025-06-06 | Eid Al Adha
2025-06-27 | Islamic New Year
2025-08-16 | Off
2025-08-23 | Off
2025-08-30 | Off
2025-09-05 | Prophet Muhammad's Birthday
2025-09-06 | Off
2025-12-25 | Christmas Day
2026-01-01 | New Year's Day
2026-01-16 | Isra Mi'raj
2026-02-17 | Chinese New Year
2026-03-19 | Hindu New Year
2026-03-20 | Eid Al-Fitr
2026-03-21 | Eid Al-Fitr
2026-03-23 | Eid Al-Fitr
2026-03-24 | Eid Al-Fitr
2026-03-25 | Eid Al-Fitr
2026-03-26 | Eid Al-Fitr
2026-04-03 | Good Friday
2026-05-01 | World Labor Day
2026-05-14 | Ascension Day of Jesus Christ
2026-05-27 | Eid Al Adha
2026-06-01 | Pancasila Day
2026-06-16 | Islamic New Year
2026-08-08 | Off
2026-08-15 | Off
2026-08-17 | Independent Day
2026-08-22 | Off
2026-08-25 | Prophet Muhammad's Birthday
2026-08-29 | Off
2026-09-05 | Off
2026-09-12 | Off
2026-12-25 | Christmas Day
2027-01-01 | New Year's Day

## B01_Summary
Line | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK
6-01 | PST840 | 2026-08-18 | 2026-08-27 | 2026-09-23 | 2026-10-02 | L6-01,6-08,6-15 | Z2850Y_C127 | 2026-09-12 | 2026-09-15 | 2026-12-16 | 2027-01-09 | L6-01,6-15,6-19
6-02 | X048GZ_C127 | 2026-08-22 | 2026-08-21 | 2026-10-09 | 2027-01-05 | L6-02 | 1194431_SP27 | 2026-10-07 | 2026-10-05 | 2026-10-24 | 2027-01-28 | L6-02 | CFM271SH09 | 2026-11-05 | 2026-10-20 | 2026-11-28 | 2026-12-07 | L6-02,6-14,6-15
6-03 | ST841_FA26 | 2026-07-23 | 2026-08-21 | 2026-09-09 | 2026-09-19 | L6-03 | 1196262_HO26_PF | 2026-09-07 | 2026-09-03 | 2026-10-09 | 2026-10-15 | L6-03,6-10,6-19 | 1195255_SP27 | 2026-10-07 | 2026-10-05 | 2026-10-23 | 2026-11-05 | L6-03 | 1196262_SP27 | 2026-10-10 | 2026-10-19 | 2026-11-05 | 2026-12-31 | L6-03 | 1195255_SP27 | 2026-10-07 | 2026-10-31 | 2026-12-07 | 2027-01-07 | L6-03 | 1197198/1197204 | 2026-11-30 | 2026-12-02 | 2027-01-15 | 2027-01-28 | L6-03,6-04,6-08,6-09,6-11,6-13,6-16,6-17
6-04 | 766362_HO26/766362_V1 | 2026-07-30 | 2026-08-03 | 2026-09-08 | 2026-10-28 | L6-04 | MRLPMM_3PC_C127 | 2026-08-24 | 2026-08-28 | 2026-09-29 | 2026-10-08 | L6-04,6-11,6-17 | 766362_V1 | 2026-05-22 | 2026-09-24 | 2026-10-17 | 2026-11-12 | L6-04 | L0303X_6PK_C127 | 2026-10-12 | 2026-10-13 | 2026-11-21 | 2026-12-23 | L6-04,6-10 | 1197198/1197204 | 2026-11-30 | 2026-11-17 | 2027-01-05 | 2027-01-28 | L6-03,6-04,6-08,6-09,6-11,6-13,6-16,6-17
6-05 | LPST840 | 2026-08-18 | 2026-08-27 | 2026-09-08 | 2026-10-02 | L6-05,6-15 | 5GK4L2_C127 | 2026-09-10 | 2026-09-02 | 2026-09-19 | 2026-10-10 | L6-05 | 6ZE54X_C127 | 2026-09-21 | 2026-09-10 | 2026-10-27 | 2026-11-02 | L6-05,6-20 | RDW271LE13 | 2026-10-23 | 2026-10-22 | 2026-11-20 | 2026-11-26 | L6-05,6-12,6-13,6-18 | CFW271SH01 | 2026-11-09 | 2026-11-12 | 2026-12-04 | 2026-12-10 | L6-05,6-16,6-17
6-06 | 777362_FA26 | 2026-05-26 | 2026-06-15 | 2026-09-07 | 2026-10-15 |  | 777362_HO26_GLD | 2026-08-29 | 2026-09-01 | 2026-09-10 | 2026-09-24 | L6-06 | 777362_VMI/777362_V2 | 2026-08-01 | 2026-09-04 | 2026-10-21 | 2026-11-12 | L6-06,6-16 | MRLPMM_SSLLC127 | 2026-10-15 | 2026-10-16 | 2026-11-05 | 2026-11-06 | L6-06,6-18 | 777362_V2/777362_VMI | 2026-08-27 | 2026-10-31 | 2026-11-27 | 2026-12-10 | L6-06
6-07 | 352E6Y_SL_C127 | 2026-08-24 | 2026-08-18 | 2026-10-01 | 2027-01-05 | L6-07 | 440ZP9_C127 | 2026-10-17 | 2026-09-26 | 2026-11-25 | 2026-12-17 | L6-07,6-10
6-08 | PST840 | 2026-08-18 | 2026-08-27 | 2026-10-15 | 2026-12-03 | L6-01,6-08,6-15 | 546462_6PK_C127 | 2026-10-13 | 2026-10-10 | 2026-11-28 | 2026-12-30 | L6-08 | 1197198/1197204 | 2026-11-30 | 2026-11-24 | 2027-01-14 | 2027-01-28 | L6-03,6-04,6-08,6-09,6-11,6-13,6-16,6-17
6-09 | W9ZMM8_7PK_C426 | 2026-06-27 | 2026-07-17 | 2026-09-19 | 2026-11-04 | L6-09 | 9KM9L2_C127 | 2026-09-08 | 2026-09-15 | 2026-11-10 | 2026-12-16 | L6-09,6-12,6-13 | W9ZMM8_7PK_C127 | 2026-10-13 | 2026-11-02 | 2026-12-05 | 2026-12-30 | L6-09 | 1197198/1197204 | 2026-11-30 | 2026-12-01 | 2027-01-14 | 2027-01-28 | L6-03,6-04,6-08,6-09,6-11,6-13,6-16,6-17
6-10 | 1188289_HO26 | 2026-08-06 | 2026-08-24 | 2026-09-19 | 2026-10-15 | L6-10,6-13,6-19 | 1196262_HO26_PF | 2026-09-07 | 2026-09-15 | 2026-10-07 | 2026-10-15 | L6-03,6-10,6-19 | L0303X_6PK_C127 | 2026-10-12 | 2026-10-02 | 2026-10-23 | 2026-11-12 | L6-04,6-10 | 440ZP9_C127 | 2026-10-31 | 2026-10-19 | 2026-11-28 | 2026-12-17 | L6-07,6-10
6-11 | MRLPMM_3PC_C127 | 2026-08-24 | 2026-08-19 | 2026-11-25 | 2027-01-05 | L6-04,6-11,6-17 | 1197198/1197204 | 2026-11-30 | 2026-11-20 | 2027-01-08 | 2027-01-28 | L6-03,6-04,6-08,6-09,6-11,6-13,6-16,6-17
6-12 | ZC6HY000 | 2026-07-30 | 2026-08-19 | 2026-09-11 | 2026-09-28 | L6-12 | 9KM9L2_C127 | 2026-09-08 | 2026-09-07 | 2026-10-27 | 2026-12-16 | L6-09,6-12,6-13 | RDW271LE13 | 2026-10-23 | 2026-10-22 | 2026-11-23 | 2026-11-26 | L6-05,6-12,6-13,6-18 | 9KM9L2_C127 | 2026-09-08 | 2026-11-18 | 2027-01-14 | 2027-01-13 | L6-09,6-12,6-13
6-13 | 1188289_HO26 | 2026-08-06 | 2026-08-28 | 2026-09-30 | 2026-11-12 | L6-10,6-13,6-19 | 9KM9L2_C127 | 2026-09-08 | 2026-09-25 | 2026-10-27 | 2026-11-18 | L6-09,6-12,6-13 | RDW271LE13 | 2026-10-23 | 2026-10-22 | 2026-11-25 | 2026-11-26 | L6-05,6-12,6-13,6-18 | 1197198/1197204 | 2026-11-30 | 2026-11-20 | 2027-01-15 | 2027-01-28 | L6-03,6-04,6-08,6-09,6-11,6-13,6-16,6-17
6-14 | 00GG4Z_C127IND | 2026-08-22 | 2026-08-13 | 2026-10-08 | 2026-12-28 | L6-14 | L06X27_SSLLC127 | 2026-10-15 | 2026-10-03 | 2026-11-02 | 2026-12-07 | L6-14 | CFM271SH09 | 2026-11-05 | 2026-10-28 | 2026-12-03 | 2026-12-07 | L6-02,6-14,6-15
6-15 | LPST840 | 2026-08-18 | 2026-08-24 | 2026-09-10 | 2026-10-02 | L6-05,6-15 | PST840 | 2026-08-18 | 2026-09-04 | 2026-09-11 | 2026-09-22 | L6-01,6-08,6-15 | LPST840 | 2026-08-24 | 2026-09-07 | 2026-09-25 | 2026-11-02 | L6-05,6-15 | PST840 | 2026-08-24 | 2026-09-21 | 2026-10-06 | 2026-12-03 | L6-01,6-08,6-15 | Z2850Y_C127 | 2026-09-12 | 2026-09-28 | 2026-11-10 | 2026-11-23 | L6-01,6-15,6-19 | CFM271SH09 | 2026-11-05 | 2026-11-05 | 2026-12-07 | 2026-12-07 | L6-02,6-14,6-15
6-16 | 777362_VMI | 2026-06-23 | 2026-08-03 | 2026-10-03 | 2026-10-15 | L6-06,6-16 | 1194585_HO26_NB | 2026-09-10 | 2026-09-25 | 2026-10-08 | 2026-10-29 | L6-16 | 1193182_SP27 | 2026-10-09 | 2026-09-30 | 2026-11-04 | 2027-01-28 | L6-16 | CFW271SH01 | 2026-11-09 | 2026-10-27 | 2026-11-30 | 2026-12-10 | L6-05,6-16,6-17 | 1197198/1197204 | 2026-11-30 | 2026-11-25 | 2027-01-12 | 2027-01-28 | L6-03,6-04,6-08,6-09,6-11,6-13,6-16,6-17
6-17 | MRLPMM_3PC_C127 | 2026-08-24 | 2026-08-24 | 2026-11-14 | 2026-12-05 | L6-04,6-11,6-17 | CFW271SH01 | 2026-11-09 | 2026-11-06 | 2026-12-07 | 2026-12-10 | L6-05,6-16,6-17 | 1197198/1197204 | 2026-11-30 | 2026-12-02 | 2027-01-13 | 2027-01-28 | L6-03,6-04,6-08,6-09,6-11,6-13,6-16,6-17
6-18 | 352E6Y_LL_C127 | 2026-08-18 | 2026-08-26 | 2026-10-13 | 2026-12-05 | L6-18 | 1KE9E9_SSLLC127 | 2026-10-15 | 2026-10-08 | 2026-10-24 | 2026-11-06 | L6-18 | MRLPMM_SSLLC127 | 2026-10-15 | 2026-10-20 | 2026-11-02 | 2026-11-06 | L6-06,6-18 | RDW271LE13 | 2026-10-23 | 2026-10-28 | 2026-11-23 | 2026-11-26 | L6-05,6-12,6-13,6-18
6-19 | 1188289_HO26 | 2026-08-06 | 2026-08-28 | 2026-09-21 | 2026-10-15 | L6-10,6-13,6-19 | 1196262_HO26_PF | 2026-09-07 | 2026-09-16 | 2026-10-06 | 2026-10-15 | L6-03,6-10,6-19 | Z2850Y_C127 | 2026-09-12 | 2026-09-28 | 2026-11-20 | 2026-12-07 | L6-01,6-15,6-19
6-20 | 4401EW_C127 | 2026-08-18 | 2026-08-20 | 2026-09-30 | 2026-12-16 | L6-20 | 6ZE54X_C127 | 2026-09-21 | 2026-09-22 | 2026-12-15 | 2027-01-11 | L6-05,6-20

## B02_Summary_By _Order
款式 Style | 產品 Product Item | 可開裁日 CRFP | 組別 Line | 預計開裁日 Est. Start Cut | 預計上線日 Sewing Start | 工作時數 Work hr | 預計日產 Target Output | 預計下線日 Est. Sewing Fin. | 剩餘工作天 Need Work Days | 剩餘數量 Remainning Qty | 分配訂單數量 Allocate Qty
00GG4Z_C127IND | Pull On Pants | 2026-08-22 | 6-14 | 2026-08-13 | 2026-08-18 | 8.7569 | 760.406 | 2026-10-08 | 25.3312 | 19262 | 26467
00GG4Z_C127IND 合計 | [9 empty] | 19262 | 26467
1182430_HO26_HT | Pull On Pants | 2026-08-06 | 6-01 | 2026-07-24 | 2026-07-27 | 7.8679 | 1134.2557 | 2026-09-02 | 0 | 0 | 27270
| Pull On Pants | 2026-08-24 | 6-17 | 2026-08-10 | 2026-08-12 | 9 | 1546.8923 | 2026-09-02 | 0.0096969 | 15 | 17242
1182430_HO26_HT 合計 | [9 empty] | 15 | 44512
1182719_HO26 | Skorts | 2026-07-11 | 6-10 | 2026-08-03 | 2026-08-05 | 8 | 1659.9607 | 2026-08-31 | 0 | 0 | 23350
| Skorts | 2026-07-11 | 6-11 | 2026-08-01 | 2026-08-04 | 8 | 1288.3006 | 2026-08-28 | 0 | 0 | 17407
1182719_HO26 合計 | [9 empty] | 0 | 40757
1182723_HO26 | Skorts | 2026-07-14 | 6-13 | 2026-07-22 | 2026-07-24 | 7.8718 | 1178.6229 | 2026-09-03 | 0 | 0 | 32276
| Skorts | 2026-07-14 | 6-19 | 2026-07-22 | 2026-07-24 | 7.9363 | 1334.965 | 2026-09-03 | 0 | 0 | 36303
1182723_HO26 合計 | [9 empty] | 0 | 68579
1184403_HO26 | Pull On Pants | 2026-07-13 | 6-10 | 2026-07-18 | 2026-07-21 | 7.2192 | 562.4717 | 2026-08-07 | 0 | 0 | 7414
1184403_HO26 合計 | [9 empty] | 0 | 7414
1184404_HO26 | Tee | 2026-07-13 | 6-05 | 2026-07-16 | 2026-07-18 | 6.9853 | 671.4355 | 2026-07-30 | 0 | 0 | 5350
1184404_HO26 合計 | [9 empty] | 0 | 5350
1188289_HO26 | Pull On Pants | 2026-08-06 | 6-10 | 2026-08-24 | 2026-08-27 | 8.8153 | 2283.2272 | 2026-09-19 | 10.7449 | 24533 | 34097
| Pull On Pants | 2026-08-06 | 6-13 | 2026-08-28 | 2026-09-01 | 8.6946 | 2057.4951 | 2026-09-30 | 19.4975 | 40116 | 43504
| Pull On Pants | 2026-08-06 | 6-19 | 2026-08-28 | 2026-09-01 | 8.7528 | 2249.3794 | 2026-09-21 | 12.3176 | 27707 | 31273
1188289_HO26 合計 | [9 empty] | 92356 | 108874
1193182_SP27 | Tee | 2026-10-09 | 6-16 | 2026-09-30 | 2026-10-06 | 8.5094 | 1705.1832 | 2026-11-04 | 23.4737 | 40027 | 40027
1193182_SP27 合計 | [9 empty] | 40027 | 40027
1194431_SP27 | Tee | 2026-10-07 | 6-02 | 2026-10-05 | 2026-10-07 | 8.4417 | 780.7159 | 2026-10-24 | 13.3006 | 10384 | 10384
1194431_SP27 合計 | [9 empty] | 10384 | 10384
1194585_HO26_NB | Pull On Pants | 2026-09-10 | 6-16 | 2026-09-25 | 2026-10-01 | 8.0813 | 801.4637 | 2026-10-08 | 3.7432 | 3000 | 3000
1194585_HO26_NB 合計 | [9 empty] | 3000 | 3000
1195255_SP27 | Tee | 2026-10-07 | 6-03 | 2026-10-05 | 2026-10-07 | 8.4123 | 1425.1752 | 2026-10-23 | 12.71 | 18114 | 18114
| Tee | 2026-10-07 | 6-03 | 2026-10-31 | 2026-11-03 | 8.5719 | 2099.8476 | 2026-12-07 | 27.5701 | 57893 | 57893
1195255_SP27 合計 | [9 empty] | 76007 | 76007
1196262_HO26_PF | Tee | 2026-09-07 | 6-03 | 2026-09-03 | 2026-09-07 | 8.4898 | 1248.5354 | 2026-10-09 | 25.1471 | 31397 | 31397
| Tee | 2026-09-07 | 6-10 | 2026-09-15 | 2026-09-17 | 8.3781 | 1119.4716 | 2026-10-07 | 15.3474 | 17181 | 17181
| Tee | 2026-09-07 | 6-19 | 2026-09-16 | 2026-09-18 | 8.3319 | 1017.9489 | 2026-10-06 | 12.703 | 12931 | 12931
1196262_HO26_PF 合計 | [9 empty] | 61509 | 61509
1196262_SP27 | Tee | 2026-10-10 | 6-03 | 2026-10-19 | 2026-10-21 | 8.3947 | 1200.7837 | 2026-11-05 | 10.8554 | 13035 | 13035
1196262_SP27 合計 | [9 empty] | 13035 | 13035
1197198/1197204 | Dress | 2026-11-30 | 6-03 | 2026-12-02 | 2026-12-04 | 8.4856 | 1133.7183 | 2027-01-15 | 32.2611 | 36575 | 36575
| Dress | 2026-11-30 | 6-04 | 2026-11-17 | 2026-11-19 | 8.4985 | 1180.6532 | 2027-01-05 | 35.2644 | 41635 | 41635
| Dress | 2026-11-30 | 6-08 | 2026-11-24 | 2026-11-26 | 8.5036 | 1183.0802 | 2027-01-14 | 37.3052 | 44135 | 44135
| Dress | 2026-11-30 | 6-09 | 2026-12-01 | 2026-12-03 | 8.4847 | 1129.4075 | 2027-01-14 | 32.0389 | 36185 | 36185
| Dress | 2026-11-30 | 6-11 | 2026-11-20 | 2026-11-23 | 8.4744 | 906.5008 | 2027-01-08 | 36.1114 | 32735 | 32735
| Dress | 2026-11-30 | 6-13 | 2026-11-20 | 2026-11-23 | 8.5089 | 1104.586 | 2027-01-15 | 42.6721 | 47135 | 47135
| Dress | 2026-11-30 | 6-16 | 2026-11-25 | 2026-11-27 | 8.4963 | 1177.1566 | 2027-01-12 | 34.5196 | 40635 | 40635
| Dress | 2026-11-30 | 6-17 | 2026-12-02 | 2026-12-04 | 8.4778 | 1148.6426 | 2027-01-13 | 29.2824 | 33635 | 33635
1197198/1197204 合計 | [9 empty] | 312670 | 312670
1KE9E9_SSLLC127 | Pajama | 2026-10-15 | 6-18 | 2026-10-08 | 2026-10-10 | 8.4959 | 2240.2808 | 2026-10-24 | 8.856 | 19840 | 19840
1KE9E9_SSLLC127 合計 | [9 empty] | 19840 | 19840
352E6Y_LL_C127 | Pajama | 2026-08-18 | 6-18 | 2026-08-21 | 2026-08-31 | 8.63 | 1907.4486 | 2026-10-13 | 32.0098 | 61057 | 63409
352E6Y_LL_C127 合計 | [9 empty] | 61057 | 63409
352E6Y_SL_C127 | Pajama | 2026-08-15 | 6-07 | 2026-08-13 | 2026-08-21 | 8.6894 | 2008.6323 | 2026-10-01 | 21.7347 | 43657 | 57411
352E6Y_SL_C127 合計 | [9 empty] | 43657 | 57411
4401EW_C127 | Robe | 2026-08-18 | 6-20 | 2026-08-20 | 2026-08-24 | 8.7645 | 1138.8101 | 2026-09-30 | 19.4975 | 22204 | 29796
4401EW_C127 合計 | [9 empty] | 22204 | 29796
440ZP9_C127 | Pull On Pants | 2026-10-17 | 6-07 | 2026-09-26 | 2026-09-29 | 8.5286 | 1454.5923 | 2026-11-25 | 46.8592 | 68161 | 68161
| Pull On Pants | 2026-10-31 | 6-10 | 2026-10-19 | 2026-10-21 | 8.4745 | 1359.4267 | 2026-11-28 | 30.0847 | 40898 | 40898
440ZP9_C127 合計 | [9 empty] | 109059 | 109059
45M87P_C426 | Pull On Pants | 2026-06-27 | 6-01 | 2026-07-02 | 2026-07-04 | 8.0771 | 836.0225 | 2026-07-29 | 0 | 0 | 15985
45M87P_C426 合計 | [9 empty] | 0 | 15985
546462_6PK_C127 | Panties | 2026-10-13 | 6-08 | 2026-10-10 | 2026-10-13 | 8.5582 | 5292.2703 | 2026-11-28 | 39.2497 | 207720 | 207720
546462_6PK_C127 合計 | [9 empty] | 207720 | 207720
5GK4L2_C127 | Jumper | 2026-09-10 | 6-05 | 2026-09-02 | 2026-09-04 | 8.0837 | 365.3982 | 2026-09-19 | 7.9803 | 2916 | 2916
5GK4L2_C127 合計 | [9 empty] | 2916 | 2916
5GK4L2_C426 | Jumper | 2026-07-03 | 6-05 | 2026-07-08 | 2026-07-10 | 7.5859 | 393.2819 | 2026-07-21 | 0 | 0 | 2892
5GK4L2_C426 合計 | [9 empty] | 0 | 2892
6ZE54X_C127 | Pull On Pants | 2026-09-21 | 6-05 | 2026-09-10 | 2026-09-17 | 8.3846 | 516.4596 | 2026-10-27 | 32.9067 | 16995 | 16995
| Pull On Pants | 2026-09-21 | 6-20 | 2026-09-22 | 2026-09-28 | 8.4986 | 707.6629 | 2026-12-15 | 66.1063 | 46781 | 46781
6ZE54X_C127 合計 | [9 empty] | 63776 | 63776
766362_HO26 | Pull On Pants | 2026-07-09 | 6-04 | 2026-06-26 | 2026-06-29 | 8.2229 | 1239.9326 | 2026-07-24 | 0 | 0 | 24434
| Pull On Pants | 2026-07-17 | 6-04 | 2026-08-01 | 2026-08-04 | 8.4727 | 1376.5933 | 2026-09-07 | 1.0461 | 1440 | 27675
| Pull On Pants | 2026-07-17 | 6-08 | 2026-07-09 | 2026-07-11 | 7.9857 | 1481.616 | 2026-08-20 | 0 | 0 | 43769
766362_HO26 合計 | [9 empty] | 1440 | 95878
766362_V1 | Pull On Pants | 2026-05-22 | 6-04 | 2026-09-01 | 2026-09-03 | 9 | 1703.6372 | 2026-09-08 | 0.22247 | 379 | 855
| Pull On Pants | 2026-05-22 | 6-04 | 2026-09-24 | 2026-09-26 | 8.2933 | 1179.9728 | 2026-10-17 | 14.9673 | 17661 | 17661
| Pull On Pants | 2026-05-11 | 6-08 | 2026-06-04 | 2026-06-06 | 9.2186 | 1422.6791 | 2026-07-14 | 0 | 0 | 41082
| Pull On Pants | 2026-05-22 | 6-08 | 2026-08-13 | 2026-08-18 | 8.5958 | 1714.08 | 2026-09-02 | 0.032671 | 56 | 14368
766362_V1 合計 | [9 empty] | 18096 | 73966
777362_FA26 | Pull On Pants | 2026-05-23 | 6-03 | 2026-05-09 | 2026-05-12 | 9.1023 | 1259.5162 | 2026-06-04 | 0 | 0 | 19159
| Pull On Pants | 2026-04-25 | 6-04 | 2026-04-09 | 2026-04-11 | 8.8333 | 1159.316 | 2026-05-12 | 0 | 0 | 26479
| Pull On Pants | 2026-05-26 | 6-05 | 2026-06-11 | 2026-06-13 | 9.1485 | 1399.0404 | 2026-07-13 | 0 | 0 | 31058
| Pull On Pants | 2026-05-26 | 6-06 | 2026-06-15 | 2026-06-18 | 9.4584 | 1510.9939 | 2026-07-10 | 0 | 0 | 25055
| Pull On Pants | 2026-05-26 | 6-08 | 2026-05-26 | 2026-05-29 | 8.7363 | 1308.6032 | 2026-06-09 | 0 | 0 | 7260
| Pull On Pants | 2026-04-25 | 6-10 | 2026-04-11 | 2026-04-14 | 8.5757 | 1103.5488 | 2026-05-04 | 0 | 0 | 15160
| Pull On Pants | 2026-05-26 | 6-13 | 2026-06-26 | 2026-06-29 | 9.3933 | 1193.554 | 2026-07-16 | 0 | 0 | 15589
| Pull On Pants | 2026-05-26 | 6-15 | 2026-06-20 | 2026-06-23 | 9.3739 | 1550.6758 | 2026-07-14 | 0 | 0 | 24345
| Pull On Pants | 2026-05-23 | 6-19 | 2026-07-22 | 2026-07-24 | 7.482 | 817.4638 | 2026-07-27 | 0 | 0 | 176
| Pull On Pants | 2026-05-23 | 6-20 | 2026-04-10 | 2026-04-13 | 9.4002 | 1779.9917 | 2026-07-21 | 0 | 0 | 138695
777362_FA26 合計 | [9 empty] | 0 | 302976
777362_HO26_GLD | Pull On Pants | 2026-08-29 | 6-06 | 2026-09-01 | 2026-09-03 | 9 | 1751.7031 | 2026-09-10 | 3.4252 | 6000 | 6000
777362_HO26_GLD 合計 | [9 empty] | 6000 | 6000
777362_V2 | Pull On Pants | 2026-10-08 | 6-06 | 2026-10-09 | 2026-10-12 | 8.6 | 1673.8497 | 2026-10-21 | 5.5417 | 9276 | 9276
| Pull On Pants | 2026-08-27 | 6-06 | 2026-10-31 | 2026-11-03 | 8.4762 | 1232.6586 | 2026-11-21 | 13.505 | 16647 | 16647
777362_V2 合計 | [9 empty] | 25923 | 25923
777362_VMI | Pull On Pants | 2026-05-04 | 6-03 | 2026-04-11 | 2026-04-14 | 9.1703 | 1300.1298 | 2026-05-15 | 0 | 0 | 29699
| Pull On Pants | 2026-05-07 | 6-05 | 2026-03-27 | 2026-03-30 | 8.9946 | 1259.8102 | 2026-05-28 | 0 | 0 | 56118
| Pull On Pants | 2026-04-13 | 6-06 | 2026-04-08 | 2026-04-10 | 8.7258 | 1219.0291 | 2026-05-06 | 0 | 0 | 24866
| Pull On Pants | 2026-06-23 | 6-06 | 2026-07-06 | 2026-07-08 | 8.6261 | 1586.805 | 2026-09-07 | 0.92954 | 1475 | 67559
| Pull On Pants | 2026-08-01 | 6-06 | 2026-09-04 | 2026-09-08 | 8.6 | 1673.8497 | 2026-10-14 | 27.7576 | 46462 | 46462
| Pull On Pants | 2026-08-20 | 6-06 | 2026-11-17 | 2026-11-19 | 8.6 | 1673.8497 | 2026-11-27 | 5.4939 | 9196 | 9196
| Pull On Pants | 2026-05-07 | 6-07 | 2026-07-06 | 2026-07-08 | 8.2762 | 1035.0792 | 2026-07-24 | 0 | 0 | 11906
| Pull On Pants | 2026-05-07 | 6-08 | 2026-04-17 | 2026-04-20 | 9.3938 | 1434.8257 | 2026-06-02 | 0 | 0 | 43947
| Pull On Pants | 2026-05-04 | 6-12 | 2026-04-18 | 2026-04-21 | 9.1441 | 1376.3212 | 2026-05-26 | 0 | 0 | 36158
| Pull On Pants | 2026-06-23 | 6-13 | 2026-07-11 | 2026-07-14 | 7.9762 | 1104.5568 | 2026-07-27 | 0 | 0 | 10000
| Pull On Pants | 2026-06-23 | 6-15 | 2026-07-09 | 2026-07-11 | 7.855 | 1210.7956 | 2026-07-20 | 0 | 0 | 5783
| Pull On Pants | 2026-05-07 | 6-16 | 2026-04-07 | 2026-04-09 | 9.2232 | 1414.0742 | 2026-05-30 | 0 | 0 | 55281
| Pull On Pants | 2026-06-23 | 6-16 | 2026-08-03 | 2026-08-05 | 8.7442 | 1581.758 | 2026-10-03 | 23.6654 | 37433 | 65164
| Pull On Pants | 2026-05-07 | 6-18 | 2026-04-01 | 2026-04-04 | 9.0947 | 1505.6912 | 2026-05-25 | 0 | 0 | 58617
| Pull On Pants | 2026-06-23 | 6-18 | 2026-08-12 | 2026-08-14 | 8.0143 | 1260.476 | 2026-08-21 | 0 | 0 | 2978
| Pull On Pants | 2026-06-23 | 6-19 | 2026-07-06 | 2026-07-08 | 8.0928 | 1260.0109 | 2026-07-27 | 0 | 0 | 17165
| Pull On Pants | 2026-06-23 | 6-20 | 2026-07-16 | 2026-07-18 | 7.995 | 1436.8349 | 2026-07-22 | 0 | 0 | 770
777362_VMI 合計 | [9 empty] | 94566 | 541669
826369_HO26 | Pull On Pants | 2026-07-13 | 6-10 | 2026-07-14 | 2026-07-16 | 7.2576 | 622.6666 | 2026-07-23 | 0 | 0 | 2235
826369_HO26 合計 | [9 empty] | 0 | 2235
890955_FA26 | Pull On Pants | 2026-04-30 | 6-06 | 2026-04-30 | 2026-05-04 | 8.5835 | 1045.603 | 2026-05-15 | 0 | 0 | 7023
| Pull On Pants | 2026-04-13 | 6-06 | 2026-06-11 | 2026-06-13 | 9.4007 | 1112.5004 | 2026-06-20 | 0 | 0 | 3293
890955_FA26 合計 | [9 empty] | 0 | 10316
905200_FA26 | Pull On Pants | 2026-05-02 | 6-06 | 2026-05-09 | 2026-05-12 | 9.4741 | 1056.0642 | 2026-06-17 | 0 | 0 | 26558
| Pull On Pants | 2026-05-15 | 6-10 | 2026-05-04 | 2026-05-06 | 9.3511 | 1100.8636 | 2026-07-13 | 0 | 0 | 57498
905200_FA26 合計 | [9 empty] | 0 | 84056
907938_FA26 | Leggings | 2026-05-07 | 6-12 | 2026-05-21 | 2026-05-23 | 7.881 | 502.1956 | 2026-05-29 | 0 | 0 | 1178
907938_FA26 合計 | [9 empty] | 0 | 1178
910047_FA26 | Pajama | 2026-06-03 | 6-01 | 2026-06-09 | 2026-06-11 | 9.2169 | 873.476 | 2026-07-07 | 0 | 0 | 16401
| Pajama | 2026-06-03 | 6-03 | 2026-05-29 | 2026-06-02 | 9.5107 | 1006.3981 | 2026-07-08 | 0 | 0 | 28598
| Pajama | 2026-06-03 | 6-04 | 2026-05-21 | 2026-05-23 | 9.1249 | 816.4257 | 2026-06-25 | 0 | 0 | 18832
| Pajama | 2026-06-03 | 6-07 | 2026-06-02 | 2026-06-04 | 9.211 | 868.1993 | 2026-07-10 | 0 | 0 | 24374
| Pajama | 2026-06-03 | 6-12 | 2026-05-23 | 2026-05-26 | 9.4353 | 957.9881 | 2026-07-09 | 0 | 0 | 31999
| Pajama | 2026-06-03 | 6-15 | 2026-06-03 | 2026-06-05 | 9.1261 | 899.3507 | 2026-06-25 | 0 | 0 | 12675
| Pajama | 2026-06-03 | 6-18 | 2026-05-20 | 2026-05-22 | 9.4411 | 1055.0911 | 2026-07-08 | 0 | 0 | 36668
| Pajama | 2026-06-03 | 6-19 | 2026-05-29 | 2026-06-02 | 9.3862 | 1000.7301 | 2026-07-10 | 0 | 0 | 30137
910047_FA26 合計 | [9 empty] | 0 | 199684
910047_HO26DIS | Pajama | 2026-07-06 | 6-03 | 2026-07-03 | 2026-07-06 | 8.4758 | 1018.4268 | 2026-07-21 | 0 | 0 | 11308
| Pajama | 2026-07-06 | 6-12 | 2026-07-04 | 2026-07-07 | 8.2028 | 948.3748 | 2026-08-13 | 0 | 0 | 27677
| Pajama | 2026-07-06 | 6-18 | 2026-07-03 | 2026-07-06 | 8.2635 | 1164.4988 | 2026-08-19 | 0 | 0 | 38392
| Pajama | 2026-07-06 | 6-18 | 2026-08-14 | 2026-08-19 | 8.5299 | 1141.6509 | 2026-09-02 | 0 | 0 | 8515
910047_HO26DIS 合計 | [9 empty] | 0 | 85892
915810_FA26 | Tee | 2026-05-15 | 6-04 | 2026-05-07 | 2026-05-09 | 8.7965 | 610.2657 | 2026-05-26 | 0 | 0 | 6456
| Tee | 2026-06-04 | 6-04 | 2026-06-20 | 2026-06-23 | 7.7074 | 596.92 | 2026-07-01 | 0 | 0 | 3182
915810_FA26 合計 | [9 empty] | 0 | 9638
962148_FA26 | Leggings | 2026-04-15 | 6-10 | 2026-04-28 | 2026-04-30 | 8.0175 | 1209.8277 | 2026-05-08 | 0 | 0 | 4540
962148_FA26 合計 | [9 empty] | 0 | 4540
9KM9L2_C127 | Pull On Pants | 2026-09-08 | 6-09 | 2026-09-15 | 2026-09-17 | 8.5032 | 1005.4062 | 2026-11-10 | 42.6236 | 42854 | 42854
| Pull On Pants | 2026-09-08 | 6-12 | 2026-09-07 | 2026-09-09 | 8.4952 | 1030.456 | 2026-10-27 | 37.9153 | 39070 | 39070
| Pull On Pants | 2026-09-08 | 6-12 | 2026-11-18 | 2026-11-20 | 8.4998 | 1107.8032 | 2027-01-14 | 44.1631 | 48924 | 48924
| Pull On Pants | 2026-09-08 | 6-13 | 2026-09-25 | 2026-09-28 | 8.4029 | 754.0372 | 2026-10-27 | 22.0281 | 16610 | 16610
9KM9L2_C127 合計 | [9 empty] | 147458 | 147458
CFM271SH09 | Pull On Pants | 2026-11-05 | 6-02 | 2026-10-20 | 2026-10-22 | 8.4516 | 857.4996 | 2026-11-28 | 29.4251 | 25232 | 25232
| Pull On Pants | 2026-11-05 | 6-14 | 2026-10-28 | 2026-10-30 | 8.4339 | 800.8188 | 2026-12-03 | 27.1372 | 21732 | 21732
| Pull On Pants | 2026-11-05 | 6-15 | 2026-11-05 | 2026-11-07 | 8.4184 | 811.1024 | 2026-12-07 | 23.5877 | 19132 | 19132
CFM271SH09 合計 | [9 empty] | 66096 | 66096
CFW271SH01 | Pull On Pants | 2026-11-09 | 6-05 | 2026-11-12 | 2026-11-18 | 8.2901 | 849.9427 | 2026-12-04 | 11.4455 | 9728 | 9728
| Pull On Pants | 2026-11-09 | 6-16 | 2026-10-27 | 2026-11-02 | 8.443 | 1165.0566 | 2026-11-30 | 20.8101 | 24245 | 24245
| Pull On Pants | 2026-11-09 | 6-17 | 2026-11-06 | 2026-11-12 | 8.4246 | 1130.1473 | 2026-12-07 | 18.6268 | 21051 | 21051
CFW271SH01 合計 | [9 empty] | 55024 | 55024
CPM263PA05_26Q4 | Pull On Pants | 2026-07-10 | 6-07 | 2026-07-16 | 2026-07-22 | 7.6793 | 755.5279 | 2026-08-26 | 0 | 0 | 17364
| Pull On Pants | 2026-07-10 | 6-20 | 2026-07-14 | 2026-07-20 | 7.7377 | 808.2034 | 2026-08-27 | 0 | 0 | 20835
CPM263PA05_26Q4 合計 | [9 empty] | 0 | 38199
CPM263PA81 | Pull On Pants | 2026-05-23 | 6-20 | 2026-07-14 | 2026-07-20 | 8 | 942.2492 | 2026-07-22 | 0 | 0 | 31
CPM263PA81 合計 | [9 empty] | 0 | 31
CPM263TL32_26Q4 | Tee | 2026-07-10 | 6-04 | 2026-07-16 | 2026-07-22 | 7.4953 | 1072.3844 | 2026-08-06 | 0 | 0 | 12021
| Tee | 2026-07-10 | 6-15 | 2026-07-11 | 2026-07-17 | 7.6394 | 1140.9978 | 2026-08-18 | 0 | 0 | 25311
CPM263TL32_26Q4 合計 | [9 empty] | 0 | 37332
CPW264TL38 | Tee | 2026-07-10 | 6-03 | 2026-07-13 | 2026-07-18 | 7.5879 | 1087.3719 | 2026-08-18 | 0 | 0 | 22323
| Tee | 2026-07-10 | 6-05 | 2026-07-22 | 2026-07-28 | 7.746 | 1167.0888 | 2026-08-20 | 0 | 0 | 17942
CPW264TL38 合計 | [9 empty] | 0 | 40265
G917K0_C426 | Pajama | 2026-06-12 | 6-02 | 2026-05-25 | 2026-06-02 | 8.5997 | 1282.5237 | 2026-08-31 | 0 | 0 | 87714
| Pajama | 2026-05-26 | 6-16 | 2026-05-21 | 2026-05-28 | 9.2646 | 1283.0131 | 2026-07-11 | 0 | 0 | 43173
G917K0_C426 合計 | [9 empty] | 0 | 130887
G9M018_C426 | Pajama | 2026-05-25 | 6-09 | 2026-05-11 | 2026-05-18 | 9.5019 | 1837.1199 | 2026-07-04 | 0 | 0 | 65630
| Pajama | 2026-06-25 | 6-14 | 2026-06-24 | 2026-06-30 | 8.5318 | 1730.0941 | 2026-08-20 | 0 | 0 | 67974
| Pajama | 2026-06-25 | 6-16 | 2026-07-03 | 2026-07-09 | 8.0933 | 1800.1043 | 2026-08-07 | 0 | 0 | 41073
| Pajama | 2026-06-25 | 6-17 | 2026-05-20 | 2026-05-26 | 9.0274 | 1815.7792 | 2026-08-14 | 0 | 0 | 114421
G9M018_C426 合計 | [9 empty] | 0 | 289098
HQ263487_FA26 | Pull On Pants | 2026-05-21 | 6-05 | 2026-05-22 | 2026-05-25 | 9.1873 | 1315.2706 | 2026-06-17 | 0 | 0 | 20277
HQ263487_FA26 合計 | [9 empty] | 0 | 20277
L0303X_6PK_C127 | Panties | 2026-10-12 | 6-04 | 2026-10-13 | 2026-10-15 | 8.5537 | 4688.3299 | 2026-11-21 | 31.6821 | 148536 | 148536
| Panties | 2026-10-12 | 6-10 | 2026-10-02 | 2026-10-05 | 8.4976 | 4132.2706 | 2026-10-23 | 14.3224 | 59184 | 59184
L0303X_6PK_C127 合計 | [9 empty] | 207720 | 207720
L06X27_SSLLC127 | Pajama | 2026-10-15 | 6-14 | 2026-10-03 | 2026-10-06 | 8.4666 | 1639.1633 | 2026-11-02 | 20.8887 | 34240 | 34240
L06X27_SSLLC127 合計 | [9 empty] | 34240 | 34240
LPST840 | Pull On Pants | 2026-08-18 | 6-05 | 2026-08-13 | 2026-08-18 | 8.7311 | 672.7291 | 2026-09-08 | 2.5627 | 1724 | 8459
| Pull On Pants | 2026-08-18 | 6-15 | 2026-08-11 | 2026-08-13 | 8.7394 | 642.4484 | 2026-09-10 | 4.6307 | 2975 | 10415
| Pull On Pants | 2026-08-24 | 6-15 | 2026-09-07 | 2026-09-09 | 8.6996 | 852.9227 | 2026-09-25 | 11.3164 | 9652 | 9652
LPST840 合計 | [9 empty] | 14351 | 28526
MRLPMM_3PC_C127 | Pajama | 2026-08-24 | 6-04 | 2026-08-28 | 2026-09-04 | 8.3897 | 907.4526 | 2026-09-29 | 17.3221 | 15719 | 15719
| Pajama | 2026-08-24 | 6-11 | 2026-08-18 | 2026-08-26 | 8.6251 | 1195.1099 | 2026-11-25 | 67.7042 | 80914 | 86696
| Pajama | 2026-08-24 | 6-17 | 2026-08-21 | 2026-08-31 | 8.6194 | 1375.3372 | 2026-11-14 | 59.3316 | 81601 | 83049
MRLPMM_3PC_C127 合計 | [9 empty] | 178234 | 185464
MRLPMM_C426 | Pajama | 2026-06-08 | 6-11 | 2026-05-12 | 2026-05-19 | 8.7955 | 1554.7148 | 2026-08-06 | 0 | 0 | 98283
| Pajama | 2026-05-26 | 6-14 | 2026-05-22 | 2026-05-29 | 9.4588 | 1678.4133 | 2026-07-02 | 0 | 0 | 41982
MRLPMM_C426 合計 | [9 empty] | 0 | 140265
MRLPMM_SSLLC127 | Pajama | 2026-10-15 | 6-06 | 2026-10-16 | 2026-10-19 | 8.3942 | 1469.7055 | 2026-11-05 | 12.397 | 18220 | 18220
| Pajama | 2026-10-15 | 6-18 | 2026-10-20 | 2026-10-22 | 8.4583 | 2077.5261 | 2026-11-02 | 5.8233 | 12098 | 12098
MRLPMM_SSLLC127 合計 | [9 empty] | 30318 | 30318
PST840 | Pull On Pants | 2026-08-18 | 6-01 | 2026-08-27 | 2026-08-31 | 8.7544 | 748.6657 | 2026-09-23 | 13.3811 | 10018 | 12173
| Pull On Pants | 2026-08-18 | 6-08 | 2026-08-27 | 2026-08-31 | 8.5412 | 642.7039 | 2026-10-15 | 35.2495 | 22655 | 23101
| Pull On Pants | 2026-08-18 | 6-15 | 2026-09-04 | 2026-09-08 | 8.0254 | 727.297 | 2026-09-11 | 1.375 | 1000 | 1000
| Pull On Pants | 2026-08-24 | 6-15 | 2026-09-21 | 2026-09-23 | 8.6 | 794.1383 | 2026-10-06 | 8.9808 | 7132 | 7132
PST840 合計 | [9 empty] | 40805 | 43406
RDW271LE13 | Leggings | 2026-10-23 | 6-05 | 2026-10-22 | 2026-10-24 | 8.4444 | 1051.5296 | 2026-11-20 | 22.2295 | 23375 | 23375
| Leggings | 2026-10-23 | 6-12 | 2026-10-22 | 2026-10-24 | 8.461 | 1169.2536 | 2026-11-23 | 22.7726 | 26627 | 26627
| Leggings | 2026-10-23 | 6-13 | 2026-10-22 | 2026-10-24 | 8.4641 | 1075.775 | 2026-11-25 | 25.4486 | 27377 | 27377
| Leggings | 2026-10-23 | 6-18 | 2026-10-28 | 2026-10-30 | 8.4171 | 1097.9083 | 2026-11-23 | 17.4195 | 19125 | 19125
RDW271LE13 合計 | [9 empty] | 96504 | 96504
ST841_FA26 | Tee | 2026-07-23 | 6-03 | 2026-08-11 | 2026-08-13 | 8.6044 | 486.7991 | 2026-09-09 | 3.332 | 1622 | 7232
ST841_FA26 合計 | [9 empty] | 1622 | 7232
W9ZMM8_7PK_C127 | Panties | 2026-10-13 | 6-09 | 2026-11-02 | 2026-11-07 | 8.4417 | 7350.6623 | 2026-12-05 | 20.1239 | 147924 | 147924
W9ZMM8_7PK_C127 合計 | [9 empty] | 147924 | 147924
W9ZMM8_7PK_C426 | Panties | 2026-06-27 | 6-09 | 2026-06-26 | 2026-07-02 | 8.2971 | 10258.2421 | 2026-09-19 | 11.6719 | 119733 | 607416
W9ZMM8_7PK_C426 合計 | [9 empty] | 119733 | 607416
X048GZ_C127 | Pajama | 2026-08-22 | 6-02 | 2026-08-19 | 2026-08-27 | 8.6271 | 1757.5386 | 2026-10-09 | 28.7476 | 50525 | 56264
X048GZ_C127 合計 | [9 empty] | 50525 | 56264
X25413_C426 | Pull On Pants | 2026-07-06 | 6-10 | 2026-07-08 | 2026-07-10 | 7.7928 | 582.7032 | 2026-07-18 | 0 | 0 | 3123
| Pull On Pants | 2026-07-06 | 6-12 | 2026-08-07 | 2026-08-11 | 8 | 456.6583 | 2026-08-26 | 0 | 0 | 3075
X25413_C426 合計 | [9 empty] | 0 | 6198
Z2850Y_C127 | Pull On Pants | 2026-09-12 | 6-01 | 2026-09-15 | 2026-09-21 | 8.5168 | 745.9249 | 2026-12-16 | 70.5889 | 52654 | 52654
| Pull On Pants | 2026-09-12 | 6-15 | 2026-09-28 | 2026-10-03 | 8.4046 | 585.2927 | 2026-11-10 | 30.8632 | 18064 | 18064
| Pull On Pants | 2026-09-12 | 6-19 | 2026-09-28 | 2026-10-03 | 8.4453 | 641.601 | 2026-11-20 | 37.9395 | 24342 | 24342
Z2850Y_C127 合計 | [9 empty] | 95060 | 95060
ZC6HY000 | Gown | 2026-07-30 | 6-12 | 2026-08-19 | 2026-08-21 | 9 | 1459.1493 | 2026-09-11 | 4.4855 | 6545 | 17914
總計 | [10 empty] | 5364458