## B04_Capacity
IND-GLD6-2026092101
| * | 9月 Sep | 10月 Oct | 11月 Nov | 12月 Dec | 1月 Jan | 2月 Feb | 3月 Mar | 4月 Apr | 5月 May | 6月 Jun | 7月 Jul | 8月 Aug
A = B04_Gannt_Chart_Detail 裡面的實際標打+排線標打(不含無訂單產能) = 來源是底稿加工票 | 已排線產能 Scheduled Capacity | 47496.8294 | 54767.8681 | 54755.61 | 54031.9903 | 26818.9315 | 4519.8317 | 0 | 0 | 0 |  | 59025.3942 | 39355.2192
B = B04_Gannt_Chart_Detail 裡面的無訂單產能 來源為Parameter設人數/效率/工時計算出，抓最後一組下線+30天，這樣至少讓尾數月的產能資料完整，後面不完整月份直接看產銷產能預估即可 | 未排線產能 Unscheduled Capacity |  |  |  |  | 24168 | 44096 | 42400 | 55120 | 31800
C = A+B | 總產能 Total Capacity | 47496.8294 | 54767.8681 | 54755.61 | 54031.9903 | 50986.9315 | 48615.8317 | 42400 | 55120 | 31800 | 0 | 59025.3942 | 39355.2192
D = 產銷匯入最新預計產能 | 預估產能 Estimated Capacity | 47000 | 53500 | 49500 | 51500 | 50000 | 48000 | 37500 | 54000 | 45500 | 52000 | 59000 | 54500
E = ERP屬於該Maker的EXP標打數 | 出口總數 Confirmed Order | 34740.5708 | 54227.225 | 51962.3392 | 34488.5142 | 5509.8075
F = B04_Gannt_Chart_Detail 裡面的實際標打+排線標打 / B04_Gannt_Chart_Detail人數工時計算出100%效率標打數 = 效率 = 來源是底稿加工票 | 已排線效率 Scheduled Efficiency | 1.5953 | 1.5411 | 1.6668 | 1.5844 | 1.602 | 1.558 |  |  |  |  | 1.7943 | 1.5841
G = B04_Gannt_Chart_Detail 裡面的實際人數 + 排線人數 加總除以各組加總工作天次 = 來源是底稿加工票 | 已排線人數 Scheduled Sewers | 36.6193 | 36.8907 | 36.6833 | 36.6202 | 36.7172 | 36.4421 |  |  |  |  | 36.2385 | 36.6825
H = Parameter 參數設定 | 排線標準工時 Standard Working Hours | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
I = B04_Gannt_Chart_Detail 裡面的實際工時 + 排線工時，加總起來扣除排線標準工時再除上排線標準工時得之 = 來源是底稿加工票 | 已排線加班率 Scheduled OT Rate | 0.097911 | 0.059939 | 0.064201 | 0.064051 | 0.075 | 0.075 |  |  |  |  | 0.037247 | 0.0060144
J = 扣除禮拜天 & Holidays Table的工作天數 | 工作天 Working Days | 22 | 27 | 25 | 26 | 24 | 23 | 20 | 25 | 23 | 24 | 27 | 20
K = B04_Gannt_Chart_Detail 裡面的實際標打+排線標打 真正有訂單標打數的天數 除以 工作天 (換句話說單組休年假或拆組會少計) | 已排線數 Lines | 20 | 20 | 20 | 20 | 10.5 | 1.913 |  | 20 | 20 | 20 | 20 | 20
L = 發生換款(同Style_N2不算換)的次數除以排線數 | 換款率 Turnover Rate | 1.8 | 1.2 | 0.75 | 0.75 | 0.28571 | [5 empty] | 0.95 | 1.05
M = B04_Gannt_Chart_Detail 裡面的Suspend work停工產能總計 | 停工產能 Suspend Work Capacity
N = 該月提前生產兩個月後交期訂單的比例 | 提前完成% Advance Production % | 0.17711 | 0.12024 | 0.042243 | 0.031553 | 0.013177 | 0 | 0 | 0.30056 | 0.75102 | 0 | 0.25886 | 0.34553
O = 上週排線結果的已排線產能(因排線作業時間為五六日一，抓上一個作業區間的最新版本) | 上週產能 Last Week Plan Capacity | 47073.2467 | 54846.2067 | 53084.7858 | 54882.6383 | 53707.7033 | 50880 | 57240 | 53000 | 0 | 0 | 59025.3942 | 39355.2192
| 總產能-預估產能 | 496.8294 | 1267.8681 | 5255.61 | 2531.9903 | 986.9315 | 615.8317 | 4900 | 1120 | -13700 | -52000 | 25.3942 | -15144.7808
from Essbase 純目標產能 | 目標產能 Target Capacity | 52500 | 53000 | 49500 | 51500 | 0 | 0 | 0 | 0 | 0 |  | 54500 | 48500
| 出口/產能二維分析 | 產能月份 Month Capacity
| 出口月份 Exp Month | 9月 Sep | 10月 Oct | 11月 Nov | 12月 Dec | 1月 Jan | 2月 Feb | 3月 Mar | 4月 Apr | 5月 May | 6月 Jun | 7月 Jul | 8月 Aug
| 9月 Sep | 7105.1263 | [8 empty] | 2938.5071 | 12545.5069 | 13039.0046
| 10月 Oct | 32391.2648 | 17149.0864 | [8 empty] | 863.652 | 11057.0879
| 11月 Nov | 5890.5322 | 31033.5292 | 23072.8816 | [7 empty] | 1870.4104 | 1320.2897
| 12月 Dec | 2521.4805 | 6467.3148 | 29369.6896 | 30022.7037 | 1070.5151 | [6 empty] | 1220.94
| 1月 Jan |  | 117.9378 | 2038.5268 | 22304.4225 | 21274.573
| 2月 Feb |  |  | 274.512 | 1231.692 | 3802.0114 | 3333.6411
| 3月 Mar |  |  |  | 473.172 | 111.972 | 1186.1906
| 4月 Apr |  |  |  |  | 559.86
5月 May
| 6月 Jun | [7 empty] | 4078.1144 | 4304.2705 | 2607.1207
| 7月 Jul | [7 empty] | 12488.5934 | 22828.3167 | 37176.4264 | 17441.539
| 8月 Aug | [8 empty] | 1054.0738 | 7739.9234 | 28411.6562 | 14514.0671
| Total | 47908.4038 | 54767.8681 | 54755.61 | 54031.9903 | 26818.9315 | 4519.8317 | 0 | 16566.7078 | 28186.661 | 50461.9776 | 61132.7645 | 41151.3894

## B04_Capacity_Three_of_Month
* | 9月 上旬 | 9月 中旬 | 9月 下旬 | 10月 上旬 | 10月 中旬 | 10月 下旬 | 11月 上旬 | 11月 中旬 | 11月 下旬 | 12月 上旬 | 12月 中旬 | 12月 下旬 | 1月 上旬 | 1月 中旬 | 1月 下旬 | 2月 上旬 | 2月 中旬 | 2月 下旬 | 3月 上旬 | 3月 中旬 | 3月 下旬 | 4月 上旬 | 4月 中旬 | 4月 下旬 | 5月 上旬 | 5月 中旬 | 5月 下旬 | 6月 上旬 | 6月 中旬 | 6月 下旬 | 7月 上旬 | 7月 中旬 | 7月 下旬 | 8月 上旬 | 8月 中旬 | 8月 下旬
月份/Month | 9月Sep |  |  | 10月Oct |  |  | 11月Nov |  |  | 12月Dec |  |  | 1月Jan |  |  | 2月Feb |  |  | 3月Mar |  |  | 4月Apr |  |  | 5月May |  |  | 6月Jun |  |  | 7月Jul |  |  | 8月Aug
旬別 | 上旬 | 中旬 | 下旬 | 上旬 | 中旬 | 下旬 | 上旬 | 中旬 | 下旬 | 上旬 | 中旬 | 下旬 | 上旬 | 中旬 | 下旬 | 上旬 | 中旬 | 下旬 | 上旬 | 中旬 | 下旬 | 上旬 | 中旬 | 下旬 | 上旬 | 中旬 | 下旬 | 上旬 | 中旬 | 下旬 | 上旬 | 中旬 | 下旬 | 上旬 | 中旬 | 下旬
已排線產能 Scheduled Capacity | 16341.2725 | 13428.03 | 17727.5269 | 17788.3907 | 15680.7955 | 21298.6819 | 17873.3097 | 18311.017 | 18571.2832 | 19770.9013 | 15130.3413 | 19130.7477 | 12108.8714 | 10883.8053 | 3826.2548 | 2638.0975 | 1779.2859 | 102.4483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 20655.4175 | 18984.1775 | 19385.7992 | 14076.3525 | 13504.395 | 11774.4717
未排線產能 Unscheduled Capacity | [12 empty] | 954 | 7950 | 15264 | 14310 | 17172 | 12614 | 12720 | 12720 | 16960 | 19080 | 16960 | 19080 | 12720 | 14840 | 4240
總產能 Total Capacity | 16341.2725 | 13428.03 | 17727.5269 | 17788.3907 | 15680.7955 | 21298.6819 | 17873.3097 | 18311.017 | 18571.2832 | 19770.9013 | 15130.3413 | 19130.7477 | 13062.8714 | 18833.8053 | 19090.2548 | 16948.0975 | 18951.2859 | 12716.4483 | 12720 | 12720 | 16960 | 19080 | 16960 | 19080 | 12720 | 14840 | 4240 | 0 | 0 | 0 | 20655.4175 | 18984.1775 | 19385.7992 | 14076.3525 | 13504.395 | 11774.4717
預估產能 Estimated Capacity | 17090.9091 | 12818.1818 | 17090.9091 | 17833.3333 | 15851.8519 | 19814.8148 | 15840 | 17820 | 15840 | 17826.9231 | 15846.1538 | 17826.9231 | 12500 | 18750 | 18750 | 16695.6522 | 18782.6087 | 12521.7391 | 11250 | 11250 | 15000 | 17280 | 17280 | 19440 | 13847.8261 | 15826.087 | 15826.087 | 17333.3333 | 17333.3333 | 17333.3333 | 19666.6667 | 17481.4815 | 21851.8519 | 19075 | 19075 | 16350
出口總數 Confirmed Order | 23628.9233 | 5108.7067 | 6002.9408 | 19420.8358 | 18112.385 | 16694.0042 | 25138.4592 | 13354.0983 | 13469.7817 | 17288.9517 | 6712.6808 | 10486.8817 | 1305.28 | 2328.2 | 1876.3275
排線效率 Scheduled Efficiency | 1.5241 | 1.6481 | 1.6258 | 1.5157 | 1.4869 | 1.6069 | 1.6978 | 1.5588 | 1.7558 | 1.6858 | 1.448 | 1.6043 | 1.6485 | 1.5473 | 1.6208 | 1.6044 | 1.4973 | 1.4973 | [12 empty] | 1.8526 | 1.8658 | 1.6753 | 1.6977 | 1.565 | 1.4861
排線人數 Scheduled Sewers | 36.5312 | 36.4 | 36.8719 | 36.9035 | 36.9029 | 36.8695 | 36.7495 | 36.6755 | 36.6258 | 36.6258 | 36.6178 | 36.6167 | 36.5764 | 37.028 | 36.2446 | 36.3531 | 36.4892 | 37.8178 | [12 empty] | 36.0125 | 36.0562 | 36.565 | 36.75 | 36.5571 | 36.75
排線加班率 Scheduled OT Rate | 0.089927 | 0.10826 | 0.09816 | 0.049795 | 0.06125 | 0.068028 | 0.063813 | 0.057253 | 0.072419 | 0.056981 | 0.059689 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | 0.075 | [12 empty] | 0.14971 | 0.04795 | -0.059808 | -0.042444 | 0.0017585 | 0.067489
工作天 Working Days | 8 | 6 | 8 | 9 | 8 | 10 | 8 | 9 | 8 | 9 | 8 | 9 | 6 | 9 | 9 | 8 | 9 | 6 | 6 | 6 | 8 | 8 | 8 | 9 | 7 | 8 | 8 | 8 | 8 | 8 | 9 | 8 | 10 | 7 | 7 | 6
排線數 Lines | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 18.5 | 11.6667 | 4 | 3.125 | 2 | 0.16667 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
換款率 Turnover Rate | 0.4 | 0.25 | 1.15 | 0.55 | 0.4 | 0.25 | 0.2 | 0.4 | 0.15 | 0.45 | 0.2 | 0.1 | 0.19048 | 0.095238 | [16 empty] | 0.25 | 0.2 | 0.5 | 0.25 | 0.3 | 0.5
停工產能 Suspend Work Capacity
上週產能 Last Week Plan Capacity | 16341.2725 | 13659.6692 | 17072.305 | 17879.9425 | 15517.7825 | 21448.4817 | 16601.0358 | 18804.7917 | 17678.9583 | 19450.3483 | 16513.4833 | 18918.8067 | 14955.1433 | 19270.2033 | 19482.3567 | 19080 | 19080 | 12720 | 19080 | 19080 | 19080 | 19080 | 16960 | 16960 | 0 | 0 | 0 | 0 | 0 | 0 | 20655.4175 | 18984.1775 | 19385.7992 | 14076.3525 | 13504.395 | 11774.4717

## Production_Planning
Factory |  | Barcode Info Import Function | Version |  | Send to Manager |  | Excel版本： | 1.2.9 | Country: | ALL | Manual Data | Factory Schedule Data | Formula | System Data
[7 empty] | 組件版本： | 1.2.9 |  |  | 手動維護 | 系統資料 | 公式 | 系統帶入
[7 empty] | Lastest Version: | 1.2.9 | ReConnect:
Now is process data till row number 730 |  |  | CreateBy : GLD6ADMProduksi |  |  | IND-GLD6-2026092101
Line | BUYER | STYLE | Product Item | Special Production | Color (自選欄位1) | Shipmode (自選欄位2) | Order QTY | Allocate QTY | Barcode EQC QTY | Allocate unfinished | Alloctate Std Dz | CRFP | Cutting Date of acquistion | Sewing Start | Sewing Finish | Packing Finish | Delivery | Holiday | EFF | IE | Work HR | Sewing Workers Per Line | Daily Target | Days | Hourly Target | Garment Color | Delivery – Sewing Finish
組別 | 客戶 | 款式 | 產品 | 特工 | 顏色 | Shipmode | 訂單數 | 分配生產數(組) | 工票完成數 | 未完成 | 標打 | 可開裁日 | 開裁需求日 | 車縫上線日 | 車縫完成日 | 包裝完成日 | 交期 | 非例假 | 效率% | IE | 時數 | 人數 | 目標 | 天數 | 小時件數 | 成衣色 | 交期 – 車縫完成
2026-06-11
6-01 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 16401 | 16401 | 0 | 1899.7825 | 2026-06-03 | 2026-06-06 | 2026-06-09 | 2026-07-04 | 2026-07-06 | 2026-07-09 |  | 1.4696 | 1.39 | 9.2169 | 35.5696 | 873.476 | 18.7767 | 94.94 |  | 4
6-01 | TGT | 45M87P_C426 | Pull On Pants |  | all po |  |  | 15985 | 15985 | 0 | 2224.5792 | 2026-06-27 | 2026-06-30 | 2026-07-02 | 2026-07-27 | 2026-07-29 | 2026-08-19 |  | 1.8441 | 1.67 | 8.0771 | 37.1957 | 836.0225 | 19.1203 | 103.6922 |  | 17
6-01 | ONY | 1182430_HO26_HT | Pull On Pants |  | all po |  |  | 27270 | 27270 | 0 | 1772.55 | 2026-08-06 | 2026-07-22 | 2026-07-24 | 2026-08-31 | 2026-09-02 | 2026-09-24 |  | 1.1923 | 0.78 | 7.8679 | 37.4232 | 1134.2557 | 24.0422 | 144.4217 |  | 18
6-01 | SMA | PST840 | Pull On Pants |  | 1352813, _AH |  |  | 4108 | 4108 | 0 | 558.0033 | 2026-08-18 | 2026-08-24 | 2026-08-27 | 2026-09-09 | 2026-09-11 | 2026-09-22 |  | 1.1415 | 1.63 | 8.6104 | 36.4716 | 554.199 | 7.4125 | 64.4803 |  | 9
6-01 | SMA | PST840 | Pull On Pants |  | 1354809_SS, _AH |  |  | 79 | 79 | 0 | 10.7308 | 2026-08-18 | 2026-09-03 | 2026-09-07 | 2026-09-09 | 2026-09-11 | 2026-09-23 |  | 0.72246 | 1.63 | 9 | 37 | 371.9397 | 0.2124 | 41.4012 |  | 10
6-01 | SMA | PST840 | Pull On Pants |  | 1352814, _AH |  |  | 7938 | 6514 | 1424 | 1078.245 | 2026-08-24 | 2026-09-03 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 2026-10-02 |  | 1.79 | 1.63 | 9 | 38 | 946.4378 | 8.3872 | 105.3494 |  | 9
6-01 | SMA | PST840 | Pull On Pants |  | 1352815, _AH |  |  | 1500 | 0 | 1500 | 203.75 | 2026-09-14 | 2026-09-15 | 2026-09-17 | 2026-09-23 | 2026-09-25 | 2026-11-02 |  | 1.8 | 1.63 | 9 | 38 | 951.7252 | 1.5761 | 105.9379 |  | 33
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 750 | 0 | 750 | 105 | 2026-09-12 | 2026-09-14 | 2026-09-21 | 2026-09-29 | 2026-10-01 | 2026-10-29 |  | 0.5 | 1.68 | 7 | 38 | 199.5 | 3.7594 | 28.5514 |  | 26
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 1500 | 0 | 1500 | 210 | 2026-09-12 | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-04 | 2026-10-29 |  | 1 | 1.68 | 8.6 | 38 | 490.2 | 3.06 | 57.1028 |  | 23
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 2500 | 0 | 2500 | 350 | 2026-09-12 | 2026-09-23 | 2026-09-30 | 2026-10-08 | 2026-10-10 | 2026-10-29 |  | 1.1 | 1.68 | 8.6 | 38 | 539.22 | 4.6363 | 62.8131 |  | 18
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 3500 | 0 | 3500 | 490 | 2026-09-12 | 2026-09-30 | 2026-10-06 | 2026-10-15 | 2026-10-17 | 2026-10-29 |  | 1.2 | 1.68 | 8.6 | 38 | 588.24 | 5.95 | 68.5233 |  | 12
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 4000 | 0 | 4000 | 560 | 2026-09-12 | 2026-10-07 | 2026-10-13 | 2026-10-22 | 2026-10-24 | 2026-10-29 |  | 1.4 | 1.68 | 8.6 | 38 | 686.28 | 5.8285 | 79.9439 |  | 6
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 4000 | 0 | 4000 | 560 | 2026-09-12 | 2026-10-14 | 2026-10-20 | 2026-10-28 | 2026-10-30 | 2026-10-29 |  | 1.5 | 1.68 | 8.6 | 38 | 735.3 | 5.44 | 85.6542 |  | 1
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0130 |  |  | 4332 | 0 | 4332 | 606.48 | 2026-10-03 | 2026-10-20 | 2026-10-26 | 2026-11-04 | 2026-11-06 | 2026-11-09 |  | 1.6 | 1.68 | 8.6 | 38 | 784.32 | 5.5233 | 91.3645 |  | 4
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0213 |  |  | 4000 | 0 | 4000 | 560 | 2026-10-17 | 2026-10-27 | 2026-11-02 | 2026-11-10 | 2026-11-12 | 2026-11-23 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 4.5333 | 102.785 |  | 11
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0227 |  |  | 4452 | 0 | 4452 | 623.28 | 2026-10-31 | 2026-11-02 | 2026-11-07 | 2026-11-16 | 2026-11-18 | 2026-12-07 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 5.0456 | 102.785 |  | 18
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0313 |  |  | 10896 | 0 | 10896 | 1525.44 | 2026-10-31 | 2026-11-07 | 2026-11-13 | 2026-11-30 | 2026-12-02 | 2026-12-28 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 12.3487 | 102.785 |  | 23
6-01 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0327 |  |  | 8952 | 0 | 8952 | 1253.28 | 2026-10-31 | 2026-11-21 | 2026-11-27 | 2026-12-11 | 2026-12-13 | 2027-01-09 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 10.1455 | 102.785 |  | 22
6-01 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0321 |  |  | 716 | 0 | 716 | 115.1567 | 2026-12-04 | 2026-12-07 | 2026-12-09 | 2026-12-16 | 2026-12-18 | 2027-01-09 |  | 0.5 | 1.93 | 7 | 37.8178 | 172.8252 | 4.1429 | 24.7338 |  | 18
6-01 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0321 |  |  | 1500 | 0 | 1500 | 241.25 | 2026-12-04 | 2026-12-11 | 2026-12-14 | 2026-12-21 | 2026-12-23 | 2027-01-09 |  | 1 | 1.93 | 8.6 | 37.8178 | 424.6563 | 3.5323 | 49.4677 |  | 14
6-01 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0321 |  |  | 2500 | 0 | 2500 | 402.0833 | 2026-12-04 | 2026-12-16 | 2026-12-18 | 2026-12-28 | 2026-12-30 | 2027-01-09 |  | 1.1 | 1.93 | 8.6 | 37.8178 | 467.122 | 5.3519 | 54.4145 |  | 9
6-01 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0321 |  |  | 2700 | 0 | 2700 | 434.25 | 2026-12-04 | 2026-12-22 | 2026-12-24 | 2027-01-04 | 2027-01-06 | 2027-01-09 |  | 1.2 | 1.93 | 8.6 | 37.8178 | 509.5876 | 5.2984 | 59.3612 |  | 4
6-01 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0328 |  |  | 5022 | 0 | 5022 | 807.705 | 2026-12-04 | 2026-12-29 | 2026-12-31 | 2027-01-15 | 2027-01-17 | 2027-01-16 |  | 1.3 | 1.93 | 8.6 | 37.8178 | 552.0532 | 9.0969 | 64.308 |  | 1
6-01 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0404 |  |  | 5522 | 0 | 5522 | 888.1217 | 2026-12-11 | 2027-01-11 | 2027-01-13 | 2027-01-26 | 2027-01-28 | 2027-01-23 |  | 1.4 | 1.93 | 8.6 | 37.8178 | 594.5189 | 9.2882 | 69.2548 |  | -4
6-01 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0418 |  |  | 5022 | 0 | 5022 | 807.705 | 2026-12-26 | 2027-01-21 | 2027-01-23 | 2027-02-04 | 2027-02-06 | 2027-02-06 |  | 1.5 | 1.93 | 8.6 | 37.8178 | 636.9845 | 7.884 | 74.2015 |  | 1
6-01 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0502 |  |  | 5024 | 0 | 5024 | 808.0267 | 2027-01-08 | 2027-01-30 | 2027-02-02 | 2027-02-15 | 2027-02-17 | 2027-02-20 |  | 1.5 | 1.93 | 8.6 | 37.8178 | 636.9845 | 7.8872 | 74.2015 |  | 5
6-01 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0516 |  |  | 3767.5 | 0 | 3767.5 | 605.9396 | 2027-01-22 | 2027-02-10 | 2027-02-12 | 2027-02-22 | 2027-02-24 | 2027-03-06 |  | 1.5 | 1.93 | 8.6 | 37.8178 | 636.9845 | 5.9146 | 74.2015 |  | 11
2026-06-03
6-02 | TGT | G917K0_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 87912 | 87912 | 0 | 9157.5 | 2026-06-12 | 2026-05-23 | 2026-05-30 | 2026-08-31 | 2026-09-02 | 2026-09-05 |  | 2.0657 | 1.25 | 8.6007 | 35.7993 | 1282.2576 | 68.5603 | 149.3561 |  | 4
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014311_1219E |  |  | 2040 | 2040 | 0 | 142.8 | 2026-08-22 | 2026-08-19 | 2026-08-27 | 2026-09-02 | 2026-09-04 | 2026-09-28 |  | 0.96978 | 0.84 | 8 | 36.2304 | 843.254 | 2.4192 | 105.5968 |  | 18
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014298_SET_1212, 10002014297_T1_1212 |  |  | 33950 | 20429 | 13521 | 2376.5 | 2026-08-22 | 2026-08-21 | 2026-08-31 | 2026-09-30 | 2026-10-02 | 2026-10-01 |  | 1.74 | 0.84 | 9 | 36.2796 | 1704.4165 | 19.9188 | 189.7211 |  | 1
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014310_1219 |  |  | 2640 | 0 | 2640 | 184.8 | 2026-08-29 | 2026-09-21 | 2026-09-28 | 2026-10-02 | 2026-10-04 | 2026-10-10 |  | 1.8 | 0.84 | 8.6 | 36.2796 | 1684.8256 | 1.5669 | 196.2632 |  | 7
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014306_E_0102 |  |  | 3600 | 0 | 3600 | 252 | 2026-08-29 | 2026-09-23 | 2026-09-30 | 2026-10-05 | 2026-10-07 | 2026-10-12 |  | 1.8 | 0.84 | 8.6 | 36.2796 | 1684.8256 | 2.1367 | 196.2632 |  | 6
6-02 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014305_0102 |  |  | 4704 | 0 | 4704 | 329.28 | 2026-08-29 | 2026-09-25 | 2026-10-02 | 2026-10-08 | 2026-10-10 | 2026-10-24 |  | 1.8 | 0.84 | 8.6 | 36.2796 | 1684.8256 | 2.792 | 196.2632 |  | 14
6-02 | ONY | 1195255_SP27 | Tee |  | 62345060 |  |  | 572 | 0 | 572 | 31.46 | 2026-10-07 | 2026-10-03 | 2026-10-06 | 2026-10-09 | 2026-10-11 | 2026-11-04 |  | 0.5 | 0.66 | 7 | 36.2796 | 484.8276 | 1.1798 | 69.386 |  | 22
6-02 | ONY | 1195255_SP27 | Tee |  | 62345060 |  |  | 800 | 0 | 800 | 44 | 2026-10-07 | 2026-10-05 | 2026-10-07 | 2026-10-10 | 2026-10-12 | 2026-11-04 |  | 1 | 0.66 | 8.6 | 36.2796 | 1191.2908 | 0.67154 | 138.772 |  | 21
6-02 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 1685 | 0 | 1685 | 92.675 | 2026-10-07 | 2026-10-06 | 2026-10-08 | 2026-10-12 | 2026-10-14 | 2026-11-05 |  | 1.1 | 0.66 | 8.6 | 36.2796 | 1310.4199 | 1.2858 | 152.6492 |  | 21
6-02 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 2500 | 0 | 2500 | 137.5 | 2026-10-07 | 2026-10-07 | 2026-10-09 | 2026-10-14 | 2026-10-16 | 2026-11-05 |  | 1.2 | 0.66 | 8.6 | 36.2796 | 1429.549 | 1.7488 | 166.5264 |  | 19
6-02 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 3500 | 0 | 3500 | 192.5 | 2026-10-07 | 2026-10-09 | 2026-10-12 | 2026-10-16 | 2026-10-18 | 2026-11-05 |  | 1.4 | 0.66 | 8.6 | 36.2796 | 1667.8071 | 2.0986 | 194.2808 |  | 17
6-02 | ONY | 1194431_SP27 | Tee |  | 62315014 |  |  | 329 | 0 | 329 | 35.0933 | 2026-10-07 | 2026-10-12 | 2026-10-14 | 2026-10-17 | 2026-10-19 | 2026-10-29 |  | 0.5 | 1.28 | 7 | 36.2796 | 249.9893 | 1.3161 | 35.7771 |  | 10
6-02 | ONY | 1194431_SP27 | Tee |  | 62330730, 732, 735, 739 |  |  | 2611 | 0 | 2611 | 278.5067 | 2026-10-10 | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-10-24 | 2026-11-05 |  | 1 | 1.28 | 8.6 | 36.2796 | 614.2593 | 4.2506 | 71.5543 |  | 12
6-02 | ONY | 1194431_SP27 | Tee |  | 62326898, 440 |  |  | 271 | 0 | 271 | 28.9067 | 2026-10-10 | 2026-10-17 | 2026-10-20 | 2026-10-22 | 2026-10-24 | 2026-11-26 |  | 1.2 | 1.28 | 8.6 | 36.2796 | 737.1112 | 0.36765 | 85.8652 |  | 30
6-02 | ONY | 1194431_SP27 | Tee |  | 62330583, 585, 589, 590, 439, 441, 443, 445 |  |  | 3087 | 0 | 3087 | 329.28 | 2026-11-10 | 2026-10-17 | 2026-10-20 | 2026-10-27 | 2026-10-29 | 2026-12-03 |  | 1.4 | 1.28 | 8.6 | 36.2796 | 859.963 | 3.5897 | 100.176 |  | 32
6-02 | ONY | 1194431_SP27 | Tee |  | 62326668, 12.24 |  |  | 717 | 0 | 717 | 76.48 | 2026-11-03 | 2026-10-22 | 2026-10-24 | 2026-10-28 | 2026-10-30 | 2026-12-24 |  | 1.6 | 1.28 | 8.6 | 36.2796 | 982.8149 | 0.72954 | 114.4869 |  | 49
6-02 | ONY | 1194431_SP27 | Tee |  | 62330544, 548, 552, 556, 12.31 |  |  | 2253 | 0 | 2253 | 240.32 | 2026-11-03 | 2026-10-23 | 2026-10-26 | 2026-10-30 | 2026-11-01 | 2026-12-31 |  | 1.8 | 1.28 | 8.6 | 36.2796 | 1105.6668 | 2.0377 | 128.7977 |  | 52
6-02 | ONY | 1194431_SP27 | Tee |  | 62326618, 01.21 |  |  | 475 | 0 | 475 | 50.6667 | 2026-11-03 | 2026-10-26 | 2026-10-28 | 2026-10-30 | 2026-11-01 | 2027-01-21 |  | 1.8 | 1.28 | 8.6 | 36.2796 | 1105.6668 | 0.42961 | 128.7977 |  | 68
6-02 | ONY | 1194431_SP27 | Tee |  | 01.28 |  |  | 641 | 0 | 641 | 68.3733 | 2026-11-30 | 2026-10-26 | 2026-10-28 | 2026-10-31 | 2026-11-02 | 2027-01-28 |  | 1.8 | 1.28 | 8.6 | 36.2796 | 1105.6668 | 0.57974 | 128.7977 |  | 73
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 716 | 0 | 716 | 72.7933 | 2026-11-05 | 2026-10-27 | 2026-10-29 | 2026-11-04 | 2026-11-06 | 2026-11-30 |  | 0.5 | 1.22 | 7 | 36.2796 | 262.2838 | 2.7299 | 37.5367 |  | 22
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 1500 | 0 | 1500 | 152.5 | 2026-11-05 | 2026-10-30 | 2026-11-02 | 2026-11-06 | 2026-11-08 | 2026-11-30 |  | 1 | 1.22 | 8.6 | 36.2796 | 644.4688 | 2.3275 | 75.0734 |  | 20
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 2500 | 0 | 2500 | 254.1667 | 2026-11-05 | 2026-11-02 | 2026-11-04 | 2026-11-11 | 2026-11-13 | 2026-11-30 |  | 1.1 | 1.22 | 8.6 | 36.2796 | 708.9157 | 3.5265 | 82.5807 |  | 16
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 3500 | 0 | 3500 | 355.8333 | 2026-11-05 | 2026-11-06 | 2026-11-09 | 2026-11-17 | 2026-11-19 | 2026-11-30 |  | 1.2 | 1.22 | 8.6 | 36.2796 | 773.3625 | 4.5257 | 90.088 |  | 11
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 4500 | 0 | 4500 | 457.5 | 2026-11-05 | 2026-11-12 | 2026-11-14 | 2026-11-23 | 2026-11-25 | 2026-11-30 |  | 1.4 | 1.22 | 8.6 | 36.2796 | 902.2563 | 4.9875 | 105.1027 |  | 6
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 5000 | 0 | 5000 | 508.3333 | 2026-11-05 | 2026-11-18 | 2026-11-20 | 2026-11-28 | 2026-11-30 | 2026-12-07 |  | 1.6 | 1.22 | 8.6 | 36.2796 | 1031.1501 | 4.849 | 120.1174 |  | 7
6-02 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 9516 | 0 | 9516 | 967.46 | 2026-11-05 | 2026-11-24 | 2026-11-26 | 2026-12-08 | 2026-12-10 | 2026-12-07 |  | 1.8 | 1.22 | 8.6 | 36.2796 | 1160.0438 | 8.2031 | 135.1321 |  | -3
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-12-03 | 2026-12-05 | 2026-12-10 | 2026-12-15 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 36.2796 | 347.8111 | 2.3432 | 49.7769 |  | 12
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-12-05 | 2026-12-08 | 2026-12-12 | 2026-12-17 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 36.2796 | 854.6217 | 1.7552 | 99.5538 |  | 10
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-12-08 | 2026-12-10 | 2026-12-16 | 2026-12-21 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 36.2796 | 940.0838 | 2.6593 | 109.5092 |  | 7
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-11 | 2026-12-14 | 2026-12-19 | 2026-12-24 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 36.2796 | 1025.546 | 2.9253 | 119.4646 |  | 4
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4942 | 0 | 4942 | 378.8867 | 2026-12-07 | 2026-12-15 | 2026-12-17 | 2026-12-24 | 2026-12-29 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 36.2796 | 1111.0082 | 4.4482 | 129.42 |  | 5
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 8375 | 0 | 8375 | 642.0833 | 2026-12-07 | 2026-12-19 | 2026-12-22 | 2027-01-04 | 2027-01-09 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 36.2796 | 1196.4703 | 6.9998 | 139.3753 |  | -4
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-29 | 2026-12-31 | 2027-01-07 | 2027-01-12 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 36.2796 | 1281.9325 | 1.5009 | 149.3307 |  | 6
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-31 | 2027-01-04 | 2027-01-14 | 2027-01-19 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 36.2796 | 1281.9325 | 6.0814 | 149.3307 |  | 6
6-02 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-09 | 2027-01-12 | 2027-01-20 | 2027-01-25 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 36.2796 | 1281.9325 | 5.1555 | 149.3307 |  | 7
2026-04-17
6-03 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 29699 | 29699 | 0 | 2598.6625 | 2026-05-04 | 2026-04-13 | 2026-04-15 | 2026-05-16 | 2026-05-21 | 2026-07-23 |  | 1.6453 | 1.05 | 9.1703 | 35.9036 | 1300.1298 | 22.8431 | 142.0323 |  | 55
6-03 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 19159 | 19159 | 0 | 1676.4125 | 2026-05-23 | 2026-05-11 | 2026-05-13 | 2026-06-05 | 2026-06-10 | 2026-07-02 |  | 1.6134 | 1.05 | 9.1023 | 35.7343 | 1259.5162 | 15.2114 | 138.6222 |  | 22
6-03 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 28598 | 28598 | 0 | 3312.6017 | 2026-06-03 | 2026-05-30 | 2026-06-03 | 2026-07-09 | 2026-07-11 | 2026-07-09 |  | 1.734 | 1.39 | 9.5107 | 33.6617 | 1006.3981 | 28.4162 | 106.0086 |  | 0
6-03 | ONY | 910047_HO26DIS | Pajama |  | all po |  |  | 11308 | 11308 | 0 | 1338.1133 | 2026-07-06 | 2026-07-04 | 2026-07-07 | 2026-07-22 | 2026-07-24 | 2026-08-06 |  | 1.8663 | 1.42 | 8.4758 | 36.2794 | 1018.4268 | 11.1034 | 120.3737 |  | 13
6-03 | HLF | CPW264TL38 | Tee | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 22323 | 22323 | 0 | 1674.225 | 2026-07-10 | 2026-07-14 | 2026-07-20 | 2026-08-19 | 2026-08-21 | 2026-08-21 |  | 1.3631 | 0.9 | 7.5879 | 37.546 | 1087.3719 | 20.5293 | 143.5626 |  | 2
6-03 | SMA | ST841_FA26 | Tee |  | all po |  |  | 7230 | 7230 | 0 | 1048.35 | 2026-07-23 | 2026-08-12 | 2026-08-14 | 2026-09-14 | 2026-09-16 | 2026-09-19 |  | 0.94809 | 1.74 | 8.4122 | 36.7685 | 424.7018 | 17.0237 | 50.5776 |  | 4
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 10284 | 5744 | 4540 | 839.86 | 2026-09-07 | 2026-09-08 | 2026-09-10 | 2026-09-24 | 2026-09-29 | 2026-10-01 |  | 1.47 | 0.98 | 9 | 37.3361 | 1270.1724 | 8.0965 | 141.3848 |  | 5
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62239979, 378, 565, 268, 269 |  |  | 1503 | 0 | 1503 | 122.745 | 2026-09-07 | 2026-09-18 | 2026-09-22 | 2026-09-25 | 2026-09-30 | 2026-10-08 |  | 1.6 | 0.98 | 9 | 37.3361 | 1382.5006 | 1.0872 | 153.8882 |  | 10
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 5000 | 0 | 5000 | 408.3333 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 2026-09-30 | 2026-10-05 | 2026-10-15 |  | 1.8 | 0.98 | 9 | 37.3361 | 1555.3132 | 3.2148 | 173.1242 |  | 13
6-03 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 15960 | 0 | 15960 | 1303.4 | 2026-09-07 | 2026-09-24 | 2026-09-28 | 2026-10-13 | 2026-10-18 | 2026-10-15 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 10.7389 | 173.1242 |  | 2
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62369477, 752, 716, 717, 734, 740, 046, 049, 054, 056 |  |  | 3697 | 0 | 3697 | 301.9217 | 2026-10-10 | 2026-10-08 | 2026-10-10 | 2026-10-15 | 2026-10-20 | 2026-11-05 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 2.4876 | 173.1242 |  | 18
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62387718, 721, 722, 725, 735, 736, 742, 743 |  |  | 5239 | 0 | 5239 | 427.8517 | 2026-10-10 | 2026-10-10 | 2026-10-13 | 2026-10-20 | 2026-10-25 | 2026-11-12 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 3.5251 | 173.1242 |  | 20
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62369454, 413, 719, 720, 057, 079, 080 |  |  | 1938 | 0 | 1938 | 158.27 | 2026-11-07 | 2026-10-15 | 2026-10-17 | 2026-10-21 | 2026-10-26 | 2026-12-03 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 1.304 | 173.1242 |  | 37
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62387723, 724, 726, 727 |  |  | 1261 | 0 | 1261 | 102.9817 | 2026-11-07 | 2026-10-16 | 2026-10-19 | 2026-10-22 | 2026-10-27 | 2026-12-10 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 0.84848 | 173.1242 |  | 42
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62387728, 729 |  |  | 262 | 0 | 262 | 21.3967 | 2026-11-07 | 2026-10-17 | 2026-10-20 | 2026-10-22 | 2026-10-27 | 2026-12-31 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 0.17629 | 173.1242 |  | 59
6-03 | ONY | 1196262_SP27 | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62387730, 731, 732, 733 |  |  | 638 | 0 | 638 | 52.1033 | 2026-11-07 | 2026-10-17 | 2026-10-20 | 2026-10-22 | 2026-10-27 | 2027-01-07 |  | 1.8 | 0.98 | 8.6 | 37.3361 | 1486.1881 | 0.42929 | 173.1242 |  | 63
6-03 | ONY | 1195255_SP27 | Tee |  | 62345060 |  |  | 572 | 0 | 572 | 31.46 | 2026-10-07 | 2026-10-17 | 2026-10-20 | 2026-10-23 | 2026-10-25 | 2026-11-04 |  | 0.5 | 0.66 | 7 | 37.3361 | 498.9454 | 1.1464 | 71.4064 |  | 10
6-03 | ONY | 1195255_SP27 | Tee |  | 62345060 |  |  | 800 | 0 | 800 | 44 | 2026-10-07 | 2026-10-19 | 2026-10-21 | 2026-10-24 | 2026-10-26 | 2026-11-04 |  | 1 | 0.66 | 8.6 | 37.3361 | 1225.9801 | 0.65254 | 142.8129 |  | 9
6-03 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 1685 | 0 | 1685 | 92.675 | 2026-10-07 | 2026-10-20 | 2026-10-22 | 2026-10-26 | 2026-10-28 | 2026-11-05 |  | 1.1 | 0.66 | 8.6 | 37.3361 | 1348.5781 | 1.2495 | 157.0942 |  | 9
6-03 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 2500 | 0 | 2500 | 137.5 | 2026-10-07 | 2026-10-21 | 2026-10-23 | 2026-10-28 | 2026-10-30 | 2026-11-05 |  | 1.2 | 0.66 | 8.6 | 37.3361 | 1471.1761 | 1.6993 | 171.3755 |  | 7
6-03 | ONY | 1195255_SP27 | Tee |  | 62314846, 099, 842, 540, 613, 615, 616 |  |  | 3500 | 0 | 3500 | 192.5 | 2026-10-07 | 2026-10-23 | 2026-10-26 | 2026-10-30 | 2026-11-01 | 2026-11-05 |  | 1.4 | 0.66 | 8.6 | 37.3361 | 1716.3722 | 2.0392 | 199.938 |  | 5
6-03 | ONY | 1195255_SP27 | Tee |  | 62344872 |  |  | 484 | 0 | 484 | 26.62 | 2026-10-07 | 2026-10-26 | 2026-10-28 | 2026-10-30 | 2026-11-01 | 2026-11-11 |  | 1.4 | 0.66 | 8.6 | 37.3361 | 1716.3722 | 0.28199 | 199.938 |  | 10
6-03 | ONY | 1195255_SP27 | Tee |  | 62323334, 336, 338, 339, 843, 844 |  |  | 4076 | 0 | 4076 | 224.18 | 2026-10-07 | 2026-10-26 | 2026-10-28 | 2026-11-02 | 2026-11-04 | 2026-11-12 |  | 1.6 | 0.66 | 8.6 | 37.3361 | 1961.5682 | 2.0779 | 228.5006 |  | 9
6-03 | ONY | 1195255_SP27 | Tee |  | 62323334, 336, 338, 339, 843, 844 |  |  | 9500 | 0 | 9500 | 522.5 | 2026-10-07 | 2026-10-28 | 2026-10-30 | 2026-11-06 | 2026-11-08 | 2026-11-12 |  | 1.8 | 0.66 | 8.6 | 37.3361 | 2206.7642 | 4.3049 | 257.0632 |  | 5
6-03 | ONY | 1195255_SP27 | Tee |  | 62323824, 861 |  |  | 11020 | 0 | 11020 | 606.1 | 2026-10-07 | 2026-11-02 | 2026-11-04 | 2026-11-12 | 2026-11-14 | 2026-12-03 |  | 1.8 | 0.66 | 8.6 | 37.3361 | 2206.7642 | 4.9937 | 257.0632 |  | 18
6-03 | ONY | 1195255_SP27 | Tee |  | 62323388, 390, 392, 394, 463, 466, 468, 469, 826, 827, 862, 863 |  |  | 30372 | 0 | 30372 | 1670.46 | 2026-10-07 | 2026-11-07 | 2026-11-10 | 2026-11-28 | 2026-11-30 | 2026-12-10 |  | 1.8 | 0.66 | 8.6 | 36.8624 | 2178.7713 | 13.94 | 253.8023 |  | 10
6-03 | ONY | 1195255_SP27 | Tee |  | 12.31 |  |  | 732 | 0 | 732 | 40.26 | 2026-10-07 | 2026-11-24 | 2026-11-26 | 2026-11-28 | 2026-11-30 | 2026-12-31 |  | 1.8 | 0.66 | 8.6 | 36.8624 | 2178.7713 | 0.33597 | 253.8023 |  | 27
6-03 | ONY | 1195255_SP27 | Tee |  | 01.07 |  |  | 1709 | 0 | 1709 | 93.995 | 2026-10-07 | 2026-11-24 | 2026-11-26 | 2026-11-30 | 2026-12-02 | 2027-01-07 |  | 1.8 | 0.66 | 8.6 | 36.8624 | 2178.7713 | 0.78439 | 253.8023 |  | 30
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-11-25 | 2026-11-27 | 2026-12-02 | 2026-12-07 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 36.8624 | 353.3986 | 2.3062 | 50.5766 |  | 19
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-11-27 | 2026-11-30 | 2026-12-04 | 2026-12-09 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 36.8624 | 868.3509 | 1.7274 | 101.1531 |  | 17
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2026-12-08 | 2026-12-13 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 36.8624 | 955.186 | 2.6173 | 111.2684 |  | 14
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-03 | 2026-12-05 | 2026-12-11 | 2026-12-16 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 36.8624 | 1042.021 | 2.879 | 121.3837 |  | 11
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 3550 | 0 | 3550 | 272.1667 | 2026-12-07 | 2026-12-07 | 2026-12-09 | 2026-12-15 | 2026-12-20 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 36.8624 | 1128.8561 | 3.1448 | 131.499 |  | 13
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 5992 | 0 | 5992 | 459.3867 | 2026-12-07 | 2026-12-10 | 2026-12-12 | 2026-12-21 | 2026-12-26 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 36.8624 | 1215.6912 | 4.9289 | 141.6143 |  | 8
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 11425 | 0 | 11425 | 875.9167 | 2026-12-07 | 2026-12-16 | 2026-12-18 | 2027-01-02 | 2027-01-07 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 8.7714 | 151.7297 |  | -3
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-28 | 2026-12-30 | 2027-01-04 | 2027-01-09 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 1.4771 | 151.7297 |  | 8
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-29 | 2026-12-31 | 2027-01-12 | 2027-01-17 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 5.9853 | 151.7297 |  | 8
6-03 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-07 | 2027-01-09 | 2027-01-18 | 2027-01-23 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 5.074 | 151.7297 |  | 9
2026-04-20
6-04 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 26479 | 26479 | 0 | 2316.9125 | 2026-04-25 | 2026-04-15 | 2026-04-17 | 2026-05-19 | 2026-05-24 | 2026-06-04 |  | 1.489 | 1.05 | 8.8333 | 36.727 | 1159.316 | 22.8402 | 131.4811 |  | 12
6-04 | ONY | 915810_FA26 | Tee |  | all po |  |  | 6456 | 6456 | 0 | 634.84 | 2026-05-15 | 2026-05-13 | 2026-05-16 | 2026-06-03 | 2026-06-05 | 2026-06-11 |  | 0.8934 | 1.18 | 8.7965 | 36.3618 | 610.2657 | 10.579 | 69.5009 |  | 7
6-04 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 18832 | 18832 | 0 | 2181.3733 | 2026-06-03 | 2026-05-28 | 2026-05-30 | 2026-07-01 | 2026-07-03 | 2026-07-09 |  | 1.4109 | 1.39 | 9.1249 | 34.9781 | 816.4257 | 23.0664 | 89.6341 |  | 7
6-04 | ONY | 915810_FA26 | Tee |  | all po |  |  | 3182 | 3182 | 0 | 312.8967 | 2026-06-04 | 2026-06-26 | 2026-06-29 | 2026-07-07 | 2026-07-09 | 2026-07-09 |  | 0.99489 | 1.18 | 7.7074 | 36.4515 | 596.92 | 5.3307 | 77.5873 |  | 2
6-04 | ONY | 766362_HO26 | Pull On Pants |  | all po |  |  | 24434 | 24434 | 0 | 1751.1033 | 2026-07-09 | 2026-07-02 | 2026-07-04 | 2026-07-30 | 2026-08-01 | 2026-08-06 |  | 1.3668 | 0.86 | 8.2229 | 37.6497 | 1239.9326 | 19.7059 | 151.0617 |  | 6
6-04 | HLF | CPM263TL32_26Q4 | Tee | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 12021 | 12021 | 0 | 901.575 | 2026-07-10 | 2026-07-22 | 2026-07-28 | 2026-08-13 | 2026-08-15 | 2026-08-21 |  | 1.3542 | 0.9 | 7.4953 | 37.7324 | 1072.3844 | 11.2096 | 143.3328 |  | 5
6-04 | ONY | 766362_HO26 | Pull On Pants |  | all po |  |  | 27675 | 27442 | 233 | 1983.375 | 2026-08-18 | 2026-08-07 | 2026-08-11 | 2026-09-08 | 2026-09-10 | 2026-12-17 |  | 1.7 | 0.86 | 9 | 38 | 1703.6372 | 16.2447 | 189.6344 |  | 83
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62047538 |  |  | 855 | 842 | 13 | 61.275 | 2026-05-22 | 2026-09-02 | 2026-09-04 | 2026-09-09 | 2026-09-11 | 2026-10-29 |  | 1.7 | 0.86 | 9 | 38 | 1703.6372 | 0.50187 | 189.6344 |  | 40
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004922_T1_W |  |  | 720 | 720 | 0 | 63.6 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-11 | 2026-09-13 | 2026-10-01 |  | 0.63617 | 1.06 | 8 | 37.2693 | 450.9301 | 1.5967 | 56.4679 |  | 14
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 11000 | 7114 | 3886 | 971.6667 | 2026-08-24 | 2026-09-02 | 2026-09-09 | 2026-09-24 | 2026-09-26 | 2026-10-08 |  | 1.45 | 1.06 | 9 | 37.4565 | 1162.0699 | 9.4659 | 129.3517 |  | 11
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 5000 | 0 | 5000 | 441.6667 | 2026-08-24 | 2026-09-15 | 2026-09-22 | 2026-09-30 | 2026-10-02 | 2026-10-08 |  | 1.6 | 1.06 | 9 | 38 | 1300.8906 | 3.8435 | 144.804 |  | 7
6-04 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 3577 | 0 | 3577 | 315.9683 | 2026-08-24 | 2026-09-21 | 2026-09-28 | 2026-10-03 | 2026-10-05 | 2026-10-08 |  | 1.8 | 1.06 | 8.6 | 38 | 1398.4574 | 2.5578 | 162.9045 |  | 4
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62047538 |  |  | 750 | 0 | 750 | 53.75 | 2026-05-22 | 2026-09-29 | 2026-10-01 | 2026-10-06 | 2026-10-08 | 2026-10-29 |  | 0.5 | 0.86 | 7 | 38 | 389.7209 | 1.9245 | 55.7748 |  | 20
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62047538 |  |  | 1582 | 0 | 1582 | 113.3767 | 2026-05-22 | 2026-10-01 | 2026-10-03 | 2026-10-08 | 2026-10-10 | 2026-10-29 |  | 1 | 0.86 | 8.6 | 38 | 957.6 | 1.652 | 111.5496 |  | 18
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62047539, 028, 030, 031, 121 |  |  | 2500 | 0 | 2500 | 179.1667 | 2026-05-22 | 2026-10-03 | 2026-10-06 | 2026-10-10 | 2026-10-12 | 2026-11-05 |  | 1.2 | 0.86 | 8.6 | 38 | 1149.12 | 2.1756 | 133.8596 |  | 22
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62047539, 028, 030, 031, 121 |  |  | 2915 | 0 | 2915 | 208.9083 | 2026-05-22 | 2026-10-06 | 2026-10-08 | 2026-10-13 | 2026-10-15 | 2026-11-05 |  | 1.4 | 0.86 | 8.6 | 38 | 1340.64 | 2.1743 | 156.1695 |  | 20
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62047539, 028, 030, 031, 121 |  |  | 3500 | 0 | 3500 | 250.8333 | 2026-05-22 | 2026-10-08 | 2026-10-10 | 2026-10-15 | 2026-10-17 | 2026-11-05 |  | 1.6 | 0.86 | 8.6 | 38 | 1532.16 | 2.2844 | 178.4794 |  | 18
6-04 | ONY | 766362_V1 | Pull On Pants |  | 62047540, 029, 123, 124 |  |  | 6422 | 0 | 6422 | 460.2433 | 2026-05-22 | 2026-10-10 | 2026-10-13 | 2026-10-20 | 2026-10-22 | 2026-11-12 |  | 1.7 | 0.86 | 8.6 | 38 | 1627.92 | 3.9449 | 189.6344 |  | 20
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 960 | 0 | 960 | 25.6 | 2026-10-12 | 2026-10-15 | 2026-10-17 | 2026-10-21 | 2026-10-23 | 2026-11-02 |  | 0.5 | 0.32 | 7 | 38 | 1047.375 | 0.91658 | 149.8948 |  | 10
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 1500 | 0 | 1500 | 40 | 2026-10-12 | 2026-10-16 | 2026-10-19 | 2026-10-22 | 2026-10-24 | 2026-11-02 |  | 1 | 0.32 | 8.6 | 38 | 2573.55 | 0.58285 | 299.7896 |  | 9
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 2500 | 0 | 2500 | 66.6667 | 2026-10-12 | 2026-10-17 | 2026-10-20 | 2026-10-23 | 2026-10-25 | 2026-11-02 |  | 1.1 | 0.32 | 8.6 | 38 | 2830.905 | 0.88311 | 329.7686 |  | 8
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 3500 | 0 | 3500 | 93.3333 | 2026-10-12 | 2026-10-19 | 2026-10-21 | 2026-10-24 | 2026-10-26 | 2026-11-02 |  | 1.2 | 0.32 | 8.6 | 38 | 3088.26 | 1.1333 | 359.7475 |  | 7
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 4500 | 0 | 4500 | 120 | 2026-10-12 | 2026-10-20 | 2026-10-22 | 2026-10-26 | 2026-10-28 | 2026-11-02 |  | 1.3 | 0.32 | 8.6 | 38 | 3345.615 | 1.345 | 389.7265 |  | 6
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0130_W |  |  | 1044 | 0 | 1044 | 27.84 | 2026-10-20 | 2026-10-21 | 2026-10-23 | 2026-10-26 | 2026-10-28 | 2026-11-11 |  | 1.4 | 0.32 | 8.6 | 38 | 3602.97 | 0.28976 | 419.7055 |  | 14
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 5000 | 0 | 5000 | 133.3333 | 2026-10-12 | 2026-10-21 | 2026-10-23 | 2026-10-27 | 2026-10-29 | 2026-11-12 |  | 1.6 | 0.32 | 8.6 | 38 | 4117.68 | 1.2143 | 479.6634 |  | 14
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 7000 | 0 | 7000 | 186.6667 | 2026-10-12 | 2026-10-22 | 2026-10-24 | 2026-10-29 | 2026-10-31 | 2026-11-12 |  | 1.8 | 0.32 | 8.6 | 38 | 4632.39 | 1.5111 | 539.6213 |  | 12
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 31180 | 0 | 31180 | 831.4667 | 2026-10-12 | 2026-10-24 | 2026-10-27 | 2026-11-05 | 2026-11-07 | 2026-11-12 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 6.0578 | 599.5792 |  | 6
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0213_W |  |  | 9108 | 0 | 9108 | 242.88 | 2026-10-20 | 2026-10-31 | 2026-11-03 | 2026-11-07 | 2026-11-09 | 2026-11-25 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7695 | 599.5792 |  | 15
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0220_W |  |  | 8892 | 0 | 8892 | 237.12 | 2026-10-27 | 2026-11-03 | 2026-11-05 | 2026-11-10 | 2026-11-12 | 2026-12-02 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7276 | 599.5792 |  | 19
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0227_W |  |  | 8892 | 0 | 8892 | 237.12 | 2026-10-27 | 2026-11-05 | 2026-11-07 | 2026-11-12 | 2026-11-14 | 2026-12-09 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7276 | 599.5792 |  | 23
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0306_W |  |  | 8892 | 0 | 8892 | 237.12 | 2026-10-27 | 2026-11-07 | 2026-11-10 | 2026-11-14 | 2026-11-16 | 2026-12-16 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7276 | 599.5792 |  | 27
6-04 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0313_W |  |  | 8892 | 0 | 8892 | 237.12 | 2026-10-27 | 2026-11-10 | 2026-11-12 | 2026-11-17 | 2026-11-19 | 2026-12-23 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7276 | 599.5792 |  | 31
6-04 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 1500 | 0 | 1500 | 52.5 | 2026-11-13 | 2026-11-12 | 2026-11-14 | 2026-11-18 | 2026-11-20 | 2026-11-27 |  | 1.5 | 0.42 | 7 | 38 | 2394 | 0.62657 | 342.6167 |  | 8
6-04 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 3500 | 0 | 3500 | 122.5 | 2026-11-13 | 2026-11-13 | 2026-11-16 | 2026-11-19 | 2026-11-21 | 2026-11-27 |  | 1.8 | 0.42 | 8.6 | 38 | 3529.44 | 0.99166 | 411.1401 |  | 7
6-04 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 25000 | 0 | 25000 | 875 | 2026-11-13 | 2026-11-14 | 2026-11-17 | 2026-11-26 | 2026-11-28 | 2026-11-27 |  | 2 | 0.42 | 8.6 | 38 | 3921.6 | 6.3749 | 456.8223 |  | 1
6-04 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_W |  |  | 35000 | 0 | 35000 | 1225 | 2026-11-13 | 2026-11-21 | 2026-11-24 | 2026-12-07 | 2026-12-09 | 2026-12-08 |  | 2 | 0.42 | 8.6 | 38 | 3921.6 | 8.9249 | 456.8223 |  | 1
6-04 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0314_W |  |  | 10000 | 0 | 10000 | 350 | 2026-11-13 | 2026-12-02 | 2026-12-04 | 2026-12-10 | 2026-12-12 | 2026-12-11 |  | 2 | 0.42 | 8.6 | 38 | 3921.6 | 2.55 | 456.8223 |  | 1
6-04 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0328_W |  |  | 26640 | 0 | 26640 | 932.4 | 2026-12-11 | 2026-12-05 | 2026-12-08 | 2026-12-18 | 2026-12-20 | 2026-12-24 |  | 2 | 0.42 | 8.6 | 38 | 3921.6 | 6.7931 | 456.8223 |  | 5
6-04 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0411_W |  |  | 26640 | 0 | 26640 | 932.4 | 2026-12-11 | 2026-12-14 | 2026-12-16 | 2026-12-28 | 2026-12-30 | 2027-01-08 |  | 2 | 0.42 | 8.6 | 38 | 3921.6 | 6.7931 | 456.8223 |  | 8
6-04 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0418_W |  |  | 26640 | 0 | 26640 | 932.4 | 2027-01-08 | 2026-12-22 | 2026-12-24 | 2027-01-07 | 2027-01-09 | 2027-01-15 |  | 2 | 0.42 | 8.6 | 38 | 3921.6 | 6.7931 | 456.8223 |  | 7
2026-04-02
6-05 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 56118 | 56118 | 0 | 4910.325 | 2026-05-07 | 2026-03-28 | 2026-03-31 | 2026-05-29 | 2026-06-03 | 2026-07-30 |  | 1.6939 | 1.05 | 8.9946 | 34.4529 | 1259.8102 | 44.5448 | 140.3152 |  | 51
6-05 | WMT | HQ263487_FA26 | Pull On Pants |  | all po |  |  | 20277 | 20277 | 0 | 1436.2875 | 2026-05-21 | 2026-05-23 | 2026-05-26 | 2026-06-18 | 2026-06-20 | 2026-06-27 |  | 1.4761 | 0.85 | 9.1873 | 32.7131 | 1315.2706 | 15.4166 | 143.4206 |  | 8
6-05 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 31058 | 31058 | 0 | 2717.575 | 2026-05-26 | 2026-06-12 | 2026-06-15 | 2026-07-14 | 2026-07-19 | 2026-07-16 |  | 1.7623 | 1.05 | 9.1485 | 36.1574 | 1399.0404 | 22.1995 | 153.2011 |  | 2
6-05 | TGT | 5GK4L2_C426 | Jumper |  | all po |  |  | 2892 | 2892 | 0 | 383.19 | 2026-07-03 | 2026-07-09 | 2026-07-11 | 2026-07-22 | 2026-07-24 | 2026-08-21 |  | 0.91766 | 1.59 | 7.5859 | 35.6461 | 393.2819 | 7.3535 | 51.9374 |  | 23
6-05 | ONY | 1184404_HO26 | Tee |  | all po |  |  | 5350 | 5350 | 0 | 347.75 | 2026-07-13 | 2026-07-17 | 2026-07-20 | 2026-07-31 | 2026-08-02 | 2026-08-13 |  | 0.85133 | 0.78 | 6.9853 | 34.9478 | 671.4355 | 7.968 | 96.2951 |  | 10
6-05 | HLF | CPW264TL38 | Tee | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 17942 | 17942 | 0 | 1345.65 | 2026-07-10 | 2026-07-23 | 2026-07-29 | 2026-08-21 | 2026-08-23 | 2026-08-21 |  | 1.5414 | 0.9 | 7.746 | 34.9112 | 1167.0888 | 15.3733 | 150.9414 |  | 0
6-05 | SMA | LPST840 | Pull On Pants |  | 1352772, _AH |  |  | 4836 | 4836 | 0 | 596.44 | 2026-08-18 | 2026-08-14 | 2026-08-19 | 2026-09-03 | 2026-09-05 | 2026-09-22 |  | 1.1327 | 1.48 | 8.586 | 35.7551 | 592.0812 | 8.1678 | 69.0835 |  | 13
6-05 | SMA | LPST840 | Pull On Pants |  | 1354810_SS, _AH |  |  | 79 | 79 | 0 | 9.7433 | 2026-08-18 | 2026-08-28 | 2026-09-01 | 2026-09-03 | 2026-09-05 | 2026-09-23 |  | 0.32267 | 1.48 | 9 | 36 | 178.0081 | 0.4438 | 19.8143 |  | 14
6-05 | SMA | LPST840 | Pull On Pants |  | 1352773, _AH |  |  | 3544 | 3544 | 0 | 437.0933 | 2026-08-24 | 2026-08-28 | 2026-09-01 | 2026-09-11 | 2026-09-13 | 2026-10-02 |  | 1.1538 | 1.48 | 8.2517 | 36.0829 | 584.9533 | 6.0586 | 71.0167 |  | 15
6-05 | TGT | 5GK4L2_C127 | Jumper |  | 10002064559_0110 |  |  | 3135 | 2592 | 543 | 415.3875 | 2026-09-10 | 2026-09-07 | 2026-09-09 | 2026-09-21 | 2026-09-23 | 2026-10-10 |  | 1.03 | 1.59 | 9 | 35 | 514.2226 | 6.0966 | 57.2389 |  | 16
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 795 | 0 | 795 | 113.95 | 2026-09-21 | 2026-09-10 | 2026-09-17 | 2026-09-25 | 2026-09-27 | 2026-11-02 |  | 0.5 | 1.72 | 7 | 35 | 179.4767 | 4.4295 | 25.6858 |  | 31
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 1500 | 0 | 1500 | 215 | 2026-09-21 | 2026-09-16 | 2026-09-23 | 2026-09-30 | 2026-10-02 | 2026-11-02 |  | 1 | 1.72 | 8.6 | 35 | 441 | 3.4014 | 51.3715 |  | 28
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 2500 | 0 | 2500 | 358.3333 | 2026-09-21 | 2026-09-21 | 2026-09-28 | 2026-10-06 | 2026-10-08 | 2026-11-02 |  | 1.1 | 1.72 | 8.6 | 35 | 485.1 | 5.1536 | 56.5087 |  | 23
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 3000 | 0 | 3000 | 430 | 2026-09-21 | 2026-09-28 | 2026-10-03 | 2026-10-13 | 2026-10-15 | 2026-11-02 |  | 1.2 | 1.72 | 8.6 | 35 | 529.2 | 5.6689 | 61.6458 |  | 17
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 3200 | 0 | 3200 | 458.6667 | 2026-09-21 | 2026-10-05 | 2026-10-10 | 2026-10-19 | 2026-10-21 | 2026-11-02 |  | 1.4 | 1.72 | 8.6 | 35 | 617.4 | 5.183 | 71.9202 |  | 12
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 6500 | 0 | 6500 | 931.6667 | 2026-09-21 | 2026-10-10 | 2026-10-16 | 2026-10-30 | 2026-11-01 | 2026-11-02 |  | 1.5 | 1.72 | 8.6 | 35 | 661.5 | 9.8262 | 77.0573 |  | 2
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041497 |  |  | 2994 | 0 | 2994 | 429.14 | 2026-10-19 | 2026-10-22 | 2026-10-28 | 2026-11-05 | 2026-11-07 | 2026-11-16 |  | 1.5 | 1.72 | 8.6 | 35 | 661.5 | 4.5261 | 77.0573 |  | 9
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041486 |  |  | 3318 | 0 | 3318 | 475.58 | 2026-10-19 | 2026-10-28 | 2026-11-03 | 2026-11-11 | 2026-11-13 | 2026-11-30 |  | 1.5 | 1.72 | 8.6 | 35 | 661.5 | 5.0159 | 77.0573 |  | 16
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041480 |  |  | 5556 | 0 | 5556 | 796.36 | 2026-11-02 | 2026-11-03 | 2026-11-09 | 2026-11-19 | 2026-11-21 | 2026-12-14 |  | 1.8 | 1.72 | 8.6 | 35 | 793.8 | 6.9992 | 92.4688 |  | 21
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041498 |  |  | 2874 | 0 | 2874 | 411.94 | 2026-11-02 | 2026-11-11 | 2026-11-17 | 2026-11-24 | 2026-11-26 | 2026-12-28 |  | 1.8 | 1.72 | 8.6 | 35 | 793.8 | 3.6206 | 92.4688 |  | 28
6-05 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041488 |  |  | 996 | 0 | 996 | 142.76 | 2026-11-02 | 2026-11-16 | 2026-11-21 | 2026-11-25 | 2026-11-27 | 2027-01-11 |  | 1.8 | 1.72 | 8.6 | 35 | 793.8 | 1.2547 | 92.4688 |  | 37
6-05 | TGT | 6ZE54X_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0321 |  |  | 7988 | 0 | 7988 | 1144.9467 | 2026-11-23 | 2026-11-17 | 2026-11-23 | 2026-12-07 | 2026-12-09 | 2027-01-02 |  | 1.8 | 1.72 | 8.6 | 35 | 793.8 | 10.063 | 92.4688 |  | 21
6-05 | TGT | 6ZE54X_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0328 |  |  | 7947 | 0 | 7947 | 1139.07 | 2026-12-07 | 2026-11-28 | 2026-12-04 | 2026-12-18 | 2026-12-20 | 2027-01-05 |  | 1.8 | 1.72 | 8.6 | 35 | 793.8 | 10.0113 | 92.4688 |  | 12
6-05 | TGT | 6ZE54X_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0404 |  |  | 7947 | 0 | 7947 | 1139.07 | 2026-12-21 | 2026-12-10 | 2026-12-16 | 2026-12-31 | 2027-01-02 | 2027-01-12 |  | 1.8 | 1.72 | 8.6 | 35 | 793.8 | 10.0113 | 92.4688 |  | 8
6-05 | TGT | 6ZE54X_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0418 |  |  | 7947 | 0 | 7947 | 1139.07 | 2026-12-21 | 2026-12-22 | 2026-12-29 | 2027-01-14 | 2027-01-16 | 2027-01-26 |  | 1.8 | 1.72 | 8.6 | 35 | 793.8 | 10.0113 | 92.4688 |  | 10
6-05 | TGT | 6ZE54X_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0502 |  |  | 7947 | 0 | 7947 | 1139.07 | 2027-01-04 | 2027-01-06 | 2027-01-12 | 2027-01-26 | 2027-01-28 | 2027-02-09 |  | 1.8 | 1.72 | 8.6 | 35 | 793.8 | 10.0113 | 92.4688 |  | 11
6-05 | TGT | 6ZE54X_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0516 |  |  | 5963 | 0 | 5963 | 854.6967 | 2027-01-11 | 2027-01-18 | 2027-01-23 | 2027-02-04 | 2027-02-06 | 2027-02-23 |  | 1.8 | 1.72 | 8.6 | 35 | 793.8 | 7.512 | 92.4688 |  | 15
2026-04-10
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 24866 | 24866 | 0 | 2175.775 | 2026-04-13 | 2026-04-06 | 2026-04-08 | 2026-05-05 | 2026-05-10 | 2026-06-25 |  | 1.592 | 1.05 | 8.7258 | 36.5651 | 1219.0291 | 20.3982 | 139.9557 |  | 40
6-06 | ONY | 890955_FA26 | Pull On Pants |  | all po |  |  | 7023 | 7023 | 0 | 550.135 | 2026-04-30 | 2026-04-29 | 2026-05-02 | 2026-05-13 | 2026-05-15 | 2026-06-04 |  | 1.2371 | 0.94 | 8.5835 | 36.7291 | 1045.603 | 6.7167 | 122.0354 |  | 16
6-06 | ONY | 905200_FA26 | Pull On Pants |  | all po |  |  | 26558 | 26558 | 0 | 2478.7467 | 2026-05-02 | 2026-05-08 | 2026-05-11 | 2026-06-15 | 2026-06-17 | 2026-06-11 |  | 1.3726 | 1.12 | 9.4741 | 36.0936 | 1056.0642 | 25.1481 | 111.6698 |  | -5
6-06 | ONY | 890955_FA26 | Pull On Pants |  | all po |  |  | 3293 | 3293 | 0 | 257.9517 | 2026-04-13 | 2026-06-10 | 2026-06-12 | 2026-06-19 | 2026-06-21 | 2026-07-16 |  | 1.2036 | 0.94 | 9.4007 | 36.6757 | 1112.5004 | 2.96 | 118.5556 |  | 23
6-06 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 25055 | 25055 | 0 | 2192.3125 | 2026-05-26 | 2026-06-13 | 2026-06-17 | 2026-07-09 | 2026-07-14 | 2026-07-16 |  | 1.9617 | 1.05 | 9.4584 | 33.9307 | 1510.9939 | 16.5818 | 160.0393 |  | 6
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 29586 | 29586 | 0 | 2588.775 | 2026-06-23 | 2026-07-04 | 2026-07-07 | 2026-08-03 | 2026-08-08 | 2026-09-24 |  | 1.9974 | 1.05 | 8.1876 | 36.0189 | 1413.7104 | 20.9279 | 172.977 |  | 36
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 38318 | 38318 | 0 | 3352.825 | 2026-08-01 | 2026-07-29 | 2026-07-31 | 2026-09-08 | 2026-09-13 | 2026-10-15 |  | 2.1642 | 1.05 | 8.4213 | 36.4061 | 1592.4221 | 24.0627 | 189.4351 |  | 29
6-06 | ONY | 777362_HO26_GLD | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 62212924, 927, 931, 933 |  |  | 6683 | 6081 | 602 | 584.7625 | 2026-08-29 | 2026-09-02 | 2026-09-04 | 2026-09-14 | 2026-09-19 | 2026-09-24 |  | 2.01 | 1.05 | 9 | 36.8624 | 1600.4197 | 4.1758 | 178.1451 |  | 8
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 21000 | 8338 | 12662 | 1837.5 | 2026-08-01 | 2026-09-08 | 2026-09-10 | 2026-09-30 | 2026-10-05 | 2026-10-15 |  | 2.19 | 1.05 | 9 | 36.8624 | 1743.7409 | 12.0431 | 194.0984 |  | 13
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 13880 | 0 | 13880 | 1214.5 | 2026-08-01 | 2026-09-24 | 2026-09-28 | 2026-10-09 | 2026-10-14 | 2026-10-15 |  | 2.2 | 1.05 | 8.6 | 36.8624 | 1673.8497 | 8.2923 | 194.9847 |  | 5
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.29 |  |  | 165 | 0 | 165 | 14.4375 | 2026-08-18 | 2026-10-05 | 2026-10-07 | 2026-10-09 | 2026-10-14 | 2026-10-29 |  | 2.2 | 1.05 | 8.6 | 36.8624 | 1673.8497 | 0.098575 | 194.9847 |  | 17
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 11.12 |  |  | 4477 | 0 | 4477 | 391.7375 | 2026-08-20 | 2026-10-05 | 2026-10-07 | 2026-10-13 | 2026-10-18 | 2026-11-12 |  | 2.2 | 1.05 | 8.6 | 36.8624 | 1673.8497 | 2.6747 | 194.9847 |  | 26
6-06 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 11.26 |  |  | 165 | 0 | 165 | 14.4375 | 2026-08-20 | 2026-10-08 | 2026-10-10 | 2026-10-13 | 2026-10-18 | 2026-11-26 |  | 2.2 | 1.05 | 8.6 | 36.8624 | 1673.8497 | 0.098575 | 194.9847 |  | 38
6-06 | ONY | 1204591_SP27_ID | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 62523441, 442, 443 |  |  | 750 | 0 | 750 | 80 | 2026-10-12 | 2026-10-08 | 2026-10-10 | 2026-10-16 | 2026-10-21 | 2026-11-06 |  | 0.5 | 1.28 | 7 | 36.8624 | 254.0053 | 2.9527 | 36.3519 |  | 18
6-06 | ONY | 1204591_SP27_ID | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 62523441, 442, 443 |  |  | 1750 | 0 | 1750 | 186.6667 | 2026-10-12 | 2026-10-12 | 2026-10-14 | 2026-10-20 | 2026-10-25 | 2026-11-06 |  | 1 | 1.28 | 8.6 | 36.8624 | 624.1272 | 2.8039 | 72.7038 |  | 15
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 720 | 0 | 720 | 43.2 | 2026-10-15 | 2026-10-15 | 2026-10-17 | 2026-10-22 | 2026-10-24 | 2026-11-06 |  | 0.5 | 0.72 | 7 | 36.8624 | 451.5649 | 1.5945 | 64.6256 |  | 13
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 1500 | 0 | 1500 | 90 | 2026-10-15 | 2026-10-17 | 2026-10-20 | 2026-10-23 | 2026-10-25 | 2026-11-06 |  | 1 | 0.72 | 8.6 | 36.8624 | 1109.5594 | 1.3519 | 129.2512 |  | 12
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 2000 | 0 | 2000 | 120 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 2026-10-26 | 2026-10-28 | 2026-11-06 |  | 1.2 | 0.72 | 8.6 | 36.8624 | 1331.4713 | 1.5021 | 155.1014 |  | 10
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 3000 | 0 | 3000 | 180 | 2026-10-15 | 2026-10-21 | 2026-10-23 | 2026-10-28 | 2026-10-30 | 2026-11-06 |  | 1.4 | 0.72 | 8.6 | 36.8624 | 1553.3832 | 1.9313 | 180.9517 |  | 8
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 4000 | 0 | 4000 | 240 | 2026-10-15 | 2026-10-23 | 2026-10-26 | 2026-10-30 | 2026-11-01 | 2026-11-06 |  | 1.6 | 0.72 | 8.6 | 36.8624 | 1775.2951 | 2.2531 | 206.8019 |  | 6
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 5000 | 0 | 5000 | 300 | 2026-10-15 | 2026-10-26 | 2026-10-28 | 2026-11-03 | 2026-11-05 | 2026-11-06 |  | 1.8 | 0.72 | 8.6 | 36.8624 | 1997.207 | 2.5035 | 232.6521 |  | 3
6-06 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 5000 | 0 | 5000 | 300 | 2026-10-15 | 2026-10-29 | 2026-10-31 | 2026-11-05 | 2026-11-07 | 2026-11-06 |  | 2 | 0.72 | 8.6 | 36.8624 | 2219.1189 | 2.2531 | 258.5024 |  | 1
6-06 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 728 | 0 | 728 | 57.0267 | 2026-11-09 | 2026-10-28 | 2026-11-03 | 2026-11-07 | 2026-11-09 | 2026-12-03 |  | 0.5 | 0.94 | 7 | 36.8624 | 345.8795 | 2.1048 | 49.5005 |  | 22
6-06 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 1500 | 0 | 1500 | 117.5 | 2026-11-09 | 2026-10-30 | 2026-11-05 | 2026-11-10 | 2026-11-12 | 2026-12-03 |  | 1 | 0.94 | 8.6 | 36.8624 | 849.8753 | 1.765 | 99.0009 |  | 20
6-06 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 2500 | 0 | 2500 | 195.8333 | 2026-11-09 | 2026-11-02 | 2026-11-07 | 2026-11-13 | 2026-11-15 | 2026-12-03 |  | 1.1 | 0.94 | 8.6 | 36.8624 | 934.8629 | 2.6742 | 108.901 |  | 17
6-06 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 3500 | 0 | 3500 | 274.1667 | 2026-11-09 | 2026-11-05 | 2026-11-11 | 2026-11-17 | 2026-11-19 | 2026-12-03 |  | 1.2 | 0.94 | 8.6 | 36.8624 | 1019.8504 | 3.4319 | 118.8011 |  | 14
6-06 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 5300 | 0 | 5300 | 415.1667 | 2026-11-09 | 2026-11-09 | 2026-11-14 | 2026-11-21 | 2026-11-23 | 2026-12-03 |  | 1.4 | 0.94 | 8.6 | 36.8624 | 1189.8254 | 4.4544 | 138.6013 |  | 10
6-06 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1210, 4500041655_BJSHVS_1210, 4500041655_BJSHVS_HTR_1210, 4500041657_HTR_1210 |  |  | 5000 | 0 | 5000 | 391.6667 | 2026-11-09 | 2026-11-13 | 2026-11-19 | 2026-11-26 | 2026-11-28 | 2026-12-10 |  | 1.6 | 0.94 | 8.6 | 36.8624 | 1359.8005 | 3.677 | 158.4015 |  | 12
6-06 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1210, 4500041655_BJSHVS_1210, 4500041655_BJSHVS_HTR_1210, 4500041657_HTR_1210 |  |  | 10484 | 0 | 10484 | 821.2467 | 2026-11-09 | 2026-11-18 | 2026-11-24 | 2026-12-04 | 2026-12-06 | 2026-12-10 |  | 1.8 | 0.94 | 8.6 | 36.8624 | 1529.7756 | 6.8533 | 178.2016 |  | 5
6-06 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-11-30 | 2026-12-02 | 2026-12-07 | 2026-12-12 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 36.8624 | 353.3986 | 2.3062 | 50.5766 |  | 15
6-06 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-12-02 | 2026-12-04 | 2026-12-09 | 2026-12-14 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 36.8624 | 868.3509 | 1.7274 | 101.1531 |  | 13
6-06 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-12-04 | 2026-12-07 | 2026-12-12 | 2026-12-17 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 36.8624 | 955.186 | 2.6173 | 111.2684 |  | 10
6-06 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-08 | 2026-12-10 | 2026-12-16 | 2026-12-21 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 36.8624 | 1042.021 | 2.879 | 121.3837 |  | 7
6-06 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4042 | 0 | 4042 | 309.8867 | 2026-12-07 | 2026-12-11 | 2026-12-14 | 2026-12-21 | 2026-12-26 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 36.8624 | 1128.8561 | 3.5806 | 131.499 |  | 8
6-06 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4000 | 0 | 4000 | 306.6667 | 2026-12-07 | 2026-12-16 | 2026-12-18 | 2026-12-24 | 2026-12-29 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 36.8624 | 1215.6912 | 3.2903 | 141.6143 |  | 5
6-06 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 9415 | 0 | 9415 | 721.8167 | 2026-12-07 | 2026-12-19 | 2026-12-22 | 2027-01-04 | 2027-01-09 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 7.2283 | 151.7297 |  | -4
6-06 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-29 | 2026-12-31 | 2027-01-06 | 2027-01-11 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 1.4771 | 151.7297 |  | 7
6-06 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-30 | 2027-01-02 | 2027-01-13 | 2027-01-18 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 5.9853 | 151.7297 |  | 7
6-06 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-08 | 2027-01-11 | 2027-01-19 | 2027-01-24 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 36.8624 | 1302.5263 | 5.074 | 151.7297 |  | 8
2026-06-05
6-07 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 24374 | 24374 | 0 | 2823.3217 | 2026-06-03 | 2026-05-30 | 2026-06-03 | 2026-07-09 | 2026-07-11 | 2026-07-09 |  | 1.4647 | 1.39 | 9.211 | 35.496 | 868.1993 | 28.0742 | 94.4264 |  | 0
6-07 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 11906 | 11906 | 0 | 1041.775 | 2026-05-07 | 2026-07-04 | 2026-07-07 | 2026-07-23 | 2026-07-28 | 2026-07-30 |  | 1.5471 | 1.05 | 8.2762 | 33.6826 | 1035.0792 | 11.5025 | 125.2931 |  | 6
6-07 | HLF | CPM263PA05_26Q4 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 17364 | 17364 | 0 | 1750.87 | 2026-07-10 | 2026-07-15 | 2026-07-21 | 2026-08-24 | 2026-08-26 | 2026-08-21 |  | 1.304 | 1.21 | 7.6793 | 36.2259 | 755.5279 | 22.9826 | 98.5623 |  | -3
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014226_TRN |  |  | 2160 | 2160 | 0 | 129.6 | 2026-08-15 | 2026-08-12 | 2026-08-20 | 2026-08-27 | 2026-08-29 | 2026-10-01 |  | 0.88104 | 0.72 | 8 | 36.1737 | 892.3775 | 2.4205 | 111.7483 |  | 25
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002008674_SET |  |  | 13794 | 13794 | 0 | 827.64 | 2026-08-24 | 2026-08-14 | 2026-08-24 | 2026-09-08 | 2026-09-10 | 2026-10-08 |  | 1.5488 | 0.72 | 8.7773 | 37 | 1760.4271 | 7.8356 | 200.9276 |  | 23
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014233 |  |  | 5496 | 5496 | 0 | 329.76 | 2026-08-22 | 2026-08-28 | 2026-09-04 | 2026-09-10 | 2026-09-12 | 2026-10-12 |  | 1.9029 | 0.72 | 9 | 37.6268 | 2255.4172 | 2.4368 | 251.0538 |  | 24
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014232 |  |  | 7296 | 7296 | 0 | 437.76 | 2026-08-18 | 2026-09-01 | 2026-09-08 | 2026-09-15 | 2026-09-17 | 2026-10-24 |  | 1.9632 | 0.72 | 9 | 38 | 2349.9855 | 3.1047 | 261.5803 |  | 32
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014238 |  |  | 4536 | 4536 | 0 | 272.16 | 2026-08-22 | 2026-09-04 | 2026-09-11 | 2026-09-17 | 2026-09-19 | 2026-10-26 |  | 2.1015 | 0.72 | 9 | 37.7537 | 2499.1733 | 1.815 | 278.1867 |  | 31
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014236 |  |  | 4200 | 3898 | 302 | 252 | 2026-08-24 | 2026-09-08 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 2026-11-07 |  | 2.09 | 0.72 | 9 | 37 | 2435.895 | 1.7242 | 271.1431 |  | 40
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014237 |  |  | 3624 | 0 | 3624 | 217.44 | 2026-08-29 | 2026-09-10 | 2026-09-17 | 2026-09-22 | 2026-09-24 | 2026-11-09 |  | 2.1 | 0.72 | 9 | 37 | 2447.55 | 1.4807 | 272.4404 |  | 40
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014235 |  |  | 4872 | 0 | 4872 | 292.32 | 2026-08-29 | 2026-09-11 | 2026-09-18 | 2026-09-24 | 2026-09-26 | 2026-11-21 |  | 2.1 | 0.72 | 9 | 37 | 2447.55 | 1.9906 | 272.4404 |  | 49
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014240 |  |  | 3624 | 0 | 3624 | 217.44 | 2026-09-05 | 2026-09-15 | 2026-09-22 | 2026-09-25 | 2026-09-27 | 2026-11-23 |  | 2.1 | 0.72 | 9 | 37 | 2447.55 | 1.4807 | 272.4404 |  | 49
6-07 | TGT | 352E6Y_SL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014239 |  |  | 4872 | 0 | 4872 | 292.32 | 2026-09-05 | 2026-09-16 | 2026-09-23 | 2026-09-29 | 2026-10-01 | 2026-12-05 |  | 2.1 | 0.72 | 9 | 37 | 2447.55 | 1.9906 | 272.4404 |  | 58
6-07 | ONY | 1194585_HO26_NB | Pull On Pants | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); Normal Garment Wash 清水洗/普通水洗; | 62242721, 726, 728, 729, 837, 838, 839 |  |  | 490 | 0 | 490 | 33.8917 | 2026-09-10 | 2026-09-18 | 2026-09-25 | 2026-09-30 | 2026-10-05 | 2026-10-08 |  | 0.5 | 0.83 | 7 | 37 | 393.1807 | 1.2462 | 56.27 |  | 7
6-07 | ONY | 1194585_HO26_NB | Pull On Pants | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); Normal Garment Wash 清水洗/普通水洗; | 62242721, 726, 728, 729, 837, 838, 839 |  |  | 1000 | 0 | 1000 | 69.1667 | 2026-09-10 | 2026-09-21 | 2026-09-28 | 2026-10-01 | 2026-10-06 | 2026-10-08 |  | 1 | 0.83 | 8.6 | 37 | 966.1012 | 1.0351 | 112.5399 |  | 6
6-07 | ONY | 1194585_HO26_NB | Pull On Pants | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); Normal Garment Wash 清水洗/普通水洗; | 62242165, 169, 172, 174 |  |  | 1510 | 0 | 1510 | 104.4417 | 2026-09-10 | 2026-09-22 | 2026-09-29 | 2026-10-03 | 2026-10-08 | 2026-10-29 |  | 1 | 0.83 | 8.6 | 37 | 966.1012 | 1.563 | 112.5399 |  | 22
6-07 | ONY | 1194432_SP27 | Tee |  | 62344810 |  |  | 761 | 0 | 761 | 40.5867 | 2026-10-09 | 2026-09-29 | 2026-10-01 | 2026-10-05 | 2026-10-07 | 2026-10-28 |  | 0.5 | 0.64 | 7 | 37 | 509.9062 | 1.4924 | 72.9751 |  | 20
6-07 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 1586 | 0 | 1586 | 84.5867 | 2026-10-09 | 2026-09-30 | 2026-10-02 | 2026-10-06 | 2026-10-08 | 2026-10-29 |  | 1 | 0.64 | 8.6 | 37 | 1252.9125 | 1.2659 | 145.9502 |  | 20
6-07 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 2500 | 0 | 2500 | 133.3333 | 2026-10-09 | 2026-10-01 | 2026-10-03 | 2026-10-08 | 2026-10-10 | 2026-10-29 |  | 1.2 | 0.64 | 8.6 | 37.461 | 1522.2285 | 1.6423 | 177.3225 |  | 18
6-07 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 3500 | 0 | 3500 | 186.6667 | 2026-10-09 | 2026-10-03 | 2026-10-06 | 2026-10-10 | 2026-10-12 | 2026-10-29 |  | 1.4 | 0.64 | 8.6 | 37.461 | 1775.9333 | 1.9708 | 206.8762 |  | 16
6-07 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 4000 | 0 | 4000 | 213.3333 | 2026-10-09 | 2026-10-06 | 2026-10-08 | 2026-10-13 | 2026-10-15 | 2026-10-29 |  | 1.6 | 0.64 | 8.6 | 37.461 | 2029.6381 | 1.9708 | 236.43 |  | 14
6-07 | ONY | 1194432_SP27 | Tee |  | 62344978 |  |  | 288 | 0 | 288 | 15.36 | 2026-10-09 | 2026-10-08 | 2026-10-10 | 2026-10-13 | 2026-10-15 | 2026-11-04 |  | 1.8 | 0.64 | 8.6 | 37.461 | 2283.3428 | 0.12613 | 265.9837 |  | 19
6-07 | ONY | 1194432_SP27 | Tee |  | 62323026, 027, 733, 738, 744, 745 |  |  | 10000 | 0 | 10000 | 533.3333 | 2026-10-09 | 2026-10-08 | 2026-10-10 | 2026-10-17 | 2026-10-19 | 2026-11-05 |  | 1.8 | 0.64 | 8.6 | 37.461 | 2283.3428 | 4.3795 | 265.9837 |  | 16
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0206_E_SET |  |  | 750 | 0 | 750 | 57.5 | 2026-10-09 | 2026-10-13 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-11-14 |  | 0.5 | 0.92 | 7 | 37.461 | 359.1372 | 2.0883 | 51.3978 |  | 22
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0206_E_SET |  |  | 1500 | 0 | 1500 | 115 | 2026-10-09 | 2026-10-15 | 2026-10-17 | 2026-10-22 | 2026-10-24 | 2026-11-14 |  | 1 | 0.92 | 8.6 | 37.461 | 882.4513 | 1.6998 | 102.7957 |  | 20
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0206_E_SET |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-10-09 | 2026-10-17 | 2026-10-20 | 2026-10-26 | 2026-10-28 | 2026-11-14 |  | 1.1 | 0.92 | 8.6 | 37.461 | 970.6965 | 2.5755 | 113.0752 |  | 17
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0206_E_SET |  |  | 3500 | 0 | 3500 | 268.3333 | 2026-10-09 | 2026-10-21 | 2026-10-23 | 2026-10-29 | 2026-10-31 | 2026-11-14 |  | 1.2 | 0.92 | 8.6 | 37.461 | 1058.9416 | 3.3052 | 123.3548 |  | 14
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0206_E_SET |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-10-09 | 2026-10-24 | 2026-10-27 | 2026-11-03 | 2026-11-05 | 2026-11-14 |  | 1.4 | 0.92 | 8.6 | 37.461 | 1235.4319 | 4.0472 | 143.9139 |  | 10
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0206_E_SET |  |  | 6100 | 0 | 6100 | 467.6667 | 2026-10-09 | 2026-10-29 | 2026-10-31 | 2026-11-07 | 2026-11-09 | 2026-11-14 |  | 1.6 | 0.92 | 8.6 | 37.461 | 1411.9221 | 4.3204 | 164.473 |  | 6
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0130_E |  |  | 900 | 0 | 900 | 69 | 2026-10-09 | 2026-11-03 | 2026-11-05 | 2026-11-09 | 2026-11-11 | 2026-11-19 |  | 1.8 | 0.92 | 8.6 | 37.461 | 1588.4124 | 0.5666 | 185.0322 |  | 9
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0206_W_SET |  |  | 18700 | 0 | 18700 | 1433.6667 | 2026-10-16 | 2026-11-04 | 2026-11-06 | 2026-11-21 | 2026-11-23 | 2026-11-26 |  | 2 | 0.92 | 8.6 | 37.461 | 1764.9027 | 10.5955 | 205.5913 |  | 4
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0220_E |  |  | 11654 | 0 | 11654 | 893.4733 | 2026-10-16 | 2026-11-17 | 2026-11-19 | 2026-11-30 | 2026-12-02 | 2026-11-28 |  | 2 | 0.92 | 8.6 | 37.461 | 1764.9027 | 6.6032 | 205.5913 |  | -3
6-07 | TGT | 440ZP9_C127 | Pull On Pants |  | 0220_W |  |  | 15980 | 0 | 15980 | 1225.1333 | 2026-10-16 | 2026-11-25 | 2026-11-27 | 2026-12-10 | 2026-12-12 | 2026-12-10 |  | 2 | 0.92 | 8.6 | 37.461 | 1764.9027 | 9.0543 | 205.5913 |  | 0
6-07 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-12-05 | 2026-12-08 | 2026-12-12 | 2026-12-17 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 37.461 | 359.1372 | 2.2693 | 51.3978 |  | 10
6-07 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-12-08 | 2026-12-10 | 2026-12-15 | 2026-12-20 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 37.461 | 882.4513 | 1.6998 | 102.7957 |  | 8
6-07 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-12-10 | 2026-12-12 | 2026-12-18 | 2026-12-23 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 37.461 | 970.6965 | 2.5755 | 113.0752 |  | 5
6-07 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-14 | 2026-12-16 | 2026-12-22 | 2026-12-27 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 37.461 | 1058.9416 | 2.833 | 123.3548 |  | 2
6-07 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4442 | 0 | 4442 | 340.5533 | 2026-12-07 | 2026-12-17 | 2026-12-19 | 2026-12-28 | 2027-01-02 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 37.461 | 1147.1867 | 3.8721 | 133.6343 |  | 3
6-07 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 5875 | 0 | 5875 | 450.4167 | 2026-12-07 | 2026-12-22 | 2026-12-24 | 2027-01-04 | 2027-01-09 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 37.461 | 1235.4319 | 4.7554 | 143.9139 |  | -4
6-07 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-29 | 2026-12-31 | 2027-01-06 | 2027-01-11 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 37.461 | 1323.677 | 1.4535 | 154.1935 |  | 7
6-07 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-30 | 2027-01-02 | 2027-01-13 | 2027-01-18 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 37.461 | 1323.677 | 5.8897 | 154.1935 |  | 7
6-07 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-08 | 2027-01-11 | 2027-01-19 | 2027-01-24 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 37.461 | 1323.677 | 4.9929 | 154.1935 |  | 8
2026-04-21
6-08 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 43947 | 43947 | 0 | 3845.3625 | 2026-05-07 | 2026-04-16 | 2026-04-18 | 2026-05-30 | 2026-06-04 | 2026-07-30 |  | 1.6982 | 1.05 | 9.3938 | 37.476 | 1434.8257 | 30.6288 | 153.0167 |  | 50
6-08 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 7260 | 7260 | 0 | 635.25 | 2026-05-26 | 2026-05-25 | 2026-05-28 | 2026-06-08 | 2026-06-13 | 2026-07-09 |  | 1.6754 | 1.05 | 8.7363 | 37.2525 | 1308.6032 | 5.5479 | 150.0591 |  | 26
6-08 | ONY | 766362_V1 | Pull On Pants |  | all po Juni, Juli, Agustus |  |  | 39555 | 39555 | 0 | 2834.775 | 2026-05-22 | 2026-06-03 | 2026-06-05 | 2026-07-11 | 2026-07-13 | 2026-08-13 |  | 1.4081 | 0.86 | 9.3671 | 37.1994 | 1437.6838 | 27.513 | 153.7592 |  | 27
6-08 | ONY | 766362_HO26 | Pull On Pants |  | all po |  |  | 43769 | 43769 | 0 | 3136.7783 | 2026-08-04 | 2026-07-07 | 2026-07-09 | 2026-08-18 | 2026-08-20 | 2026-11-05 |  | 1.7416 | 0.86 | 7.985 | 37.6745 | 1535.2206 | 28.5099 | 192.6093 |  | 61
6-08 | ONY | 766362_V1 | Pull On Pants |  | 10.08 |  |  | 10549 | 10549 | 0 | 756.0117 | 2026-05-22 | 2026-08-11 | 2026-08-13 | 2026-08-28 | 2026-08-30 | 2026-10-08 |  | 1.7658 | 0.86 | 7.9478 | 37.9015 | 1558.6804 | 6.7679 | 196.4674 |  | 30
6-08 | ONY | 766362_V1 | Pull On Pants |  | 10.28 |  |  | 4622 | 4622 | 0 | 331.2433 | 2026-05-22 | 2026-08-21 | 2026-08-26 | 2026-09-03 | 2026-09-05 | 2026-10-28 |  | 1.4079 | 0.86 | 8.2749 | 38.5544 | 1316.1342 | 3.5118 | 159.3391 |  | 43
6-08 | ONY | 766362_V1 | Pull On Pants |  | 62047538 |  |  | 724 | 724 | 0 | 51.8867 | 2026-05-22 | 2026-08-28 | 2026-09-01 | 2026-09-04 | 2026-09-06 | 2026-10-29 |  | 0.56272 | 0.86 | 8.0295 | 37.9378 | 502.2893 | 1.4414 | 62.6684 |  | 43
6-08 | SMA | PST840 | Pull On Pants |  | 1352813, _AH |  |  | 3708 | 3708 | 0 | 503.67 | 2026-08-18 | 2026-08-31 | 2026-09-02 | 2026-09-15 | 2026-09-17 | 2026-09-22 |  | 1.1021 | 1.63 | 8.557 | 36.7203 | 535.3662 | 6.9261 | 62.6777 |  | 5
6-08 | SMA | PST840 | Pull On Pants |  | 1354809_SS, _AH |  |  | 79 | 79 | 0 | 10.7308 | 2026-08-18 | 2026-09-09 | 2026-09-11 | 2026-09-15 | 2026-09-17 | 2026-09-23 |  | 1.4001 | 1.63 | 9 | 37 | 720.8029 | 0.1096 | 80.2336 |  | 6
6-08 | SMA | PST840 | Pull On Pants |  | 1352814, _AH |  |  | 4938 | 3784 | 1154 | 670.745 | 2026-08-24 | 2026-09-09 | 2026-09-11 | 2026-09-22 | 2026-09-24 | 2026-10-02 |  | 1.7 | 1.63 | 9 | 38 | 898.8515 | 5.4937 | 100.0525 |  | 8
6-08 | SMA | PST840 | Pull On Pants |  | 1352815, _AH |  |  | 5000 | 0 | 5000 | 679.1667 | 2026-09-14 | 2026-09-16 | 2026-09-18 | 2026-09-30 | 2026-10-02 | 2026-11-02 |  | 1.7 | 1.63 | 9 | 38 | 898.8515 | 5.5627 | 100.0525 |  | 28
6-08 | SMA | PST840 | Pull On Pants |  | 1352815, _AH |  |  | 4876 | 0 | 4876 | 662.3233 | 2026-09-14 | 2026-09-24 | 2026-09-28 | 2026-10-07 | 2026-10-09 | 2026-11-02 |  | 1.7 | 1.63 | 8.6 | 38 | 858.9026 | 5.677 | 100.0525 |  | 22
6-08 | SMA | PST840 | Pull On Pants |  | 1352816, _AH |  |  | 4816 | 0 | 4816 | 654.1733 | 2026-09-14 | 2026-10-02 | 2026-10-05 | 2026-10-14 | 2026-10-16 | 2026-12-03 |  | 1.7 | 1.63 | 8.6 | 38 | 858.9026 | 5.6072 | 100.0525 |  | 43
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 1140 | 0 | 1140 | 28.5 | 2026-10-13 | 2026-10-09 | 2026-10-12 | 2026-10-15 | 2026-10-17 | 2026-11-14 |  | 0.5 | 0.3 | 7 | 37.8178 | 1111.8424 | 1.0253 | 159.1211 |  | 26
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 2500 | 0 | 2500 | 62.5 | 2026-10-13 | 2026-10-10 | 2026-10-13 | 2026-10-16 | 2026-10-18 | 2026-11-14 |  | 1 | 0.3 | 8.6 | 37.8178 | 2731.9557 | 0.9151 | 318.2421 |  | 25
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 3500 | 0 | 3500 | 87.5 | 2026-10-13 | 2026-10-12 | 2026-10-14 | 2026-10-17 | 2026-10-19 | 2026-11-14 |  | 1.2 | 0.3 | 8.6 | 37.8178 | 3278.3468 | 1.0676 | 381.8905 |  | 24
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 5000 | 0 | 5000 | 125 | 2026-10-13 | 2026-10-13 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 2026-11-14 |  | 1.4 | 0.3 | 8.6 | 37.8178 | 3824.738 | 1.3073 | 445.5389 |  | 23
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 10000 | 0 | 10000 | 250 | 2026-10-13 | 2026-10-14 | 2026-10-16 | 2026-10-21 | 2026-10-23 | 2026-11-14 |  | 1.6 | 0.3 | 8.6 | 37.8178 | 4371.1291 | 2.2877 | 509.1874 |  | 21
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 10000 | 0 | 10000 | 250 | 2026-10-13 | 2026-10-16 | 2026-10-19 | 2026-10-23 | 2026-10-25 | 2026-11-14 |  | 1.8 | 0.3 | 8.6 | 37.8178 | 4917.5203 | 2.0335 | 572.8358 |  | 19
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0123_BA, 0123_SET_W, 0123_SET_E |  |  | 84140 | 0 | 84140 | 2103.5 | 2026-10-13 | 2026-10-19 | 2026-10-21 | 2026-11-10 | 2026-11-12 | 2026-11-14 |  | 2 | 0.3 | 8.6 | 37.8178 | 5463.9114 | 15.3992 | 636.4842 |  | 4
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0130_TRN |  |  | 2088 | 0 | 2088 | 52.2 | 2026-10-27 | 2026-11-05 | 2026-11-07 | 2026-11-10 | 2026-11-12 | 2026-11-18 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 0.3474 | 700.1326 |  | 7
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0213_BA |  |  | 18216 | 0 | 18216 | 455.4 | 2026-10-27 | 2026-11-05 | 2026-11-07 | 2026-11-13 | 2026-11-15 | 2026-12-03 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 3.0308 | 700.1326 |  | 17
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0220_BA |  |  | 17784 | 0 | 17784 | 444.6 | 2026-10-27 | 2026-11-09 | 2026-11-11 | 2026-11-17 | 2026-11-19 | 2026-12-09 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 2.9589 | 700.1326 |  | 19
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0227_BA |  |  | 17784 | 0 | 17784 | 444.6 | 2026-10-27 | 2026-11-12 | 2026-11-14 | 2026-11-20 | 2026-11-22 | 2026-12-16 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 2.9589 | 700.1326 |  | 22
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0306_BA |  |  | 17784 | 0 | 17784 | 444.6 | 2026-10-27 | 2026-11-16 | 2026-11-18 | 2026-11-24 | 2026-11-26 | 2026-12-23 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 2.9589 | 700.1326 |  | 25
6-08 | TGT | 546462_6PK_C127 | Panties | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0313_BA |  |  | 17784 | 0 | 17784 | 444.6 | 2026-10-27 | 2026-11-19 | 2026-11-21 | 2026-11-27 | 2026-11-29 | 2026-12-30 |  | 2.2 | 0.3 | 8.6 | 37.8178 | 6010.3026 | 2.9589 | 700.1326 |  | 27
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-11-23 | 2026-11-25 | 2026-11-30 | 2026-12-05 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 37.8178 | 362.5573 | 2.2479 | 51.8873 |  | 21
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-11-25 | 2026-11-27 | 2026-12-02 | 2026-12-07 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 37.8178 | 890.8551 | 1.6838 | 103.7746 |  | 19
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-11-27 | 2026-11-30 | 2026-12-05 | 2026-12-10 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 37.8178 | 979.9406 | 2.5512 | 114.1521 |  | 16
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-01 | 2026-12-03 | 2026-12-09 | 2026-12-14 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 37.8178 | 1069.0261 | 2.8063 | 124.5295 |  | 13
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4942 | 0 | 4942 | 378.8867 | 2026-12-07 | 2026-12-04 | 2026-12-07 | 2026-12-14 | 2026-12-19 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 37.8178 | 1158.1117 | 4.2673 | 134.907 |  | 14
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 5000 | 0 | 5000 | 383.3333 | 2026-12-07 | 2026-12-09 | 2026-12-11 | 2026-12-18 | 2026-12-23 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 37.8178 | 1247.1972 | 4.009 | 145.2844 |  | 10
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 13350 | 0 | 13350 | 1023.5 | 2026-12-07 | 2026-12-14 | 2026-12-16 | 2026-12-31 | 2027-01-05 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 9.9904 | 155.6619 |  | 0
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-26 | 2026-12-29 | 2027-01-02 | 2027-01-07 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 1.4398 | 155.6619 |  | 9
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-28 | 2026-12-30 | 2027-01-11 | 2027-01-16 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 5.8341 | 155.6619 |  | 9
6-08 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-06 | 2027-01-08 | 2027-01-16 | 2027-01-21 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 37.8178 | 1336.2827 | 4.9458 | 155.6619 |  | 10
2026-05-21
6-09 | TGT | G9M018_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 65630 | 65630 | 0 | 4648.7917 | 2026-05-25 | 2026-05-12 | 2026-05-19 | 2026-07-06 | 2026-07-08 | 2026-07-11 |  | 1.8566 | 0.85 | 9.5019 | 35.1267 | 1837.1199 | 35.7244 | 193.6912 |  | 5
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874451_BA_E |  |  | 171876 | 171876 | 0 | 3151.06 | 2026-06-27 | 2026-06-27 | 2026-07-03 | 2026-07-27 | 2026-07-29 | 2026-08-05 |  | 2.8155 | 0.22 | 8.2809 | 35.8848 | 9583.592 | 17.9344 | 1159.3956 |  | 8
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874422_TRN_W |  |  | 8820 | 8820 | 0 | 161.7 | 2026-06-27 | 2026-07-18 | 2026-07-24 | 2026-07-28 | 2026-07-30 | 2026-08-13 |  | 2.7968 | 0.22 | 5.7489 | 36.7452 | 6767.434 | 1.3033 | 1179.2848 |  | 13
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874468_BA_E |  |  | 50484 | 50484 | 0 | 925.54 | 2026-06-27 | 2026-07-20 | 2026-07-25 | 2026-08-03 | 2026-08-05 | 2026-08-19 |  | 3.1083 | 0.22 | 7.8618 | 36.8165 | 10305.3766 | 4.8988 | 1313.1718 |  | 11
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874454_BA_E |  |  | 43596 | 43596 | 0 | 799.26 | 2026-07-04 | 2026-07-25 | 2026-07-31 | 2026-08-07 | 2026-08-09 | 2026-08-26 |  | 3.1181 | 0.22 | 7.4901 | 36.8261 | 9851.7605 | 4.4252 | 1317.6761 |  | 11
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874439_BA_E |  |  | 107016 | 107016 | 0 | 1961.96 | 2026-07-01 | 2026-07-30 | 2026-08-05 | 2026-08-24 | 2026-08-26 | 2026-09-02 |  | 3.056 | 0.22 | 8.0032 | 36.8073 | 10311.806 | 10.378 | 1290.7773 |  | 6
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874453_BA_E |  |  | 42420 | 42420 | 0 | 777.7 | 2026-07-11 | 2026-08-12 | 2026-08-20 | 2026-08-31 | 2026-09-02 | 2026-09-09 |  | 3.1196 | 0.22 | 9 | 36.5448 | 11752.9707 | 3.6093 | 1308.2405 |  | 7
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874469_BA_E |  |  | 28896 | 28896 | 0 | 529.76 | 2026-07-08 | 2026-08-19 | 2026-08-27 | 2026-09-02 | 2026-09-04 | 2026-10-07 |  | 3.1621 | 0.22 | 9 | 36.4108 | 11869.3771 | 2.4345 | 1321.1978 |  | 26
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874471_BA_E |  |  | 55356 | 55356 | 0 | 1014.86 | 2026-07-11 | 2026-08-21 | 2026-08-31 | 2026-09-09 | 2026-09-11 | 2026-10-14 |  | 3.0441 | 0.22 | 9 | 37.1892 | 11670.8478 | 4.7431 | 1299.0992 |  | 27
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874444_BA_E |  |  | 49392 | 49392 | 0 | 905.52 | 2026-07-11 | 2026-08-31 | 2026-09-07 | 2026-09-15 | 2026-09-17 | 2026-10-21 |  | 3.0176 | 0.22 | 9 | 38.2409 | 11896.2392 | 4.1519 | 1324.1879 |  | 29
6-09 | TGT | W9ZMM8_7PK_C426 | Panties | Pad Printing Machine 移印機; | 10001874473_BA_E |  |  | 50428 | 38389 | 12039 | 924.5133 | 2026-07-11 | 2026-09-04 | 2026-09-11 | 2026-09-21 | 2026-09-23 | 2026-11-04 |  | 2.9 | 0.22 | 9 | 37.8178 | 11306.138 | 4.4602 | 1258.5029 |  | 37
6-09 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014298_SET_1212, 10002014297_T1_1212 |  |  | 750 | 0 | 750 | 52.5 | 2026-08-22 | 2026-09-10 | 2026-09-17 | 2026-09-23 | 2026-09-25 | 2026-10-01 |  | 0.5 | 0.84 | 7 | 37.8178 | 397.0866 | 1.8888 | 56.8289 |  | 6
6-09 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014298_SET_1212, 10002014297_T1_1212 |  |  | 1500 | 0 | 1500 | 105 | 2026-08-22 | 2026-09-14 | 2026-09-21 | 2026-09-24 | 2026-09-26 | 2026-10-01 |  | 1 | 0.84 | 9 | 37.8178 | 1021.0798 | 1.469 | 113.6579 |  | 5
6-09 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014298_SET_1212, 10002014297_T1_1212 |  |  | 2000 | 0 | 2000 | 140 | 2026-08-22 | 2026-09-15 | 2026-09-22 | 2026-09-28 | 2026-09-30 | 2026-10-01 |  | 1.2 | 0.84 | 9 | 37.8178 | 1225.2957 | 1.6323 | 136.3895 |  | 3
6-09 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014298_SET_1212, 10002014297_T1_1212 |  |  | 2150 | 0 | 2150 | 150.5 | 2026-08-22 | 2026-09-17 | 2026-09-24 | 2026-09-30 | 2026-10-02 | 2026-10-01 |  | 1.3 | 0.84 | 9 | 37.8178 | 1327.4037 | 1.6197 | 147.7553 |  | 1
6-09 | TGT | X048GZ_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002014298_SET_1212, 10002014297_T1_1212 |  |  | 2500 | 0 | 2500 | 175 | 2026-08-22 | 2026-09-21 | 2026-09-28 | 2026-10-02 | 2026-10-04 | 2026-10-01 |  | 1.4 | 0.84 | 9 | 37.8178 | 1429.5117 | 1.7488 | 159.1211 |  | -3
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021697_T1 |  |  | 704 | 0 | 704 | 64.5333 | 2026-09-08 | 2026-09-28 | 2026-09-30 | 2026-10-05 | 2026-10-07 | 2026-10-22 |  | 0.5 | 1.1 | 7 | 37.8178 | 303.2298 | 2.3217 | 43.3967 |  | 15
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021697_T1 |  |  | 1800 | 0 | 1800 | 165 | 2026-09-08 | 2026-09-30 | 2026-10-02 | 2026-10-07 | 2026-10-09 | 2026-10-22 |  | 1 | 1.1 | 9 | 37.8178 | 779.7337 | 2.3085 | 86.7933 |  | 13
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 2666 | 0 | 2666 | 244.3833 | 2026-09-08 | 2026-10-02 | 2026-10-05 | 2026-10-10 | 2026-10-12 | 2026-10-29 |  | 1.1 | 1.1 | 9 | 37.8178 | 857.707 | 3.1083 | 95.4726 |  | 16
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 3000 | 0 | 3000 | 275 | 2026-09-08 | 2026-10-06 | 2026-10-08 | 2026-10-14 | 2026-10-16 | 2026-10-29 |  | 1.2 | 1.1 | 8.6 | 37.8178 | 894.0946 | 3.3553 | 104.152 |  | 13
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 3500 | 0 | 3500 | 320.8333 | 2026-09-08 | 2026-10-09 | 2026-10-12 | 2026-10-17 | 2026-10-19 | 2026-10-29 |  | 1.4 | 1.1 | 8.6 | 37.8178 | 1043.1104 | 3.3553 | 121.5106 |  | 10
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021703 |  |  | 4440 | 0 | 4440 | 407 | 2026-09-08 | 2026-10-13 | 2026-10-15 | 2026-10-22 | 2026-10-24 | 2026-11-18 |  | 1.6 | 1.1 | 8.6 | 37.8178 | 1192.1261 | 3.7244 | 138.8693 |  | 23
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021703 |  |  | 5516 | 0 | 5516 | 505.6333 | 2026-09-08 | 2026-10-17 | 2026-10-20 | 2026-10-27 | 2026-10-29 | 2026-11-18 |  | 1.8 | 1.1 | 8.6 | 37.8178 | 1341.1419 | 4.1129 | 156.2279 |  | 19
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021702 |  |  | 11676 | 0 | 11676 | 1070.3 | 2026-09-08 | 2026-10-22 | 2026-10-24 | 2026-11-06 | 2026-11-08 | 2026-12-02 |  | 1.8 | 1.1 | 8.6 | 37.8178 | 1341.1419 | 8.706 | 156.2279 |  | 22
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021705 |  |  | 4000 | 0 | 4000 | 366.6667 | 2026-09-08 | 2026-11-02 | 2026-11-04 | 2026-11-10 | 2026-11-12 | 2026-12-16 |  | 1.8 | 1.1 | 8.6 | 37.8178 | 1341.1419 | 2.9825 | 156.2279 |  | 31
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0130_TRN |  |  | 2940 | 0 | 2940 | 53.9 | 2026-10-13 | 2026-11-02 | 2026-11-07 | 2026-11-12 | 2026-11-14 | 2026-11-18 |  | 0.5 | 0.22 | 7 | 37.8178 | 1516.1488 | 1.9391 | 216.9833 |  | 5
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0206_BA |  |  | 10000 | 0 | 10000 | 183.3333 | 2026-10-13 | 2026-11-04 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 2026-11-25 |  | 1 | 0.22 | 8.6 | 37.8178 | 3725.3941 | 2.6843 | 433.9665 |  | 8
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0206_BA |  |  | 15000 | 0 | 15000 | 275 | 2026-10-13 | 2026-11-07 | 2026-11-13 | 2026-11-19 | 2026-11-21 | 2026-11-25 |  | 1.5 | 0.22 | 8.6 | 37.8178 | 5588.0912 | 2.6843 | 650.9498 |  | 5
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0206_BA |  |  | 17244 | 0 | 17244 | 316.14 | 2026-10-13 | 2026-11-11 | 2026-11-17 | 2026-11-21 | 2026-11-23 | 2026-11-25 |  | 2 | 0.22 | 8.6 | 37.8178 | 7450.7883 | 2.3144 | 867.933 |  | 3
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0206_BA |  |  | 20000 | 0 | 20000 | 366.6667 | 2026-10-13 | 2026-11-13 | 2026-11-19 | 2026-11-24 | 2026-11-26 | 2026-11-25 |  | 2.5 | 0.22 | 8.6 | 37.8178 | 9313.4854 | 2.1474 | 1084.9163 |  | 1
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0213_BA |  |  | 16548 | 0 | 16548 | 303.38 | 2026-10-13 | 2026-11-16 | 2026-11-21 | 2026-11-26 | 2026-11-28 | 2026-12-02 |  | 2.7 | 0.22 | 8.6 | 37.8178 | 10058.5642 | 1.6452 | 1171.7096 |  | 5
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0220_BA |  |  | 16548 | 0 | 16548 | 303.38 | 2026-10-27 | 2026-11-18 | 2026-11-24 | 2026-11-28 | 2026-11-30 | 2026-12-09 |  | 2.8 | 0.22 | 8.6 | 37.8178 | 10431.1036 | 1.5864 | 1215.1062 |  | 9
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0227_BA |  |  | 16548 | 0 | 16548 | 303.38 | 2026-10-27 | 2026-11-20 | 2026-11-26 | 2026-12-01 | 2026-12-03 | 2026-12-16 |  | 2.9 | 0.22 | 8.6 | 37.8178 | 10803.643 | 1.5317 | 1258.5029 |  | 13
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0306_BA |  |  | 16548 | 0 | 16548 | 303.38 | 2026-10-27 | 2026-11-23 | 2026-11-28 | 2026-12-03 | 2026-12-05 | 2026-12-23 |  | 2.9 | 0.22 | 8.6 | 37.8178 | 10803.643 | 1.5317 | 1258.5029 |  | 17
6-09 | TGT | W9ZMM8_7PK_C127 | Panties | Pad Printing Machine 移印機; | 0313_BA |  |  | 16548 | 0 | 16548 | 303.38 | 2026-10-27 | 2026-11-25 | 2026-12-01 | 2026-12-05 | 2026-12-07 | 2026-12-30 |  | 2.9 | 0.22 | 8.6 | 37.8178 | 10803.643 | 1.5317 | 1258.5029 |  | 20
6-09 | TGT | 9KM9L2_C227 | Pull On Pants |  | 0328 |  |  | 754 | 0 | 754 | 69.1167 | 2026-12-03 | 2026-12-01 | 2026-12-03 | 2026-12-08 | 2026-12-10 | 2027-01-05 |  | 0.5 | 1.1 | 7 | 37.8178 | 303.2298 | 2.4866 | 43.3967 |  | 21
6-09 | TGT | 9KM9L2_C227 | Pull On Pants |  | 0328 |  |  | 1500 | 0 | 1500 | 137.5 | 2026-12-03 | 2026-12-03 | 2026-12-05 | 2026-12-10 | 2026-12-12 | 2027-01-05 |  | 1 | 1.1 | 8.6 | 37.8178 | 745.0788 | 2.0132 | 86.7933 |  | 19
6-09 | TGT | 9KM9L2_C227 | Pull On Pants |  | 0328 |  |  | 2500 | 0 | 2500 | 229.1667 | 2026-12-03 | 2026-12-05 | 2026-12-08 | 2026-12-14 | 2026-12-16 | 2027-01-05 |  | 1.2 | 1.1 | 8.6 | 37.8178 | 894.0946 | 2.7961 | 104.152 |  | 16
6-09 | TGT | 9KM9L2_C227 | Pull On Pants |  | 0328 |  |  | 3500 | 0 | 3500 | 320.8333 | 2026-12-03 | 2026-12-09 | 2026-12-11 | 2026-12-17 | 2026-12-19 | 2027-01-05 |  | 1.4 | 1.1 | 8.6 | 37.8178 | 1043.1104 | 3.3553 | 121.5106 |  | 13
6-09 | TGT | 9KM9L2_C227 | Pull On Pants |  | 0328 |  |  | 4500 | 0 | 4500 | 412.5 | 2026-12-03 | 2026-12-12 | 2026-12-15 | 2026-12-22 | 2026-12-24 | 2027-01-05 |  | 1.6 | 1.1 | 8.6 | 37.8178 | 1192.1261 | 3.7748 | 138.8693 |  | 9
6-09 | TGT | 9KM9L2_C227 | Pull On Pants |  | 0328 |  |  | 6700 | 0 | 6700 | 614.1667 | 2026-12-03 | 2026-12-17 | 2026-12-19 | 2026-12-29 | 2026-12-31 | 2027-01-05 |  | 1.8 | 1.1 | 8.6 | 37.8178 | 1341.1419 | 4.9957 | 156.2279 |  | 4
6-09 | TGT | 9KM9L2_C227 | Pull On Pants |  | 0404 |  |  | 2594 | 0 | 2594 | 237.7833 | 2026-12-10 | 2026-12-23 | 2026-12-26 | 2026-12-31 | 2027-01-02 | 2027-01-12 |  | 1.8 | 1.1 | 8.6 | 37.8178 | 1341.1419 | 1.9342 | 156.2279 |  | 8
6-09 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021707 |  |  | 11676 | 0 | 11676 | 1070.3 | 2026-11-06 | 2026-12-26 | 2026-12-29 | 2027-01-13 | 2027-01-15 | 2027-01-13 |  | 1.8 | 1.1 | 8.6 | 37.8178 | 1341.1419 | 8.706 | 156.2279 |  | 0
6-09 | TGT | 9KM9L2_C227 | Pull On Pants |  | 0418 |  |  | 2594 | 0 | 2594 | 237.7833 | 2026-12-24 | 2027-01-08 | 2027-01-11 | 2027-01-15 | 2027-01-17 | 2027-01-26 |  | 1.8 | 1.1 | 8.6 | 37.8178 | 1341.1419 | 1.9342 | 156.2279 |  | 9
2026-04-14
6-10 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 15160 | 15160 | 0 | 1326.5 | 2026-04-25 | 2026-04-09 | 2026-04-11 | 2026-04-30 | 2026-05-05 | 2026-06-04 |  | 1.4219 | 1.05 | 8.5757 | 37.7094 | 1103.5488 | 13.7375 | 128.9159 |  | 26
6-10 | ONY | 962148_FA26 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | all po |  |  | 4540 | 4540 | 0 | 211.8667 | 2026-04-15 | 2026-04-25 | 2026-04-28 | 2026-05-06 | 2026-05-08 | 2026-08-06 |  | 0.88245 | 0.56 | 8.0175 | 38 | 1209.8277 | 3.7526 | 151.1709 |  | 75
6-10 | ONY | 905200_FA26 | Pull On Pants |  | all po |  |  | 57498 | 57498 | 0 | 5366.48 | 2026-05-15 | 2026-04-30 | 2026-05-04 | 2026-07-10 | 2026-07-12 | 2026-07-16 |  | 1.4275 | 1.12 | 9.3511 | 36.6522 | 1100.8636 | 52.2299 | 117.9376 |  | 5
6-10 | TGT | X25413_C426 | Pull On Pants |  | all po |  |  | 3123 | 3123 | 0 | 379.965 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-16 | 2026-07-18 | 2026-08-15 |  | 1.2038 | 1.46 | 7.7928 | 35.9876 | 582.7032 | 5.3595 | 74.9092 |  | 24
6-10 | ONY | 826369_HO26 | Pull On Pants |  | all po |  |  | 2235 | 2235 | 0 | 167.625 | 2026-07-13 | 2026-07-11 | 2026-07-14 | 2026-07-21 | 2026-07-23 | 2026-08-13 |  | 0.82751 | 0.9 | 7.2576 | 37.0282 | 622.6666 | 3.5894 | 85.9499 |  | 19
6-10 | ONY | 1184403_HO26 | Pull On Pants |  | all po |  |  | 7414 | 7414 | 0 | 716.6867 | 2026-07-13 | 2026-07-16 | 2026-07-18 | 2026-08-05 | 2026-08-07 | 2026-08-20 |  | 0.95783 | 1.16 | 7.2192 | 37.4439 | 562.4717 | 13.1811 | 78.0539 |  | 10
6-10 | ONY | 1182719_HO26 | Skorts |  | all po |  |  | 23350 | 23350 | 0 | 1148.0417 | 2026-07-11 | 2026-07-31 | 2026-08-03 | 2026-08-27 | 2026-08-29 | 2026-08-27 |  | 1.2859 | 0.59 | 8 | 37.7782 | 1659.9607 | 14.0666 | 207.8692 |  | 0
6-10 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 26827 | 26827 | 0 | 1184.8592 | 2026-08-06 | 2026-08-20 | 2026-08-24 | 2026-09-17 | 2026-09-19 | 2026-09-17 |  | 1.1652 | 0.53 | 8.6733 | 36.6132 | 1759.3202 | 15.2485 | 203.2095 |  | 0
6-10 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016283, 292, 296 |  |  | 4190 | 3437 | 753 | 185.0583 | 2026-08-06 | 2026-09-11 | 2026-09-15 | 2026-09-21 | 2026-09-23 | 2026-10-15 |  | 1.52 | 0.53 | 9 | 38 | 2471.6921 | 1.6952 | 275.1277 |  | 20
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 750 | 0 | 750 | 61.25 | 2026-09-07 | 2026-09-15 | 2026-09-17 | 2026-09-23 | 2026-09-28 | 2026-10-01 |  | 0.5 | 0.98 | 7 | 38 | 342 | 2.193 | 48.9452 |  | 6
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 1500 | 0 | 1500 | 122.5 | 2026-09-07 | 2026-09-17 | 2026-09-21 | 2026-09-25 | 2026-09-30 | 2026-10-01 |  | 1 | 0.98 | 9 | 38 | 879.4286 | 1.7057 | 97.8905 |  | 4
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62239979, 378, 565, 268, 269 |  |  | 1503 | 0 | 1503 | 122.745 | 2026-09-07 | 2026-09-21 | 2026-09-23 | 2026-09-28 | 2026-10-03 | 2026-10-08 |  | 1.2 | 0.98 | 9 | 38 | 1055.3143 | 1.4242 | 117.4686 |  | 9
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 2500 | 0 | 2500 | 204.1667 | 2026-09-07 | 2026-09-22 | 2026-09-24 | 2026-09-30 | 2026-10-05 | 2026-10-15 |  | 1.4 | 0.98 | 9 | 38 | 1231.2 | 2.0305 | 137.0467 |  | 13
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 4500 | 0 | 4500 | 367.5 | 2026-09-07 | 2026-09-24 | 2026-09-28 | 2026-10-03 | 2026-10-08 | 2026-10-15 |  | 1.6 | 0.98 | 8.6 | 38 | 1344.5486 | 3.3468 | 156.6248 |  | 10
6-10 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 5753 | 0 | 5753 | 469.8283 | 2026-09-07 | 2026-09-29 | 2026-10-01 | 2026-10-08 | 2026-10-13 | 2026-10-15 |  | 1.8 | 0.98 | 8.6 | 38 | 1512.6171 | 3.8033 | 176.2029 |  | 6
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 960 | 0 | 960 | 25.6 | 2026-10-12 | 2026-10-03 | 2026-10-06 | 2026-10-09 | 2026-10-11 | 2026-11-02 |  | 0.5 | 0.32 | 7 | 38 | 1047.375 | 0.91658 | 149.8948 |  | 20
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 1500 | 0 | 1500 | 40 | 2026-10-12 | 2026-10-05 | 2026-10-07 | 2026-10-10 | 2026-10-12 | 2026-11-02 |  | 1 | 0.32 | 8.6 | 38 | 2573.55 | 0.58285 | 299.7896 |  | 19
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 2500 | 0 | 2500 | 66.6667 | 2026-10-12 | 2026-10-06 | 2026-10-08 | 2026-10-12 | 2026-10-14 | 2026-11-02 |  | 1.1 | 0.32 | 8.6 | 38 | 2830.905 | 0.88311 | 329.7686 |  | 18
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 3500 | 0 | 3500 | 93.3333 | 2026-10-12 | 2026-10-07 | 2026-10-09 | 2026-10-13 | 2026-10-15 | 2026-11-02 |  | 1.2 | 0.32 | 8.6 | 38 | 3088.26 | 1.1333 | 359.7475 |  | 17
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_E |  |  | 4500 | 0 | 4500 | 120 | 2026-10-12 | 2026-10-08 | 2026-10-10 | 2026-10-14 | 2026-10-16 | 2026-11-02 |  | 1.3 | 0.32 | 8.6 | 38 | 3345.615 | 1.345 | 389.7265 |  | 16
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0130_W |  |  | 1044 | 0 | 1044 | 27.84 | 2026-10-20 | 2026-10-09 | 2026-10-12 | 2026-10-14 | 2026-10-16 | 2026-11-11 |  | 1.4 | 0.32 | 8.6 | 38 | 3602.97 | 0.28976 | 419.7055 |  | 24
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 5000 | 0 | 5000 | 133.3333 | 2026-10-12 | 2026-10-09 | 2026-10-12 | 2026-10-15 | 2026-10-17 | 2026-11-12 |  | 1.6 | 0.32 | 8.6 | 38 | 4117.68 | 1.2143 | 479.6634 |  | 24
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 7000 | 0 | 7000 | 186.6667 | 2026-10-12 | 2026-10-10 | 2026-10-13 | 2026-10-17 | 2026-10-19 | 2026-11-12 |  | 1.8 | 0.32 | 8.6 | 38 | 4632.39 | 1.5111 | 539.6213 |  | 22
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0123_SET_W, 0123_W |  |  | 35180 | 0 | 35180 | 938.1333 | 2026-10-12 | 2026-10-13 | 2026-10-15 | 2026-10-26 | 2026-10-28 | 2026-11-12 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 6.8349 | 599.5792 |  | 15
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0213_W |  |  | 9108 | 0 | 9108 | 242.88 | 2026-10-20 | 2026-10-21 | 2026-10-23 | 2026-10-28 | 2026-10-30 | 2026-11-25 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7695 | 599.5792 |  | 24
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0220_W |  |  | 8892 | 0 | 8892 | 237.12 | 2026-10-27 | 2026-10-23 | 2026-10-26 | 2026-10-30 | 2026-11-01 | 2026-12-02 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7276 | 599.5792 |  | 28
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0227_W |  |  | 8892 | 0 | 8892 | 237.12 | 2026-10-27 | 2026-10-26 | 2026-10-28 | 2026-11-02 | 2026-11-04 | 2026-12-09 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7276 | 599.5792 |  | 32
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0306_W |  |  | 8892 | 0 | 8892 | 237.12 | 2026-10-27 | 2026-10-28 | 2026-10-30 | 2026-11-04 | 2026-11-06 | 2026-12-16 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7276 | 599.5792 |  | 36
6-10 | TGT | L0303X_6PK_C127 | Panties | Main-Knit-Rib-Cotton 100%-155g/m2;Main-Knit-Rib-Cotton 100%-155g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-160g/m2;Trim-Knit-Double Knit-Recycled Polyester 100%-150g/m2 | 0313_W |  |  | 8892 | 0 | 8892 | 237.12 | 2026-10-27 | 2026-10-30 | 2026-11-02 | 2026-11-06 | 2026-11-08 | 2026-12-23 |  | 2 | 0.32 | 8.6 | 38 | 5147.1 | 1.7276 | 599.5792 |  | 40
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0206_E_SET |  |  | 750 | 0 | 750 | 57.5 | 2026-10-09 | 2026-11-02 | 2026-11-04 | 2026-11-09 | 2026-11-11 | 2026-11-14 |  | 0.5 | 0.92 | 7 | 38 | 364.3043 | 2.0587 | 52.1373 |  | 5
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0206_E_SET |  |  | 1500 | 0 | 1500 | 115 | 2026-10-09 | 2026-11-04 | 2026-11-06 | 2026-11-11 | 2026-11-13 | 2026-11-14 |  | 1 | 0.92 | 8.6 | 38 | 895.1478 | 1.6757 | 104.2747 |  | 3
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0130_E |  |  | 900 | 0 | 900 | 69 | 2026-10-09 | 2026-11-06 | 2026-11-09 | 2026-11-12 | 2026-11-14 | 2026-11-19 |  | 1.1 | 0.92 | 8.6 | 38 | 984.6626 | 0.91402 | 114.7021 |  | 6
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0206_W_SET |  |  | 2200 | 0 | 2200 | 168.6667 | 2026-10-16 | 2026-11-07 | 2026-11-10 | 2026-11-14 | 2026-11-16 | 2026-11-26 |  | 1.2 | 0.92 | 8.6 | 38 | 1074.1774 | 2.0481 | 125.1296 |  | 10
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0206_W_SET |  |  | 3500 | 0 | 3500 | 268.3333 | 2026-10-16 | 2026-11-10 | 2026-11-12 | 2026-11-18 | 2026-11-20 | 2026-11-26 |  | 1.4 | 0.92 | 8.6 | 38 | 1253.207 | 2.7928 | 145.9845 |  | 7
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0206_W_SET |  |  | 4000 | 0 | 4000 | 306.6667 | 2026-10-16 | 2026-11-13 | 2026-11-16 | 2026-11-21 | 2026-11-23 | 2026-11-26 |  | 1.6 | 0.92 | 8.6 | 38 | 1432.2365 | 2.7928 | 166.8394 |  | 4
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0206_W_SET |  |  | 4000 | 0 | 4000 | 306.6667 | 2026-10-16 | 2026-11-17 | 2026-11-19 | 2026-11-24 | 2026-11-26 | 2026-11-26 |  | 1.8 | 0.92 | 8.6 | 38 | 1611.2661 | 2.4825 | 187.6944 |  | 2
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0220_E |  |  | 9654 | 0 | 9654 | 740.14 | 2026-10-16 | 2026-11-19 | 2026-11-21 | 2026-11-30 | 2026-12-02 | 2026-11-28 |  | 2 | 0.92 | 8.6 | 38 | 1790.2957 | 5.3924 | 208.5493 |  | -3
6-10 | TGT | 440ZP9_C127 | Pull On Pants |  | 0220_W |  |  | 15980 | 0 | 15980 | 1225.1333 | 2026-10-16 | 2026-11-25 | 2026-11-27 | 2026-12-10 | 2026-12-12 | 2026-12-10 |  | 2 | 0.92 | 8.6 | 38 | 1790.2957 | 8.9259 | 208.5493 |  | 0
6-10 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-12-05 | 2026-12-08 | 2026-12-12 | 2026-12-17 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 38 | 364.3043 | 2.2371 | 52.1373 |  | 10
6-10 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-12-08 | 2026-12-10 | 2026-12-15 | 2026-12-20 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 38 | 895.1478 | 1.6757 | 104.2747 |  | 8
6-10 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-12-10 | 2026-12-12 | 2026-12-18 | 2026-12-23 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 38 | 984.6626 | 2.5389 | 114.7021 |  | 5
6-10 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-14 | 2026-12-16 | 2026-12-22 | 2026-12-27 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 38 | 1074.1774 | 2.7928 | 125.1296 |  | 2
6-10 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4042 | 0 | 4042 | 309.8867 | 2026-12-07 | 2026-12-17 | 2026-12-19 | 2026-12-26 | 2026-12-31 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 38 | 1163.6922 | 3.4734 | 135.557 |  | 4
6-10 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4000 | 0 | 4000 | 306.6667 | 2026-12-07 | 2026-12-21 | 2026-12-23 | 2026-12-30 | 2027-01-04 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 38 | 1253.207 | 3.1918 | 145.9845 |  | 1
6-10 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4000 | 0 | 4000 | 306.6667 | 2026-12-07 | 2026-12-24 | 2026-12-28 | 2027-01-04 | 2027-01-09 | 2026-12-31 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 2.979 | 156.412 |  | -4
6-10 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-29 | 2026-12-31 | 2027-01-06 | 2027-01-11 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 1.4329 | 156.412 |  | 7
6-10 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-30 | 2027-01-02 | 2027-01-13 | 2027-01-18 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 5.8061 | 156.412 |  | 7
6-10 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-08 | 2027-01-11 | 2027-01-19 | 2027-01-24 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 4.9221 | 156.412 |  | 8
2026-05-22
6-11 | TGT | MRLPMM_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 98283 | 98283 | 0 | 7371.225 | 2026-06-08 | 2026-05-13 | 2026-05-20 | 2026-08-07 | 2026-08-09 | 2026-08-22 |  | 2.1566 | 0.9 | 8.7955 | 29.273 | 1554.7148 | 63.2161 | 177.0823 |  | 9
6-11 | ONY | 1182719_HO26 | Skorts |  | all po |  |  | 17407 | 17407 | 0 | 855.8442 | 2026-07-11 | 2026-08-03 | 2026-08-05 | 2026-08-31 | 2026-09-02 | 2026-08-27 |  | 1.242 | 0.59 | 8 | 30.358 | 1288.3006 | 13.5116 | 161.328 |  | -4
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004922_T1_W |  |  | 720 | 720 | 0 | 63.6 | 2026-08-24 | 2026-08-19 | 2026-08-27 | 2026-09-01 | 2026-09-03 | 2026-10-01 |  | 0.88836 | 1.06 | 8 | 29.4464 | 497.5125 | 1.4472 | 62.3012 |  | 22
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 21000 | 17935 | 3065 | 1855 | 2026-08-24 | 2026-08-20 | 2026-08-28 | 2026-09-23 | 2026-09-25 | 2026-10-08 |  | 2.03 | 1.06 | 9 | 31 | 1346.4645 | 15.5964 | 149.8769 |  | 12
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004937_BA_E |  |  | 4528 | 0 | 4528 | 399.9733 | 2026-09-10 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-09-30 | 2026-10-12 |  | 2 | 1.06 | 9 | 31 | 1326.566 | 3.4133 | 147.662 |  | 12
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004936_BA_E |  |  | 7078 | 0 | 7078 | 625.2233 | 2026-08-29 | 2026-09-17 | 2026-09-24 | 2026-10-05 | 2026-10-07 | 2026-10-24 |  | 2 | 1.06 | 8.6 | 31 | 1267.6075 | 5.5837 | 147.662 |  | 17
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004947_BA_E |  |  | 6792 | 0 | 6792 | 599.96 | 2026-09-05 | 2026-09-25 | 2026-10-02 | 2026-10-10 | 2026-10-12 | 2026-10-26 |  | 2 | 1.06 | 8.6 | 31 | 1267.6075 | 5.3581 | 147.662 |  | 13
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004946_BA_E |  |  | 9078 | 0 | 9078 | 801.89 | 2026-09-05 | 2026-10-02 | 2026-10-08 | 2026-10-19 | 2026-10-21 | 2026-11-07 |  | 2 | 1.06 | 8.6 | 31 | 1267.6075 | 7.1615 | 147.662 |  | 17
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004950_BA_E |  |  | 3792 | 0 | 3792 | 334.96 | 2026-09-05 | 2026-10-10 | 2026-10-16 | 2026-10-22 | 2026-10-24 | 2026-11-09 |  | 2 | 1.06 | 8.6 | 31 | 1267.6075 | 2.9915 | 147.662 |  | 15
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004948_BA_E |  |  | 9078 | 0 | 9078 | 801.89 | 2026-09-05 | 2026-10-14 | 2026-10-20 | 2026-10-30 | 2026-11-01 | 2026-11-21 |  | 2 | 1.06 | 8.6 | 31 | 1267.6075 | 7.1615 | 147.662 |  | 19
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004939_BA_E |  |  | 6792 | 0 | 6792 | 599.96 | 2026-09-05 | 2026-10-22 | 2026-10-28 | 2026-11-05 | 2026-11-07 | 2026-11-23 |  | 2 | 1.06 | 8.6 | 31 | 1267.6075 | 5.3581 | 147.662 |  | 15
6-11 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004938_BA_E |  |  | 8928 | 0 | 8928 | 788.64 | 2026-09-05 | 2026-10-28 | 2026-11-03 | 2026-11-13 | 2026-11-15 | 2026-12-05 |  | 2 | 1.06 | 8.6 | 31 | 1267.6075 | 7.0432 | 147.662 |  | 19
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 580 | 0 | 580 | 25.1333 | 2026-10-24 | 2026-11-09 | 2026-11-11 | 2026-11-14 | 2026-11-16 | 2026-11-27 |  | 0.5 | 0.52 | 7 | 31 | 525.8077 | 1.1031 | 75.2508 |  | 11
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 1500 | 0 | 1500 | 65 | 2026-10-24 | 2026-11-10 | 2026-11-12 | 2026-11-16 | 2026-11-18 | 2026-11-27 |  | 1 | 0.52 | 8.6 | 31 | 1291.9846 | 1.161 | 150.5017 |  | 10
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 2500 | 0 | 2500 | 108.3333 | 2026-10-24 | 2026-11-11 | 2026-11-13 | 2026-11-18 | 2026-11-20 | 2026-11-27 |  | 1.2 | 0.52 | 8.6 | 31 | 1550.3815 | 1.6125 | 180.602 |  | 8
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 3000 | 0 | 3000 | 130 | 2026-10-24 | 2026-11-13 | 2026-11-16 | 2026-11-20 | 2026-11-22 | 2026-11-27 |  | 1.4 | 0.52 | 8.6 | 31 | 1808.7785 | 1.6586 | 210.7023 |  | 6
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_W |  |  | 5000 | 0 | 5000 | 216.6667 | 2026-10-26 | 2026-11-16 | 2026-11-18 | 2026-11-23 | 2026-11-25 | 2026-12-08 |  | 1.6 | 0.52 | 8.6 | 31 | 2067.1754 | 2.4188 | 240.8027 |  | 13
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_W |  |  | 7000 | 0 | 7000 | 303.3333 | 2026-10-26 | 2026-11-18 | 2026-11-20 | 2026-11-26 | 2026-11-28 | 2026-12-08 |  | 1.8 | 0.52 | 8.6 | 31 | 2325.5723 | 3.01 | 270.903 |  | 10
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_W |  |  | 18318 | 0 | 18318 | 793.78 | 2026-10-26 | 2026-11-21 | 2026-11-24 | 2026-12-04 | 2026-12-06 | 2026-12-08 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 7.0891 | 301.0033 |  | 3
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0328_E |  |  | 3138 | 0 | 3138 | 135.98 | 2026-11-02 | 2026-11-30 | 2026-12-02 | 2026-12-05 | 2026-12-07 | 2026-12-24 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 1.2144 | 301.0033 |  | 16
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0328_W |  |  | 12548 | 0 | 12548 | 543.7467 | 2026-11-02 | 2026-12-01 | 2026-12-03 | 2026-12-11 | 2026-12-13 | 2027-01-05 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 4.8561 | 301.0033 |  | 18
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0425_E |  |  | 6266 | 0 | 6266 | 271.5267 | 2026-11-09 | 2026-12-07 | 2026-12-09 | 2026-12-14 | 2026-12-16 | 2027-01-22 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 2.425 | 301.0033 |  | 31
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0425_W |  |  | 25066 | 0 | 25066 | 1086.1933 | 2026-11-09 | 2026-12-09 | 2026-12-11 | 2026-12-26 | 2026-12-28 | 2027-02-02 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 9.7006 | 301.0033 |  | 30
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0530_E |  |  | 1880 | 0 | 1880 | 81.4667 | 2026-11-16 | 2026-12-21 | 2026-12-23 | 2026-12-28 | 2026-12-30 | 2027-02-26 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 0.72756 | 301.0033 |  | 49
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0530_W |  |  | 7522 | 0 | 7522 | 325.9533 | 2026-11-16 | 2026-12-22 | 2026-12-24 | 2026-12-31 | 2027-01-02 | 2027-03-09 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 2.911 | 301.0033 |  | 53
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0627_E |  |  | 3138 | 0 | 3138 | 135.98 | 2026-11-23 | 2026-12-26 | 2026-12-29 | 2027-01-02 | 2027-01-04 | 2027-03-26 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 1.2144 | 301.0033 |  | 62
6-11 | TGT | 458476_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side) 筒型三本車(附右修刀); High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0627_W |  |  | 12548 | 0 | 12548 | 543.7467 | 2026-11-23 | 2026-12-28 | 2026-12-30 | 2027-01-09 | 2027-01-11 | 2027-04-06 |  | 2 | 0.52 | 8.6 | 31 | 2583.9692 | 4.8561 | 301.0033 |  | 66
2026-04-23
6-12 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 36158 | 36158 | 0 | 3163.825 | 2026-05-04 | 2026-04-18 | 2026-04-21 | 2026-05-26 | 2026-05-31 | 2026-07-23 |  | 1.6893 | 1.05 | 9.1441 | 37.1237 | 1376.3212 | 26.2715 | 150.7858 |  | 47
6-12 | ONY | 907938_FA26 | Leggings | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | all po |  |  | 1178 | 1178 | 0 | 89.3317 | 2026-05-07 | 2026-05-21 | 2026-05-23 | 2026-05-29 | 2026-05-31 | 2026-06-11 |  | 0.65017 | 0.91 | 7.881 | 35.392 | 502.1956 | 2.3457 | 63.837 |  | 10
6-12 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 31999 | 31999 | 0 | 3706.5508 | 2026-06-03 | 2026-05-23 | 2026-05-26 | 2026-07-09 | 2026-07-11 | 2026-07-09 |  | 1.5521 | 1.39 | 9.4353 | 36.0815 | 957.9881 | 33.4023 | 101.7153 |  | 0
6-12 | ONY | 910047_HO26DIS | Pajama |  | all po |  |  | 27677 | 27677 | 0 | 3275.1117 | 2026-07-06 | 2026-07-04 | 2026-07-07 | 2026-08-13 | 2026-08-15 | 2026-09-03 |  | 1.7232 | 1.42 | 8.2028 | 37.8066 | 948.3748 | 29.1836 | 115.8242 |  | 13
6-12 | TGT | X25413_C426 | Pull On Pants |  | all po |  |  | 3075 | 3075 | 0 | 374.125 | 2026-07-06 | 2026-08-07 | 2026-08-11 | 2026-08-26 | 2026-08-28 | 2026-09-01 |  | 0.88558 | 1.46 | 8 | 37.3443 | 456.6583 | 6.7337 | 57.1852 |  | 4
6-12 | KOH | ZC6HY000 | Gown |  | 16439999, 00, 001 |  |  | 18161 | 18161 | 0 | 998.855 | 2026-07-30 | 2026-08-19 | 2026-08-21 | 2026-09-14 | 2026-09-16 | 2026-09-28 |  | 1.0893 | 0.66 | 8.7494 | 37.3523 | 1359.1938 | 13.3616 | 155.6278 |  | 10
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021697_T1 |  |  | 5320 | 3618 | 1702 | 487.6667 | 2026-09-08 | 2026-09-08 | 2026-09-10 | 2026-09-22 | 2026-09-24 | 2026-10-22 |  | 1.22 | 1.1 | 9 | 38.2541 | 962.2498 | 5.5287 | 107.1094 |  | 25
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 2666 | 0 | 2666 | 244.3833 | 2026-09-08 | 2026-09-16 | 2026-09-18 | 2026-09-24 | 2026-09-26 | 2026-10-29 |  | 1.4 | 1.1 | 9 | 38.2541 | 1104.2211 | 2.4144 | 122.9125 |  | 29
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 5000 | 0 | 5000 | 458.3333 | 2026-09-08 | 2026-09-18 | 2026-09-22 | 2026-09-30 | 2026-10-02 | 2026-10-29 |  | 1.6 | 1.1 | 9 | 38.2541 | 1261.967 | 3.9621 | 140.4714 |  | 25
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021698_SET |  |  | 10666 | 0 | 10666 | 977.7167 | 2026-09-08 | 2026-09-24 | 2026-09-28 | 2026-10-09 | 2026-10-11 | 2026-10-29 |  | 1.8 | 1.1 | 8.6 | 38.2541 | 1356.6145 | 7.8622 | 158.0303 |  | 17
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021703 |  |  | 13396 | 0 | 13396 | 1227.9667 | 2026-09-08 | 2026-10-05 | 2026-10-07 | 2026-10-20 | 2026-10-22 | 2026-11-18 |  | 2 | 1.1 | 8.6 | 38.2541 | 1507.3495 | 8.8871 | 175.5893 |  | 25
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021702 |  |  | 11676 | 0 | 11676 | 1070.3 | 2026-09-08 | 2026-10-15 | 2026-10-17 | 2026-10-29 | 2026-10-31 | 2026-12-02 |  | 2 | 1.1 | 8.6 | 38.2541 | 1507.3495 | 7.746 | 175.5893 |  | 29
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021705 |  |  | 19352 | 0 | 19352 | 1773.9333 | 2026-09-08 | 2026-10-24 | 2026-10-27 | 2026-11-13 | 2026-11-15 | 2026-12-16 |  | 2 | 1.1 | 8.6 | 38.2541 | 1507.3495 | 12.8384 | 175.5893 |  | 28
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021704 |  |  | 23352 | 0 | 23352 | 2140.6 | 2026-09-15 | 2026-11-09 | 2026-11-11 | 2026-12-01 | 2026-12-03 | 2026-12-30 |  | 2 | 1.1 | 8.6 | 38.2541 | 1507.3495 | 15.4921 | 175.5893 |  | 24
6-12 | TGT | 9KM9L2_C227 | Pull On Pants |  | 0321_T1 |  |  | 2593 | 0 | 2593 | 237.6917 | 2026-11-30 | 2026-11-26 | 2026-11-28 | 2026-12-03 | 2026-12-05 | 2027-01-02 |  | 2 | 1.1 | 8.6 | 38.2541 | 1507.3495 | 1.7202 | 175.5893 |  | 24
6-12 | TGT | 9KM9L2_C227 | Pull On Pants |  | 0328 |  |  | 19454 | 0 | 19454 | 1783.2833 | 2026-12-03 | 2026-11-28 | 2026-12-01 | 2026-12-18 | 2026-12-20 | 2027-01-05 |  | 2 | 1.1 | 8.6 | 38.2541 | 1507.3495 | 12.9061 | 175.5893 |  | 12
6-12 | TGT | 9KM9L2_C227 | Pull On Pants |  | 0404 |  |  | 2594 | 0 | 2594 | 237.7833 | 2026-12-10 | 2026-12-14 | 2026-12-16 | 2026-12-21 | 2026-12-23 | 2027-01-12 |  | 2 | 1.1 | 8.6 | 38.2541 | 1507.3495 | 1.7209 | 175.5893 |  | 16
6-12 | TGT | 9KM9L2_C127 | Pull On Pants |  | 10002021707 |  |  | 11676 | 0 | 11676 | 1070.3 | 2026-11-06 | 2026-12-16 | 2026-12-18 | 2026-12-31 | 2027-01-02 | 2027-01-13 |  | 2 | 1.1 | 8.6 | 38.2541 | 1507.3495 | 7.746 | 175.5893 |  | 9
6-12 | TGT | 9KM9L2_C227 | Pull On Pants |  | 0418 |  |  | 2594 | 0 | 2594 | 237.7833 | 2026-12-24 | 2026-12-26 | 2026-12-29 | 2027-01-04 | 2027-01-06 | 2027-01-26 |  | 2 | 1.1 | 8.6 | 38.2541 | 1507.3495 | 1.7209 | 175.5893 |  | 18
2026-07-01
6-13 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 15589 | 15589 | 0 | 1364.0375 | 2026-05-26 | 2026-06-26 | 2026-06-29 | 2026-07-16 | 2026-07-21 | 2026-07-30 |  | 1.5565 | 1.05 | 9.3933 | 34.0142 | 1193.554 | 13.061 | 127.2931 |  | 12
6-13 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 10000 | 10000 | 0 | 875 | 2026-06-23 | 2026-07-11 | 2026-07-14 | 2026-07-27 | 2026-08-01 | 2026-08-20 |  | 1.7463 | 1.05 | 7.9762 | 33.0413 | 1104.5568 | 9.0534 | 138.7318 |  | 18
6-13 | ONY | 1182723_HO26 | Skorts |  | all po |  |  | 32276 | 32276 | 0 | 2447.5967 | 2026-07-14 | 2026-07-22 | 2026-07-24 | 2026-09-03 | 2026-09-05 | 2026-10-01 |  | 1.5586 | 0.91 | 7.8718 | 34.6897 | 1178.6229 | 27.3845 | 149.9965 |  | 20
6-13 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 20847 | 20847 | 0 | 920.7425 | 2026-08-06 | 2026-08-28 | 2026-09-01 | 2026-09-18 | 2026-09-20 | 2026-09-17 |  | 1.3116 | 0.53 | 8.8611 | 34.4485 | 1903.6095 | 10.9513 | 215.2163 |  | -3
6-13 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016283, 292, 296 |  |  | 21450 | 3237 | 18213 | 947.375 | 2026-08-06 | 2026-09-14 | 2026-09-16 | 2026-10-01 | 2026-10-03 | 2026-10-15 |  | 1.6 | 0.53 | 9 | 35 | 2396.3774 | 8.951 | 266.7443 |  | 12
6-13 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016287 |  |  | 7319 | 0 | 7319 | 323.2558 | 2026-08-06 | 2026-09-25 | 2026-09-29 | 2026-10-05 | 2026-10-07 | 2026-11-12 |  | 1.6 | 0.53 | 8.6 | 35 | 2289.8717 | 3.1962 | 266.7443 |  | 33
6-13 | ONY | 1194432_SP27 | Tee |  | 62344810 |  |  | 761 | 0 | 761 | 40.5867 | 2026-10-09 | 2026-09-30 | 2026-10-02 | 2026-10-07 | 2026-10-09 | 2026-10-28 |  | 0.5 | 0.64 | 7 | 35 | 482.3438 | 1.5777 | 69.0305 |  | 18
6-13 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 1586 | 0 | 1586 | 84.5867 | 2026-10-09 | 2026-10-02 | 2026-10-05 | 2026-10-08 | 2026-10-10 | 2026-10-29 |  | 1 | 0.64 | 8.6 | 35 | 1185.1875 | 1.3382 | 138.061 |  | 18
6-13 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 2500 | 0 | 2500 | 133.3333 | 2026-10-09 | 2026-10-03 | 2026-10-06 | 2026-10-10 | 2026-10-12 | 2026-10-29 |  | 1.2 | 0.64 | 8.6 | 35 | 1422.225 | 1.7578 | 165.6732 |  | 16
6-13 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 3500 | 0 | 3500 | 186.6667 | 2026-10-09 | 2026-10-06 | 2026-10-08 | 2026-10-13 | 2026-10-15 | 2026-10-29 |  | 1.4 | 0.64 | 8.6 | 35 | 1659.2625 | 2.1094 | 193.2854 |  | 14
6-13 | ONY | 1194432_SP27 | Tee |  | 62314873, 025, 240 |  |  | 4000 | 0 | 4000 | 213.3333 | 2026-10-09 | 2026-10-08 | 2026-10-10 | 2026-10-15 | 2026-10-17 | 2026-10-29 |  | 1.6 | 0.64 | 8.6 | 35 | 1896.3 | 2.1094 | 220.8976 |  | 12
6-13 | ONY | 1194432_SP27 | Tee |  | 62344978 |  |  | 288 | 0 | 288 | 15.36 | 2026-10-09 | 2026-10-10 | 2026-10-13 | 2026-10-15 | 2026-10-17 | 2026-11-04 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 0.135 | 248.5098 |  | 17
6-13 | ONY | 1194432_SP27 | Tee |  | 62323026, 027, 733, 738, 744, 745 |  |  | 32475 | 0 | 32475 | 1732 | 2026-10-09 | 2026-10-10 | 2026-10-13 | 2026-11-02 | 2026-11-04 | 2026-11-05 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 15.2226 | 248.5098 |  | 3
6-13 | ONY | 1194432_SP27 | Tee |  | 62377441, 442, 182, 113, 170, 255 |  |  | 6632 | 0 | 6632 | 353.7067 | 2026-11-13 | 2026-10-28 | 2026-10-30 | 2026-11-05 | 2026-11-07 | 2026-11-26 |  | 2 | 0.64 | 8.6 | 35 | 2370.375 | 2.7979 | 276.122 |  | 18
6-13 | ONY | 1194432_SP27 | Tee |  | 62344833 |  |  | 126 | 0 | 126 | 6.72 | 2026-11-13 | 2026-10-31 | 2026-11-03 | 2026-11-05 | 2026-11-07 | 2026-12-02 |  | 2 | 0.64 | 8.6 | 35 | 2370.375 | 0.053156 | 276.122 |  | 23
6-13 | ONY | 1194432_SP27 | Tee |  | 62379115 |  |  | 55924 | 0 | 55924 | 2982.6133 | 2026-11-06 | 2026-10-31 | 2026-11-03 | 2026-12-03 | 2026-12-05 | 2026-12-03 |  | 2 | 0.64 | 8.6 | 35 | 2370.375 | 23.5929 | 276.122 |  | 0
6-13 | ONY | 1194432_SP27 | Tee |  | 12.24 |  |  | 11866 | 0 | 11866 | 632.8533 | 2026-11-30 | 2026-11-28 | 2026-12-01 | 2026-12-09 | 2026-12-11 | 2026-12-24 |  | 2 | 0.64 | 8.6 | 35 | 2370.375 | 5.006 | 276.122 |  | 13
6-13 | ONY | 1194432_SP27 | Tee |  | 12.31 |  |  | 26558 | 0 | 26558 | 1416.4267 | 2026-11-30 | 2026-12-04 | 2026-12-07 | 2026-12-22 | 2026-12-24 | 2026-12-31 |  | 2 | 0.64 | 8.6 | 35 | 2370.375 | 11.2041 | 276.122 |  | 7
6-13 | ONY | 1194432_SP27 | Tee |  | 01.21 |  |  | 8902 | 0 | 8902 | 474.7733 | 2026-11-30 | 2026-12-17 | 2026-12-19 | 2026-12-28 | 2026-12-30 | 2027-01-21 |  | 2 | 0.64 | 8.6 | 35 | 2370.375 | 3.7555 | 276.122 |  | 19
6-13 | ONY | 1194432_SP27 | Tee |  | 01.28 |  |  | 19778 | 0 | 19778 | 1054.8267 | 2026-11-30 | 2026-12-22 | 2026-12-24 | 2027-01-08 | 2027-01-10 | 2027-01-28 |  | 2 | 0.64 | 8.6 | 35 | 2370.375 | 8.3438 | 276.122 |  | 17
2026-05-29
6-14 | TGT | MRLPMM_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 41982 | 41982 | 0 | 3148.65 | 2026-05-26 | 2026-05-20 | 2026-05-26 | 2026-06-30 | 2026-07-02 | 2026-07-25 |  | 1.9917 | 0.9 | 9.4588 | 31.818 | 1678.4133 | 25.0129 | 177.7655 |  | 22
6-14 | TGT | G9M018_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 67974 | 67974 | 0 | 4814.825 | 2026-06-25 | 2026-06-22 | 2026-06-27 | 2026-08-18 | 2026-08-20 | 2026-08-22 |  | 1.8952 | 0.85 | 8.5318 | 36.0905 | 1730.0941 | 39.2892 | 203.1487 |  | 3
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 10002039574, 76, 78 |  |  | 10452 | 10452 | 0 | 1315.21 | 2026-08-22 | 2026-08-11 | 2026-08-13 | 2026-09-11 | 2026-09-13 | 2026-10-05 |  | 1.1829 | 1.51 | 8.5852 | 36.4735 | 618.1324 | 16.909 | 72.13 |  | 17
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 10002039579 |  |  | 4176 | 4176 | 0 | 525.48 | 2026-08-22 | 2026-09-07 | 2026-09-09 | 2026-09-18 | 2026-09-20 | 2026-11-16 |  | 1.4365 | 1.51 | 9 | 36.3466 | 784.2106 | 5.3251 | 87.2916 |  | 48
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 10002039580 |  |  | 4176 | 823 | 3353 | 525.48 | 2026-08-22 | 2026-09-14 | 2026-09-16 | 2026-09-24 | 2026-09-26 | 2026-11-30 |  | 1.85 | 1.51 | 9 | 35.1606 | 976.9993 | 4.2743 | 108.7512 |  | 56
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 10002039581 |  |  | 4176 | 0 | 4176 | 525.48 | 2026-08-22 | 2026-09-18 | 2026-09-22 | 2026-10-01 | 2026-10-03 | 2026-12-14 |  | 1.6 | 1.51 | 8.6 | 35.1606 | 807.418 | 5.172 | 94.0551 |  | 63
6-14 | TGT | 00GG4Z_C127IND | Pull On Pants |  | 10002039582 |  |  | 3036 | 0 | 3036 | 382.03 | 2026-08-22 | 2026-09-25 | 2026-09-29 | 2026-10-06 | 2026-10-08 | 2026-12-28 |  | 1.6 | 1.51 | 8.6 | 35.1606 | 807.418 | 3.7601 | 94.0551 |  | 70
6-14 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 750 | 0 | 750 | 105 | 2026-09-12 | 2026-09-28 | 2026-10-03 | 2026-10-10 | 2026-10-12 | 2026-10-29 |  | 0.5 | 1.68 | 7 | 35.1606 | 184.5932 | 4.063 | 26.418 |  | 16
6-14 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 1500 | 0 | 1500 | 210 | 2026-09-12 | 2026-10-02 | 2026-10-08 | 2026-10-14 | 2026-10-16 | 2026-10-29 |  | 1 | 1.68 | 8.6 | 35.1606 | 453.5719 | 3.3071 | 52.836 |  | 13
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 740 | 0 | 740 | 45.0167 | 2026-10-15 | 2026-10-09 | 2026-10-12 | 2026-10-16 | 2026-10-18 | 2026-11-06 |  | 0.5 | 0.73 | 7 | 35.1606 | 424.8172 | 1.7419 | 60.7976 |  | 18
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 1500 | 0 | 1500 | 91.25 | 2026-10-15 | 2026-10-12 | 2026-10-14 | 2026-10-17 | 2026-10-19 | 2026-11-06 |  | 1 | 0.73 | 8.6 | 35.1606 | 1043.8366 | 1.437 | 121.5952 |  | 17
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 2500 | 0 | 2500 | 152.0833 | 2026-10-15 | 2026-10-13 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-11-06 |  | 1.2 | 0.73 | 8.6 | 35.1606 | 1252.604 | 1.9958 | 145.9143 |  | 15
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 3500 | 0 | 3500 | 212.9167 | 2026-10-15 | 2026-10-15 | 2026-10-17 | 2026-10-22 | 2026-10-24 | 2026-11-06 |  | 1.4 | 0.73 | 8.6 | 35.1606 | 1461.3713 | 2.395 | 170.2333 |  | 13
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 5000 | 0 | 5000 | 304.1667 | 2026-10-15 | 2026-10-17 | 2026-10-20 | 2026-10-26 | 2026-10-28 | 2026-11-09 |  | 1.6 | 0.73 | 8.6 | 35.1606 | 1670.1386 | 2.9938 | 194.5524 |  | 12
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 5000 | 0 | 5000 | 304.1667 | 2026-10-15 | 2026-10-21 | 2026-10-23 | 2026-10-29 | 2026-10-31 | 2026-11-06 |  | 1.8 | 0.73 | 8.6 | 35.1606 | 1878.9059 | 2.6611 | 218.8714 |  | 7
6-14 | TGT | L06X27_SSLLC127 | Pajama |  | 1206 |  |  | 16000 | 0 | 16000 | 973.3333 | 2026-10-15 | 2026-10-24 | 2026-10-27 | 2026-11-07 | 2026-11-09 | 2026-11-06 |  | 2 | 0.73 | 8.6 | 35.1606 | 2087.6733 | 7.664 | 243.1904 |  | -3
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 716 | 0 | 716 | 72.7933 | 2026-11-05 | 2026-11-03 | 2026-11-05 | 2026-11-11 | 2026-11-13 | 2026-11-30 |  | 0.5 | 1.22 | 7 | 35.1606 | 254.1939 | 2.8167 | 36.3789 |  | 16
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 1500 | 0 | 1500 | 152.5 | 2026-11-05 | 2026-11-06 | 2026-11-09 | 2026-11-13 | 2026-11-15 | 2026-11-30 |  | 1 | 1.22 | 8.6 | 35.1606 | 624.5908 | 2.4016 | 72.7578 |  | 14
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 2500 | 0 | 2500 | 254.1667 | 2026-11-05 | 2026-11-09 | 2026-11-11 | 2026-11-18 | 2026-11-20 | 2026-11-30 |  | 1.1 | 1.22 | 8.6 | 35.1606 | 687.0498 | 3.6387 | 80.0336 |  | 10
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 3000 | 0 | 3000 | 305 | 2026-11-05 | 2026-11-13 | 2026-11-16 | 2026-11-23 | 2026-11-25 | 2026-11-30 |  | 1.2 | 1.22 | 8.6 | 35.1606 | 749.5089 | 4.0026 | 87.3094 |  | 6
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 4000 | 0 | 4000 | 406.6667 | 2026-11-05 | 2026-11-18 | 2026-11-20 | 2026-11-28 | 2026-11-30 | 2026-11-30 |  | 1.4 | 1.22 | 8.6 | 35.1606 | 874.4271 | 4.5744 | 101.8609 |  | 1
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 3000 | 0 | 3000 | 305 | 2026-11-05 | 2026-11-24 | 2026-11-26 | 2026-12-02 | 2026-12-04 | 2026-12-07 |  | 1.6 | 1.22 | 8.6 | 35.1606 | 999.3452 | 3.002 | 116.4125 |  | 4
6-14 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 5516 | 0 | 5516 | 560.7933 | 2026-11-05 | 2026-11-27 | 2026-11-30 | 2026-12-08 | 2026-12-10 | 2026-12-07 |  | 1.8 | 1.22 | 8.6 | 35.1606 | 1124.2634 | 4.9063 | 130.964 |  | -3
6-14 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0321 |  |  | 716 | 0 | 716 | 115.1567 | 2026-12-04 | 2026-12-03 | 2026-12-05 | 2026-12-12 | 2026-12-14 | 2027-01-09 |  | 0.5 | 1.93 | 7 | 35.1606 | 160.6822 | 4.456 | 22.996 |  | 21
6-14 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0321 |  |  | 1500 | 0 | 1500 | 241.25 | 2026-12-04 | 2026-12-08 | 2026-12-10 | 2026-12-17 | 2026-12-19 | 2027-01-09 |  | 1 | 1.93 | 8.6 | 35.1606 | 394.819 | 3.7992 | 45.992 |  | 17
6-14 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0321 |  |  | 2500 | 0 | 2500 | 402.0833 | 2026-12-04 | 2026-12-12 | 2026-12-15 | 2026-12-24 | 2026-12-26 | 2027-01-09 |  | 1.1 | 1.93 | 8.6 | 35.1606 | 434.3009 | 5.7564 | 50.5912 |  | 11
6-14 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0321 |  |  | 2700 | 0 | 2700 | 434.25 | 2026-12-04 | 2026-12-19 | 2026-12-22 | 2027-01-02 | 2027-01-04 | 2027-01-09 |  | 1.2 | 1.93 | 8.6 | 35.1606 | 473.7828 | 5.6988 | 55.1904 |  | 5
6-14 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0328 |  |  | 5022 | 0 | 5022 | 807.705 | 2026-12-04 | 2026-12-28 | 2026-12-30 | 2027-01-15 | 2027-01-17 | 2027-01-16 |  | 1.3 | 1.93 | 8.6 | 35.1606 | 513.2647 | 9.7844 | 59.7896 |  | 1
6-14 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0404 |  |  | 4522 | 0 | 4522 | 727.2883 | 2026-12-11 | 2027-01-11 | 2027-01-13 | 2027-01-25 | 2027-01-27 | 2027-01-23 |  | 1.4 | 1.93 | 8.6 | 35.1606 | 552.7467 | 8.181 | 64.3888 |  | -3
6-14 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0418 |  |  | 5022 | 0 | 5022 | 807.705 | 2026-12-26 | 2027-01-20 | 2027-01-22 | 2027-02-03 | 2027-02-05 | 2027-02-06 |  | 1.5 | 1.93 | 8.6 | 35.1606 | 592.2286 | 8.4798 | 68.988 |  | 2
6-14 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0502 |  |  | 5024 | 0 | 5024 | 808.0267 | 2027-01-08 | 2027-01-29 | 2027-02-01 | 2027-02-13 | 2027-02-15 | 2027-02-20 |  | 1.5 | 1.93 | 8.6 | 35.1606 | 592.2286 | 8.4832 | 68.988 |  | 6
6-14 | TGT | LR16E1_C227 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; High Speed Zig-Zag Sewing Machine 人字車; | 0516 |  |  | 3767.5 | 0 | 3767.5 | 605.9396 | 2027-01-22 | 2027-02-09 | 2027-02-11 | 2027-02-20 | 2027-02-22 | 2027-03-06 |  | 1.5 | 1.93 | 8.6 | 35.1606 | 592.2286 | 6.3616 | 68.988 |  | 12
2026-06-10
6-15 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 12675 | 12675 | 0 | 1468.1875 | 2026-06-03 | 2026-06-05 | 2026-06-08 | 2026-06-27 | 2026-06-29 | 2026-07-09 |  | 1.4468 | 1.39 | 9.1261 | 37.5708 | 899.3507 | 14.0935 | 98.7251 |  | 10
6-15 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 24345 | 24345 | 0 | 2130.1875 | 2026-05-26 | 2026-06-23 | 2026-06-25 | 2026-07-16 | 2026-07-21 | 2026-07-30 |  | 1.8746 | 1.05 | 9.3739 | 36.7685 | 1550.6758 | 15.6996 | 165.723 |  | 12
6-15 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 5783 | 5783 | 0 | 506.0125 | 2026-06-23 | 2026-07-11 | 2026-07-14 | 2026-07-22 | 2026-07-27 | 2026-08-20 |  | 1.6985 | 1.05 | 7.855 | 37.8144 | 1210.7956 | 4.7762 | 154.4219 |  | 22
6-15 | HLF | CPM263TL32_26Q4 | Tee | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 25311 | 25311 | 0 | 1898.325 | 2026-07-10 | 2026-07-14 | 2026-07-20 | 2026-08-20 | 2026-08-22 | 2026-08-21 |  | 1.4303 | 0.9 | 7.6394 | 37.2943 | 1140.9978 | 22.1832 | 149.6259 |  | 1
6-15 | SMA | LPST840 | Pull On Pants |  | 1352772, _AH |  |  | 4836 | 4836 | 0 | 596.44 | 2026-08-18 | 2026-08-13 | 2026-08-18 | 2026-09-02 | 2026-09-04 | 2026-09-22 |  | 1.1218 | 1.48 | 8.4698 | 37.5236 | 607.0652 | 7.9662 | 71.8036 |  | 14
6-15 | SMA | LPST840 | Pull On Pants |  | 1354810_SS, _AH |  |  | 79 | 79 | 0 | 9.7433 | 2026-08-18 | 2026-08-27 | 2026-08-31 | 2026-09-02 | 2026-09-04 | 2026-09-23 |  | 0.32977 | 1.48 | 9 | 37 | 186.9822 | 0.4225 | 20.8133 |  | 15
6-15 | SMA | LPST840 | Pull On Pants |  | 1352773, _AH |  |  | 5900 | 5900 | 0 | 727.6667 | 2026-08-24 | 2026-08-27 | 2026-08-31 | 2026-09-14 | 2026-09-16 | 2026-10-02 |  | 1.3628 | 1.48 | 8.5944 | 37.7478 | 752.8195 | 7.8372 | 87.7519 |  | 14
6-15 | SMA | PST840 | Pull On Pants |  | 1352813, _AH |  |  | 2006 | 1955 | 51 | 272.4817 | 2026-08-18 | 2026-09-08 | 2026-09-10 | 2026-09-16 | 2026-09-18 | 2026-09-22 |  | 1.65 | 1.63 | 9 | 36.6361 | 841.1024 | 2.385 | 93.6243 |  | 4
6-15 | SMA | LPST840 | Pull On Pants |  | 1352773, _AH |  |  | 1884 | 1884 | 0 | 232.36 | 2026-08-24 | 2026-09-10 | 2026-09-14 | 2026-09-18 | 2026-09-20 | 2026-10-02 |  | 1.539 | 1.48 | 9 | 37.3004 | 879.6751 | 2.1417 | 97.9179 |  | 10
6-15 | SMA | LPST840 | Pull On Pants |  | 1352774, _AH |  |  | 7368 | 530 | 6838 | 908.72 | 2026-09-14 | 2026-09-14 | 2026-09-16 | 2026-09-30 | 2026-10-02 | 2026-11-02 |  | 1.65 | 1.48 | 9 | 37 | 935.55 | 7.8756 | 104.1374 |  | 28
6-15 | SMA | PST840 | Pull On Pants |  | 1352815, _AH |  |  | 1500 | 0 | 1500 | 203.75 | 2026-09-14 | 2026-09-24 | 2026-09-28 | 2026-10-02 | 2026-10-04 | 2026-11-02 |  | 1.65 | 1.63 | 8.6 | 37 | 811.7028 | 1.848 | 94.5542 |  | 26
6-15 | SMA | PST840 | Pull On Pants |  | 1352816, _AH |  |  | 2816 | 0 | 2816 | 382.5067 | 2026-10-05 | 2026-09-28 | 2026-09-30 | 2026-10-06 | 2026-10-08 | 2026-12-03 |  | 1.65 | 1.63 | 8.6 | 37.461 | 821.8166 | 3.4266 | 95.7324 |  | 50
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 750 | 0 | 750 | 105 | 2026-09-12 | 2026-09-28 | 2026-10-03 | 2026-10-10 | 2026-10-12 | 2026-10-29 |  | 0.5 | 1.68 | 7 | 37 | 194.25 | 3.861 | 27.8 |  | 16
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 1500 | 0 | 1500 | 210 | 2026-09-12 | 2026-10-02 | 2026-10-08 | 2026-10-14 | 2026-10-16 | 2026-10-29 |  | 1 | 1.68 | 8.6 | 37 | 477.3 | 3.1427 | 55.6001 |  | 13
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 2000 | 0 | 2000 | 280 | 2026-09-12 | 2026-10-06 | 2026-10-12 | 2026-10-19 | 2026-10-21 | 2026-10-29 |  | 1.1 | 1.68 | 8.6 | 37 | 525.03 | 3.8093 | 61.1601 |  | 9
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 3000 | 0 | 3000 | 420 | 2026-09-12 | 2026-10-10 | 2026-10-16 | 2026-10-24 | 2026-10-26 | 2026-10-29 |  | 1.2 | 1.68 | 8.6 | 37 | 572.76 | 5.2378 | 66.7201 |  | 4
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0130 |  |  | 4332 | 0 | 4332 | 606.48 | 2026-10-03 | 2026-10-16 | 2026-10-22 | 2026-10-31 | 2026-11-02 | 2026-11-09 |  | 1.4 | 1.68 | 8.6 | 37 | 668.22 | 6.4829 | 77.8401 |  | 7
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0213 |  |  | 4000 | 0 | 4000 | 560 | 2026-10-17 | 2026-10-23 | 2026-10-29 | 2026-11-07 | 2026-11-09 | 2026-11-23 |  | 1.5 | 1.68 | 8.6 | 37 | 715.95 | 5.587 | 83.4001 |  | 13
6-15 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0227 |  |  | 4452 | 0 | 4452 | 623.28 | 2026-10-31 | 2026-10-30 | 2026-11-05 | 2026-11-14 | 2026-11-16 | 2026-12-07 |  | 1.6 | 1.68 | 8.6 | 37 | 763.68 | 5.8297 | 88.9601 |  | 19
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 1500 | 0 | 1500 | 52.5 | 2026-11-13 | 2026-11-10 | 2026-11-12 | 2026-11-17 | 2026-11-19 | 2026-11-27 |  | 0.5 | 0.42 | 7 | 35 | 735 | 2.0408 | 105.1893 |  | 9
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 3500 | 0 | 3500 | 122.5 | 2026-11-13 | 2026-11-12 | 2026-11-14 | 2026-11-19 | 2026-11-21 | 2026-11-27 |  | 1 | 0.42 | 8.6 | 35 | 1806 | 1.938 | 210.3787 |  | 7
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 5000 | 0 | 5000 | 175 | 2026-11-13 | 2026-11-14 | 2026-11-17 | 2026-11-21 | 2026-11-23 | 2026-11-27 |  | 1.2 | 0.42 | 8.6 | 35 | 2167.2 | 2.3071 | 252.4544 |  | 5
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 5000 | 0 | 5000 | 175 | 2026-11-13 | 2026-11-17 | 2026-11-19 | 2026-11-24 | 2026-11-26 | 2026-11-27 |  | 1.4 | 0.42 | 8.6 | 35 | 2528.4 | 1.9775 | 294.5302 |  | 3
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 10000 | 0 | 10000 | 350 | 2026-11-13 | 2026-11-19 | 2026-11-21 | 2026-11-27 | 2026-11-29 | 2026-11-27 |  | 1.6 | 0.42 | 8.6 | 35 | 2889.6 | 3.4607 | 336.6059 |  | 0
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_W |  |  | 10000 | 0 | 10000 | 350 | 2026-11-13 | 2026-11-23 | 2026-11-25 | 2026-12-01 | 2026-12-03 | 2026-12-08 |  | 1.8 | 0.42 | 8.6 | 35 | 3250.8 | 3.0762 | 378.6816 |  | 6
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_W |  |  | 20000 | 0 | 20000 | 700 | 2026-11-13 | 2026-11-26 | 2026-11-28 | 2026-12-08 | 2026-12-10 | 2026-12-08 |  | 2 | 0.42 | 8.6 | 35 | 3612 | 5.5371 | 420.7574 |  | 0
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0314_W |  |  | 10000 | 0 | 10000 | 350 | 2026-11-13 | 2026-12-03 | 2026-12-05 | 2026-12-11 | 2026-12-13 | 2026-12-11 |  | 2 | 0.42 | 8.6 | 35 | 3612 | 2.7685 | 420.7574 |  | 0
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0328_W |  |  | 26640 | 0 | 26640 | 932.4 | 2026-12-11 | 2026-12-07 | 2026-12-09 | 2026-12-19 | 2026-12-21 | 2026-12-24 |  | 2 | 0.42 | 8.6 | 35 | 3612 | 7.3754 | 420.7574 |  | 4
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0411_W |  |  | 26640 | 0 | 26640 | 932.4 | 2026-12-11 | 2026-12-15 | 2026-12-17 | 2026-12-29 | 2026-12-31 | 2027-01-08 |  | 2 | 0.42 | 8.6 | 35 | 3612 | 7.3754 | 420.7574 |  | 7
6-15 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0418_W |  |  | 26640 | 0 | 26640 | 932.4 | 2027-01-08 | 2026-12-23 | 2026-12-26 | 2027-01-08 | 2027-01-10 | 2027-01-15 |  | 2 | 0.42 | 8.6 | 35 | 3612 | 7.3754 | 420.7574 |  | 6
2026-04-12
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 55281 | 55281 | 0 | 4837.0875 | 2026-05-07 | 2026-04-08 | 2026-04-10 | 2026-05-30 | 2026-06-04 | 2026-07-30 |  | 1.7381 | 1.05 | 9.2232 | 36.7546 | 1414.0742 | 39.0934 | 153.5931 |  | 50
6-16 | TGT | G917K0_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 43173 | 43173 | 0 | 4497.1875 | 2026-05-26 | 2026-05-21 | 2026-05-28 | 2026-07-11 | 2026-07-13 | 2026-07-25 |  | 1.8617 | 1.25 | 9.2646 | 36.899 | 1283.0131 | 33.6497 | 138.7353 |  | 12
6-16 | TGT | G9M018_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 41073 | 41073 | 0 | 2909.3375 | 2026-06-25 | 2026-07-03 | 2026-07-09 | 2026-08-07 | 2026-08-09 | 2026-08-22 |  | 1.9856 | 0.85 | 8.0933 | 37.783 | 1800.1043 | 22.817 | 222.8196 |  | 9
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 3586 | 3586 | 0 | 313.775 | 2026-06-23 | 2026-08-03 | 2026-08-05 | 2026-08-12 | 2026-08-17 | 2026-09-24 |  | 1.5382 | 1.05 | 8 | 37.0838 | 1095.2295 | 3.2742 | 137.1506 |  | 29
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 54087 | 41045 | 13042 | 4732.6125 | 2026-08-20 | 2026-08-06 | 2026-08-10 | 2026-09-30 | 2026-10-05 | 2026-10-15 |  | 1.98 | 1.05 | 9 | 38 | 1625.184 | 33.2805 | 180.9016 |  | 13
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 5873 | 0 | 5873 | 513.8875 | 2026-08-20 | 2026-09-24 | 2026-09-28 | 2026-10-05 | 2026-10-10 | 2026-10-15 |  | 2.1 | 1.05 | 8.6 | 38 | 1647.072 | 3.5657 | 191.8654 |  | 9
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.29 |  |  | 165 | 0 | 165 | 14.4375 | 2026-08-18 | 2026-09-30 | 2026-10-02 | 2026-10-05 | 2026-10-10 | 2026-10-29 |  | 2.2 | 1.05 | 8.6 | 38 | 1725.504 | 0.095624 | 201.0018 |  | 21
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 11.12 |  |  | 4477 | 0 | 4477 | 391.7375 | 2026-08-20 | 2026-09-30 | 2026-10-02 | 2026-10-08 | 2026-10-13 | 2026-11-12 |  | 2.2 | 1.05 | 8.6 | 38 | 1725.504 | 2.5946 | 201.0018 |  | 30
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 11.26 |  |  | 165 | 0 | 165 | 14.4375 | 2026-08-20 | 2026-10-03 | 2026-10-06 | 2026-10-08 | 2026-10-13 | 2026-11-26 |  | 2.2 | 1.05 | 8.6 | 38 | 1725.504 | 0.095624 | 201.0018 |  | 42
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 12.10 |  |  | 10384 | 0 | 10384 | 908.6 | 2026-08-20 | 2026-10-03 | 2026-10-06 | 2026-10-15 | 2026-10-20 | 2026-12-10 |  | 2.2 | 1.05 | 8.6 | 38 | 1725.504 | 6.018 | 201.0018 |  | 48
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 12.24 |  |  | 1518 | 0 | 1518 | 132.825 | 2026-08-20 | 2026-10-10 | 2026-10-13 | 2026-10-16 | 2026-10-21 | 2026-12-24 |  | 2.2 | 1.05 | 8.6 | 38 | 1725.504 | 0.87974 | 201.0018 |  | 59
6-16 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 01.07 |  |  | 506 | 0 | 506 | 44.275 | 2026-08-20 | 2026-10-12 | 2026-10-14 | 2026-10-16 | 2026-10-21 | 2027-01-07 |  | 2.2 | 1.05 | 8.6 | 38 | 1725.504 | 0.29325 | 201.0018 |  | 68
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62385693 |  |  | 510 | 0 | 510 | 31.025 | 2026-10-09 | 2026-10-08 | 2026-10-14 | 2026-10-17 | 2026-10-19 | 2026-10-28 |  | 0.5 | 0.73 | 7 | 38 | 459.1233 | 1.1108 | 65.7073 |  | 9
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62385693 |  |  | 1500 | 0 | 1500 | 91.25 | 2026-10-09 | 2026-10-09 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 2026-10-28 |  | 1 | 0.73 | 8.6 | 38 | 1128.1315 | 1.3296 | 131.4146 |  | 8
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62377531, 116, 287 |  |  | 3099 | 0 | 3099 | 188.5225 | 2026-10-09 | 2026-10-10 | 2026-10-16 | 2026-10-21 | 2026-10-23 | 2026-10-29 |  | 1.1 | 0.73 | 8.6 | 38 | 1240.9447 | 2.4973 | 144.5561 |  | 7
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62385611 |  |  | 480 | 0 | 480 | 29.2 | 2026-10-09 | 2026-10-13 | 2026-10-19 | 2026-10-21 | 2026-10-23 | 2026-11-04 |  | 1.2 | 0.73 | 8.6 | 38 | 1353.7578 | 0.35457 | 157.6976 |  | 12
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62379119, 121, 451, 452, 453, 454 |  |  | 4426 | 0 | 4426 | 269.2483 | 2026-10-09 | 2026-10-13 | 2026-10-19 | 2026-10-24 | 2026-10-26 | 2026-11-05 |  | 1.4 | 0.73 | 8.6 | 38 | 1579.3841 | 2.8024 | 183.9805 |  | 10
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62379119, 121, 451, 452, 453, 454 |  |  | 7000 | 0 | 7000 | 425.8333 | 2026-10-09 | 2026-10-16 | 2026-10-22 | 2026-10-29 | 2026-10-31 | 2026-11-05 |  | 1.6 | 0.73 | 8.6 | 38 | 1805.0104 | 3.8781 | 210.2634 |  | 6
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62377481, 168, 252 |  |  | 2079 | 0 | 2079 | 126.4725 | 2026-11-04 | 2026-10-21 | 2026-10-27 | 2026-10-30 | 2026-11-01 | 2026-11-26 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 1.0238 | 236.5463 |  | 23
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 62383169, 171, 483, 485, 487, 489 |  |  | 10557 | 0 | 10557 | 642.2175 | 2026-11-04 | 2026-10-22 | 2026-10-28 | 2026-11-05 | 2026-11-07 | 2026-12-03 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 5.1989 | 236.5463 |  | 24
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 12.24 |  |  | 1889 | 0 | 1889 | 114.9142 | 2026-12-04 | 2026-10-28 | 2026-11-03 | 2026-11-06 | 2026-11-08 | 2026-12-24 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 0.93025 | 236.5463 |  | 41
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 12.31 |  |  | 3707 | 0 | 3707 | 225.5092 | 2026-12-04 | 2026-10-29 | 2026-11-04 | 2026-11-09 | 2026-11-11 | 2026-12-31 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 1.8255 | 236.5463 |  | 44
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 01.21 |  |  | 1614 | 0 | 1614 | 98.185 | 2026-12-04 | 2026-10-31 | 2026-11-06 | 2026-11-10 | 2026-11-12 | 2027-01-21 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 0.79482 | 236.5463 |  | 59
6-16 | ONY | 1193182_SP27 | Tee | [特工] Rubber Print(Area below 2,000 cm2) 膠印(面積未滿2000平方公分); | 01.28 |  |  | 3066 | 0 | 3066 | 186.515 | 2026-12-04 | 2026-11-02 | 2026-11-07 | 2026-11-12 | 2026-11-14 | 2027-01-28 |  | 1.8 | 0.73 | 8.6 | 38 | 2030.6367 | 1.5099 | 236.5463 |  | 63
6-16 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 716 | 0 | 716 | 72.7933 | 2026-11-05 | 2026-11-07 | 2026-11-10 | 2026-11-16 | 2026-11-18 | 2026-11-30 |  | 0.5 | 1.22 | 7 | 38 | 274.7213 | 2.6063 | 39.3167 |  | 12
6-16 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 1500 | 0 | 1500 | 152.5 | 2026-11-05 | 2026-11-11 | 2026-11-13 | 2026-11-18 | 2026-11-20 | 2026-11-30 |  | 1 | 1.22 | 8.6 | 38 | 675.0295 | 2.2221 | 78.6333 |  | 10
6-16 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 2500 | 0 | 2500 | 254.1667 | 2026-11-05 | 2026-11-13 | 2026-11-16 | 2026-11-21 | 2026-11-23 | 2026-11-30 |  | 1.1 | 1.22 | 8.6 | 38 | 742.5325 | 3.3669 | 86.4967 |  | 7
6-16 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1203 |  |  | 3900 | 0 | 3900 | 396.5 | 2026-11-05 | 2026-11-17 | 2026-11-19 | 2026-11-27 | 2026-11-29 | 2026-11-30 |  | 1.2 | 1.22 | 8.6 | 38 | 810.0354 | 4.8146 | 94.36 |  | 2
6-16 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 4000 | 0 | 4000 | 406.6667 | 2026-11-05 | 2026-11-23 | 2026-11-25 | 2026-12-02 | 2026-12-04 | 2026-12-07 |  | 1.4 | 1.22 | 8.6 | 38 | 945.0413 | 4.2326 | 110.0867 |  | 4
6-16 | HLF | CFM271SH09 | Pull On Pants |  | 4500041647_BJSHVS_1210 |  |  | 6016 | 0 | 6016 | 611.6267 | 2026-11-05 | 2026-11-27 | 2026-11-30 | 2026-12-09 | 2026-12-11 | 2026-12-07 |  | 1.6 | 1.22 | 8.6 | 38 | 1080.0472 | 5.5701 | 125.8133 |  | -4
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-12-04 | 2026-12-07 | 2026-12-11 | 2026-12-16 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 38 | 364.3043 | 2.2371 | 52.1373 |  | 11
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-12-07 | 2026-12-09 | 2026-12-14 | 2026-12-19 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 38 | 895.1478 | 1.6757 | 104.2747 |  | 9
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-12-09 | 2026-12-11 | 2026-12-17 | 2026-12-22 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 38 | 984.6626 | 2.5389 | 114.7021 |  | 6
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-12 | 2026-12-15 | 2026-12-21 | 2026-12-26 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 38 | 1074.1774 | 2.7928 | 125.1296 |  | 3
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4942 | 0 | 4942 | 378.8867 | 2026-12-07 | 2026-12-16 | 2026-12-18 | 2026-12-26 | 2026-12-31 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 38 | 1163.6922 | 4.2468 | 135.557 |  | 4
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 5875 | 0 | 5875 | 450.4167 | 2026-12-07 | 2026-12-21 | 2026-12-23 | 2027-01-02 | 2027-01-07 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 38 | 1253.207 | 4.688 | 145.9845 |  | -3
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-28 | 2026-12-30 | 2027-01-04 | 2027-01-09 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 1.4329 | 156.412 |  | 8
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-29 | 2026-12-31 | 2027-01-12 | 2027-01-17 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 5.8061 | 156.412 |  | 8
6-16 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-07 | 2027-01-09 | 2027-01-18 | 2027-01-23 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 4.9221 | 156.412 |  | 9
2026-05-29
6-17 | TGT | G9M018_C426 | Pajama | [特工] Fire Resistance Print 防火印花; | all po |  |  | 114421 | 114421 | 0 | 8104.8208 | 2026-06-25 | 2026-05-20 | 2026-05-26 | 2026-08-14 | 2026-08-16 | 2026-08-22 |  | 1.8494 | 0.85 | 9.0274 | 36.6846 | 1815.7792 | 63.0148 | 201.5045 |  | 4
6-17 | ONY | 1182430_HO26_HT | Pull On Pants |  | all po |  |  | 17242 | 17242 | 0 | 1120.73 | 2026-08-24 | 2026-08-10 | 2026-08-12 | 2026-09-08 | 2026-09-10 | 2026-10-15 |  | 1.1456 | 0.78 | 8.3389 | 37.797 | 1166.5206 | 14.7807 | 140.1413 |  | 29
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004922_T1_W |  |  | 720 | 720 | 0 | 63.6 | 2026-08-24 | 2026-08-28 | 2026-09-04 | 2026-09-09 | 2026-09-11 | 2026-10-01 |  | 0.87336 | 1.06 | 8 | 38 | 631.1914 | 1.1407 | 79.0412 |  | 16
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004923_SET_W |  |  | 17999 | 14033 | 3966 | 1589.9117 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-23 | 2026-09-25 | 2026-10-08 |  | 2.14 | 1.06 | 9 | 38 | 1739.9411 | 10.3446 | 193.6754 |  | 12
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004937_BA_E |  |  | 4528 | 0 | 4528 | 399.9733 | 2026-09-10 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-09-30 | 2026-10-12 |  | 2.1 | 1.06 | 9 | 38 | 1707.4189 | 2.652 | 190.0553 |  | 12
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004936_BA_E |  |  | 4000 | 0 | 4000 | 353.3333 | 2026-08-29 | 2026-09-17 | 2026-09-24 | 2026-09-30 | 2026-10-02 | 2026-10-24 |  | 2.1 | 1.06 | 9 | 38 | 1707.4189 | 2.3427 | 190.0553 |  | 21
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004936_BA_E |  |  | 7078 | 0 | 7078 | 625.2233 | 2026-08-29 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-07 | 2026-10-24 |  | 2.1 | 1.06 | 8.6 | 38 | 1631.5336 | 4.3382 | 190.0553 |  | 17
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004947_BA_E |  |  | 6792 | 0 | 6792 | 599.96 | 2026-09-05 | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-11 | 2026-10-26 |  | 2.1 | 1.06 | 8.6 | 38 | 1631.5336 | 4.163 | 190.0553 |  | 14
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004946_BA_E |  |  | 9078 | 0 | 9078 | 801.89 | 2026-09-05 | 2026-10-01 | 2026-10-07 | 2026-10-16 | 2026-10-18 | 2026-11-07 |  | 2.1 | 1.06 | 8.6 | 38 | 1631.5336 | 5.5641 | 190.0553 |  | 19
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004950_BA_E |  |  | 9792 | 0 | 9792 | 864.96 | 2026-09-05 | 2026-10-08 | 2026-10-14 | 2026-10-23 | 2026-10-25 | 2026-11-09 |  | 2.1 | 1.06 | 8.6 | 38 | 1631.5336 | 6.0017 | 190.0553 |  | 14
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004948_BA_E |  |  | 9078 | 0 | 9078 | 801.89 | 2026-09-05 | 2026-10-15 | 2026-10-21 | 2026-10-30 | 2026-11-01 | 2026-11-21 |  | 2.1 | 1.06 | 8.6 | 38 | 1631.5336 | 5.5641 | 190.0553 |  | 19
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004939_BA_E |  |  | 6792 | 0 | 6792 | 599.96 | 2026-09-05 | 2026-10-22 | 2026-10-28 | 2026-11-04 | 2026-11-06 | 2026-11-23 |  | 2.1 | 1.06 | 8.6 | 38 | 1631.5336 | 4.163 | 190.0553 |  | 16
6-17 | TGT | MRLPMM_3PC_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004938_BA_E |  |  | 10928 | 0 | 10928 | 965.3067 | 2026-09-05 | 2026-10-27 | 2026-11-02 | 2026-11-12 | 2026-11-14 | 2026-12-05 |  | 2.1 | 1.06 | 8.6 | 38 | 1631.5336 | 6.698 | 190.0553 |  | 20
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 728 | 0 | 728 | 57.0267 | 2026-11-09 | 2026-11-04 | 2026-11-10 | 2026-11-14 | 2026-11-16 | 2026-12-03 |  | 0.5 | 0.94 | 7 | 38 | 356.5532 | 2.0418 | 51.028 |  | 16
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 1500 | 0 | 1500 | 117.5 | 2026-11-09 | 2026-11-06 | 2026-11-12 | 2026-11-17 | 2026-11-19 | 2026-12-03 |  | 1 | 0.94 | 8.6 | 38 | 876.1021 | 1.7121 | 102.056 |  | 14
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 2500 | 0 | 2500 | 195.8333 | 2026-11-09 | 2026-11-09 | 2026-11-14 | 2026-11-20 | 2026-11-22 | 2026-12-03 |  | 1.1 | 0.94 | 8.6 | 38 | 963.7123 | 2.5941 | 112.2616 |  | 11
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 3500 | 0 | 3500 | 274.1667 | 2026-11-09 | 2026-11-12 | 2026-11-18 | 2026-11-24 | 2026-11-26 | 2026-12-03 |  | 1.2 | 0.94 | 8.6 | 38 | 1051.3226 | 3.3291 | 122.4672 |  | 8
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1203, 4500041657_HTR_1203 |  |  | 5300 | 0 | 5300 | 415.1667 | 2026-11-09 | 2026-11-16 | 2026-11-21 | 2026-11-28 | 2026-11-30 | 2026-12-03 |  | 1.4 | 0.94 | 8.6 | 38 | 1226.543 | 4.3211 | 142.8785 |  | 4
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1210, 4500041655_BJSHVS_1210, 4500041655_BJSHVS_HTR_1210, 4500041657_HTR_1210 |  |  | 5000 | 0 | 5000 | 391.6667 | 2026-11-09 | 2026-11-20 | 2026-11-26 | 2026-12-03 | 2026-12-05 | 2026-12-10 |  | 1.6 | 0.94 | 8.6 | 38 | 1401.7634 | 3.5669 | 163.2897 |  | 6
6-17 | HLF | CFW271SH01 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | 4500041657_1210, 4500041655_BJSHVS_1210, 4500041655_BJSHVS_HTR_1210, 4500041657_HTR_1210 |  |  | 7484 | 0 | 7484 | 586.2467 | 2026-11-09 | 2026-11-25 | 2026-12-01 | 2026-12-09 | 2026-12-11 | 2026-12-10 |  | 1.8 | 0.94 | 8.6 | 38 | 1576.9838 | 4.7458 | 183.7009 |  | 1
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 815 | 0 | 815 | 62.4833 | 2026-11-30 | 2026-12-04 | 2026-12-07 | 2026-12-11 | 2026-12-16 | 2026-12-24 |  | 0.5 | 0.92 | 7 | 38 | 364.3043 | 2.2371 | 52.1373 |  | 11
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 1500 | 0 | 1500 | 115 | 2026-11-30 | 2026-12-07 | 2026-12-09 | 2026-12-14 | 2026-12-19 | 2026-12-24 |  | 1 | 0.92 | 8.6 | 38 | 895.1478 | 1.6757 | 104.2747 |  | 9
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 2500 | 0 | 2500 | 191.6667 | 2026-11-30 | 2026-12-09 | 2026-12-11 | 2026-12-17 | 2026-12-22 | 2026-12-24 |  | 1.1 | 0.92 | 8.6 | 38 | 984.6626 | 2.5389 | 114.7021 |  | 6
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.24 |  |  | 3000 | 0 | 3000 | 230 | 2026-11-30 | 2026-12-12 | 2026-12-15 | 2026-12-21 | 2026-12-26 | 2026-12-24 |  | 1.2 | 0.92 | 8.6 | 38 | 1074.1774 | 2.7928 | 125.1296 |  | 3
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 4942 | 0 | 4942 | 378.8867 | 2026-12-07 | 2026-12-16 | 2026-12-18 | 2026-12-26 | 2026-12-31 | 2026-12-31 |  | 1.3 | 0.92 | 8.6 | 38 | 1163.6922 | 4.2468 | 135.557 |  | 4
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 12.31 |  |  | 6375 | 0 | 6375 | 488.75 | 2026-12-07 | 2026-12-21 | 2026-12-23 | 2027-01-02 | 2027-01-07 | 2026-12-31 |  | 1.4 | 0.92 | 8.6 | 38 | 1253.207 | 5.0869 | 145.9845 |  | -3
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.14 |  |  | 1924 | 0 | 1924 | 147.5067 | 2026-12-24 | 2026-12-28 | 2026-12-30 | 2027-01-04 | 2027-01-09 | 2027-01-14 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 1.4329 | 156.412 |  | 8
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.21 |  |  | 7796 | 0 | 7796 | 597.6933 | 2026-12-28 | 2026-12-29 | 2026-12-31 | 2027-01-12 | 2027-01-17 | 2027-01-21 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 5.8061 | 156.412 |  | 8
6-17 | ONY | 1197198/1197204 | Dress | [特工] Normal Garment Wash 清水洗/普通水洗; | 01.28 |  |  | 6609 | 0 | 6609 | 506.69 | 2027-01-04 | 2027-01-07 | 2027-01-09 | 2027-01-18 | 2027-01-23 | 2027-01-28 |  | 1.5 | 0.92 | 8.6 | 38 | 1342.7217 | 4.9221 | 156.412 |  | 9
2026-04-08
6-18 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 58617 | 58617 | 0 | 5128.9875 | 2026-05-07 | 2026-04-02 | 2026-04-06 | 2026-05-26 | 2026-05-31 | 2026-07-30 |  | 1.8839 | 1.05 | 9.0947 | 36.6174 | 1505.6912 | 38.9303 | 165.8552 |  | 53
6-18 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 36668 | 36668 | 0 | 4247.3767 | 2026-06-03 | 2026-05-21 | 2026-05-23 | 2026-07-09 | 2026-07-11 | 2026-07-09 |  | 1.6867 | 1.39 | 9.4411 | 36.547 | 1055.0911 | 34.7534 | 111.9562 |  | 0
6-18 | ONY | 910047_HO26DIS | Pajama |  | all po |  |  | 38392 | 38392 | 0 | 4543.0533 | 2026-07-06 | 2026-07-04 | 2026-07-07 | 2026-08-20 | 2026-08-22 | 2026-09-03 |  | 2.054 | 1.42 | 8.2635 | 38.6602 | 1164.4988 | 32.9687 | 141.1757 |  | 9
6-18 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | 10.15 |  |  | 2978 | 2978 | 0 | 260.575 | 2026-06-23 | 2026-08-13 | 2026-08-18 | 2026-08-24 | 2026-08-29 | 2026-10-15 |  | 1.7247 | 1.05 | 8.0143 | 37.9956 | 1260.476 | 2.3626 | 157.5616 |  | 39
6-18 | ONY | 910047_HO26DIS | Pajama |  | all po |  |  | 8515 | 8515 | 0 | 1007.6083 | 2026-07-06 | 2026-08-18 | 2026-08-20 | 2026-09-03 | 2026-09-05 | 2026-09-03 |  | 1.9776 | 1.42 | 8.5299 | 38.1355 | 1141.6509 | 7.4585 | 134.0827 |  | 0
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004914_T1_W |  |  | 2160 | 2160 | 0 | 140.4 | 2026-08-18 | 2026-08-24 | 2026-09-01 | 2026-09-07 | 2026-09-09 | 2026-10-01 |  | 1.1932 | 0.78 | 8 | 38 | 1171.875 | 1.8432 | 146.7485 |  | 18
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004915_SET_W |  |  | 32825 | 21613 | 11212 | 2133.625 | 2026-08-18 | 2026-08-27 | 2026-09-03 | 2026-09-25 | 2026-09-27 | 2026-10-08 |  | 2.05 | 0.78 | 9 | 38 | 2265.0923 | 14.4917 | 252.1308 |  | 10
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004943_BA_E |  |  | 3816 | 0 | 3816 | 248.04 | 2026-08-18 | 2026-09-16 | 2026-09-23 | 2026-09-29 | 2026-10-01 | 2026-10-12 |  | 2 | 0.78 | 9 | 38 | 2209.8462 | 1.7268 | 245.9812 |  | 11
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004944_BA_W |  |  | 5064 | 0 | 5064 | 329.16 | 2026-08-18 | 2026-09-18 | 2026-09-25 | 2026-10-01 | 2026-10-03 | 2026-10-24 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 2.3981 | 245.9812 |  | 20
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004935_BA_E |  |  | 3132 | 0 | 3132 | 203.58 | 2026-08-18 | 2026-09-22 | 2026-09-29 | 2026-10-02 | 2026-10-04 | 2026-10-26 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.4832 | 245.9812 |  | 20
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004934_BA_W |  |  | 4200 | 0 | 4200 | 273 | 2026-08-24 | 2026-09-23 | 2026-09-30 | 2026-10-05 | 2026-10-07 | 2026-11-07 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.989 | 245.9812 |  | 29
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004949_BA_E |  |  | 2508 | 0 | 2508 | 163.02 | 2026-09-05 | 2026-09-25 | 2026-10-02 | 2026-10-06 | 2026-10-08 | 2026-11-09 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.1877 | 245.9812 |  | 29
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004945_BA_W |  |  | 3348 | 0 | 3348 | 217.62 | 2026-09-05 | 2026-09-28 | 2026-10-03 | 2026-10-08 | 2026-10-10 | 2026-11-21 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.5855 | 245.9812 |  | 38
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004942_BA_E |  |  | 2508 | 0 | 2508 | 163.02 | 2026-08-24 | 2026-09-30 | 2026-10-06 | 2026-10-09 | 2026-10-11 | 2026-11-23 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.1877 | 245.9812 |  | 38
6-18 | TGT | 352E6Y_LL_C127 | Pajama | [特工] Fire Resistance Print 防火印花; | 10002004941_BA_W |  |  | 3348 | 0 | 3348 | 217.62 | 2026-08-29 | 2026-10-01 | 2026-10-07 | 2026-10-12 | 2026-10-14 | 2026-12-05 |  | 2 | 0.78 | 8.6 | 38 | 2111.6308 | 1.5855 | 245.9812 |  | 47
6-18 | TGT | 1KE9E9_SSLLC127 | Pajama |  | 1206 |  |  | 840 | 0 | 840 | 48.3 | 2026-10-15 | 2026-10-07 | 2026-10-09 | 2026-10-13 | 2026-10-15 | 2026-11-06 |  | 1.5 | 0.69 | 7 | 38 | 1457.2174 | 0.57644 | 208.5493 |  | 21
6-18 | TGT | 1KE9E9_SSLLC127 | Pajama |  | 1206 |  |  | 1500 | 0 | 1500 | 86.25 | 2026-10-15 | 2026-10-08 | 2026-10-10 | 2026-10-14 | 2026-10-16 | 2026-11-06 |  | 1.6 | 0.69 | 8.6 | 38 | 1909.6487 | 0.78548 | 222.4526 |  | 20
6-18 | TGT | 1KE9E9_SSLLC127 | Pajama |  | 1206 |  |  | 3500 | 0 | 3500 | 201.25 | 2026-10-15 | 2026-10-09 | 2026-10-12 | 2026-10-16 | 2026-10-18 | 2026-11-06 |  | 1.8 | 0.69 | 8.6 | 38 | 2148.3548 | 1.6292 | 250.2592 |  | 18
6-18 | TGT | 1KE9E9_SSLLC127 | Pajama |  | 1206 |  |  | 14000 | 0 | 14000 | 805 | 2026-10-15 | 2026-10-12 | 2026-10-14 | 2026-10-23 | 2026-10-25 | 2026-11-06 |  | 2 | 0.69 | 8.6 | 38 | 2387.0609 | 5.865 | 278.0657 |  | 12
6-18 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 1500 | 0 | 1500 | 90 | 2026-10-15 | 2026-10-19 | 2026-10-21 | 2026-10-24 | 2026-10-26 | 2026-11-06 |  | 1.5 | 0.72 | 7 | 38 | 1396.5 | 1.0741 | 199.8597 |  | 11
6-18 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 2098 | 0 | 2098 | 125.88 | 2026-10-15 | 2026-10-20 | 2026-10-22 | 2026-10-26 | 2026-10-28 | 2026-11-06 |  | 1.6 | 0.72 | 8.6 | 38 | 1830.08 | 1.1464 | 213.1837 |  | 10
6-18 | TGT | MRLPMM_SSLLC127 | Pajama |  | 1206 |  |  | 5500 | 0 | 5500 | 330 | 2026-10-15 | 2026-10-21 | 2026-10-23 | 2026-10-29 | 2026-10-31 | 2026-11-06 |  | 1.8 | 0.72 | 8.6 | 38 | 2058.84 | 2.6714 | 239.8317 |  | 7
6-18 | ONY | 1194432_SP27 | Tee |  | 62323026, 027, 733, 738, 744, 745 |  |  | 750 | 0 | 750 | 40 | 2026-10-09 | 2026-10-24 | 2026-10-27 | 2026-10-31 | 2026-11-02 | 2026-11-05 |  | 0.5 | 0.64 | 7 | 35 | 482.3438 | 1.5549 | 69.0305 |  | 4
6-18 | ONY | 1194432_SP27 | Tee |  | 62323026, 027, 733, 738, 744, 745 |  |  | 1500 | 0 | 1500 | 80 | 2026-10-09 | 2026-10-27 | 2026-10-29 | 2026-11-02 | 2026-11-04 | 2026-11-05 |  | 1 | 0.64 | 8.6 | 35 | 1185.1875 | 1.2656 | 138.061 |  | 3
6-18 | ONY | 1194432_SP27 | Tee |  | 62323026, 027, 733, 738, 744, 745 |  |  | 2750 | 0 | 2750 | 146.6667 | 2026-10-09 | 2026-10-28 | 2026-10-30 | 2026-11-04 | 2026-11-06 | 2026-11-05 |  | 1.2 | 0.64 | 8.6 | 35 | 1422.225 | 1.9336 | 165.6732 |  | 1
6-18 | ONY | 1194432_SP27 | Tee |  | 62377441, 442, 182, 113, 170, 255 |  |  | 3500 | 0 | 3500 | 186.6667 | 2026-11-13 | 2026-10-30 | 2026-11-02 | 2026-11-06 | 2026-11-08 | 2026-11-26 |  | 1.4 | 0.64 | 8.6 | 35 | 1659.2625 | 2.1094 | 193.2854 |  | 17
6-18 | ONY | 1194432_SP27 | Tee |  | 62377441, 442, 182, 113, 170, 255 |  |  | 4767 | 0 | 4767 | 254.24 | 2026-11-13 | 2026-11-02 | 2026-11-04 | 2026-11-10 | 2026-11-12 | 2026-11-26 |  | 1.6 | 0.64 | 8.6 | 35 | 1896.3 | 2.5138 | 220.8976 |  | 14
6-18 | ONY | 1194432_SP27 | Tee |  | 62377441, 442, 182, 113, 170, 255 |  |  | 5000 | 0 | 5000 | 266.6667 | 2026-11-13 | 2026-11-05 | 2026-11-07 | 2026-11-13 | 2026-11-15 | 2026-11-26 |  | 1.6 | 0.64 | 8.6 | 35 | 1896.3 | 2.6367 | 220.8976 |  | 11
6-18 | ONY | 1194432_SP27 | Tee |  | 62344833 |  |  | 126 | 0 | 126 | 6.72 | 2026-11-13 | 2026-11-09 | 2026-11-11 | 2026-11-13 | 2026-11-15 | 2026-12-02 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 0.059062 | 248.5098 |  | 16
6-18 | ONY | 1194432_SP27 | Tee |  | 62379115 |  |  | 5924 | 0 | 5924 | 315.9467 | 2026-11-06 | 2026-11-09 | 2026-11-11 | 2026-11-17 | 2026-11-19 | 2026-12-03 |  | 1.8 | 0.64 | 8.6 | 35 | 2133.3375 | 2.7769 | 248.5098 |  | 14
6-18 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 1500 | 0 | 1500 | 52.5 | 2026-11-13 | 2026-11-12 | 2026-11-14 | 2026-11-19 | 2026-11-21 | 2026-11-27 |  | 0.5 | 0.42 | 7 | 35 | 735 | 2.0408 | 105.1893 |  | 7
6-18 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 3500 | 0 | 3500 | 122.5 | 2026-11-13 | 2026-11-14 | 2026-11-17 | 2026-11-21 | 2026-11-23 | 2026-11-27 |  | 1 | 0.42 | 8.6 | 35 | 1806 | 1.938 | 210.3787 |  | 5
6-18 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 5000 | 0 | 5000 | 175 | 2026-11-13 | 2026-11-17 | 2026-11-19 | 2026-11-24 | 2026-11-26 | 2026-11-27 |  | 1.2 | 0.42 | 8.6 | 35 | 2167.2 | 2.3071 | 252.4544 |  | 3
6-18 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 7000 | 0 | 7000 | 245 | 2026-11-13 | 2026-11-19 | 2026-11-21 | 2026-11-27 | 2026-11-29 | 2026-11-27 |  | 1.4 | 0.42 | 8.6 | 35 | 2528.4 | 2.7685 | 294.5302 |  | 0
6-18 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_W |  |  | 10000 | 0 | 10000 | 350 | 2026-11-13 | 2026-11-23 | 2026-11-25 | 2026-12-01 | 2026-12-03 | 2026-12-08 |  | 1.6 | 0.42 | 8.6 | 35 | 2889.6 | 3.4607 | 336.6059 |  | 6
6-18 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_W |  |  | 10000 | 0 | 10000 | 350 | 2026-11-13 | 2026-11-26 | 2026-11-28 | 2026-12-04 | 2026-12-06 | 2026-12-08 |  | 1.8 | 0.42 | 8.6 | 35 | 3250.8 | 3.0762 | 378.6816 |  | 3
6-18 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_W |  |  | 10000 | 0 | 10000 | 350 | 2026-11-13 | 2026-11-30 | 2026-12-02 | 2026-12-08 | 2026-12-10 | 2026-12-08 |  | 2 | 0.42 | 8.6 | 35 | 3612 | 2.7685 | 420.7574 |  | 0
6-18 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0314_W |  |  | 10000 | 0 | 10000 | 350 | 2026-11-13 | 2026-12-03 | 2026-12-05 | 2026-12-11 | 2026-12-13 | 2026-12-11 |  | 2 | 0.42 | 8.6 | 35 | 3612 | 2.7685 | 420.7574 |  | 0
6-18 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0328_W |  |  | 26640 | 0 | 26640 | 932.4 | 2026-12-11 | 2026-12-07 | 2026-12-09 | 2026-12-19 | 2026-12-21 | 2026-12-24 |  | 2 | 0.42 | 8.6 | 35 | 3612 | 7.3754 | 420.7574 |  | 4
6-18 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0411_W |  |  | 26640 | 0 | 26640 | 932.4 | 2026-12-11 | 2026-12-15 | 2026-12-17 | 2026-12-29 | 2026-12-31 | 2027-01-08 |  | 2 | 0.42 | 8.6 | 35 | 3612 | 7.3754 | 420.7574 |  | 7
6-18 | TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0418_W |  |  | 26640 | 0 | 26640 | 932.4 | 2027-01-08 | 2026-12-23 | 2026-12-26 | 2027-01-08 | 2027-01-10 | 2027-01-15 |  | 2 | 0.42 | 8.6 | 35 | 3612 | 7.3754 | 420.7574 |  | 6
2026-06-03
6-19 | ONY | 910047_FA26 | Pajama |  | all po |  |  | 30137 | 30137 | 0 | 3490.8692 | 2026-06-03 | 2026-05-28 | 2026-05-30 | 2026-07-09 | 2026-07-11 | 2026-07-09 |  | 1.6466 | 1.39 | 9.3862 | 35.7151 | 1000.7301 | 30.115 | 106.8093 |  | 0
6-19 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 17165 | 17165 | 0 | 1501.9375 | 2026-06-23 | 2026-07-04 | 2026-07-07 | 2026-07-25 | 2026-07-30 | 2026-09-24 |  | 1.8451 | 1.05 | 8.0928 | 35.1592 | 1260.0109 | 13.6229 | 155.977 |  | 43
6-19 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 176 | 176 | 0 | 15.4 | 2026-05-23 | 2026-07-21 | 2026-07-23 | 2026-07-25 | 2026-07-30 | 2026-07-30 |  | 1.3031 | 1.05 | 7.482 | 34.9354 | 817.4638 | 0.2153 | 109.4549 |  | 4
6-19 | ONY | 1182723_HO26 | Skorts |  | all po |  |  | 36303 | 36303 | 0 | 2752.9775 | 2026-07-14 | 2026-07-21 | 2026-07-23 | 2026-09-02 | 2026-09-04 | 2026-10-01 |  | 1.628 | 0.91 | 7.9417 | 37.2825 | 1334.8651 | 27.196 | 168.3851 |  | 21
6-19 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016322, 323, 324, 325 |  |  | 23773 | 23773 | 0 | 1049.9742 | 2026-08-06 | 2026-08-27 | 2026-08-31 | 2026-09-18 | 2026-09-20 | 2026-09-17 |  | 1.3204 | 0.53 | 8.8241 | 37.1222 | 2056.559 | 11.5596 | 233.4808 |  | -3
6-19 | ONY | 1188289_HO26 | Pull On Pants | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 62016283, 292, 296 |  |  | 3698 | 2094 | 1604 | 163.3283 | 2026-08-06 | 2026-09-14 | 2026-09-16 | 2026-09-22 | 2026-09-24 | 2026-10-15 |  | 1.51 | 0.53 | 9 | 38 | 2455.4309 | 1.506 | 273.3176 |  | 19
6-19 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 750 | 0 | 750 | 61.25 | 2026-09-07 | 2026-09-16 | 2026-09-18 | 2026-09-24 | 2026-09-29 | 2026-10-01 |  | 0.5 | 0.98 | 7 | 38 | 342 | 2.193 | 48.9452 |  | 5
6-19 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62266744, 746 |  |  | 1500 | 0 | 1500 | 122.5 | 2026-09-07 | 2026-09-18 | 2026-09-22 | 2026-09-28 | 2026-10-03 | 2026-10-01 |  | 1 | 0.98 | 9 | 38 | 879.4286 | 1.7057 | 97.8905 |  | 3
6-19 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62239979, 378, 565, 268, 269 |  |  | 1503 | 0 | 1503 | 122.745 | 2026-09-07 | 2026-09-22 | 2026-09-24 | 2026-09-29 | 2026-10-04 | 2026-10-08 |  | 1.2 | 0.98 | 9 | 38 | 1055.3143 | 1.4242 | 117.4686 |  | 8
6-19 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 2500 | 0 | 2500 | 204.1667 | 2026-09-07 | 2026-09-23 | 2026-09-25 | 2026-10-01 | 2026-10-06 | 2026-10-15 |  | 1.4 | 0.98 | 9 | 38 | 1231.2 | 2.0305 | 137.0467 |  | 12
6-19 | ONY | 1196262_HO26_PF | Tee | [特工] Normal Garment Wash 清水洗/普通水洗; | 62250269, 979, 378, 565, 268, 10.08 |  |  | 6003 | 0 | 6003 | 490.245 | 2026-09-07 | 2026-09-25 | 2026-09-29 | 2026-10-06 | 2026-10-11 | 2026-10-15 |  | 1.6 | 0.98 | 8.6 | 38 | 1344.5486 | 4.4647 | 156.6248 |  | 8
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 750 | 0 | 750 | 105 | 2026-09-12 | 2026-09-28 | 2026-10-03 | 2026-10-10 | 2026-10-12 | 2026-10-29 |  | 0.5 | 1.68 | 7 | 38 | 199.5 | 3.7594 | 28.5514 |  | 16
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 1500 | 0 | 1500 | 210 | 2026-09-12 | 2026-10-02 | 2026-10-08 | 2026-10-14 | 2026-10-16 | 2026-10-29 |  | 1 | 1.68 | 8.6 | 38 | 490.2 | 3.06 | 57.1028 |  | 13
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 2000 | 0 | 2000 | 280 | 2026-09-12 | 2026-10-06 | 2026-10-12 | 2026-10-19 | 2026-10-21 | 2026-10-29 |  | 1.1 | 1.68 | 8.6 | 38 | 539.22 | 3.7091 | 62.8131 |  | 9
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 2250 | 0 | 2250 | 315 | 2026-09-12 | 2026-10-10 | 2026-10-16 | 2026-10-23 | 2026-10-25 | 2026-10-29 |  | 1.2 | 1.68 | 8.6 | 38 | 588.24 | 3.825 | 68.5233 |  | 5
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0116, _T1, _SET |  |  | 3547 | 0 | 3547 | 496.58 | 2026-09-12 | 2026-10-15 | 2026-10-21 | 2026-10-29 | 2026-10-31 | 2026-10-29 |  | 1.4 | 1.68 | 8.6 | 38 | 686.28 | 5.1684 | 79.9439 |  | 0
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0130 |  |  | 4332 | 0 | 4332 | 606.48 | 2026-10-03 | 2026-10-21 | 2026-10-27 | 2026-11-05 | 2026-11-07 | 2026-11-09 |  | 1.5 | 1.68 | 8.6 | 38 | 735.3 | 5.8915 | 85.6542 |  | 3
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0213 |  |  | 4000 | 0 | 4000 | 560 | 2026-10-17 | 2026-10-28 | 2026-11-03 | 2026-11-11 | 2026-11-13 | 2026-11-23 |  | 1.6 | 1.68 | 8.6 | 38 | 784.32 | 5.1 | 91.3645 |  | 10
6-19 | TGT | Z2850Y_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0227 |  |  | 4452 | 0 | 4452 | 623.28 | 2026-10-31 | 2026-11-03 | 2026-11-09 | 2026-11-17 | 2026-11-19 | 2026-12-07 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 5.0456 | 102.785 |  | 17
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0228_E |  |  | 1318 | 0 | 1318 | 59.31 | 2026-10-26 | 2026-11-12 | 2026-11-14 | 2026-11-19 | 2026-11-21 | 2026-11-27 |  | 0.5 | 0.54 | 7 | 38 | 620.6667 | 2.1235 | 88.8266 |  | 7
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0228_W |  |  | 2278 | 0 | 2278 | 102.51 | 2026-10-26 | 2026-11-14 | 2026-11-17 | 2026-11-20 | 2026-11-22 | 2026-12-08 |  | 1 | 0.54 | 8.6 | 38 | 1525.0667 | 1.4937 | 177.6531 |  | 15
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0228_W |  |  | 3000 | 0 | 3000 | 135 | 2026-10-26 | 2026-11-16 | 2026-11-18 | 2026-11-23 | 2026-11-25 | 2026-12-08 |  | 1.2 | 0.54 | 8.6 | 38 | 1830.08 | 1.6393 | 213.1837 |  | 13
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0323_E |  |  | 1448 | 0 | 1448 | 65.16 | 2026-11-06 | 2026-11-18 | 2026-11-20 | 2026-11-24 | 2026-11-26 | 2026-12-19 |  | 1.4 | 0.54 | 8.6 | 38 | 2135.0933 | 0.67819 | 248.7144 |  | 22
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0328_E |  |  | 1048 | 0 | 1048 | 47.16 | 2026-11-06 | 2026-11-19 | 2026-11-21 | 2026-11-24 | 2026-11-26 | 2026-12-24 |  | 1.6 | 0.54 | 8.6 | 38 | 2440.1067 | 0.42949 | 284.245 |  | 26
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0323_W |  |  | 5800 | 0 | 5800 | 261 | 2026-11-07 | 2026-11-19 | 2026-11-21 | 2026-11-26 | 2026-11-28 | 2026-12-31 |  | 1.8 | 0.54 | 8.6 | 38 | 2745.12 | 2.1128 | 319.7756 |  | 29
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0328_W |  |  | 4190 | 0 | 4190 | 188.55 | 2026-11-07 | 2026-11-21 | 2026-11-24 | 2026-11-27 | 2026-11-29 | 2027-01-05 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 1.3737 | 355.3062 |  | 30
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0427_E |  |  | 638 | 0 | 638 | 28.71 | 2026-11-16 | 2026-11-23 | 2026-11-25 | 2026-11-27 | 2026-11-29 | 2027-01-23 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.20917 | 355.3062 |  | 46
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0502_E |  |  | 460 | 0 | 460 | 20.7 | 2026-11-20 | 2026-11-23 | 2026-11-25 | 2026-11-27 | 2026-11-29 | 2027-01-29 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.15081 | 355.3062 |  | 51
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0427_W |  |  | 2552 | 0 | 2552 | 114.84 | 2026-11-16 | 2026-11-23 | 2026-11-25 | 2026-11-28 | 2026-11-30 | 2027-02-04 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.83668 | 355.3062 |  | 55
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0502_W |  |  | 1844 | 0 | 1844 | 82.98 | 2026-11-20 | 2026-11-24 | 2026-11-26 | 2026-11-30 | 2026-12-02 | 2027-02-09 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.60456 | 355.3062 |  | 57
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0530_E |  |  | 288 | 0 | 288 | 12.96 | 2026-11-30 | 2026-11-25 | 2026-11-27 | 2026-11-30 | 2026-12-02 | 2027-02-26 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.094422 | 355.3062 |  | 72
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0604_E |  |  | 396 | 0 | 396 | 17.82 | 2026-12-07 | 2026-11-25 | 2026-11-27 | 2026-11-30 | 2026-12-02 | 2027-03-03 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.12983 | 355.3062 |  | 76
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0530_W |  |  | 1146 | 0 | 1146 | 51.57 | 2026-11-30 | 2026-11-25 | 2026-11-27 | 2026-11-30 | 2026-12-02 | 2027-03-09 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.37572 | 355.3062 |  | 79
6-19 | TGT | G92X13_2PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; | 0604_W |  |  | 1578 | 0 | 1578 | 71.01 | 2026-12-07 | 2026-11-25 | 2026-11-27 | 2026-12-01 | 2026-12-03 | 2027-03-13 |  | 2 | 0.54 | 8.6 | 38 | 3050.1333 | 0.51735 | 355.3062 |  | 78
6-19 | TGT | Z2850Y_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0321 |  |  | 749 | 0 | 749 | 104.86 | 2026-11-30 | 2026-11-23 | 2026-11-28 | 2026-12-05 | 2026-12-07 | 2027-01-02 |  | 0.5 | 1.68 | 7 | 38 | 199.5 | 3.7544 | 28.5514 |  | 22
6-19 | TGT | Z2850Y_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0321 |  |  | 1500 | 0 | 1500 | 210 | 2026-11-30 | 2026-11-27 | 2026-12-03 | 2026-12-09 | 2026-12-11 | 2027-01-02 |  | 1 | 1.68 | 8.6 | 38 | 490.2 | 3.06 | 57.1028 |  | 19
6-19 | TGT | Z2850Y_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0321 |  |  | 1500 | 0 | 1500 | 210 | 2026-11-30 | 2026-12-01 | 2026-12-07 | 2026-12-12 | 2026-12-14 | 2027-01-02 |  | 1.1 | 1.68 | 8.6 | 38 | 539.22 | 2.7818 | 62.8131 |  | 16
6-19 | TGT | Z2850Y_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0321 |  |  | 1800 | 0 | 1800 | 252 | 2026-11-30 | 2026-12-04 | 2026-12-10 | 2026-12-16 | 2026-12-18 | 2027-01-02 |  | 1.2 | 1.68 | 8.6 | 38 | 588.24 | 3.06 | 68.5233 |  | 13
6-19 | TGT | Z2850Y_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0328 |  |  | 2548 | 0 | 2548 | 356.72 | 2026-12-03 | 2026-12-08 | 2026-12-14 | 2026-12-21 | 2026-12-23 | 2027-01-05 |  | 1.4 | 1.68 | 8.6 | 38 | 686.28 | 3.7128 | 79.9439 |  | 10
6-19 | TGT | Z2850Y_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0328 |  |  | 3000 | 0 | 3000 | 420 | 2026-12-03 | 2026-12-12 | 2026-12-18 | 2026-12-26 | 2026-12-28 | 2027-01-05 |  | 1.5 | 1.68 | 8.6 | 38 | 735.3 | 4.08 | 85.6542 |  | 6
6-19 | TGT | Z2850Y_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0328 |  |  | 3500 | 0 | 3500 | 490 | 2026-12-03 | 2026-12-17 | 2026-12-23 | 2026-12-31 | 2027-01-02 | 2027-01-05 |  | 1.6 | 1.68 | 8.6 | 38 | 784.32 | 4.4625 | 91.3645 |  | 2
6-19 | TGT | Z2850Y_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0404 |  |  | 6607 | 0 | 6607 | 924.98 | 2027-01-04 | 2026-12-22 | 2026-12-29 | 2027-01-11 | 2027-01-13 | 2027-01-12 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 7.4879 | 102.785 |  | 1
6-19 | TGT | Z2850Y_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0418 |  |  | 2637 | 0 | 2637 | 369.18 | 2027-01-04 | 2026-12-31 | 2027-01-08 | 2027-01-14 | 2027-01-16 | 2027-01-26 |  | 1.8 | 1.68 | 8.6 | 38 | 882.36 | 2.9886 | 102.785 |  | 10
2026-04-12
6-20 | ONY | 777362_FA26 | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po |  |  | 138695 | 138695 | 0 | 12135.8125 | 2026-05-23 | 2026-04-08 | 2026-04-10 | 2026-07-17 | 2026-07-22 | 2026-07-30 |  | 2.1304 | 1.05 | 9.4002 | 37.0349 | 1779.9917 | 77.9189 | 189.6972 |  | 11
6-20 | ONY | 777362_VMI | Pull On Pants | [特工] Garment Imitative Wash(Normal) 成衣假水洗(清水); | all po 05, 06, 07, 08, 09 |  |  | 770 | 770 | 0 | 67.375 | 2026-06-23 | 2026-07-13 | 2026-07-15 | 2026-07-18 | 2026-07-23 | 2026-08-20 |  | 2.0801 | 1.05 | 7.995 | 36 | 1436.8349 | 0.5359 | 180.0417 |  | 25
6-20 | HLF | CPM263PA81 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 31 | 31 | 0 | 2.7642 | 2026-05-23 | 2026-07-10 | 2026-07-16 | 2026-07-18 | 2026-07-20 | 2026-08-21 |  | 1.3516 | 1.07 | 8 | 37 | 942.2492 | 0.0329 | 117.9935 |  | 26
6-20 | HLF | CPM263PA05_26Q4 | Pull On Pants | [特工] General Embroidery(Within 20000 Stitches) 一般繡花(2萬針以下); | all po |  |  | 20835 | 20835 | 0 | 2100.8625 | 2026-07-10 | 2026-07-10 | 2026-07-16 | 2026-08-21 | 2026-08-23 | 2026-08-21 |  | 1.3551 | 1.21 | 7.7377 | 37.0102 | 808.2034 | 25.7794 | 104.6388 |  | 0
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025143 |  |  | 7812 | 7812 | 0 | 826.77 | 2026-08-18 | 2026-08-14 | 2026-08-19 | 2026-09-04 | 2026-09-06 | 2026-10-21 |  | 1.3827 | 1.27 | 8.781 | 35.519 | 855.7067 | 9.1293 | 97.6255 |  | 36
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025140 |  |  | 96 | 96 | 0 | 10.16 | 2026-08-18 | 2026-08-31 | 2026-09-02 | 2026-09-04 | 2026-09-06 | 2026-10-22 |  | 1.3376 | 1.27 | 9 | 34 | 812.1827 | 0.1182 | 90.4053 |  | 37
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025142 |  |  | 9384 | 9384 | 0 | 993.14 | 2026-08-18 | 2026-08-31 | 2026-09-02 | 2026-09-17 | 2026-09-19 | 2026-11-18 |  | 1.6353 | 1.27 | 9 | 35.5832 | 1039.1796 | 9.0302 | 115.6726 |  | 51
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025144 |  |  | 10000 | 947 | 9053 | 1058.3333 | 2026-08-18 | 2026-09-11 | 2026-09-15 | 2026-09-30 | 2026-10-02 | 2026-12-16 |  | 1.73 | 1.27 | 9 | 37 | 1143.1077 | 8.7481 | 127.241 |  | 66
6-20 | TGT | 4401EW_C127 | Robe |  | 10002025144 |  |  | 2504 | 0 | 2504 | 265.0067 | 2026-08-18 | 2026-09-24 | 2026-09-28 | 2026-10-02 | 2026-10-04 | 2026-12-16 |  | 1.75 | 1.27 | 8.6 | 37 | 1104.9307 | 2.2662 | 128.712 |  | 64
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 795 | 0 | 795 | 113.95 | 2026-09-21 | 2026-09-23 | 2026-09-30 | 2026-10-07 | 2026-10-09 | 2026-11-02 |  | 0.5 | 1.72 | 7 | 37 | 189.7326 | 4.1901 | 27.1535 |  | 22
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 1400 | 0 | 1400 | 200.6667 | 2026-09-21 | 2026-09-29 | 2026-10-05 | 2026-10-10 | 2026-10-12 | 2026-11-02 |  | 1 | 1.72 | 8.6 | 37 | 466.2 | 3.003 | 54.3071 |  | 19
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 1500 | 0 | 1500 | 215 | 2026-09-21 | 2026-10-02 | 2026-10-08 | 2026-10-14 | 2026-10-16 | 2026-11-02 |  | 1.1 | 1.72 | 8.6 | 37 | 512.82 | 2.925 | 59.7378 |  | 16
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 2500 | 0 | 2500 | 358.3333 | 2026-09-21 | 2026-10-06 | 2026-10-12 | 2026-10-19 | 2026-10-21 | 2026-11-02 |  | 1.2 | 1.72 | 8.6 | 37 | 559.44 | 4.4688 | 65.1685 |  | 12
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 2795 | 0 | 2795 | 400.6167 | 2026-09-21 | 2026-10-10 | 2026-10-16 | 2026-10-23 | 2026-10-25 | 2026-11-02 |  | 1.4 | 1.72 | 8.6 | 37 | 652.68 | 4.2823 | 76.0299 |  | 8
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041479_T1, 10002041478_T12, 0116_SET |  |  | 5000 | 0 | 5000 | 716.6667 | 2026-09-21 | 2026-10-15 | 2026-10-21 | 2026-10-31 | 2026-11-02 | 2026-11-02 |  | 1.5 | 1.72 | 8.6 | 37 | 699.3 | 7.15 | 81.4606 |  | 1
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041497 |  |  | 2994 | 0 | 2994 | 429.14 | 2026-10-19 | 2026-10-23 | 2026-10-29 | 2026-11-05 | 2026-11-07 | 2026-11-16 |  | 1.6 | 1.72 | 8.6 | 37 | 745.92 | 4.0138 | 86.8913 |  | 9
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041486 |  |  | 3318 | 0 | 3318 | 475.58 | 2026-10-19 | 2026-10-28 | 2026-11-03 | 2026-11-10 | 2026-11-12 | 2026-11-30 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 3.954 | 97.7527 |  | 17
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041480 |  |  | 5556 | 0 | 5556 | 796.36 | 2026-11-02 | 2026-11-02 | 2026-11-07 | 2026-11-18 | 2026-11-20 | 2026-12-14 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 6.6209 | 97.7527 |  | 22
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041498 |  |  | 2874 | 0 | 2874 | 411.94 | 2026-11-02 | 2026-11-10 | 2026-11-16 | 2026-11-21 | 2026-11-23 | 2026-12-28 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 3.4249 | 97.7527 |  | 30
6-20 | TGT | 6ZE54X_C127 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 10002041488 |  |  | 996 | 0 | 996 | 142.76 | 2026-11-02 | 2026-11-13 | 2026-11-19 | 2026-11-23 | 2026-11-25 | 2027-01-11 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 1.1869 | 97.7527 |  | 39
6-20 | TGT | 6ZE54X_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0321 |  |  | 7988 | 0 | 7988 | 1144.9467 | 2026-11-23 | 2026-11-14 | 2026-11-20 | 2026-12-04 | 2026-12-06 | 2027-01-02 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 9.519 | 97.7527 |  | 23
6-20 | TGT | 6ZE54X_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0328 |  |  | 7947 | 0 | 7947 | 1139.07 | 2026-12-07 | 2026-11-26 | 2026-12-02 | 2026-12-15 | 2026-12-17 | 2027-01-05 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 9.4702 | 97.7527 |  | 15
6-20 | TGT | Z2850Y_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0328 |  |  | 6800 | 0 | 6800 | 952 | 2026-12-03 | 2026-12-07 | 2026-12-12 | 2026-12-24 | 2026-12-26 | 2027-01-05 |  | 1.8 | 1.68 | 8.6 | 37 | 859.14 | 7.9149 | 100.0801 |  | 7
6-20 | TGT | 6ZE54X_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0404 |  |  | 7947 | 0 | 7947 | 1139.07 | 2026-12-21 | 2026-12-16 | 2026-12-22 | 2027-01-07 | 2027-01-09 | 2027-01-12 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 9.4702 | 97.7527 |  | 4
6-20 | TGT | 6ZE54X_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0418 |  |  | 7947 | 0 | 7947 | 1139.07 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-18 | 2027-01-20 | 2027-01-26 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 9.4702 | 97.7527 |  | 7
6-20 | TGT | 6ZE54X_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0502 |  |  | 7947 | 0 | 7947 | 1139.07 | 2027-01-04 | 2027-01-09 | 2027-01-15 | 2027-01-28 | 2027-01-30 | 2027-02-09 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 9.4702 | 97.7527 |  | 9
6-20 | TGT | 6ZE54X_C227 | Pull On Pants | [特工] Eyelet Grommet Hole Embroidery 雞眼繡; | 0516 |  |  | 5963 | 0 | 5963 | 854.6967 | 2027-01-11 | 2027-01-20 | 2027-01-26 | 2027-02-05 | 2027-02-07 | 2027-02-23 |  | 1.8 | 1.72 | 8.6 | 37 | 839.16 | 7.1059 | 97.7527 |  | 14
DATA END |  |  |  |  | PLEASE DO NOT REMOVE THIS ROW. NEW DATA PLEASE INSERT ABOVE ↑
| TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_E |  |  | 65892 |  |  |  | 2027-01-11: 2026-11-13; 2027-02-23: 2026-11-27 |  |  | 0.42
| TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0228_W |  |  | 113440 |  |  |  | 2027-01-11: 2026-11-13; 2027-02-23: 2026-12-08 |  |  | 0.42
| TGT | 44ZEP9_3PK_C127 | Boxer | [特車] 4-NEEDLE SEAMER M/C FOR COVERSTITCH 四針六線併縫車; Cylinder Waist Band Attaching(Cut Right side)-Auto 筒型三本車(附右修刀)-自動切線; High Speed Automatic Splicing Rubber Band Machine 自動拼接橡筋機; | 0314_W |  |  | 49920 |  |  |  | 2027-01-11: 2026-11-13; 2027-02-23: 2026-12-11 |  |  | 0.42
ORDER DATA FIRST |  |  |  |  | PLEASE DO NOT REMOVE THIS ROW. NEW DATA PLEASE INSERT BELOW ↓

## Holidays_Table
2025-01-01 | New Year's Day | 停工請C欄打勾"V"
2025-01-27 | Isra Mi'raj
2025-01-29 | Chinese New Year
2025-03-15 | Off
2025-03-22 | Off
2025-03-28 | Off
2025-03-29 | Hindu New Year
2025-03-31 | Eid Al-Fitr
2025-04-01 | Eid Al-Fitr
2025-04-02 | Eid Al-Fitr
2025-04-03 | Eid Al-Fitr
2025-04-04 | Eid Al-Fitr
2025-04-05 | Eid Al-Fitr
2025-04-07 | Off
2025-04-18 | Good Friday
2025-05-01 | World Labor Day
2025-05-12 | Waisak Day
2025-05-29 | Ascension Day of Jesus Christ
2025-06-06 | Eid Al Adha
2025-06-27 | Islamic New Year
2025-08-16 | Off
2025-08-23 | Off
2025-08-30 | Off
2025-09-05 | Prophet Muhammad's Birthday
2025-09-06 | Off
2025-12-25 | Christmas Day
2026-01-01 | New Year's Day
2026-01-16 | Isra Mi'raj
2026-02-17 | Chinese New Year
2026-03-19 | Hindu New Year
2026-03-20 | Eid Al-Fitr
2026-03-21 | Eid Al-Fitr
2026-03-23 | Eid Al-Fitr
2026-03-24 | Eid Al-Fitr
2026-03-25 | Eid Al-Fitr
2026-03-26 | Eid Al-Fitr
2026-04-03 | Good Friday
2026-05-01 | World Labor Day
2026-05-14 | Ascension Day of Jesus Christ
2026-05-27 | Eid Al Adha
2026-06-01 | Pancasila Day
2026-06-16 | Islamic New Year
2026-08-08 | Off
2026-08-15 | Off
2026-08-17 | Independent Day
2026-08-22 | Off
2026-08-25 | Prophet Muhammad's Birthday
2026-08-29 | Off
2026-09-05 | Off
2026-09-12 | Off
2026-09-19 | Off
2026-09-26 | Off
2026-12-25 | Christmas Day
2027-01-01 | New Year's Day
2027-01-05 | Isra Mi'raj
2027-02-06 | Chinese New Year
2027-03-08 | Hindu New Year
2027-03-09 | Eid Al-Fitr
2027-03-10 | Eid Al-Fitr
2027-03-11 | Eid Al-Fitr
2027-03-12 | Eid Al-Fitr
2027-03-13 | Eid Al-Fitr
2027-03-26 | Good Friday
2027-05-01 | World Labor Day
2027-05-06 | Ascension Day of Jesus Christ
2027-05-17 | Eid Al Adha
2027-05-20 | Waisak Day
2027-06-01 | Pancasila Day
2027-08-17 | Islamic New Year
2027-12-25 | Christmas Day

## B01_Summary
Line | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK | STYLE | RFP | Start Cut | FIN | SHIP | REMARK
6-01 | PST840 | 2026-08-18 | 2026-09-03 | 2026-09-23 | 2026-11-02 | L6-01,6-08,6-15 | Z2850Y_C127 | 2026-09-12 | 2026-09-14 | 2026-12-11 | 2027-01-09 | L6-01,6-14,6-15,6-19 | LR16E1_C227 | 2026-12-04 | 2026-12-07 | 2027-02-22 | 2027-03-06 | L6-01,6-14
6-02 | X048GZ_C127 | 2026-08-22 | 2026-08-21 | 2026-10-08 | 2026-10-24 | L6-02,6-09 | 1195255_SP27 | 2026-10-07 | 2026-10-03 | 2026-10-16 | 2026-11-05 | L6-02,6-03 | 1194431_SP27 | 2026-10-07 | 2026-10-12 | 2026-10-31 | 2027-01-28 | L6-02 | CFM271SH09 | 2026-11-05 | 2026-10-27 | 2026-12-08 | 2026-12-07 | L6-02,6-14,6-16 | 1197198/1197204 | 2026-11-30 | 2026-12-03 | 2027-01-20 | 2027-01-28 | L6-02,6-03,6-06,6-07,6-08,6-10,6-16,6-17
6-03 | 1196262_HO26_PF/1196262_SP27 | 2026-09-07 | 2026-09-08 | 2026-10-22 | 2027-01-07 | L6-03,6-10,6-19 | 1195255_SP27 | 2026-10-07 | 2026-10-17 | 2026-11-30 | 2027-01-07 | L6-02,6-03 | 1197198/1197204 | 2026-11-30 | 2026-11-25 | 2027-01-18 | 2027-01-28 | L6-02,6-03,6-06,6-07,6-08,6-10,6-16,6-17
6-04 | MRLPMM_3PC_C127 | 2026-08-24 | 2026-09-02 | 2026-10-03 | 2026-10-08 | L6-04,6-11,6-17 | 766362_V1 | 2026-05-22 | 2026-09-29 | 2026-10-20 | 2026-11-12 | L6-04 | L0303X_6PK_C127 | 2026-10-12 | 2026-10-15 | 2026-11-17 | 2026-12-23 | L6-04,6-10 | 44ZEP9_3PK_C127 | 2026-11-13 | 2026-11-12 | 2027-01-07 | 2027-01-15 | L6-04,6-15,6-18
6-05 | 5GK4L2_C127 | 2026-09-10 | 2026-09-07 | 2026-09-21 | 2026-10-10 | L6-05 | 6ZE54X_C127/6ZE54X_C227 | 2026-09-21 | 2026-09-10 | 2027-02-04 | 2027-02-23 | L6-05,6-20
6-06 | 777362_VMI | 2026-08-01 | 2026-09-08 | 2026-10-13 | 2026-11-26 | L6-06,6-16 | 1204591_SP27_ID | 2026-10-12 | 2026-10-08 | 2026-10-20 | 2026-11-06 | L6-06 | MRLPMM_SSLLC127 | 2026-10-15 | 2026-10-15 | 2026-11-05 | 2026-11-06 | L6-06,6-18 | CFW271SH01 | 2026-11-09 | 2026-10-28 | 2026-12-04 | 2026-12-10 | L6-06,6-17 | 1197198/1197204 | 2026-11-30 | 2026-11-30 | 2027-01-19 | 2027-01-28 | L6-02,6-03,6-06,6-07,6-08,6-10,6-16,6-17
6-07 | 352E6Y_SL_C127 | 2026-08-24 | 2026-08-14 | 2026-09-29 | 2026-12-05 | L6-07 | 1194585_HO26_NB | 2026-09-10 | 2026-09-18 | 2026-10-03 | 2026-10-29 | L6-07 | 1194432_SP27 | 2026-10-09 | 2026-09-29 | 2026-10-17 | 2026-11-05 | L6-07,6-13,6-18 | 440ZP9_C127 | 2026-10-09 | 2026-10-13 | 2026-12-10 | 2026-12-10 | L6-07,6-10 | 1197198/1197204 | 2026-11-30 | 2026-12-05 | 2027-01-19 | 2027-01-28 | L6-02,6-03,6-06,6-07,6-08,6-10,6-16,6-17
6-08 | PST840 | 2026-08-18 | 2026-09-09 | 2026-10-14 | 2026-12-03 | L6-01,6-08,6-15 | 546462_6PK_C127 | 2026-10-13 | 2026-10-09 | 2026-11-27 | 2026-12-30 | L6-08 | 1197198/1197204 | 2026-11-30 | 2026-11-23 | 2027-01-16 | 2027-01-28 | L6-02,6-03,6-06,6-07,6-08,6-10,6-16,6-17
6-09 | W9ZMM8_7PK_C426 | 2026-06-27 | 2026-07-18 | 2026-09-21 | 2026-11-04 | L6-09 | X048GZ_C127 | 2026-08-22 | 2026-09-10 | 2026-10-02 | 2026-10-01 | L6-02,6-09 | 9KM9L2_C127 | 2026-09-08 | 2026-09-28 | 2026-11-10 | 2026-12-16 | L6-09,6-12 | W9ZMM8_7PK_C127 | 2026-10-13 | 2026-11-02 | 2026-12-05 | 2026-12-30 | L6-09 | 9KM9L2_C227/9KM9L2_C127 | 2026-12-03 | 2026-12-01 | 2027-01-15 | 2027-01-26 | L6-09,6-12
6-10 | 1188289_HO26 | 2026-08-06 | 2026-09-11 | 2026-09-21 | 2026-10-15 | L6-10,6-13,6-19 | 1196262_HO26_PF | 2026-09-07 | 2026-09-15 | 2026-10-08 | 2026-10-15 | L6-03,6-10,6-19 | L0303X_6PK_C127 | 2026-10-12 | 2026-10-03 | 2026-11-06 | 2026-12-23 | L6-04,6-10 | 440ZP9_C127 | 2026-10-09 | 2026-11-02 | 2026-12-10 | 2026-12-10 | L6-07,6-10 | 1197198/1197204 | 2026-11-30 | 2026-12-05 | 2027-01-19 | 2027-01-28 | L6-02,6-03,6-06,6-07,6-08,6-10,6-16,6-17
6-11 | MRLPMM_3PC_C127 | 2026-08-24 | 2026-08-20 | 2026-11-13 | 2026-12-05 | L6-04,6-11,6-17 | 458476_2PK_C127 | 2026-10-24 | 2026-11-09 | 2027-01-09 | 2027-04-06 | L6-11
6-12 | 9KM9L2_C127/9KM9L2_C227 | 2026-09-08 | 2026-09-08 | 2027-01-04 | 2027-01-26 | L6-09,6-12
6-13 | 1188289_HO26 | 2026-08-06 | 2026-09-14 | 2026-10-05 | 2026-11-12 | L6-10,6-13,6-19 | 1194432_SP27 | 2026-10-09 | 2026-09-30 | 2027-01-08 | 2027-01-28 | L6-07,6-13,6-18
6-14 | 00GG4Z_C127IND | 2026-08-22 | 2026-09-07 | 2026-10-06 | 2026-12-28 | L6-14 | Z2850Y_C127 | 2026-09-12 | 2026-09-28 | 2026-10-14 | 2026-10-29 | L6-01,6-14,6-15,6-19 | L06X27_SSLLC127 | 2026-10-15 | 2026-10-09 | 2026-11-07 | 2026-11-06 | L6-14 | CFM271SH09 | 2026-11-05 | 2026-11-03 | 2026-12-08 | 2026-12-07 | L6-02,6-14,6-16 | LR16E1_C227 | 2026-12-04 | 2026-12-03 | 2027-02-20 | 2027-03-06 | L6-01,6-14
6-15 | LPST840 | 2026-08-24 | 2026-09-10 | 2026-09-30 | 2026-11-02 | L6-15 | PST840 | 2026-09-14 | 2026-09-24 | 2026-10-06 | 2026-12-03 | L6-01,6-08,6-15 | Z2850Y_C127 | 2026-09-12 | 2026-09-28 | 2026-11-14 | 2026-12-07 | L6-01,6-14,6-15,6-19 | 44ZEP9_3PK_C127 | 2026-11-13 | 2026-11-10 | 2027-01-08 | 2027-01-15 | L6-04,6-15,6-18
6-16 | 777362_VMI | 2026-06-23 | 2026-08-03 | 2026-10-16 | 2027-01-07 | L6-06,6-16 | 1193182_SP27 | 2026-10-09 | 2026-10-08 | 2026-11-12 | 2027-01-28 | L6-16 | CFM271SH09 | 2026-11-05 | 2026-11-07 | 2026-12-09 | 2026-12-07 | L6-02,6-14,6-16 | 1197198/1197204 | 2026-11-30 | 2026-12-04 | 2027-01-18 | 2027-01-28 | L6-02,6-03,6-06,6-07,6-08,6-10,6-16,6-17
6-17 | MRLPMM_3PC_C127 | 2026-08-24 | 2026-08-31 | 2026-11-12 | 2026-12-05 | L6-04,6-11,6-17 | CFW271SH01 | 2026-11-09 | 2026-11-04 | 2026-12-09 | 2026-12-10 | L6-06,6-17 | 1197198/1197204 | 2026-11-30 | 2026-12-04 | 2027-01-18 | 2027-01-28 | L6-02,6-03,6-06,6-07,6-08,6-10,6-16,6-17
6-18 | 352E6Y_LL_C127 | 2026-08-18 | 2026-08-27 | 2026-10-12 | 2026-12-05 | L6-18 | 1KE9E9_SSLLC127 | 2026-10-15 | 2026-10-07 | 2026-10-23 | 2026-11-06 | L6-18 | MRLPMM_SSLLC127 | 2026-10-15 | 2026-10-19 | 2026-10-29 | 2026-11-06 | L6-06,6-18 | 1194432_SP27 | 2026-10-09 | 2026-10-24 | 2026-11-17 | 2026-12-03 | L6-07,6-13,6-18 | 44ZEP9_3PK_C127 | 2026-11-13 | 2026-11-12 | 2027-01-08 | 2027-01-15 | L6-04,6-15,6-18
6-19 | 1188289_HO26 | 2026-08-06 | 2026-09-14 | 2026-09-22 | 2026-10-15 | L6-10,6-13,6-19 | 1196262_HO26_PF | 2026-09-07 | 2026-09-16 | 2026-10-06 | 2026-10-15 | L6-03,6-10,6-19 | Z2850Y_C127 | 2026-09-12 | 2026-09-28 | 2026-11-17 | 2026-12-07 | L6-01,6-14,6-15,6-19 | G92X13_2PK_C127 | 2026-10-26 | 2026-11-12 | 2026-12-01 | 2027-03-13 | L6-19 | Z2850Y_C227 | 2026-11-30 | 2026-11-23 | 2027-01-14 | 2027-01-26 | L6-19,6-20
6-20 | 4401EW_C127 | 2026-08-18 | 2026-08-31 | 2026-10-02 | 2026-12-16 | L6-20 | 6ZE54X_C127/6ZE54X_C227 | 2026-09-21 | 2026-09-23 | 2026-12-15 | 2027-01-05 | L6-05,6-20 | Z2850Y_C227 | 2026-12-03 | 2026-12-07 | 2026-12-24 | 2027-01-05 | L6-19,6-20 | 6ZE54X_C227 | 2026-12-21 | 2026-12-16 | 2027-02-05 | 2027-02-23 | L6-05,6-20

## B02_Summary_By _Order
款式 Style | 產品 Product Item | 可開裁日 CRFP | 組別 Line | 預計開裁日 Est. Start Cut | 預計上線日 Sewing Start | 工作時數 Work hr | 預計日產 Target Output | 預計下線日 Est. Sewing Fin. | 剩餘工作天 Need Work Days | 剩餘數量 Remainning Qty | 分配訂單數量 Allocate Qty
00GG4Z_C127IND | Pull On Pants | 2026-08-22 | 6-14 | 2026-08-11 | 2026-08-13 | 8.7013 | 734.0736 | 2026-10-06 | 14.3923 | 10565 | 26016
00GG4Z_C127IND 合計 | [9 empty] | 10565 | 26016
1182430_HO26_HT | Pull On Pants | 2026-08-06 | 6-01 | 2026-07-22 | 2026-07-24 | 7.8679 | 1134.2557 | 2026-08-31 | 0 | 0 | 27270
| Pull On Pants | 2026-08-24 | 6-17 | 2026-08-10 | 2026-08-12 | 8.3389 | 1166.5206 | 2026-09-08 | 0 | 0 | 17242
1182430_HO26_HT 合計 | [9 empty] | 0 | 44512
1182719_HO26 | Skorts | 2026-07-11 | 6-10 | 2026-07-31 | 2026-08-03 | 8 | 1659.9607 | 2026-08-27 | 0 | 0 | 23350
| Skorts | 2026-07-11 | 6-11 | 2026-08-03 | 2026-08-05 | 8 | 1288.3006 | 2026-08-31 | 0 | 0 | 17407
1182719_HO26 合計 | [9 empty] | 0 | 40757
1182723_HO26 | Skorts | 2026-07-14 | 6-13 | 2026-07-22 | 2026-07-24 | 7.8718 | 1178.6229 | 2026-09-03 | 0 | 0 | 32276
| Skorts | 2026-07-14 | 6-19 | 2026-07-21 | 2026-07-23 | 7.9417 | 1334.8651 | 2026-09-02 | 0 | 0 | 36303
1182723_HO26 合計 | [9 empty] | 0 | 68579
1184403_HO26 | Pull On Pants | 2026-07-13 | 6-10 | 2026-07-16 | 2026-07-18 | 7.2192 | 562.4717 | 2026-08-05 | 0 | 0 | 7414
1184403_HO26 合計 | [9 empty] | 0 | 7414
1184404_HO26 | Tee | 2026-07-13 | 6-05 | 2026-07-17 | 2026-07-20 | 6.9853 | 671.4355 | 2026-07-31 | 0 | 0 | 5350
1184404_HO26 合計 | [9 empty] | 0 | 5350
1188289_HO26 | Pull On Pants | 2026-08-06 | 6-10 | 2026-08-20 | 2026-08-24 | 8.706 | 1830.5921 | 2026-09-21 | 0.41134 | 753 | 31017
| Pull On Pants | 2026-08-06 | 6-13 | 2026-08-28 | 2026-09-01 | 8.8788 | 2148.0127 | 2026-10-05 | 11.8863 | 25532 | 49616
| Pull On Pants | 2026-08-06 | 6-19 | 2026-08-27 | 2026-08-31 | 8.8444 | 2102.5361 | 2026-09-22 | 0.76289 | 1604 | 27471
1188289_HO26 合計 | [9 empty] | 27889 | 108104
1193182_SP27 | Tee | 2026-10-09 | 6-16 | 2026-10-08 | 2026-10-14 | 8.5236 | 1716.8534 | 2026-11-12 | 23.2559 | 39927 | 39927
1193182_SP27 合計 | [9 empty] | 39927 | 39927
1194431_SP27 | Tee | 2026-10-07 | 6-02 | 2026-10-12 | 2026-10-14 | 8.4417 | 780.7159 | 2026-10-31 | 13.3006 | 10384 | 10384
1194431_SP27 合計 | [9 empty] | 10384 | 10384
1194432_SP27 | Tee | 2026-10-09 | 6-07 | 2026-09-29 | 2026-10-01 | 8.4141 | 1761.77 | 2026-10-17 | 12.8479 | 22635 | 22635
| Tee | 2026-10-09 | 6-13 | 2026-09-30 | 2026-10-02 | 8.568 | 2213.7771 | 2027-01-08 | 79.0034 | 174896 | 174896
| Tee | 2026-10-09 | 6-18 | 2026-10-24 | 2026-10-27 | 8.4325 | 1637.5107 | 2026-11-17 | 14.85 | 24317 | 24317
1194432_SP27 合計 | [9 empty] | 221848 | 221848
1194585_HO26_NB | Pull On Pants | 2026-09-10 | 6-07 | 2026-09-18 | 2026-09-25 | 8.0813 | 780.3725 | 2026-10-03 | 3.8443 | 3000 | 3000
1194585_HO26_NB 合計 | [9 empty] | 3000 | 3000
1195255_SP27 | Tee | 2026-10-07 | 6-02 | 2026-10-03 | 2026-10-06 | 8.3297 | 1296.7181 | 2026-10-16 | 6.9846 | 9057 | 9057
| Tee | 2026-10-07 | 6-03 | 2026-10-17 | 2026-10-20 | 8.5453 | 1998.1584 | 2026-11-30 | 33.5059 | 66950 | 66950
1195255_SP27 合計 | [9 empty] | 76007 | 76007
1196262_HO26_PF | Tee | 2026-09-07 | 6-03 | 2026-09-08 | 2026-09-10 | 8.8143 | 1415.3295 | 2026-10-13 | 19.0789 | 27003 | 32747
| Tee | 2026-09-07 | 6-10 | 2026-09-15 | 2026-09-17 | 8.5004 | 1138.0634 | 2026-10-08 | 14.5036 | 16506 | 16506
| Tee | 2026-09-07 | 6-19 | 2026-09-16 | 2026-09-18 | 8.4778 | 1037.0542 | 2026-10-06 | 11.8181 | 12256 | 12256
1196262_HO26_PF 合計 | [9 empty] | 55765 | 61509
1196262_SP27 | Tee | 2026-10-10 | 6-03 | 2026-10-08 | 2026-10-10 | 8.6 | 1486.1881 | 2026-10-22 | 8.7708 | 13035 | 13035
1196262_SP27 合計 | [9 empty] | 13035 | 13035
1197198/1197204 | Dress | 2026-11-30 | 6-02 | 2026-12-03 | 2026-12-05 | 8.4893 | 1106.0634 | 2027-01-20 | 33.8688 | 37461 | 37461
| Dress | 2026-11-30 | 6-03 | 2026-11-25 | 2026-11-27 | 8.5052 | 1159.3265 | 2027-01-18 | 38.9114 | 45111 | 45111
| Dress | 2026-11-30 | 6-06 | 2026-11-30 | 2026-12-02 | 8.498 | 1150.2953 | 2027-01-19 | 36.1655 | 41601 | 41601
| Dress | 2026-11-30 | 6-07 | 2026-12-05 | 2026-12-08 | 8.4803 | 1135.7816 | 2027-01-19 | 30.3412 | 34461 | 34461
| Dress | 2026-11-30 | 6-08 | 2026-11-23 | 2026-11-25 | 8.5096 | 1192.5915 | 2027-01-16 | 39.7756 | 47436 | 47436
| Dress | 2026-11-30 | 6-10 | 2026-12-05 | 2026-12-08 | 8.4847 | 1165.4107 | 2027-01-19 | 31.05 | 36186 | 36186
| Dress | 2026-11-30 | 6-16 | 2026-12-04 | 2026-12-07 | 8.482 | 1152.2868 | 2027-01-18 | 30.3405 | 34961 | 34961
| Dress | 2026-11-30 | 6-17 | 2026-12-04 | 2026-12-07 | 8.4836 | 1153.5967 | 2027-01-18 | 30.7395 | 35461 | 35461
1197198/1197204 合計 | [9 empty] | 312678 | 312678
1204591_SP27_ID | Pull On Pants | 2026-10-12 | 6-06 | 2026-10-08 | 2026-10-10 | 7.7793 | 434.2833 | 2026-10-20 | 5.7566 | 2500 | 2500
1204591_SP27_ID 合計 | [9 empty] | 2500 | 2500
1KE9E9_SSLLC127 | Pajama | 2026-10-15 | 6-18 | 2026-10-07 | 2026-10-09 | 8.4959 | 2240.2808 | 2026-10-23 | 8.856 | 19840 | 19840
1KE9E9_SSLLC127 合計 | [9 empty] | 19840 | 19840
352E6Y_LL_C127 | Pajama | 2026-08-18 | 6-18 | 2026-08-24 | 2026-09-01 | 8.7826 | 2134.0661 | 2026-10-12 | 18.3387 | 39136 | 62909
352E6Y_LL_C127 合計 | [9 empty] | 39136 | 62909
352E6Y_SL_C127 | Pajama | 2026-08-15 | 6-07 | 2026-08-12 | 2026-08-20 | 8.8415 | 2072.8891 | 2026-09-29 | 8.3429 | 17294 | 54474
352E6Y_SL_C127 合計 | [9 empty] | 17294 | 54474
4401EW_C127 | Robe | 2026-08-18 | 6-20 | 2026-08-14 | 2026-08-19 | 8.9008 | 1017.2066 | 2026-10-02 | 11.3615 | 11557 | 29796
4401EW_C127 合計 | [9 empty] | 11557 | 29796
440ZP9_C127 | Pull On Pants | 2026-10-09 | 6-07 | 2026-10-13 | 2026-10-15 | 8.5255 | 1484.3967 | 2026-12-10 | 44.8559 | 66584 | 66584
| Pull On Pants | 2026-10-09 | 6-10 | 2026-11-02 | 2026-11-04 | 8.4867 | 1460.7841 | 2026-12-10 | 29.083 | 42484 | 42484
440ZP9_C127 合計 | [9 empty] | 109068 | 109068
44ZEP9_3PK_C127 | Boxer | 2026-11-13 | 6-04 | 2026-11-12 | 2026-11-14 | 8.5748 | 3887.8204 | 2027-01-07 | 39.8475 | 154920 | 154920
| Boxer | 2026-11-13 | 6-15 | 2026-11-10 | 2026-11-12 | 8.5278 | 3203.9118 | 2027-01-08 | 45.2322 | 144920 | 144920
| Boxer | 2026-11-13 | 6-18 | 2026-11-12 | 2026-11-14 | 8.5245 | 3165.4385 | 2027-01-08 | 43.2547 | 136920 | 136920
44ZEP9_3PK_C127 合計 | [9 empty] | 436760 | 436760
458476_2PK_C127 | Boxer | 2026-10-24 | 6-11 | 2026-11-09 | 2026-11-11 | 8.5616 | 2393.569 | 2027-01-09 | 45.9581 | 110004 | 110004
458476_2PK_C127 合計 | [9 empty] | 110004 | 110004
45M87P_C426 | Pull On Pants | 2026-06-27 | 6-01 | 2026-06-30 | 2026-07-02 | 8.0771 | 836.0225 | 2026-07-27 | 0 | 0 | 15985
45M87P_C426 合計 | [9 empty] | 0 | 15985
546462_6PK_C127 | Panties | 2026-10-13 | 6-08 | 2026-10-09 | 2026-10-12 | 8.5582 | 5292.2703 | 2026-11-27 | 39.2497 | 207720 | 207720
546462_6PK_C127 合計 | [9 empty] | 207720 | 207720
5GK4L2_C127 | Jumper | 2026-09-10 | 6-05 | 2026-09-07 | 2026-09-09 | 9 | 514.2226 | 2026-09-21 | 1.056 | 543 | 3135
5GK4L2_C127 合計 | [9 empty] | 543 | 3135
5GK4L2_C426 | Jumper | 2026-07-03 | 6-05 | 2026-07-09 | 2026-07-11 | 7.5859 | 393.2819 | 2026-07-22 | 0 | 0 | 2892
5GK4L2_C426 合計 | [9 empty] | 0 | 2892
6ZE54X_C127 | Pull On Pants | 2026-09-21 | 6-05 | 2026-09-10 | 2026-09-17 | 8.4713 | 603.3689 | 2026-11-25 | 55.0791 | 33233 | 33233
| Pull On Pants | 2026-09-21 | 6-20 | 2026-09-23 | 2026-09-30 | 8.4517 | 657.413 | 2026-11-23 | 45.2197 | 29728 | 29728
6ZE54X_C127 合計 | [9 empty] | 62961 | 62961
6ZE54X_C227 | Pull On Pants | 2026-11-23 | 6-05 | 2026-11-17 | 2026-11-23 | 8.6 | 793.8 | 2027-02-04 | 57.6203 | 45739 | 45739
| Pull On Pants | 2026-11-23 | 6-20 | 2026-11-14 | 2026-11-20 | 8.6 | 839.16 | 2026-12-15 | 18.9892 | 15935 | 15935
| Pull On Pants | 2026-12-21 | 6-20 | 2026-12-16 | 2026-12-22 | 8.6 | 839.16 | 2027-02-05 | 35.5165 | 29804 | 29804
6ZE54X_C227 合計 | [9 empty] | 91478 | 91478
766362_HO26 | Pull On Pants | 2026-07-09 | 6-04 | 2026-07-02 | 2026-07-04 | 8.2229 | 1239.9326 | 2026-07-30 | 0 | 0 | 24434
| Pull On Pants | 2026-08-18 | 6-04 | 2026-08-07 | 2026-08-11 | 9 | 1703.6372 | 2026-09-08 | 0.13677 | 233 | 27675
| Pull On Pants | 2026-08-04 | 6-08 | 2026-07-07 | 2026-07-09 | 7.985 | 1535.2206 | 2026-08-18 | 0 | 0 | 43769
766362_HO26 合計 | [9 empty] | 233 | 95878
766362_V1 | Pull On Pants | 2026-05-22 | 6-04 | 2026-09-02 | 2026-09-04 | 9 | 1703.6372 | 2026-09-09 | 0.0076307 | 13 | 855
| Pull On Pants | 2026-05-22 | 6-04 | 2026-09-29 | 2026-10-01 | 8.3825 | 1248.1914 | 2026-10-20 | 14.1557 | 17669 | 17669
| Pull On Pants | 2026-05-22 | 6-08 | 2026-06-03 | 2026-06-05 | 9.3671 | 1437.6838 | 2026-07-11 | 0 | 0 | 39555
| Pull On Pants | 2026-05-22 | 6-08 | 2026-08-11 | 2026-08-13 | 8.0559 | 1356.1008 | 2026-09-04 | 0 | 0 | 15895
766362_V1 合計 | [9 empty] | 17682 | 73974
777362_FA26 | Pull On Pants | 2026-05-23 | 6-03 | 2026-05-11 | 2026-05-13 | 9.1023 | 1259.5162 | 2026-06-05 | 0 | 0 | 19159
| Pull On Pants | 2026-04-25 | 6-04 | 2026-04-15 | 2026-04-17 | 8.8333 | 1159.316 | 2026-05-19 | 0 | 0 | 26479
| Pull On Pants | 2026-05-26 | 6-05 | 2026-06-12 | 2026-06-15 | 9.1485 | 1399.0404 | 2026-07-14 | 0 | 0 | 31058
| Pull On Pants | 2026-05-26 | 6-06 | 2026-06-13 | 2026-06-17 | 9.4584 | 1510.9939 | 2026-07-09 | 0 | 0 | 25055
| Pull On Pants | 2026-05-26 | 6-08 | 2026-05-25 | 2026-05-28 | 8.7363 | 1308.6032 | 2026-06-08 | 0 | 0 | 7260
| Pull On Pants | 2026-04-25 | 6-10 | 2026-04-09 | 2026-04-11 | 8.5757 | 1103.5488 | 2026-04-30 | 0 | 0 | 15160
| Pull On Pants | 2026-05-26 | 6-13 | 2026-06-26 | 2026-06-29 | 9.3933 | 1193.554 | 2026-07-16 | 0 | 0 | 15589
| Pull On Pants | 2026-05-26 | 6-15 | 2026-06-23 | 2026-06-25 | 9.3739 | 1550.6758 | 2026-07-16 | 0 | 0 | 24345
| Pull On Pants | 2026-05-23 | 6-19 | 2026-07-21 | 2026-07-23 | 7.482 | 817.4638 | 2026-07-25 | 0 | 0 | 176
| Pull On Pants | 2026-05-23 | 6-20 | 2026-04-08 | 2026-04-10 | 9.4002 | 1779.9917 | 2026-07-17 | 0 | 0 | 138695
777362_FA26 合計 | [9 empty] | 0 | 302976
777362_HO26_GLD | Pull On Pants | 2026-08-29 | 6-06 | 2026-09-02 | 2026-09-04 | 9 | 1600.4197 | 2026-09-14 | 0.37615 | 602 | 6683
777362_HO26_GLD 合計 | [9 empty] | 602 | 6683
777362_VMI | Pull On Pants | 2026-05-04 | 6-03 | 2026-04-13 | 2026-04-15 | 9.1703 | 1300.1298 | 2026-05-16 | 0 | 0 | 29699
| Pull On Pants | 2026-05-07 | 6-05 | 2026-03-28 | 2026-03-31 | 8.9946 | 1259.8102 | 2026-05-29 | 0 | 0 | 56118
| Pull On Pants | 2026-04-13 | 6-06 | 2026-04-06 | 2026-04-08 | 8.7258 | 1219.0291 | 2026-05-05 | 0 | 0 | 24866
| Pull On Pants | 2026-06-23 | 6-06 | 2026-07-04 | 2026-07-07 | 8.3126 | 1509.2923 | 2026-09-08 | 0 | 0 | 67904
| Pull On Pants | 2026-08-01 | 6-06 | 2026-09-08 | 2026-09-10 | 8.8076 | 1710.1189 | 2026-10-13 | 18.3315 | 31349 | 39687
| Pull On Pants | 2026-05-07 | 6-07 | 2026-07-04 | 2026-07-07 | 8.2762 | 1035.0792 | 2026-07-23 | 0 | 0 | 11906
| Pull On Pants | 2026-05-07 | 6-08 | 2026-04-16 | 2026-04-18 | 9.3938 | 1434.8257 | 2026-05-30 | 0 | 0 | 43947
| Pull On Pants | 2026-05-04 | 6-12 | 2026-04-18 | 2026-04-21 | 9.1441 | 1376.3212 | 2026-05-26 | 0 | 0 | 36158
| Pull On Pants | 2026-06-23 | 6-13 | 2026-07-11 | 2026-07-14 | 7.9762 | 1104.5568 | 2026-07-27 | 0 | 0 | 10000
| Pull On Pants | 2026-06-23 | 6-15 | 2026-07-11 | 2026-07-14 | 7.855 | 1210.7956 | 2026-07-22 | 0 | 0 | 5783
| Pull On Pants | 2026-05-07 | 6-16 | 2026-04-08 | 2026-04-10 | 9.2232 | 1414.0742 | 2026-05-30 | 0 | 0 | 55281
| Pull On Pants | 2026-06-23 | 6-16 | 2026-08-03 | 2026-08-05 | 8.8265 | 1612.0843 | 2026-10-16 | 22.412 | 36130 | 80761
| Pull On Pants | 2026-05-07 | 6-18 | 2026-04-02 | 2026-04-06 | 9.0947 | 1505.6912 | 2026-05-26 | 0 | 0 | 58617
| Pull On Pants | 2026-06-23 | 6-18 | 2026-08-13 | 2026-08-18 | 8.0143 | 1260.476 | 2026-08-24 | 0 | 0 | 2978
| Pull On Pants | 2026-06-23 | 6-19 | 2026-07-04 | 2026-07-07 | 8.0928 | 1260.0109 | 2026-07-25 | 0 | 0 | 17165
| Pull On Pants | 2026-06-23 | 6-20 | 2026-07-13 | 2026-07-15 | 7.995 | 1436.8349 | 2026-07-18 | 0 | 0 | 770
777362_VMI 合計 | [9 empty] | 67479 | 541640
826369_HO26 | Pull On Pants | 2026-07-13 | 6-10 | 2026-07-11 | 2026-07-14 | 7.2576 | 622.6666 | 2026-07-21 | 0 | 0 | 2235
826369_HO26 合計 | [9 empty] | 0 | 2235
890955_FA26 | Pull On Pants | 2026-04-30 | 6-06 | 2026-04-29 | 2026-05-02 | 8.5835 | 1045.603 | 2026-05-13 | 0 | 0 | 7023
| Pull On Pants | 2026-04-13 | 6-06 | 2026-06-10 | 2026-06-12 | 9.4007 | 1112.5004 | 2026-06-19 | 0 | 0 | 3293
890955_FA26 合計 | [9 empty] | 0 | 10316
905200_FA26 | Pull On Pants | 2026-05-02 | 6-06 | 2026-05-08 | 2026-05-11 | 9.4741 | 1056.0642 | 2026-06-15 | 0 | 0 | 26558
| Pull On Pants | 2026-05-15 | 6-10 | 2026-04-30 | 2026-05-04 | 9.3511 | 1100.8636 | 2026-07-10 | 0 | 0 | 57498
905200_FA26 合計 | [9 empty] | 0 | 84056
907938_FA26 | Leggings | 2026-05-07 | 6-12 | 2026-05-21 | 2026-05-23 | 7.881 | 502.1956 | 2026-05-29 | 0 | 0 | 1178
907938_FA26 合計 | [9 empty] | 0 | 1178
910047_FA26 | Pajama | 2026-06-03 | 6-01 | 2026-06-06 | 2026-06-09 | 9.2169 | 873.476 | 2026-07-04 | 0 | 0 | 16401
| Pajama | 2026-06-03 | 6-03 | 2026-05-30 | 2026-06-03 | 9.5107 | 1006.3981 | 2026-07-09 | 0 | 0 | 28598
| Pajama | 2026-06-03 | 6-04 | 2026-05-28 | 2026-05-30 | 9.1249 | 816.4257 | 2026-07-01 | 0 | 0 | 18832
| Pajama | 2026-06-03 | 6-07 | 2026-05-30 | 2026-06-03 | 9.211 | 868.1993 | 2026-07-09 | 0 | 0 | 24374
| Pajama | 2026-06-03 | 6-12 | 2026-05-23 | 2026-05-26 | 9.4353 | 957.9881 | 2026-07-09 | 0 | 0 | 31999
| Pajama | 2026-06-03 | 6-15 | 2026-06-05 | 2026-06-08 | 9.1261 | 899.3507 | 2026-06-27 | 0 | 0 | 12675
| Pajama | 2026-06-03 | 6-18 | 2026-05-21 | 2026-05-23 | 9.4411 | 1055.0911 | 2026-07-09 | 0 | 0 | 36668
| Pajama | 2026-06-03 | 6-19 | 2026-05-28 | 2026-05-30 | 9.3862 | 1000.7301 | 2026-07-09 | 0 | 0 | 30137
910047_FA26 合計 | [9 empty] | 0 | 199684
910047_HO26DIS | Pajama | 2026-07-06 | 6-03 | 2026-07-04 | 2026-07-07 | 8.4758 | 1018.4268 | 2026-07-22 | 0 | 0 | 11308
| Pajama | 2026-07-06 | 6-12 | 2026-07-04 | 2026-07-07 | 8.2028 | 948.3748 | 2026-08-13 | 0 | 0 | 27677
| Pajama | 2026-07-06 | 6-18 | 2026-07-04 | 2026-07-07 | 8.2635 | 1164.4988 | 2026-08-20 | 0 | 0 | 38392
| Pajama | 2026-07-06 | 6-18 | 2026-08-18 | 2026-08-20 | 8.5299 | 1141.6509 | 2026-09-03 | 0 | 0 | 8515
910047_HO26DIS 合計 | [9 empty] | 0 | 85892
915810_FA26 | Tee | 2026-05-15 | 6-04 | 2026-05-13 | 2026-05-16 | 8.7965 | 610.2657 | 2026-06-03 | 0 | 0 | 6456
| Tee | 2026-06-04 | 6-04 | 2026-06-26 | 2026-06-29 | 7.7074 | 596.92 | 2026-07-07 | 0 | 0 | 3182
915810_FA26 合計 | [9 empty] | 0 | 9638
962148_FA26 | Leggings | 2026-04-15 | 6-10 | 2026-04-25 | 2026-04-28 | 8.0175 | 1209.8277 | 2026-05-06 | 0 | 0 | 4540
962148_FA26 合計 | [9 empty] | 0 | 4540
9KM9L2_C127 | Pull On Pants | 2026-09-08 | 6-09 | 2026-09-28 | 2026-09-30 | 8.5544 | 1097.9237 | 2026-11-10 | 33.975 | 37302 | 37302
| Pull On Pants | 2026-11-06 | 6-09 | 2026-12-26 | 2026-12-29 | 8.6 | 1341.1419 | 2027-01-13 | 8.706 | 11676 | 11676
| Pull On Pants | 2026-09-08 | 6-12 | 2026-09-08 | 2026-09-10 | 8.6736 | 1412.4285 | 2026-12-01 | 62.1695 | 87810 | 91428
| Pull On Pants | 2026-11-06 | 6-12 | 2026-12-16 | 2026-12-18 | 8.6 | 1507.3495 | 2026-12-31 | 7.746 | 11676 | 11676
9KM9L2_C127 合計 | [9 empty] | 148464 | 152082
9KM9L2_C227 | Pull On Pants | 2026-12-03 | 6-09 | 2026-12-01 | 2026-12-03 | 8.4137 | 1032.4064 | 2026-12-31 | 21.3559 | 22048 | 22048
| Pull On Pants | 2026-12-24 | 6-09 | 2027-01-08 | 2027-01-11 | 8.6 | 1341.1419 | 2027-01-15 | 1.9342 | 2594 | 2594
| Pull On Pants | 2026-11-30 | 6-12 | 2026-11-26 | 2026-11-28 | 8.6 | 1507.3495 | 2026-12-21 | 16.3472 | 24641 | 24641
| Pull On Pants | 2026-12-24 | 6-12 | 2026-12-26 | 2026-12-29 | 8.6 | 1507.3495 | 2027-01-04 | 1.7209 | 2594 | 2594
9KM9L2_C227 合計 | [9 empty] | 51877 | 51877
CFM271SH09 | Pull On Pants | 2026-11-05 | 6-02 | 2026-10-27 | 2026-10-29 | 8.4598 | 874.2451 | 2026-12-08 | 31.1492 | 27232 | 27232
| Pull On Pants | 2026-11-05 | 6-14 | 2026-11-03 | 2026-11-05 | 8.4222 | 798.3459 | 2026-12-08 | 25.3424 | 20232 | 20232
| Pull On Pants | 2026-11-05 | 6-16 | 2026-11-07 | 2026-11-10 | 8.4172 | 816.7413 | 2026-12-09 | 22.8126 | 18632 | 18632
CFM271SH09 合計 | [9 empty] | 66096 | 66096
CFW271SH01 | Pull On Pants | 2026-11-09 | 6-06 | 2026-10-28 | 2026-11-03 | 8.4651 | 1162.3143 | 2026-12-04 | 24.9605 | 29012 | 29012
| Pull On Pants | 2026-11-09 | 6-17 | 2026-11-04 | 2026-11-10 | 8.4536 | 1165.884 | 2026-12-09 | 22.311 | 26012 | 26012
CFW271SH01 合計 | [9 empty] | 55024 | 55024
CPM263PA05_26Q4 | Pull On Pants | 2026-07-10 | 6-07 | 2026-07-15 | 2026-07-21 | 7.6793 | 755.5279 | 2026-08-24 | 0 | 0 | 17364
| Pull On Pants | 2026-07-10 | 6-20 | 2026-07-10 | 2026-07-16 | 7.7377 | 808.2034 | 2026-08-21 | 0 | 0 | 20835
CPM263PA05_26Q4 合計 | [9 empty] | 0 | 38199
CPM263PA81 | Pull On Pants | 2026-05-23 | 6-20 | 2026-07-10 | 2026-07-16 | 8 | 942.2492 | 2026-07-18 | 0 | 0 | 31
CPM263PA81 合計 | [9 empty] | 0 | 31
CPM263TL32_26Q4 | Tee | 2026-07-10 | 6-04 | 2026-07-22 | 2026-07-28 | 7.4953 | 1072.3844 | 2026-08-13 | 0 | 0 | 12021
| Tee | 2026-07-10 | 6-15 | 2026-07-14 | 2026-07-20 | 7.6394 | 1140.9978 | 2026-08-20 | 0 | 0 | 25311
CPM263TL32_26Q4 合計 | [9 empty] | 0 | 37332
CPW264TL38 | Tee | 2026-07-10 | 6-03 | 2026-07-14 | 2026-07-20 | 7.5879 | 1087.3719 | 2026-08-19 | 0 | 0 | 22323
| Tee | 2026-07-10 | 6-05 | 2026-07-23 | 2026-07-29 | 7.746 | 1167.0888 | 2026-08-21 | 0 | 0 | 17942
CPW264TL38 合計 | [9 empty] | 0 | 40265
G917K0_C426 | Pajama | 2026-06-12 | 6-02 | 2026-05-23 | 2026-05-30 | 8.6007 | 1282.2576 | 2026-08-31 | 0 | 0 | 87912
| Pajama | 2026-05-26 | 6-16 | 2026-05-21 | 2026-05-28 | 9.2646 | 1283.0131 | 2026-07-11 | 0 | 0 | 43173
G917K0_C426 合計 | [9 empty] | 0 | 131085
G92X13_2PK_C127 | Boxer | 2026-10-26 | 6-19 | 2026-11-12 | 2026-11-14 | 8.3339 | 2191.5075 | 2026-12-01 | 12.7693 | 27984 | 27984
G92X13_2PK_C127 合計 | [9 empty] | 27984 | 27984
G9M018_C426 | Pajama | 2026-05-25 | 6-09 | 2026-05-12 | 2026-05-19 | 9.5019 | 1837.1199 | 2026-07-06 | 0 | 0 | 65630
| Pajama | 2026-06-25 | 6-14 | 2026-06-22 | 2026-06-27 | 8.5318 | 1730.0941 | 2026-08-18 | 0 | 0 | 67974
| Pajama | 2026-06-25 | 6-16 | 2026-07-03 | 2026-07-09 | 8.0933 | 1800.1043 | 2026-08-07 | 0 | 0 | 41073
| Pajama | 2026-06-25 | 6-17 | 2026-05-20 | 2026-05-26 | 9.0274 | 1815.7792 | 2026-08-14 | 0 | 0 | 114421
G9M018_C426 合計 | [9 empty] | 0 | 289098
HQ263487_FA26 | Pull On Pants | 2026-05-21 | 6-05 | 2026-05-23 | 2026-05-26 | 9.1873 | 1315.2706 | 2026-06-18 | 0 | 0 | 20277
HQ263487_FA26 合計 | [9 empty] | 0 | 20277
L0303X_6PK_C127 | Panties | 2026-10-12 | 6-04 | 2026-10-15 | 2026-10-17 | 8.5351 | 4504.3565 | 2026-11-17 | 22.6137 | 101860 | 101860
| Panties | 2026-10-12 | 6-10 | 2026-10-03 | 2026-10-06 | 8.5373 | 4525.711 | 2026-11-06 | 23.3908 | 105860 | 105860
L0303X_6PK_C127 合計 | [9 empty] | 207720 | 207720
L06X27_SSLLC127 | Pajama | 2026-10-15 | 6-14 | 2026-10-09 | 2026-10-12 | 8.4666 | 1639.1633 | 2026-11-07 | 20.8887 | 34240 | 34240
L06X27_SSLLC127 合計 | [9 empty] | 34240 | 34240
LPST840 | Pull On Pants | 2026-08-18 | 6-05 | 2026-08-14 | 2026-08-19 | 8.4604 | 576.611 | 2026-09-11 | 0 | 0 | 8459
| Pull On Pants | 2026-08-18 | 6-15 | 2026-08-13 | 2026-08-18 | 8.5438 | 666.527 | 2026-09-14 | 0 | 0 | 10815
| Pull On Pants | 2026-08-24 | 6-15 | 2026-09-10 | 2026-09-14 | 9 | 923.6039 | 2026-09-30 | 7.4036 | 6838 | 9252
LPST840 合計 | [9 empty] | 6838 | 28526
LR16E1_C227 | Pull On Pants | 2026-12-04 | 6-01 | 2026-12-07 | 2026-12-09 | 8.4865 | 544.1002 | 2027-02-22 | 58.3964 | 31773.5 | 31773.5
| Pull On Pants | 2026-12-04 | 6-14 | 2026-12-03 | 2026-12-05 | 8.4831 | 504.4803 | 2027-02-20 | 61.0004 | 30773.5 | 30773.5
LR16E1_C227 合計 | [9 empty] | 62547 | 62547
MRLPMM_3PC_C127 | Pajama | 2026-08-24 | 6-04 | 2026-08-31 | 2026-09-07 | 8.85 | 1162.2256 | 2026-10-03 | 10.7234 | 12463 | 20297
| Pajama | 2026-08-24 | 6-11 | 2026-08-19 | 2026-08-27 | 8.7102 | 1272.7888 | 2026-11-13 | 46.4578 | 59131 | 77786
| Pajama | 2026-08-24 | 6-17 | 2026-08-28 | 2026-09-04 | 8.7029 | 1638.3176 | 2026-11-12 | 43.9671 | 72032 | 86785
MRLPMM_3PC_C127 合計 | [9 empty] | 143626 | 184868
MRLPMM_C426 | Pajama | 2026-06-08 | 6-11 | 2026-05-13 | 2026-05-20 | 8.7955 | 1554.7148 | 2026-08-07 | 0 | 0 | 98283
| Pajama | 2026-05-26 | 6-14 | 2026-05-20 | 2026-05-26 | 9.4588 | 1678.4133 | 2026-06-30 | 0 | 0 | 41982
MRLPMM_C426 合計 | [9 empty] | 0 | 140265
MRLPMM_SSLLC127 | Pajama | 2026-10-15 | 6-06 | 2026-10-15 | 2026-10-17 | 8.4095 | 1584.8241 | 2026-11-05 | 13.3895 | 21220 | 21220
| Pajama | 2026-10-15 | 6-18 | 2026-10-19 | 2026-10-21 | 8.2487 | 1859.8018 | 2026-10-29 | 4.8919 | 9098 | 9098
MRLPMM_SSLLC127 合計 | [9 empty] | 30318 | 30318
PST840 | Pull On Pants | 2026-08-18 | 6-01 | 2026-08-24 | 2026-08-27 | 8.8358 | 774.666 | 2026-09-23 | 3.7745 | 2924 | 13625
| Pull On Pants | 2026-08-18 | 6-08 | 2026-08-31 | 2026-09-02 | 8.7419 | 797.142 | 2026-10-14 | 19.8785 | 15846 | 23417
| Pull On Pants | 2026-08-18 | 6-15 | 2026-09-08 | 2026-09-10 | 9 | 841.1024 | 2026-09-16 | 0.060635 | 51 | 2006
| Pull On Pants | 2026-09-14 | 6-15 | 2026-09-24 | 2026-09-28 | 8.6 | 818.2732 | 2026-10-06 | 5.2745 | 4316 | 4316
PST840 合計 | [9 empty] | 23137 | 43364
ST841_FA26 | Tee | 2026-07-23 | 6-03 | 2026-08-12 | 2026-08-14 | 8.4122 | 424.7018 | 2026-09-14 | 0 | 0 | 7230
ST841_FA26 合計 | [9 empty] | 0 | 7230
W9ZMM8_7PK_C127 | Panties | 2026-10-13 | 6-09 | 2026-11-02 | 2026-11-07 | 8.4417 | 7548.6125 | 2026-12-05 | 19.5962 | 147924 | 147924
W9ZMM8_7PK_C127 合計 | [9 empty] | 147924 | 147924
W9ZMM8_7PK_C426 | Panties | 2026-06-27 | 6-09 | 2026-06-27 | 2026-07-03 | 8.3189 | 10426.7584 | 2026-09-21 | 1.1546 | 12039 | 608284
W9ZMM8_7PK_C426 合計 | [9 empty] | 12039 | 608284
X048GZ_C127 | Pajama | 2026-08-22 | 6-02 | 2026-08-19 | 2026-08-27 | 8.826 | 1627.7499 | 2026-10-08 | 15.03 | 24465 | 46934
| Pajama | 2026-08-22 | 6-09 | 2026-09-10 | 2026-09-17 | 8.5481 | 1064.7715 | 2026-10-02 | 8.3586 | 8900 | 8900
X048GZ_C127 合計 | [9 empty] | 33365 | 55834
X25413_C426 | Pull On Pants | 2026-07-06 | 6-10 | 2026-07-06 | 2026-07-08 | 7.7928 | 582.7032 | 2026-07-16 | 0 | 0 | 3123
| Pull On Pants | 2026-07-06 | 6-12 | 2026-08-07 | 2026-08-11 | 8 | 456.6583 | 2026-08-26 | 0 | 0 | 3075
X25413_C426 合計 | [9 empty] | 0 | 6198
Z2850Y_C127 | Pull On Pants | 2026-09-12 | 6-01 | 2026-09-14 | 2026-09-21 | 8.5092 | 737.6136 | 2026-12-11 | 66.2705 | 48882 | 48882
| Pull On Pants | 2026-09-12 | 6-14 | 2026-09-28 | 2026-10-03 | 7.7179 | 305.2888 | 2026-10-14 | 7.3701 | 2250 | 2250
| Pull On Pants | 2026-09-12 | 6-15 | 2026-09-28 | 2026-10-03 | 8.418 | 590.0974 | 2026-11-14 | 33.9503 | 20034 | 20034
| Pull On Pants | 2026-09-12 | 6-19 | 2026-09-28 | 2026-10-03 | 8.4308 | 642.0626 | 2026-11-17 | 35.5588 | 22831 | 22831
Z2850Y_C127 合計 | [9 empty] | 93997 | 93997
Z2850Y_C227 | Pull On Pants | 2026-11-30 | 6-19 | 2026-11-23 | 2026-11-28 | 8.4303 | 673.7071 | 2027-01-14 | 35.3878 | 23841 | 23841
| Pull On Pants | 2026-12-03 | 6-20 | 2026-12-07 | 2026-12-12 | 8.6 | 859.14 | 2026-12-24 | 7.9149 | 6800 | 6800
Z2850Y_C227 合計 | [9 empty] | 30641 | 30641
ZC6HY000 | Gown | 2026-07-30 | 6-12 | 2026-08-19 | 2026-08-21 | 8.7494 | 1359.1938 | 2026-09-14 | 0 | 0 | 18161
總計 | [10 empty] | 6276799